## 099-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sang.Hwang | All comments shown on 098C0001R shall be applied for this item.
2 | Call-out | 1 | Hasan Al Noaimi | No.4 Hydrogen Plant
3 | Call-out | 1 | MAK | Or 4H2 Plant
4 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details (including Licensor clarifications) and be in code 2 approval status.
5 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
6 | Callout | 2 | Saeed Taher | Change to (smls)
7 | Callout | 2 | BD Mori | General comment 1) How external pressure is negative? 2) If it is full vacuum specify, 14.7 psig external pressure. 3) If it is half vacuum specify,10 psig external pressure 4) Steamout conditions are not specified in this data sheet, check and provide feedback.
8 | Call-out | 2 | Hasan Al Noaimi | No.4 Hydrogen Plant
9 | Cloud+ | 2 | BD Mori | Provide this data
10 | Text Box | 3 | Syed Ahmed | Keep one note regarding the MPT minimum pressurizing temperature
11 | Callout | 3 | BD Mori | Modify the note based on the information provided in the sketch below, including the type and opening in the Johnson screen for more clarity.
12 | Callout | 3 | BD Mori | Reword this note: Catalyst selection will be done later
13 | Callout | 3 | BD Mori | The specification for Inert balls appears to be incorrect. Check with Licensor and correct as required.
14 | Text Box | 4 | Syed Ahmed | General comment: All comments are applicable for the others zinc oxide reactors.
15 | Text Box | 4 | Syed Ahmed | General comment: please mention both units (meter and feet) as the PFD dimension using both units.
16 | Callout | 4 | BD Mori | More detail information required. Consult licensor
17 | Text Box | 4 | Syed Ahmed | Please specify/mention the dimension from the ( N6 )dump nozzle end point to the ground.
18 | Callout | 4 | Syed Ahmed | This should be drain not vent, please check with vendor, if yes, change the direction to the down side and update the nozzle schedule table below
19 | Callout | 4 | Salman Jaffer | With reference to Bid Query T1346, please review if there is necessity to add this note (The height shown in this datasheet is estimated and can vary basis requirement from selected catalyst vendor).
20 | Text Box | 5 | Syed Ahmed | COVER + LIFT LUG