## 382-G-DAT-00007-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Ebrahim.Deyab | no. of pumps inconsistent, put the third pump C
2 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Callout | 2 | Ebrahim.Deyab | Area classification to be verified.
5 | Text Box | 2 | hyunjin.paeng | Marine, dusty and corrosive
6 | Callout | 5 | Ebrahim.Deyab | Inconsistent with FEED selection ( LIQUID PENETRANT), please verify.
7 | Cloud+ | 5 | Saeed Taher | Type of inspections for welds & castings shall be as per applicable codes
8 | Callout | 8 | hyunjin.paeng | Basin dwg to be provided for vendor's reference