## Sheet1
Transmittal | Document Code | Doc. Client Code | Doc. Description | Rev. | Doc Date | Action | Recipient | Expected Date | Status/Transmittal | Response Date | Discipline
CON-BMP-EML-00112 | 076551C-000M-DL-4141-001 | 000-S-IDL-70009-001 | DEVIATION LIST FOR DESALTER PACKAGE | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00112 | 076551C-000M-ITP-4141-001 | 000-S-ITP-70009-001 | INSPECTION AND TEST PLAN FOR DESALTER PACKAGE | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00112 | 076551C-000M-MR-4141-001 | 000-S-MRQ-70009-001 | MATERIAL REQUISITION FOR DESALTER PACKAGER | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00112 | 076551C-000M-SP-4141-001 | 000-S-GRD-70009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR DESALTER PACKAGE | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00112 | 076551C-000M-SR-4141-001 | 000-S-SOW-70009-001 | SCOPE OF SUPPLY FOR DESALTER PACKAGE | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-DL-0846-001 | 000-S-IDL-60002-001 | DEVIATION LIST FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-ITP-0846-001 | 000-S-ITP-60002-001 | INSPECTIONA AND TEST PLAN FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-MR-0846-001 | 000-S-MRQ-60002-001 | MATERIAL REQUISITION FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-SP-0846-001 | 000-S-GRD-60002-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-SR-0846-001 | 000-S-SOW-60002-001 | SCOPE OF SUPPLY FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-021-SP-0841-001 | 021-S-DAT-00001-001 | DATA SHEET FOR 021U0001 FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-DL-0310-001 | 000-E-IDL-70006-001 | DEVIATION LIST FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-ITP-0310-001 | 000-E-ITP-70006-001 | INSPECTION AND TEST PLAN FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-MR-0310-001 | 000-E-MRQ-70006-001 | MATERIAL REQUISITION FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-SP-0310-001 | 000-E-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-SR-0310-001 | 000-E-SOW-70006-001 | SCOPE OF SUPPLY FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 085-E-DAT-00001-001 | 085-E-DAT-00001-001 | MECHANICAL DATA SHEET BMP MAIN COOLING TOWER 085CWT0001 | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 085-E-DAT-00002-001 | 085-E-DAT-00002-001 | MECHANICAL DATA SHEET BMP SECONDARY COOLING TOWER 085CWT0002 | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00123 | 076551C-000R-DL-0570-001 | 000-C-IDL-60007-001 | DEVIATION LIST FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-000R-ITP-0570-001 | 000-C-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-000R-MR-0570-001 | 000-C-MRQ-60007-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-000R-SP-0570-001 | 000-C-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-000R-SR-0570-001 | 000-C-SOW-60007-001 | SCOPE OF SUPPLY FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-001-001 | 018-C-GAD-00013-001 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-001-002 | 018-C-GAD-00013-002 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-001-003 | 018-C-GAD-00013-003 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-002-001 | 018-C-GAD-00011-001 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-002-002 | 018-C-GAD-00011-002 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-002-003 | 018-C-GAD-00011-003 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-004-001 | 018-C-GAD-00012-001 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-004-002 | 018-C-GAD-00012-002 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-004-003 | 018-C-GAD-00012-003 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-007-001 | 018-C-GAD-00014-001 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-007-002 | 018-C-GAD-00014-002 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-007-003 | 018-C-GAD-00014-003 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00125 | 076551C-000R-DL-0910-004 | 000-G-IDL-60001-001 | DEVIATION LIST FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-ITP-0910-004 | 000-G-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-MR-0910-004 | 000-G-MRQ-60001-001 | MATERIAL REQUISITION FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-SP-0910-004 | 000-G-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-SR-0910-004 | 000-G-SOW-60001-001 | SCOPE OF SUPPLY FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-0910-001 | 018-G-DAT-00002-001 | CENTRIFUGAL PUMPS DATA SHEET TRAIN1 & TRAIN2 FEED PUMPS 018P1001A/B & 018P2001A/B | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-0910-002 | 018-G-DAT-00003-001 | CENTRIFUGAL PUMPS DATA SHEET QUENCH OIL PUMPS 018P0001A/B | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-0910-018 | 018-G-DAT-00004-001 | CENTRIFUGAL PUMPS DATA SHEET HP LEAN AMINE PUMPS 018P0019A/B | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-1012-001 | 018-K-DAT-00003-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 018T1001A/018T2001A TRAIN 1 FEED PUMP TURBINE TRAIN 2 FEED PUMP TURBINE | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-1012-002 | 018-K-DAT-00004-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 018T0001A QUECH OIL PUMP TURBINE | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-021-SP-0910-002 | 021-G-DAT-00001-001 | CENTRIFUGAL PUMP DATA SHEET FOR FEED PUMPS 021P0001 A/B | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-DL-0960-001 | 000-G-IDL-60002-001 | DEVIATION LIST FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-ITP-0960-001 | 000-G-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-MR-0960-001 | 000-G-MRQ-60002-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-SP-0960-001 | 000-G-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-SR-0960-001 | 000-G-SOW-60002-001 | SCOPE OF SUPPLY FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-018-SP-0960-001 | 018-G-DAT-00001-001 | 1ST 2ND REACTOR RECYCLE PUMPS PACKAGE | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-DL-1020-001 | 000-K-IDL-60001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-ITP-1020-001 | 000-K-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-MR-1020-001 | 000-K-MRQ-60001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-SP-1020-001 | 000-K-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-SR-1020-001 | 000-K-SOW-60001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-018-SP-1020-001 | 018-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 018K1001/K1002/K0001/K2001/K2002 MAKE-UP HYDROGEN COMPRESSORS | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-023-SP-1020-001 | 023-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 023K0001A/B FEED GAS COMPRESSORS | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 010-K-DAT-00001-001 | 010-K-DAT-00001-001 | MECHANICAL DATA SHEET CDU OVERHEAD VAPOR COMPRESSOR 010K0001 A/B | A | 2018-05-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00132 | 019-K-DAT-00002-001 | 019-K-DAT-00002-001 | MECHANICAL DATA SHEET MAKE-UP HYDROGEN COMPRESSORS 19K0002 19K0003 19K0004 | A | 2018-05-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-DL-1020-001 | 000-K-IDL-70001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-ITP-1020-001 | 000-K-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-MR-1020-001 | 000-K-MRQ-70001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-SP-1020-001 | 000-K-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-SR-1020-001 | 000-K-SOW-70001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00139 | 019-C-DAT-00004-001 | 019-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE COLD HIGH PRESSURE SEPARATOR 019V0004 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-DAT-00006-001 | 019-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECYCLE GAS KO DRUM 019V0006 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-DAT-00009-001 | 019-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAEG COLD HIGH PRESSURE SEPARATOR 019V0009 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-DAT-10003-001 | 019-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HP H2S ABSORBER 019C0003 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-GAD-00004-001 | 019-C-GAD-00004-001 | MECHANICAL DRAWING FOR 1ST STAGE COLD HIGH PRESSURE SEPARATOR DRRUM 019V0004 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-GAD-00006-001 | 019-C-GAD-00006-001 | MECHANICAL DRAWING FOR RECYCLE GAS K.O. DRUM 019V0006 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-GAD-00009-001 | 019-C-GAD-00009-001 | MECHANICAL DRAWING FOR 2ND STAGE COLD HIGH PRESSURE SEPARATOR DRUM 019V0009 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-GAD-10003-001 | 019-C-GAD-10003-001 | MECHANICAL DRAWING FOR HP H2S ABSORBER 019C0003 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-DL-0811-002 | 000-C-IDL-70001-001 | DEVIATION LIST FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-ITP-0811-002 | 000-C-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-MR-0811-002 | 000-C-MRQ-70001-001 | MATERIAL REQUISITION FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-SP-0811-002 | 000-C-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-SR-0811-002 | 000-C-SOW-70001-001 | SCOPE OF SUPPLY FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00140 | 076551C-000R-DL-0710-001 | 000-E-IDL-60007-001 | DEVIATION LIST FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-000R-ITP-0710-001 | 000-E-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-000R-MR-0710-001 | 000-E-MRQ-60007-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-000R-SP-0710-001 | 000-E-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-000R-SR-0710-001 | 000-E-SOW-60007-001 | SCOPE OF SUPPLY FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-001 | 018-E-DAT-00005-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E1005 TRAIN 1 - HP/MT FLASH GAS COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-002 | 018-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0006 - MP/MT VAPOR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-003 | 018-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0010 - ATM COLUMN REFLUX AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-007 | 018-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0007 - QUENCH OIL COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-008 | 018-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E2005 - TRAIN 2 - HP/MT FLASH GAS COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-011 | 018-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0030 - CIRCULATION OIL AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-021-SP-0710-001 | 021-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0010 HHPS VAPOR AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-021-SP-0710-002 | 021-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0011 HLPS VAPOR AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-DL-0710-002 | 000-E-IDL-60008-001 | DEVIATION LIST FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-ITP-0710-002 | 000-E-ITP-60008-001 | INSPECTION AND TEST PLAN FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-MR-0710-002 | 000-E-MRQ-60008-001 | MATERIAL REQUISITION FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-SP-0710-002 | 000-E-GRD-60008-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-SR-0710-002 | 000-E-SOW-60008-001 | SCOPE OF SUPPLY FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-004 | 018-E-DAT-00007-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0011 - ATM COLUMN OVHD PRODUCT AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-005 | 018-E-DAT-00009-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0015 - DIESEL PRODUCT AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-006 | 018-E-DAT-00008-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0012 A/B - SOUR GAS COMPRESSOR DISCHARGE COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-009 | 018-E-DAT-00010-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0019 - LVGO AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-010 | 018-E-DAT-00011-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0023 - MVGO AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-012 | 018-E-DAT-00012-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0035 -TEMPERED WATER COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-021-SP-0710-003 | 021-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0012 -STRIPPER OVERHEAD AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-021-SP-0710-004 | 021-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0016 -DIESEL PRODUCT COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-DL-0851-001 | 000-H-IDL-70001-001 | DEVIATION LIST FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-ITP-0851-001 | 000-H-ITP-70001-001 | INSPECTION AND TEST PLAN FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-MR-0851-001 | 000-H-MRQ-70001-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-SP-0851-001 | 000-H-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-SR-0851-001 | 000-H-SOW-70001-001 | SCOPE OF SUPPLY FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 019-S-DAT-00005-001 | 019-S-DAT-00005-001 | MECHANICAL DATA SHEET FEED FILTER 019U0001 | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00155 | 076551C-000M-DL-0846-001 | 000-S-IDL-70003-001 | DEVIATION LIST FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 076551C-000M-ITP-0846-001 | 000-S-ITP-70003-001 | INSPECTION AND TEST PLAN FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 076551C-000M-MR-0846-001 | 000-S-MRQ-70003-001 | MATERIAL REQUISITION FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 076551C-000M-SP-0846-001 | 000-S-GRD-70003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 076551C-000M-SR-0846-001 | 000-S-SOW-70003-001 | SCOPE OF SUPPLY FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00157 | 019-C-GAD-00003-001 | 019-C-GAD-00003-001 | GENERAL ARRANGEMENT 019V0003 1ST STAGE HOT HIGH PRESSURE SEPARATOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 019-C-GAD-00008-001 | 019-C-GAD-00008-001 | GENERAL ARRANGEMENT 019V0008 2ND STAGE HOT HIGH PRESSURE SEPARATOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 019-C-GAD-00010-001 | 019-C-GAD-00010-001 | GENERAL ARRANGEMENT 019V0010 HOT LOW PRESSURE SEPARATOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-DL-0411-002 | 000-C-IDL-70004-001 | DEVIATION LIST FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-ITP-0411-002 | 000-C-ITP-70004-001 | INSPECTION AND TEST PLAN FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-MR-0411-002 | 000-C-MRQ-70004-001 | MATERIAL REQUISITION FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-SP-0411-002 | 000-C-GRD-70004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-SR-0411-002 | 000-C-SOW-70004-001 | SCOPE OF SUPPLY FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 010-C-GAD-10004-001 | 010-C-GAD-10004-001 | STABILIZER - ITEM 010C0004 EX 010C0005/010-C-GAD-10005-001 AS PER CLIENT COMMENTS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 010-C-GAD-10005-001 | 010-C-GAD-10005-001 | NAPHTHA SPLITTER - ITEM 010C0005 EX 010C0005/010-C-GAD-10006-001 AS PER CLIENT COMMENTS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 019-C-GAD-10006-001 | 019-C-GAD-10006-001 | KEROSENE STRIPPER - ITEM 019C0006 | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 019-C-GAD-10010-001 | 019-C-GAD-10010-001 | NAPHTHA SPLITTER - ITEM 019C0010 | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-DL-0511-001 | 000-C-IDL-70008-001 | DEVIATION LIST FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-ITP-0511-001 | 000-C-ITP-70008-001 | INSPECTION AND TEST PLAN FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-MR-0511-001 | 000-C-MRQ-70008-001 | MATERIAL REQUISITION FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-SP-0511-001 | 000-C-GRD-70008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-SR-0511-001 | 000-C-SOW-70008-001 | SCOPE OF SUPPLY FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00160 | 076551C-000S-DL-0710-002 | 000-E-IDL-80007-001 | DEVIATION LIST FOR AIR COOLERS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00160 | 076551C-000S-ITP-0710-002 | 000-E-ITP-80007-001 | INSPECTION AND TEST PLAN FOR AIR COOLERS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00160 | 076551C-000S-MR-0710-002 | 000-E-MRQ-80007-001 | MATERIAL REQUISITION FOR AIR COOLERS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00160 | 076551C-000S-SP-0710-002 | 000-E-GRD-80007-001 | PARTICULAR TECHNICAL SPEIFICATION FOR AIR COOLERS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00160 | 076551C-000S-SR-0710-002 | 000-E-SOW-80007-001 | SCOPE OF SUPPLY FOR AIR COOLERS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00001-001 | 019-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0006 A/B 1ST STAGE REACTOR EFFLUENT / FRESH FEED EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00002-001 | 019-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0004 A/B 1ST STAGE REACTOR EFFLUENT / EFFLUENT EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00003-001 | 019-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0005 A/B 1ST STAGE REACTOR EFFLUENT / FRACTIONATOR FEED EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00004-001 | 019-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0007 A/B 1ST STAGE HHPS VAPOR / RECYCLE GAS EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00005-001 | 019-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0011 A/B 2ND STAGE HHPS VAPOR /CLPS LIQUID EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00006-001 | 019-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0009 A/B 2ND STAGE REACTOR FEED /EFFLUENT EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00007-001 | 019-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0010 2ND STAGE REACTOR EFFLUENT / RECYCLE GAS EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00013-001 | 019-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0044 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00014-001 | 019-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0047 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00015-001 | 019-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0074 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-DL-0610-001 | 000-E-IDL-70001-001 | DEVIATION LIST FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-ITP-0610-001 | 000-E-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-MR-0610-001 | 000-E-MRQ-70001-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-SP-0610-001 | 000-E-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-SR-0610-001 | 000-E-SOW-70001-001 | SCOPE OF SUPPLY FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 010-E-DAT-00034-001 | 010-E-DAT-00034-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0034 BRINE AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 019-E-DAT-00008-001 | 019-E-DAT-00008-001 | AIR COOLED HEX DATA SHEET FOR 1ST STAGE HHPS VAPOR 019E0008 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 019-E-DAT-00009-001 | 019-E-DAT-00009-001 | AIR COOLED HEX DATA SHEET FOR 2ND STAGE HHPS VAPOR AIR COOLER 019E0012 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 019-E-DAT-00010-001 | 019-E-DAT-00010-001 | AIR COOLED HEX DATA SHEET FOR HLPS VAPOR AIR COOLER 019E0013 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-DL-0710-001 | 000-E-IDL-70007-001 | DEVIATION LIST FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-ITP-0710-001 | 000-E-ITP-70007-001 | INSPECTION AND TEST PLAN FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-MR-0710-001 | 000-E-MRQ-70007-001 | MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-SP-0710-001 | 000-E-GRD-70007-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-SR-0710-001 | 000-E-SOW-70007-001 | SCOPE OF SUPPLY FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-DL-1011-001 | 000-K-IDL-60002-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-ITP-1011-001 | 000-K-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-MR-1011-001 | 000-K-MRQ-60002-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-SP-1011-001 | 000-K-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-SR-1011-001 | 000-K-SOW-60002-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-018-SP-1011-001 | 018-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 018K0002 A/B SOUR GAS COMPRESSORS | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-021-SP-1011-001 | 021-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 021K0001 RECYCLE GAS COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-021-SP-1012-001 | 021-K-DAT-00002-001 | DATA SHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 021T0001 RECYCLE GAS COMPRESSOR TURBINE | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-023-SP-1011-001 | 023-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 023K0002 A/B PURGE GAS COMPRESSORS | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-051-SP-1011-001 | 051-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 051K0001 A/B PROPANE COMPRESSORS | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00170 | 010-C-DAT-10001-001 | 010-C-DAT-10001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR ATMOSPHERIC COLUMN 010C0001 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-DAT-10002-001 | 010-C-DAT-10002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR KERO STRIPPER 010C0002 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-DAT-10003-001 | 010-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR DIESEL STRIPPER 010C0003 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-GAD-10001-001 | 010-C-GAD-10001-001 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-GAD-10002-001 | 010-C-GAD-10002-001 | GENERAL ARRANGEMENT 010C0002 KERO STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-GAD-10003-001 | 010-C-GAD-10003-001 | GENERAL ARRANGEMENT 010C0003 DIESEL STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 011-C-DAT-10001-001 | 011-C-DAT-10001-001 | UNFIRED PRESSURE VESSEL DEASIGN SPECIFICATION SHEET FOR VACUUM COLUMN 011C0001 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 011-C-DAT-10002-001 | 011-C-DAT-10002-001 | UNFIRED PRESSURE VESSEL DEASIGN SPECIFICATION SHEET FOR TAIL GAS ABSORBER 011C0002 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 011-C-GAD-10001-001 | 011-C-GAD-10001-001 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 011-C-GAD-10002-001 | 011-C-GAD-10002-001 | GENERAL ARRANGEMENT 011C0002 TAL GAS ABSORBER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10004-001 | 019-C-DAT-10004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT STRIPPER 019C0004 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10005-001 | 019-C-DAT-10005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT FRACTIONATOR 019C0005 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10007-001 | 019-C-DAT-10007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LIGHT DIESEL STRIPPER 019C0007 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10008-001 | 019-C-DAT-10008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HEAVY DIESEL STRIPPER 019C0008 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10009-001 | 019-C-DAT-10009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER 019C0009 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10004-001 | 019-C-GAD-10004-001 | GENERAL ARRANGEMENT 019C0004 PRODUCT STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10005-001 | 019-C-GAD-10005-001 | GENERAL ARRANGEMENT 019C0005 PRODUCT FRACTIONATOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10007-001 | 019-C-GAD-10007-001 | GENERAL ARRANGEMENT 019C0007 LIGHT DIESEL STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10008-001 | 019-C-GAD-10008-001 | GENERAL ARRANGEMENT 019C0008 HEAVY DIESEL STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10009-001 | 019-C-GAD-10009-001 | GENERAL ARRANGEMENT 019C0009 NAPHTHA STABILIZER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-DL-0511-002 | 000-C-IDL-70009-001 | DEVIATION LIST FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-ITP-0511-002 | 000-C-ITP-70009-001 | INSPECTION AND TEST PLAN (ITP) FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-MR-0511-002 | 000-C-MRQ-70009-001 | MATERIAL REQUISITION FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-SP-0511-002 | 000-C-GRD-70009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-SR-0511-002 | 000-C-SOW-70009-001 | SCOPE OF SUPPLY FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00196 | BMPS-A-50003 |  | SYMBOLOGY FOR PIDS AND PROCESS FLOW DIAGRAMS | 1 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-A1 |  | BASIC ENGINEERING DESIGN DATA | 2 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-A15 |  | HAZOPS OF MAJOR PROJECTS | 1 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-A2 |  | SPECIFICATIONS, CODES AND STANDARDS | 1 | 2016-07-14 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-A24 |  | ALLOY 825 FOR HEAT EXCHANGERS AND PIPING IN HYDROPROCESSING REACTOR EFFLUENT SERVICE | 1 | 2016-06-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-A26 |  | CARBON STEEL PRESSURE VESSELS AND HEAT EXCHANGERS IN SOUR SERVICE | 1 | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-A4 |  | REFINERY LAYOUT AND SPACING | 1 | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-A7 |  | PROJECT INFORMATION MANAGEMENT AND HANDOVER (PIMH) | 1 | 2016-06-21 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-A8 |  | DRAFTING AND DOCUMENTATION REQUIREMENTS | 1 | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-B1 |  | GENERAL WELDING REQUIREMENTS | 1 | 2018-04-06 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-B4 |  | MATERIAL AND FABRICATION REQUIREMENTS FOR DUPLEX STAINLESS STEEL | 0 | 2016-06-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-B9 |  | POSITIVE ALLOY MATERIAL IDENTIFICATION | 1 | 2018-03-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C11 |  | BUBBLE CAP AND SIEVE TRAYS | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C2 |  | CARBON STEEL PRESSURE VESSELS | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C3 |  | 1 1/4 CR - 1/2 MO STEEL PRESSURE VESSELS OPERATING BELOW 825°F (440°C) | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C4 |  | HYDROPROCESSING REACTORS AND HIGH PRESSURE VESSELS MANUFACTURED FROM 1 1/4 CR - 1/2 MO ALLOY STEEL | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C5 |  | CONVENTIONAL 2 1/4 CR-1MO STEEL PRESSURE VESSELS | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C6 |  | HYDROPROCESSING REACTORS AND HIGH PRESSURE VESSELS MANUFACTURED FROM 2.25CR-1MO AND 2.25CR-1MO-0.25V LOW ALLOY STEELS | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C7 |  | AUSTENITIC STAINLESS STEEL PRESSURE VESSELS | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C8 |  | DUPLEX STAINLESS STEEL PRESSURE VESSELS | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-C9 |  | FIELD ERECTED CARBON STEEL STORAGE SPHERES | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-D2 |  | STORAGE TANKS TO API 650 | 1 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-D3 |  | STORAGE TANKS TO API 620 | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-E4 |  | CS HEAT EXCHANGERS FOR LOW TEMPERATURE SERVICE | 1 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-E7 |  | AIR COOLED HEAT EXCHANGERS | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-G5 |  | RECIPROCATING PUMPS | 1 | 2018-05-28 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J1 |  | CONTROL SYSTEM DESIGN BASIS | 1 | 2018-04-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J14 |  | EMERGENCY SHUT DOWN (ESD) SYSTEM | 2 | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J19 |  | FIRE ALARM SYSTEM (FAS) | 1 | 2018-04-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J2 |  | GENERAL INSTRUMENT SPECIFICATION | 1 | 2018-04-16 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J23 |  | ONLINE ANALYSER SYSTEMS | 1 | 2018-03-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J27 |  | SPI (INTOOLS) INSTRUCTIONS AND DESIGN CONVENTIONS | 1 | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J36 |  | BAPCO ALARM PHILOSOPHY STANDARD | 1 | 2016-05-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J37 |  | ALARM MANAGEMENT SYSTEM STANDARD | 1 | 2016-05-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J39 |  | CCTV, RADIO, TELECOMMUNICATIONS AND SECURITY SYSTEMS | 1 | 2018-04-03 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J6 |  | INSTRUMENTATION FOR PACKAGE UNITS | 1 | 2018-04-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J7 |  | FOUNDATION FIELDBUS HIGH POWER TRUNK - FIELDBUS BARRIER MODEL | 1 | 2018-04-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-J8 |  | CONTROL VALVES | 1 | 2018-04-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-K8 |  | GENERAL PURPOSE PRESSURE LUBRICATION SYSTEMS | 1 | 2018-03-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-K9 |  | LUBRICATION, SHAFT SEALING AND CONTROL OIL SYSTEMS FOR SPECIAL PURPOSE APPLICATIONS | 1 | 2018-03-01 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-L1 |  | REFINERY PIPING | 1 | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-L11 |  | DESIGN OF PIPE SUPPORTS | 1 | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-L3 |  | PIPING LAYOUT AND PIPING DESIGN | 2 | 2018-05-28 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-L9 |  | PIPING FLEXIBILITY AND STRESS ANALYSIS | 1 | 2018-05-28 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-M1 |  | BASIC CIVIL AND STRUCTURAL DESIGN DATA | 1 | 2016-06-09 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-M3 |  | STEEL STRUCTURES | 1 | 2016-06-09 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-M5 |  | MARINE LOADING ARMS | 1 | 2018-05-28 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P1 |  | GENERAL DESIGN RULES FOR ELECTRICAL SYSTEM | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P12 |  | POWER FACTOR CORRECTION SYSTEM | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P18 |  | HV INDUCTION MOTORS | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P19 |  | LV INDUCTION MOTORS | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P2 |  | CLASSIFICATION OF LOCATIONS FOR SELECTION OF ELECTRICAL EQUIPMENT | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P3 |  | ELECTRICAL REQUIREMENTS FOR PACKAGE UNITS | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P6 |  | HV GAS INSULATED SWITCHGEAR (GIS) | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P7 |  | HV AIR INSULATED SWITCHGEARS | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P8 |  | LOW VOLTAGE SWITCHGEARS | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-P9 |  | POWER TRANSFORMERS | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-Q1 |  | CONCRETE FOUNDATIONS | 1 | 2018-05-28 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00196 | BMPS-S12 |  | GUIDELINES FOR PREPARATION OF SPARE PARTS AND INTERCHANGEABILITY LISTS (SPILS) | 1 | 2018-05-29 | FOR BAPCO INFORMATION | BMP Project Director
CON-BMP-EML-00197 | 019-G-DAT-00004-001 | 019-G-DAT-00004-001 | MECHANICAL DATA SHEET INJECTION WATER PUMPS 019P0022 AB | A | 2018-05-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00197 | 076551C-000M-DL-0910-005 | 000-G-IDL-70005-001 | DEVIATION LIST FOR API 610 HIGH SPEED PUMPS | A | 2018-05-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00197 | 076551C-000M-ITP-0910-005 | 000-G-ITP-70005-001 | INSPECTION AND TEST PLAN FOR API 610 HIGH SPEED PUMPS | A | 2018-05-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00197 | 076551C-000M-MR-0910-005 | 000-G-MRQ-70005-001 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | A | 2018-05-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00197 | 076551C-000M-SP-0910-005 | 000-G-GRD-70005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR API 610 HIGH SPEED PUMPS | A | 2018-05-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00197 | 076551C-000M-SR-0910-005 | 000-G-SOW-70005-001 | SCOPE OF SUPPLY FOR API 610 HIGH SPEED PUMPS | A | 2018-05-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00208 | 076551C-000S-DL-1020-001 | 000-K-IDL-80001-001 | LIST OF DEVIATION FOR RECIPROCATING COMPRESSOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00208 | 076551C-000S-ITP-1020-001 | 000-K-ITP-80001-001 | INSPECTION AND TESTS PLAN FOR RECIPROCATING COMPRESSORS | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00208 | 076551C-000S-MR-1020-001 | 000-K-MRQ-80001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSORS | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00208 | 076551C-000S-SP-1020-001 | 000-K-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00208 | 076551C-000S-SR-1020-001 | 000-K-SOW-80001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSORS | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00208 | SO6001-EJ2E-TDS-09820001-001 | 098-K-DAT-00001-001 | DATASHEET FOR RECIPROCATING COMPRESSOR FOR 098K0002 CIRCULATION NITROGEN COMPRESSOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00208 | SO6001-EJ2E-TDS-09920001-001 | 099-K-DAT-00001-001 | DATASHEET FOR RECIPROCATING COMPRESSOR FOR 099K0002 CIRCULATION NITROGEN COMPRESSOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00209 | 019-G-DAT-00001-001 | 019-G-DAT-00001-001 | MECHANICAL DATA SHEET 1ST STAGE REACTOR FEED PUMP 019P0002A/B | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00209 | 019-G-DAT-00002-001 | 019-G-DAT-00002-001 | MECHANICAL DATA SHEET 2ND STAGE REACTOR FEED PUMP 019P0003A/B | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00209 | 019-G-DAT-00003-001 | 019-G-DAT-00003-001 | MECHANICAL DATA SHEET HIGH PRESSURE LEAN AMINE PUMP 019P0021A/B | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00209 | 076551C-000M-DL-0910-004 | 000-G-IDL-70001-001 | DEVIATION LIST FOR BB5 PUMPS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00209 | 076551C-000M-ITP-0910-004 | 000-G-ITP-70001-001 | INSPECTION AND TEST PLAN FOR BB5 PUMPS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00209 | 076551C-000M-MR-0910-004 | 000-G-MRQ-70001-001 | MATERIAL REQUISITION FOR BB5 PUMPS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00209 | 076551C-000M-SP-0910-004 | 000-G-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB5 PUMPS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00209 | 076551C-000M-SR-0910-004 | 000-G-SOW-70001-001 | SCOPE OF SUPPLY FOR BB5 PUMPS | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00210 | 019-K-DAT-00001-001 | 019-K-DAT-00001-001 | MECHANICAL DATA SHEET RECYCLE GAS COMPRESSOR 019K0001 | A | 2018-05-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00210 | 019-K-DAT-00003-001 | 019-K-DAT-00003-001 | MECHANICAL DATA SHEET RECYCLE GAS COMPRESSOR TURBINE | A | 2018-05-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00210 | 076551C-000M-DL-1011-001 | 000-K-IDL-70002-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00210 | 076551C-000M-ITP-1011-001 | 000-K-ITP-70002-001 | INSPECTION AND TEST PLAN (ITP) FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00210 | 076551C-000M-MR-1011-001 | 000-K-MRQ-70002-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00210 | 076551C-000M-SP-1011-001 | 000-K-GRD-70002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00210 | 076551C-000M-SR-1011-001 | 000-K-SOW-70002-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00213 | 019-F-DAT-00001-001 | 019-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F0001 1ST STAGE REACTOR FEED FURNACE | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00213 | 019-F-DAT-00002-001 | 019-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F0002 2ND STAGE REACTOR FEED FURNACE | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00213 | 019-F-DAT-00003-001 | 019-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F0003 FRACTIONATOR FEED FURNACE | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00213 | 076551C-000M-DL-0110-001 | 000-F-IDL-70001-001 | DEVIATION LIST FOR HCU FIRED HEATERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00213 | 076551C-000M-ITP-0110-001 | 000-F-ITP-70001-001 | INSPECTION AND TEST PLANT (ITP) FOR HCU HEATER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00213 | 076551C-000M-MR-0110-001 | 000-F-MRQ-70001-001 | MATERIAL REQUISITION HCU HEATER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00213 | 076551C-000M-SP-0110-001 | 000-F-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HCU HEATER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00213 | 076551C-000M-SR-0110-001 | 000-F-SOW-70001-001 | SCOPE OF SUPPLY FOR HCU HEATER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00214 | 010-F-DAT-00001-001 | 010-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS - 010F0001 ATMOSPHERIC COLUMN HEATER | A | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00214 | 011-F-DAT-00001-001 | 011-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS - 011F0001 VACUUM COLUMN HEATER | A | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00214 | 076551C-000M-DL-0110-002 | 000-F-IDL-70002-001 | DEVIATION LIST FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00214 | 076551C-000M-ITP-0110-002 | 000-F-ITP-70002-001 | INSPECTION AND TEST PLAN FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00214 | 076551C-000M-MR-0110-002 | 000-F-MRQ-70002-001 | MATERIAL REQUISITION FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00214 | 076551C-000M-SP-0110-002 | 000-F-GRD-70002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00214 | 076551C-000M-SR-0110-002 | 000-F-SOW-70002-001 | SCOPE OF SUPPLY FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00218 | 076551C-000R-DL-0110-001 | 000-F-IDL-60001-001 | DEVIATION LIST 1 RHCU FIRED HEATERS | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00218 | 076551C-000R-ITP-0110-001 | 000-F-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) 1 RHCU FIRED HEATERS | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00218 | 076551C-000R-MR-0110-001 | 000-F-MRQ-60001-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00218 | 076551C-000R-SP-0110-001 | 000-F-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 1 RHCU FIRED HEATERS 18F1001/18-F1002/18F2001/18F2002/18F0001/18F0002 | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00218 | 076551C-018-SP-0110-001 | 018-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1001 /F 018F2001 TRAIN 1&2 - REACTOR FEED FURNACE | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00218 | 076551C-018-SP-0110-002 | 018-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F0001 ATM COLUMN FEED FURNACE | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00218 | 076551C-018-SP-0110-003 | 018-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F0002 VACUUM COLUMN FEED FURNACE | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00218 | 076551C-018-SP-0110-004 | 018-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1002 / 018F2002 TRAIN 1&2 - RECYCLE HYDROGEN FURNACE | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00219 | 076551C-000S-DL-0511-002 | 000-C-IDL-80007-001 | LIST OF DEVIATION FOR CLADDED COLUMNS | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | 076551C-000S-ITP-0511-002 | 000-C-ITP-80007-001 | INSPECTION AND TEST PLAN FOR CLADDED COLUMNS | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | 076551C-000S-MR-0511-002 | 000-C-MRQ-80007-001 | MATERIAL REQUISITION FOR CLADDED COLUMNS | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | 076551C-000S-SP-0511-002 | 000-C-GRD-80007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CLADDED COLUMNS | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | 076551C-000S-SR-0511-002 | 000-C-SOW-80007-001 | SCOPE OF SUPPLY FOR CLADDED COLUMNS | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-03600004-001 | 036-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036C0002 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-03600004-002-001 | 036-C-GAD-00002-001 | 036C0002 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-03600004-003-002 | 036-C-GAD-00002-002 | 036C0002 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-03600004-004-003 | 036-C-GAD-00002-003 | 036C0002 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-03700004-001 | 037-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037C0002 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-03700004-002-001 | 037-C-GAD-00002-001 | 037C0002 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-03700004-003-002 | 037-C-GAD-00002-002 | 037C0002 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-03700004-004-003 | 037-C-GAD-00002-003 | 037C0002 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04400011-001 | 044-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0004 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04400011-002-001 | 044-C-GAD-00004-001 | 044C0004 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04400011-003-002 | 044-C-GAD-00004-002 | 044C0004 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04400011-004-003 | 044-C-GAD-00004-003 | 044C0004 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04500006-001 | 045-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0004 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04500006-002-001 | 045-C-GAD-00004-001 | 045C0004 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04500006-003-002 | 045-C-GAD-00004-002 | 045C0004 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04500006-004-003 | 045-C-GAD-00004-003 | 045C0004 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04600003-001 | 046-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046C0001 REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04600003-002-001 | 046-C-GAD-00001-001 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04600003-003-002 | 046-C-GAD-00001-002 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04600003-004-003 | 046-C-GAD-00001-003 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04700003-001 | 047-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 047C0001 PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04700003-002-001 | 047-C-GAD-00001-001 | 047C0001 PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04700003-003-002 | 047-C-GAD-00001-002 | 047C0001 PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04700003-004-003 | 047-C-GAD-00001-003 | 047C0001 PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04800005-001 | 048-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048C0001 AMINE REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04800005-002-001 | 048-C-GAD-00001-001 | 048C0001 PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04800005-003-002 | 048-C-GAD-00001-002 | 048C0001 PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04800005-004-003 | 048-C-GAD-00001-003 | 048C0001 PHENOLIC SOUR WATER STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04900003-001 | 049-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 049C0001 AMINE REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04900003-002-001 | 049-C-GAD-00001-001 | 049C0001 AMINE REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04900003-003-002 | 049-C-GAD-00001-002 | 049C0001 AMINE REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-04900003-004-003 | 049-C-GAD-00001-003 | 049C0001 AMINE REGENERATOR | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-09800005-001 | 098-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098C0004 HIGH PRESSURE STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-09800005-002-001 | 098-C-GAD-00004-001 | 098C0004 HIGH PRESSURE STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-09800005-003-002 | 098-C-GAD-00004-002 | 098C0004 HIGH PRESSURE STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-09800005-004-003 | 098-C-GAD-00004-003 | 098C0004 HIGH PRESSURE STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-09900005-001 | 099-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099C0004 HIGH PRESSURE STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-09900005-002-001 | 099-C-GAD-00004-001 | 099C0004 HIGH PRESSURE STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-09900005-003-002 | 099-C-GAD-00004-002 | 099C0004 HIGH PRESSURE STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00219 | SO6001-EJ1E-TDS-09900005-004-003 | 099-C-GAD-00004-003 | 099C0004 HIGH PRESSURE STRIPPER | A | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00243 | 076551C-000M-DL-0910-003 | 000-G-IDL-70004-001 | DEVIATION LIST FOR BB1 BB2 AND BB3 PUMPS | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00243 | 076551C-000M-ITP-0910-003 | 000-G-ITP-70004-001 | INSPECTION AND TEST PLAN FOR BB1 BB2 AND BB3 PUMPS | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00243 | 076551C-000M-MR-0910-003 | 000-G-MRQ-70004-001 | MATERIAL REQUISITION FOR BB1 BB2 AND BB3 PUMPS | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00243 | 076551C-000M-SP-0910-003 | 000-G-GRD-70004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB1 BB2 AND BB3 PUMPS | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00243 | 076551C-000M-SR-0910-003 | 000-G-SOW-70004-001 | SCOPE OF SUPPLY FOR BB1 BB2 AND BB3 PUMPS | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00245 | 019-C-DAT-30001-001 | 019-C-DAT-30001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE REACTOR 019C0001R | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00245 | 019-C-DAT-30002-001 | 019-C-DAT-30002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAGE REACTOR 019C0002R | A | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00245 | 019-C-GAD-30001-001 | 019-C-GAD-30001-001 | GENERAL ARRANGEMENT 019C0001R 1ST STAGE REACTOR | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00245 | 019-C-GAD-30002-001 | 019-C-GAD-30002-001 | GENERAL ARRANGEMENT 019C0002R 2ND STAGE REACTOR | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00245 | 076551C-000M-DL-0411-001 | 000-C-IDL-70006-001 | DEVIATION LIST FOR REACTORS HCU | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00245 | 076551C-000M-ITP-0411-001 | 000-C-ITP-70006-001 | INSPECTION AND TEST PLAN FOR REACTORS HCU | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00245 | 076551C-000M-MR-0411-001 | 000-C-MRQ-70006-001 | MATERIAL REQUISITION FOR REACTORS HCU | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00245 | 076551C-000M-SP-0411-001 | 000-C-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR REACTORS HCU | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00245 | 076551C-000M-SR-0411-001 | 000-C-SOW-70006-001 | SCOPE OF SUPPLY FOR REACTORS HCU | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-000R-DL-0610-001 | 000-E-IDL-60001-001 | DEVIATION LIST FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00258 | 076551C-000R-ITP-0610-001 | 000-E-ITP-60001-001 | INSPECTION AND TEST PLAN FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00258 | 076551C-000R-MR-0610-001 | 000-E-MRQ-60001-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00258 | 076551C-000R-SP-0610-001 | 000-E-GRD-60001-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00258 | 076551C-000R-SR-0610-001 | 000-E-SOW-60001-001 | SCOPE OF SUPPLY FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00258 | 076551C-018-DW-0610-001-001 | 018-E-GAD-00003-001 | 018E1001 TRAIN 1 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-001-002 | 018-E-GAD-00003-002 | 018E1001 TRAIN 1 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-001-003 | 018-E-GAD-00003-003 | 018E1001 TRAIN 1 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-001-004 | 018-E-GAD-00003-004 | 018E1001 TRAIN 1 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-001-005 | 018-E-GAD-00003-005 | 018E1001 TRAIN 1 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-002-001 | 018-E-GAD-00004-001 | 018E1002 TRAIN 1 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-002-002 | 018-E-GAD-00004-002 | 018E1002 TRAIN 1 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-002-003 | 018-E-GAD-00004-003 | 018E1002 TRAIN 1 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-002-004 | 018-E-GAD-00004-004 | 018E1002 TRAIN 1 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-002-005 | 018-E-GAD-00004-005 | 018E1002 TRAIN 1 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-003-001 | 018-E-GAD-00005-001 | 018E1003 TRAIN 1 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-003-002 | 018-E-GAD-00005-002 | 018E1003 TRAIN 1 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-003-003 | 018-E-GAD-00005-003 | 018E1003 TRAIN 1 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-003-004 | 018-E-GAD-00005-004 | 018E1003 TRAIN 1 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-003-005 | 018-E-GAD-00005-005 | 018E1003 TRAIN 1 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-004-001 | 018-E-GAD-00006-001 | 018E1004 TRAIN 1 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-004-002 | 018-E-GAD-00006-002 | 018E1004 TRAIN 1 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-004-003 | 018-E-GAD-00006-003 | 018E1004 TRAIN 1 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-004-004 | 018-E-GAD-00006-004 | 018E1004 TRAIN 1 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-004-005 | 018-E-GAD-00006-005 | 018E1004 TRAIN 1 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-007-001 | 018-E-GAD-00007-001 | 018E1006 TRAIN 1 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-007-002 | 018-E-GAD-00007-002 | 018E1006 TRAIN 1 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-007-003 | 018-E-GAD-00007-003 | 018E1006 TRAIN 1 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-007-004 | 018-E-GAD-00007-004 | 018E1006 TRAIN 1 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-007-005 | 018-E-GAD-00007-005 | 018E1006 TRAIN 1 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-008-001 | 018-E-GAD-00008-001 | 018E1007 TRAIN 1 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-008-002 | 018-E-GAD-00008-002 | 018E1007 TRAIN 1 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-008-003 | 018-E-GAD-00008-003 | 018E1007 TRAIN 1 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-008-004 | 018-E-GAD-00008-004 | 018E1007 TRAIN 1 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-008-005 | 018-E-GAD-00008-005 | 018E1007 TRAIN 1 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-014-001 | 018-E-GAD-00009-001 | 018E2001 TRAIN 2 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-014-002 | 018-E-GAD-00009-002 | 018E2001 TRAIN 2 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-014-003 | 018-E-GAD-00009-003 | 018E2001 TRAIN 2 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-014-004 | 018-E-GAD-00009-004 | 018E2001 TRAIN 2 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-014-005 | 018-E-GAD-00009-005 | 018E2001 TRAIN 2 - RG + H2 PREHEAT EXCHANGER NO 2 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-015-001 | 018-E-GAD-00010-001 | 018E2002 TRAIN 2 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-015-002 | 018-E-GAD-00010-002 | 018E2002 TRAIN 2 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-015-003 | 018-E-GAD-00010-003 | 018E2002 TRAIN 2 - FEED PREHEAT EXCHANGER | A | 2018-06-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-015-004 | 018-E-GAD-00010-004 | 018E2002 TRAIN 2 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-015-005 | 018-E-GAD-00010-005 | 018E2002 TRAIN 2 - FEED PREHEAT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-016-001 | 018-E-GAD-00011-001 | 018E2003 TRAIN 2 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-016-002 | 018-E-GAD-00011-002 | 018E2003 TRAIN 2 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-016-003 | 018-E-GAD-00011-003 | 018E2003 TRAIN 2 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-016-004 | 018-E-GAD-00011-004 | 018E2003 TRAIN 2 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-016-005 | 018-E-GAD-00011-005 | 018E2003 TRAIN 2 - RG+H2 PREHEAT EXCHANGER NO 1 | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-017-001 | 018-E-GAD-00012-001 | 018E2004 TRAIN 2 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-017-002 | 018-E-GAD-00012-002 | 018E2004 TRAIN 2 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-017-003 | 018-E-GAD-00012-003 | 018E2004 TRAIN 2 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-017-004 | 018-E-GAD-00012-004 | 018E2004 TRAIN 2 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-017-005 | 018-E-GAD-00012-005 | 018E2004 TRAIN 2 - HP/HT STEAM GENERATOR | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-018-001 | 018-E-GAD-00001-001 | 018E2006 TRAIN 2 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-018-002 | 018-E-GAD-00001-002 | 018E2006 TRAIN 2 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-018-003 | 018-E-GAD-00001-003 | 018E2006 TRAIN 2 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-018-004 | 018-E-GAD-00001-004 | 018E2006 TRAIN 2 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-018-005 | 018-E-GAD-00001-005 | 018E2006 TRAIN 2 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-019-001 | 018-E-GAD-00002-001 | 018E2007 TRAIN 2 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-019-002 | 018-E-GAD-00002-002 | 018E2007 TRAIN 2 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-019-003 | 018-E-GAD-00002-003 | 018E2007 TRAIN 2 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-019-004 | 018-E-GAD-00002-004 | 018E2007 TRAIN 2 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-018-DW-0610-019-005 | 018-E-GAD-00002-005 | 018E2007 TRAIN 2 - MEMBRANE FEED HEATER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-003-001 | 021-E-GAD-00003-001 | 021E0006 A/B REACTOR EFFLUENT/FEED COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-003-002 | 021-E-GAD-00003-002 | 021E0006 A/B REACTOR EFFLUENT/FEED COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-003-003 | 021-E-GAD-00003-003 | 021E0006 A/B REACTOR EFFLUENT/FEED COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-003-004 | 021-E-GAD-00003-004 | 021E0006 A/B REACTOR EFFLUENT/FEED COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-003-005 | 021-E-GAD-00003-005 | 021E0006 A/B REACTOR EFFLUENT/FEED COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-004-001 | 021-E-GAD-00004-001 | 021E0004 A/B REACTOR EFFLUENT/FEED HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-004-002 | 021-E-GAD-00004-002 | 021E0004 A/B REACTOR EFFLUENT/FEED HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-004-003 | 021-E-GAD-00004-003 | 021E0004 A/B REACTOR EFFLUENT/FEED HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-004-004 | 021-E-GAD-00004-004 | 021E0004 A/B REACTOR EFFLUENT/FEED HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-004-005 | 021-E-GAD-00004-005 | 021E0004 A/B REACTOR EFFLUENT/FEED HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-005-001 | 021-E-GAD-00005-001 | 021E0003 REACTOR EFFLUENT/RECYCLE GAS HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-005-002 | 021-E-GAD-00005-002 | 021E0003 REACTOR EFFLUENT/RECYCLE GAS HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-005-003 | 021-E-GAD-00005-003 | 021E0003 REACTOR EFFLUENT/RECYCLE GAS HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-005-004 | 021-E-GAD-00005-004 | 021E0003 REACTOR EFFLUENT/RECYCLE GAS HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-005-005 | 021-E-GAD-00005-005 | 021E0003 REACTOR EFFLUENT/RECYCLE GAS HOT EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-006-001 | 021-E-GAD-00006-001 | 021E0005 REACTOR EFFLUENT/RECYCLE GAS COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-006-002 | 021-E-GAD-00006-002 | 021E0005 REACTOR EFFLUENT/RECYCLE GAS COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-006-003 | 021-E-GAD-00006-003 | 021E0005 REACTOR EFFLUENT/RECYCLE GAS COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-006-004 | 021-E-GAD-00006-004 | 021E0005 REACTOR EFFLUENT/RECYCLE GAS COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-006-005 | 021-E-GAD-00006-005 | 021E0005 REACTOR EFFLUENT/RECYCLE GAS COLD EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-007-001 | 021-E-GAD-00007-001 | 021E0007 HHPS VAPOR/FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-007-002 | 021-E-GAD-00007-002 | 021E0007 HHPS VAPOR/FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-007-003 | 021-E-GAD-00007-003 | 021E0007 HHPS VAPOR/FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-007-004 | 021-E-GAD-00007-004 | 021E0007 HHPS VAPOR/FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-007-005 | 021-E-GAD-00007-005 | 021E0007 HHPS VAPOR/FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-008-001 | 021-E-GAD-00002-001 | 021E0008 HHPS VAPOR/RECYCLE GAS EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-008-002 | 021-E-GAD-00002-002 | 021E0008 HHPS VAPOR/RECYCLE GAS EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-008-003 | 021-E-GAD-00002-003 | 021E0008 HHPS VAPOR/RECYCLE GAS EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-008-004 | 021-E-GAD-00002-004 | 021E0008 HHPS VAPOR/RECYCLE GAS EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-008-005 | 021-E-GAD-00002-005 | 021E0008 HHPS VAPOR/RECYCLE GAS EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-009-001 | 021-E-GAD-00001-001 | 021E0009 HHPS VAPOR/STRIPPER FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-009-002 | 021-E-GAD-00001-002 | 021E0009 HHPS VAPOR/STRIPPER FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-009-003 | 021-E-GAD-00001-003 | 021E0009 HHPS VAPOR/STRIPPER FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-009-004 | 021-E-GAD-00001-004 | 021E0009 HHPS VAPOR/STRIPPER FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00258 | 076551C-021-DW-0610-009-005 | 021-E-GAD-00001-005 | 021E0009 HHPS VAPOR/STRIPPER FEED EXCHANGER | A | 2018-06-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00266 | 076551C-000S-DL-0113-001 | 000-F-IDL-80001-001 | DEVIATION LIST FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | 076551C-000S-ITP-0113-001 | 000-F-ITP-80001-001 | INSPECTION AND TEST PLAN FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | 076551C-000S-MR-0113-001 | 000-F-MRQ-80001-001 | MATERIAL REQUISITION FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | 076551C-000S-SP-0113-001 | 000-F-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | 076551C-000S-SR-0113-001 | 000-F-SOW-80001-001 | SCOPE OF SUPPLY FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | SO6001-EJ1E-TDS-09800007-001 | 098-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 098F0001 REFORMING FURNACE | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | SO6001-EJ1E-TDS-09800008-001 | 098-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 098V0004 STEAM DRUM | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | SO6001-EJ1E-TDS-09800009-001 | 098-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 098E0001 PROCESS GAS BOILER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | SO6001-EJ1E-TDS-09800010-001 | 098-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 098F0001 REFORMING FURNACE BURNERS | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | SO6001-EJ1E-TDS-09900007-001 | 099-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 099F0001 REFORMING FURNACE | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | SO6001-EJ1E-TDS-09900008-001 | 099-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 099V0004 STEAM DRUM | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | SO6001-EJ1E-TDS-09900009-001 | 099-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 099E0001 PROCESS GAS BOILER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00266 | SO6001-EJ1E-TDS-09900010-001 | 099-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 099F00011 REFORMING FURNACE BURNERS | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00267 | 076551C-000S-DL-0140-001 | 000-F-IDL-80003-001 | DEVIATION LIST FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00267 | 076551C-000S-ITP-0140-001 | 000-F-ITP-80003-001 | INSPECTION AND TEST PLAN FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00267 | 076551C-000S-MR-0140-001 | 000-F-MRQ-80003-001 | MATERIAL REQUISITION FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00267 | 076551C-000S-SP-0140-001 | 000-F-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00267 | 076551C-000S-SR-0140-001 | 000-F-SOW-80003-001 | SCOPE OF SUPPLY FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00267 | SO6001-EJ1E-TDS-04400007-001 | 044-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 044U4401 | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00267 | SO6001-EJ1E-TDS-04500007-001 | 045-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 045U4501 | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00268 | 076551C-000S-DL-0150-001 | 000-F-IDL-80004-001 | DEVIATION LIST FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00268 | 076551C-000S-ITP-0150-001 | 000-F-ITP-80004-001 | INSPECTION AND TEST PLAN FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00268 | 076551C-000S-MR-0150-001 | 000-F-MRQ-80004-001 | MATERIAL REQUISITION FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00268 | 076551C-000S-SP-0150-001 | 000-F-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00268 | 076551C-000S-SR-0150-001 | 000-F-SOW-80004-001 | SCOPE OF SUPPLY FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00268 | SO6001-EJ1E-TDS-31000001-001 | 310-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 310F0001 AUXILIARY STEAM BOILER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00268 | SO6001-EJ1E-TDS-31100001-001 | 311-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 311F0001 AUXILIARY STEAM BOILER | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00295 | 076551C-000M-DL-0811-001 | 000-C-IDL-70003-001 | DEVIATION LIST FOR STAINLESS STEEL & CLAD VESSELS | A | 2018-06-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00295 | 076551C-000M-ITP-0811-001 | 000-C-ITP-70003-001 | INSPECTION AND TEST PLAN (ITP) FOR STAINLESS STEEL & CLAD VESSELS | A | 2018-06-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00295 | 076551C-000M-MR-0811-001 | 000-C-MRQ-70003-001 | MATERIAL REQUISITION FOR STAINLESS STEEL & CLAD VESSELS | A | 2018-06-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00295 | 076551C-000M-SP-0811-001 | 000-C-GRD-70003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR STAINLESS STEEL & CLAD VESSELS | A | 2018-06-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00295 | 076551C-000M-SR-0811-001 | 000-C-SOW-70003-001 | SCOPE OF SUPPLY FOR STAINLESS STEEL & CLAD VESSELS | A | 2018-06-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00319 | 076551C-000M-DL-1011-002 | 000-K-IDL-70007-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSORS UNIT 012 AND 017 | A | 2018-07-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00319 | 076551C-000M-ITP-1011-002 | 000-K-ITP-70007-001 | INSPECTION AND TEST PLAN FOR CENTRIFUGAL COMPRESSORS UNIT 012 AND 017 | A | 2018-07-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00319 | 076551C-000M-MR-1011-002 | 000-K-MRQ-70007-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSORS UNIT 012 AND 017 | A | 2018-07-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00319 | 076551C-000M-SP-1011-002 | 000-K-GRD-70007-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSORS UNIT 012 AND 017 | A | 2018-07-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00319 | 076551C-000M-SR-1011-002 | 000-K-SOW-70007-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSORS UNIT 012 AND 017 | A | 2018-07-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00328 | 076551C-000S-DL-0411-001 | 000-C-IDL-80004-001 | DEVIATION LIST FOR REACTORS | A | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00328 | 076551C-000S-ITP-0411-001 | 000-C-ITP-80004-001 | INSPECTION AND TEST PLAN FOR REACTORS | A | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00328 | 076551C-000S-MR-0411-001 | 000-C-MRQ-80004-001 | MATERIAL REQUISITION FOR REACTORS | A | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00328 | 076551C-000S-SP-0411-001 | 000-C-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR REACTORS | A | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00328 | 076551C-000S-SR-0411-001 | 000-C-SOW-80004-001 | SCOPE OF SUPPLY FOR REACTORS | A | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00329 | 076551C-000S-DL-0119-004 | 000-F-IDL-80002-001 | DEVIATION LIST FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00329 | 076551C-000S-ITP-0119-004 | 000-F-ITP-80002-001 | INSPECTION AND TEST PLAN FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00329 | 076551C-000S-MR-0119-004 | 000-F-MRQ-80002-001 | MATERIAL REQUISITION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00329 | 076551C-000S-SP-0119-004 | 000-F-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00329 | 076551C-000S-SR-0119-004 | 000-F-SOW-80002-001 | SCOPE OF SUPPLY FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00330 | 076551C-000S-DL-4112-001 | 000-S-IDL-80008-001 | DEVIATION LIST FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00330 | 076551C-000S-ITP-4112-001 | 000-S-ITP-80008-001 | INSPECTION AND TEST PLAN FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00330 | 076551C-000S-MR-4112-001 | 000-S-MRQ-80008-001 | MATERIAL REQUISITION FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00330 | 076551C-000S-SP-4112-001 | 000-S-GRD-80008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00330 | 076551C-000S-SR-4112-001 | 000-S-SOW-80008-001 | SCOPE OF SUPPLY FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00382 | 076551C-000S-DL-0215-001 | 000-S-IDL-80002-001 | DEVIATION LIST FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00382 | 076551C-000S-ITP-0215-001 | 000-S-ITP-80002-001 | INSPECTION AND TEST PLAN FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00382 | 076551C-000S-MR-0215-001 | 000-S-MRQ-80002-001 | MATERIAL REQUISITION FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00382 | 076551C-000S-SP-0215-001 | 000-S-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00382 | 076551C-000S-SR-0215-001 | 000-S-SOW-80002-001 | SCOPE OF SUPPLY FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00383 | 076551C-000S-DL-4010-001 | 000-S-IDL-80003-001 | DEVIATION LIST FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00383 | 076551C-000S-ITP-4010-001 | 000-S-ITP-80003-001 | INSPECTION AND TEST PLAN FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00383 | 076551C-000S-MR-4010-001 | 000-S-MRQ-80003-001 | MATERIAL REQUISITION FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00383 | 076551C-000S-SP-4010-001 | 000-S-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00383 | 076551C-000S-SR-4010-001 | 000-S-SOW-80003-001 | SCOPE OF SUPPLY FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00384 | 076551C-000S-DL-4352-001 | 000-S-IDL-80010-001 | LIST OF DEVIATION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00384 | 076551C-000S-ITP-4352-001 | 000-S-ITP-80010-001 | INSPECTION AND TESTS PLAN FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00384 | 076551C-000S-MR-4352-001 | 000-S-MRQ-80010-001 | MATERIAL REQUISITION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00384 | 076551C-000S-SP-4352-001 | 000-S-GRD-80010-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00384 | 076551C-000S-SR-4352-001 | 000-S-SOW-80010-001 | SCOPE OF SUPPLY FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-TRA-000001 | 076551C-000D-PP-101 | 000-A-PRO-50001-001 | PROJECT EXECUTION PLAN | A | 2018-03-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3 - REVIEWED WITH COMMENTS | 2018-03-28 | CLASS 1
CON-BMP-TRA-000001 | 076551C-000D-PP-102 | 000-A-PRO-50002-001 | COORDINATION PROCEDURE BETWEEN THE BAHRAIN PETROLEUM COMPANY B.S.C. (CLOSED) BAPCO AND TTSJV | A | 2018-03-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-03 | CLASS 1
CON-BMP-TRA-000001 | 076551C-000D-PP-124 | 000-A-PRO-50018-001 | TTSJV ENGINEERING MANAGEMENT PLAN | A | 2018-03-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3 - REVIEWED WITH COMMENTS | 2018-03-28 | CLASS 1
CON-BMP-TRA-000002 | 076551C-000D-PP-107 | 000-A-PRO-50005-001 | PROJECT DOCUMENT CODING | A | 2018-03-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3 - REVIEWED WITH COMMENTS | 2018-03-28 | CLASS 1
CON-BMP-TRA-000002 | 076551C-000D-PP-110 | 000-A-PRO-50008-001 | DOCUMENT ISSUE DISTRIBUTION TO AND APPROVAL BY BAPCO | A | 2018-03-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3 - REVIEWED WITH COMMENTS | 2018-03-28 | CLASS 1
CON-BMP-TRA-000004 | 076551C-000D-SL-0811-001 | 000-A-INX-50001-001 | BIDDERS LIST FOR HP VESSELS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  | 1 - APPROVED | 2018-04-17 | CLASS 3
CON-BMP-TRA-000004 | 076551C-000D-SL-0910-004 | 000-A-INX-50002-001 | BIDDERS LIST FOR BB5 CENTRIFUGAL PUMPS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  | 1 - APPROVED | 2018-04-17 | CLASS 3
CON-BMP-TRA-000004 | 076551C-000D-SL-1011-001 | 000-A-INX-50003-001 | BIDDERS LIST FOR BB5 CENTRIFUGAL COMPRESSORS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  | 1 - APPROVED | 2018-04-17 | CLASS 3
CON-BMP-TRA-000004 | 076551C-000D-SL-1020-001 | 000-A-INX-50004-001 | BIDDERS LIST FOR RECIPROCATING COMPRESSORS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  | 1 - APPROVED | 2018-04-17 | CLASS 3
CON-BMP-TRA-000005 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE | 0 | 2018-03-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-03-28 | CLASS 3
CON-BMP-TRA-000006 | 076551C-000D-PP-015 | 000-A-PRI-50011-001 | PRESCRIPTIONS FOR PREPARATION OF MANUFACTURING DATA RECORD BOOK (MDRB) | A | 2018-03-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 2
CON-BMP-TRA-000007 | 076551C-000D-PP-601 | 000-A-PRO-50045-001 | PROCUREMENT EXECUTION PLAN | A | 2018-03-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 3 - REVIEWED WITH COMMENTS | 2018-04-12 | CLASS 2
CON-BMP-TRA-000007 | 076551C-000D-PP-605 | 000-A-PRI-50006-001 | QA QC/INSPECTION AND EXPEDITING REQUIREMENTS FOR VENDORS | A | 2018-03-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 3 - REVIEWED WITH COMMENTS | 2018-04-12 | CLASS 2
CON-BMP-TRA-000008 | 076551C-000D-PP-104 | 000-A-PRO-50003-001 | COORDINATION PROCEDURE AMONG THE BAHRAIN PETROLEUM COMPANY B.S.C. (CLOSED) BAPCO AND TTSJV AND LICENSORS | A | 2018-03-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-04 | CLASS 2
CON-BMP-TRA-000009 | 076551C-000D-PP-401 | 000-A-PRO-50037-001 | INVOICING PROCEDURE | A | 2018-03-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-03 | 3 - REVIEWED WITH COMMENTS | 2018-03-30 | CLASS 1
CON-BMP-TRA-000010 | 076551C-000D-PLG-102 | 000-A-PMP-50001-001 | WORK BREAKDOWN STRUCTURE | A | 2018-03-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-04 | 3 - REVIEWED WITH COMMENTS | 2018-03-30 | CLASS 1
CON-BMP-TRA-000011 | 076551C-000D-PP-100 | 000-A-ORG-50001-001 | TTSJV PROJECT ORGANIZATION CHART | 0 | 2018-03-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000012 | 076551C-000D-RR-1001 | 000-A-RPT-50001-001 | WEEKLY PROGRESS REPORT N.01 AS OF MARCH 16TH, 2018 (WEEK 03) | 0 | 2018-03-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000013 | 076551C-000D-SL-0113-001 | 000-A-INX-50006-001 | BIDDERS LIST FOR HYDROGEN STEAM REFORMER | 0 | 2018-03-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000013 | 076551C-000D-SL-0470-001 | 000-A-INX-50008-001 | BIDDERS LIST FOR HCU REACTOR INTERNALS | 0 | 2018-03-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000013 | 076551C-000D-SL-4141-001 | 000-A-INX-50012-001 | BIDDERS LIST FOR DESALTER PACKAGE | 0 | 2018-03-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000014 | 076551C-000D-PP-551 | 000-A-PRO-50041-001 | PROJECT HSSE PLAN | A | 2018-03-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 2
CON-BMP-TRA-000015 | 076551C-000D-PP-108 | 000-A-PRO-50006-001 | HOMOGENIZATION PROCEDURE | A | 2018-03-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-04 | CLASS 2
CON-BMP-TRA-000016 | 076551C-000D-PP-500 | 000-A-PRO-50039-001 | OVERALL PROJECT QUALITY PLAN | A | 2018-03-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-000016 | 076551C-000D-PP-502 | 000-A-PRO-50040-001 | CONFIDENTIALITY PLAN | A | 2018-03-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-000017 | 076551C-000D-SL-0960-001 | 000-A-INX-50005-001 | BIDDERS LIST FOR EBULLATING PUMPS | 0 | 2018-03-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000018 | 076551C-000D-PP-111 | 000-A-PRO-50009-001 | REPORTING PROCEDURE | A | 2018-03-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-000019 | 076551C-000D-RR-1002 | 000-A-RPT-50002-001 | WEEKLY PROGRESS REPORT N.02 AS OF MARCH 23RD, 2018 (WEEK 04) | 0 | 2018-03-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000020 | 076551C-000D-PP-610 | 000-A-PRI-50002-001 | VENDOR PRE-QUALIFICATION PROCEDURE | A | 2018-03-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-18 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-000021 | 076551C-000D-SL-0110-001 | 000-A-INX-50013-001 | BIDDERS LIST FOR HCU HEATERS LICENSED FIRED HEATERS (RHCU) | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000021 | 076551C-000D-SL-0215-001 | 000-A-INX-50014-001 | BIDDERS LIST FOR MULTI EFFECT DESALINATION PACKAGE | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000021 | 076551C-000D-SL-0710-002 | 000-A-INX-50011-001 | BIDDERS LIST FOR AIR COOLERS | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000021 | 076551C-000D-SL-4010-001 | 000-A-INX-50015-001 | BIDDERS LIST FOR BMP SOLID SULPHUR HANDLING PACKAGE | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000021 | 076551C-000D-SL-4352-001 | 000-A-INX-50016-001 | BIDDERS LIST FOR BMP SOLIDIFICATION PACKAGE | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000022 | 076551C-000D-PP-261 | 000-A-PRI-50012-001 | REQUIREMENTS FOR EQUIPMENT SUPPLIER 3D MODEL | A | 2018-03-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-17 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 2
CON-BMP-TRA-000023 | 076551C-000D-RR-1002 | 000-A-RPT-50002-001 | WEEKLY PROGRESS REPORT N.02 AS OF MARCH 23RD, 2018 (WEEK 04) | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000024 | 076551C-000D-PP-128 | 000-A-PRO-50019-001 | PROJECT INTERFACE MANAGEMENT PLAN | A | 2018-03-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-17 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 2
CON-BMP-TRA-000025 | 076551C-000D-RR-1003 | 000-A-RPT-50003-001 | WEEKLY PROGRESS REPORT N.03 AS OF MARCH 30TH, 2018 (WEEK 005) | 0 | 2018-04-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000026 | 076551C-000D-PP-121 | 000-A-PRO-50015-001 | DEVIATION WAIVER AND TECHNICAL QUERY REQUEST PROCEDURE | A | 2018-04-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-19 | 3 - REVIEWED WITH COMMENTS | 2018-04-19 | CLASS 2
CON-BMP-TRA-000027 | 076551C-000D-PP-101 | 000-A-PRO-50001-001 | PROJECT EXECUTION PLAN | B | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 4 - NOT APPROVED | 2018-05-03 | CLASS 1
CON-BMP-TRA-000028 | 076551C-000D-PP-401 | 000-A-PRO-50037-001 | INVOICING PROCEDURE | B | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-30 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-000029 | 076551C-000D-PP-307 | 000-A-PRO-50036-001 | VARIATION PROCEDURE | A | 2018-04-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-20 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 2
CON-BMP-TRA-000030 | 076551C-000D-PP-301 | 000-A-PRO-50031-001 | PLANNING AND SCHEDULING PROCEDURE | A | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-000031 | 076551C-000D-SL-0570-001 | 000-A-INX-50010-001 | BIDDERS LIST FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | 0 | 2018-04-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000032 | 076551C-000D-NM-0000-001 | 000-A-PLD-50001-001 | ENGINEERING DELIVERABLE LIST | A | 2018-04-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-18 | CLASS 2
CON-BMP-TRA-000032-REV.1 | 076551C-000D-NM-0000-001 | 000-A-PLD-50001-001 | ENGINEERING DELIVERABLE LIST | A | 2018-05-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-18 | CLASS 2
CON-BMP-TRA-000033 | 076551C-000D-SL-0411-001 | 000-A-INX-50020-001 | BIDDERS LIST FOR 2.25CR-1MO-V REACTORS AND INTERNALS | 0 | 2018-04-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000033 | 076551C-000D-SL-0610-001 | 000-A-INX-50018-001 | BIDDERS LIST FOR HP S&T HEAT EXCHANGERS | 0 | 2018-04-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000033 | 076551C-000D-SL-0710-002 | 000-A-INX-50011-001 | BIDDERS LIST FOR AIR COOLERS | 0A | 2018-04-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000033 | 076551C-000D-SL-1013-001 | 000-A-INX-50019-001 | BIDDERS LIST FOR INTEGRALLY GEARED AIR COMPRESSOR | 0 | 2018-04-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000034 | 076551C-000D-PP-564 | 000-A-PRI-50004-001 | HSSE REQUIREMENTS FOR VENDORS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 2
CON-BMP-TRA-000035 | 076551C-000D-PLG-303 | 000-A-SCH-50002-001 | LEVEL 1 PROJECT CONTRACT SCHEDULE AS OF 30-MARCH-2018 | 0 | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-000036 | 076551C-000D-PP-312 | 000-A-PRO-50073-001 | PROGRESS MEASUREMENT AND MILESTONE CERTIFICATE PROCEDURE | A | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-18 | CLASS 2
CON-BMP-TRA-000037 | 076551C-000D-RR-1004 | 000-A-RPT-50004-001 | WEEKLY PROGRESS REPORT N.04 AS OF APRIL 6TH, 2018 (WEEK 006) | 0 | 2018-04-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000038 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE | 0A | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 |  |  | CLASS 3
CON-BMP-TRA-000039 | 076551C-000D-RR-101 | 000-A-MRS-50001-001 | MONTHLY PROGRESS REPORT N.01 AS OF MARCH 30TH, 2018 (MONTH 01) | 0 | 2018-04-11 | FOR BAPCO INFORMATION | BMP Project Director | 2018-04-27 |  |  | CLASS 2
CON-BMP-TRA-000040 | 076551C-000D-SL-0110-002 | 000-A-INX-50017-001 | BIDDERS LIST FOR FIRED HEATERS CDU/VDU | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000040 | 076551C-000D-SL-0119-004 | 000-A-INX-50021-001 | BIDDERS LIST FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000040 | 076551C-000D-SL-0140-001 | 000-A-INX-50022-001 | BIDDERS LIST FOR INCINERATOR PACKAGE | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000040 | 076551C-000D-SL-0150-001 | 000-A-INX-50023-001 | BIDDERS LIST FOR AUXILIARY STEAM BOILERS | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000040 | 076551C-000D-SL-0411-001 | 000-A-INX-50020-001 | BIDDERS LIST FOR 2.25CR-1MO-V REACTORS AND INTERNALS | 0A | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000041 | 076551C-000D-SL-0310-001 | 000-A-INX-50025-001 | BIDDERS LIST FOR INDUCED DRAFT COOLING TOWER | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000042 | 076551C-000D-PP-500 | 000-A-PRO-50039-001 | OVERALL PROJECT QUALITY PLAN | B | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-20 | CLASS 1
CON-BMP-TRA-000043 | 076551C-000D-PP-502 | 000-A-PRO-50040-001 | CONFIDENTIALITY PLAN | 0 | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-000044 | 076551C-000D-PP-256 | 000-A-PRO-50027-001 | 3D MODELLING CIVIL PROCEDURE | A | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 4 - NOT APPROVED | 2018-05-03 | CLASS 2
CON-BMP-TRA-000045 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF APRIL 13TH - WEEK 007 | 0B | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000046 | 076551C-000D-RR-1005 | 000-A-RPT-50005-001 | WEEKLY PROGRESS REPORT N.05 AS OF APRIL 13TH, 2018 (WEEK 007) | 0 | 2018-04-17 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000047 | 076551C-000D-PP-111 | 000-A-PRO-50009-001 | REPORTING PROCEDURE | 0 | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director | 2018-05-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-000048 | 076551C-000D-SL-0846-001 | 000-A-INX-50033-001 | BIDDERS LIST FOR FEED FILTERS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000049 | 076551C-000D-SL-1410-001 | 000-A-INX-50024-001 | BIDDERS LIST FOR ADDITIONL SOIL INVESTIGATION | 0 | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000050 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF APRIL 20TH - WEEK 008 | 0C | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 |  |  | CLASS 3
CON-BMP-TRA-000051 | 076551C-000D-PP-104 | 000-A-PRO-50003-001 | COORDINATION PROCEDURE AMONG THE BAHRAIN PETROLEUM COMPANY B.S.C. (CLOSED) BAPCO AND TTSJV AND LICENSORS | B | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-000052 | 076551C-000D-SL-0511-001 | 000-A-INX-50035-001 | BIDDERS LIST FOR CS COLUMNS | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-0511-002 | 000-A-INX-50009-001 | BIDDERS LIST FOR CLADDED COLUMNS (LLI) | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-0848-002 | 000-A-INX-50030-001 | BIDDERS LIST FOR CALCITE BED PACKAGE | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-0910-005 | 000-A-INX-50031-001 | BIDDERS LIST FOR API 610 HIGH SPEED PUMPS | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-4112-001 | 000-A-INX-50029-001 | BIDDERS LIST FOR NITROGEN GENERATION STORAGE AND VAPORIZATION | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-4171-001 | 000-A-INX-50036-001 | BIDDERS LIST FOR AIR DRYERS PACKAGE | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000053 | 076551C-000D-RR-1006 | 000-A-RPT-50006-001 | WEEKLY PROGRESS REPORT N.06 AS OF APRIL 20TH, 2018 (WEEK 008) | 0 | 2018-04-24 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000054 | 076551C-000D-JSS-1300-001 | 000-L-TSP-50001-001 | GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-000054 | 076551C-000D-JSS-1310-001 | 000-L-TSP-50004-001 | JOB SUPPLY SPECIFICATION FOR VALVES (GATE - GLOBE - CHECK) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-000054 | 076551C-000D-JSS-1320-001 | 000-L-TSP-50008-001 | JOB SUPPLY SPECIFICATION FOR PIPES | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-000054 | 076551C-000D-JSS-1330-001 | 000-L-TSP-50010-001 | JOB SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-000054 | 076551C-000D-JSS-1350-001 | 000-L-TSP-50012-001 | JOB SUPPLY SPECIFICATION FOR FLANGES | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-000055 | CON-BMP-MOM-000013 | 000-A-MOM-50001-001 | SPPID REVIEW MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000014 | 000-A-MOM-50002-001 | S3D REVIEW MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000015 | 000-A-MOM-50003-001 | WEEKLY PROGRESS MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000016 | 000-A-MOM-50004-001 | WEEKLY PROGRESS MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000017 | 000-A-MOM-50005-001 | 1ST PROCUREMENT WEEKLY MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000018 | 000-A-MOM-50006-001 | SPEL CAP ANALYSIS REVIEW | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000019 | 000-A-MOM-50007-001 | WEEKLY PROGRESS MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000020 | 000-A-MOM-50008-001 | PROJECT CONTROL MEETING N 1 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000022 | 000-A-MOM-50009-001 | ESAP ITEMS REVIEW MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000023 | 000-A-MOM-50010-001 | PROCUREMENT WEEKLY MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000024 | 000-A-MOM-50011-001 | ESIA FOLLOW UP KOM | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000025 | 000-A-MOM-50012-001 | 3RD PROCUREMENT WEEKLY MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000026 | 000-A-MOM-50013-001 | WEEKLY PROGRESS MEETING N 4 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000028 | 000-A-MOM-50014-001 | PROJECT CONTROL MEETING N 2 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000029 | 000-A-MOM-50015-001 | PROJECT CONTROL MEETING N 3 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000030 | 000-A-MOM-50016-001 | INSTRUMENTATION TAGGING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000031 | 000-A-MOM-50017-001 | MONTHLY MEETING N 1 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000056 | 076551C-000D-PP-264 | 000-A-PRO-50077-001 | PIPING MATERIAL MANAGEMENT PROCEDURE | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-000057 | 076551C-000D-PP-401 | 000-A-PRO-50037-001 | INVOICING PROCEDURE | C | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-000058 | 076551C-000D-SL-0710-001 | 000-A-INX-50027-001 | BIDDERS LIST FOR HP AND SPECIAL MATERIAL AIR COOLERS | 0 | 2018-05-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000058 | 076551C-000D-SL-0840-002 | 000-A-INX-50037-001 | BIDDERS LIST FOR SIDE STREAM FILTERS | 0 | 2018-05-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000058 | 076551C-000D-SL-0910-003 | 000-A-INX-50034-001 | BIDDERS LIST FOR BB1 BB2 AND BB3 PUMPS | 0 | 2018-05-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000059 | 076551C-000D-PP-109 | 000-A-PRO-50007-001 | COMMENT MANAGEMENT PROCEDURE | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 3 - REVIEWED WITH COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-000060 | 076551C-000D-PP-853 | 000-A-PRI-50009-001 | HSSE REQUIREMENTS FOR SUBCONTRACTORS | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-000061 | 076551C-000D-PP-804 | 000-A-PRO-50052-001 | CONSTRUCTION EXECUTION PLAN | A | 2018-05-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-17 | 4 - NOT APPROVED | 2018-05-16 | CLASS 1
CON-BMP-TRA-000062 | 076551C-000D-SL-1430-005 | 000-A-INX-50040-001 | BIDDERS LIST FOR OVERALL PILING WARKS | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-22 | CLASS 3
CON-BMP-TRA-000062 | 076551C-000D-SL-8200-015 | 000-A-INX-50039-001 | BIDDERS LIST FOR TEMPORARY CONTRUCTION FACILITIES | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-22 | CLASS 3
CON-BMP-TRA-000063 | 076551C-000D-PLG-102 | 000-A-PMP-50001-001 | WORK BREAKDOWN STRUCTURE | B | 2018-05-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-000064 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF APRIL 27TH - WEEK 009 | 0D | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000065 | 076551C-000D-PP-500 | 000-A-PRO-50039-001 | OVERALL PROJECT QUALITY PLAN | 0 | 2018-05-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-18 |  |  | CLASS 1
CON-BMP-TRA-000066 | 076551C-000D-PP-505 | 000-A-PRO-50078-001 | PROJECT AUDIT PROCEDURE | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-000066 | 076551C-000D-PP-506 | 000-A-PRO-50079-001 | NON CONFORMANCE CONTROL PROCEDURE | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-000067 | 076551C-000D-SL-0411-002 | 000-A-INX-50026-001 | BIDDERS LIST FOR SEPARATOR CR-MB | 0 | 2018-05-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000067 | 076551C-000D-SL-0851-001 | 000-A-INX-50032-001 | BIDDERS LIST FOR VACUUM UNIT PACKAGE | 0 | 2018-05-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000067 | 076551C-000D-SL-0910-007 | 000-A-INX-50038-001 | BIDDERS LIST FOR SULPHUR TRANSFER PUMPS | 0 | 2018-05-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000068 | 076551C-000D-RR-1007 | 000-A-RPT-50007-001 | WEEKLY PROGRESS REPORT N.07 AS OF APRIL 27TH, 2018 (WEEK 009) | 0 | 2018-05-04 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000069 | 076551C-000D-PP-609 | 000-A-PRO-50013-001 | INSPECTION PROCEDURE | A | 2018-05-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-000070 | 076551C-000D-PP-611 | 000-A-PRO-50074-001 | PROJECT EXPEDITING PROCEDURE | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-000071 | 076551C-000D-PP-605 | 000-A-PRI-50006-001 | QA QC/INSPECTION AND EXPEDITING REQUIREMENTS FOR VENDORS | B | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 1 - APPROVED | 2018-05-15 | CLASS 2
CON-BMP-TRA-000072 | 076551C-000D-PP-014 | 000-A-PRI-50001-001 | REQUIREMENTS FOR VENDOR DOCUMENTATION AND EXCHANGE OF CORRESPONDENCE | A | 2018-05-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-000073 | 076551C-000D-PP-015 | 000-A-PRI-50011-001 | PRESCRIPTIONS FOR PREPARATION OF QUALITY CONTROL MANUFACTURING DOSSIER (QCMD) | B | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 2
CON-BMP-TRA-000074 | 076551C-000D-PP-856 | 000-A-PRO-50075-001 | HSSE TRAINING PLAN | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-24 | CLASS 2
CON-BMP-TRA-000075 | CON-BMP-MOM-000027 | 000-A-MOM-50018-001 | SPF GAP ANALISYS REVIEW | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000032 | 000-A-MOM-50019-001 | EXTERNAL INTERFACES WITH EWA | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000033 | 000-A-MOM-50020-001 | INTERFACE MEETING WITH BAPCO CLIENT N.1 | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000035 | 000-A-MOM-50021-001 | PROJECT CONTROL MEETING N¿04 | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000038 | 000-A-MOM-50022-001 | 4TH PROCUREMENT WEEKLY MEETING | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000039 | 000-A-MOM-50023-001 | 5TH PROCUREMENT WEEKLY MEETING | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000076 | 076551C-000D-PP-304 | 000-A-PRO-50034-001 | TREND PROCEDURE | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 1 - APPROVED | 2018-05-15 | CLASS 2
CON-BMP-TRA-000076 | 076551C-000D-PP-307 | 000-A-PRO-50036-001 | VARIATION PROCEDURE | B | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 1 - APPROVED | 2018-05-15 | CLASS 2
CON-BMP-TRA-000077 | 076551C-000D-PP-121 | 000-A-PRO-50015-001 | DEVIATION WAIVER AND TECHNICAL QUERY REQUEST PROCEDURE | B | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-000078 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF MAY 4TH - WEEK 010 | 0E | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000079 | 076551C-000D-SL-0610-002 | 000-A-INX-50028-001 | BIDDERS LIST FOR CLAD & ALLOY SHELL AND TUBES HEAT EXCHANGERS | 0 | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000079 | 076551C-000D-SL-4111-002 | 000-A-INX-50043-001 | BIDDERS LIST FOR PSA | 0 | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000080 | 076551C-000D-RR-1008 | 000-A-RPT-50008-001 | WEEKLY PROGRESS REPORT N.08 AS OF MAY 4TH, 2018 (WEEK 0010) | 0 | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000082 | 076551C-000D-NM-601 | 000-A-PSR-50001-001 | MATERIAL REQUISITION STATUS REPORT | 0 | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-24 |  |  | CLASS 2
CON-BMP-TRA-000083 | 076551C-000D-SL-0110-003 | 000-A-INX-50041-001 | BIDDERS LIST FOR UOP LICENSED FIRED HEATERS | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000083 | 076551C-000D-SL-0411-003 | 000-A-INX-50042-001 | BIDDERS LIST FOR REACTORS | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000084 | CON-BMP-MOM-000041 | 000-A-MOM-50025-001 | LEVEL 3 SCHEDULE AND ASSOCIATED DELIVERABLES DEVELOPMENT STATUS WORKSHOP | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000084 | CON-BMP-MOM-000043 | 000-A-MOM-50026-001 | 6TH PROCUREMENT WEEKLY MEETING | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000084 | CON-BMP-MOM-000044 | 000-A-MOM-50027-001 | WEEKLY PROGRESS MEETING N 6 | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000085 | 000-C-TCQ-00001-001 | 000-C-TCQ-00001-001 | TECHNICAL QUERY FOR GASKET MATERIAL FOR PV&HE | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000086 | 076551C-000D-PP-401 | 000-A-PRO-50037-001 | INVOICING PROCEDURE | D | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 1 - APPROVED | 2018-05-11 | CLASS 1
CON-BMP-TRA-000087 | 076551C-000D-PP-814 | 000-A-PRI-50014-001 | CONSTRUCTION SUBCONTRACTORS PRE-QUALIFICATION PROCEDURE | A | 2018-05-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-000088 | 076551C-000D-PP-312 | 000-A-PRO-50073-001 | PROGRESS MEASUREMENT AND MILESTONE CERTIFICATE PROCEDURE | B | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-27 | 3 - REVIEWED WITH COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-000089 | 076551C-000D-PP-610 | 000-A-PRI-50002-001 | VENDOR PRE-QUALIFICATION PROCEDURE | B | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000090 | 076551C-000D-PP-106 | 000-A-PRO-50004-001 | PROJECT TAGGING SYSTEM | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-000091 | 076551C-000D-PP-857 | 000-A-PRO-50076-001 | SITE HSSE PROCEDURE FOR GEOTECHNICAL WORKS | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-000092 | 076551C-000D-SL-0950-001 | 000-A-INX-50047-001 | BIDDERS LIST FOR MECHANICAL SEAL | 0 | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000093 | CON-BMP-MOM-000040 | 000-A-MOM-50028-001 | PROJECT CONTROL MEETING N. 5 | 0 | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000094 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF MAY 11TH - WEEK 011 | 0F | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000095 | 076551C-000D-RR-1009 | 000-A-RPT-50009-001 | WEEKLY PROGRESS REPORT N 09 AS OF MAY 11TH 2018 (WEEK 011) | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000096 | 076551C-000D-MTO-1311-004 | 000-L-MTO-50001-001 | PIPING MATERIAL TAKE OFF SPECIFICATION | A | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000097 | CON-BMP-MOM-000037 | 000-A-MOM-50029-001 | BMP UNITS' ASSIGNMENT TO ESD SYSTEM | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000097 | CON-BMP-MOM-000045 | 000-A-MOM-50031-001 | WEEKLY CONSTRUCTION MEETING N.1 | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000097 | CON-BMP-MOM-000046 | 000-A-MOM-50032-001 | PROCUREMENT WEEKLY MEETING N.7 | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000097 | CON-BMP-MOM-000048 | 000-A-MOM-50030-001 | MONTHLY MEETING NO.2 | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000098 | 076551C-000D-PP-815 | 000-A-PRO-50081-001 | CONSTRUCTION SUBCONTRACTING PLAN | A | 2018-05-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 4 - NOT APPROVED | 2018-05-24 | CLASS 2
CON-BMP-TRA-000099 | 076551C-000D-PP-507 | 000-A-PRO-50082-001 | PROJECT AUDIT PLAN AND SCHEDULE | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-000099 | 076551C-000D-PP-508 | 000-A-PRO-50083-001 | CORRECTIVE ACTION PROCEDURE | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-000100 | 076551C-000D-JSD-1300-030 | 000-L-TSP-50016-001 | JOB DESIGN SPECIFICATION FOR ALLOWABLE NOZZLE LOADS FOR EQUIPMENT | A | 2018-05-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-000101 | 000-L-TCQ-00006-001 | 000-L-TCQ-00006-001 | TECHNICAL QUERY FOR PWHT REQUIREMENT OF PIPING CLASS D3H | 0 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000101 | 000-L-TCQ-00007-001 | 000-L-TCQ-00007-001 | TECHNICAL QUERY FOR BODY TO BONNET CONNECTION OF SMALL BORE VALVES IN HYDROGEN SERVICE #900 AND #1500 | 0 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000101 | 000-L-TCQ-00010-001 | 000-L-TCQ-00010-001 | TECHNICAL QUERY FOR LINE-MOUNTED BY PASS FOR GATE VALVES IN STEAM SERVICE 8 AND ABOVE | 0 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000102 | 076551C-000D-SL-1750-280 | 000-A-INX-50045-001 | BIDDERS LIST FOR MARINE WORKS | 0 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000103 | 076551C-000D-SL-1410-002 | 000-A-INX-50044-001 | BIDDERS LIST FOR TOPOGRAPHIC SURVEY | 0 | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000104 | 076551C-000D-PP-123 | 000-A-PRO-50017-001 | EQUIPMENT AND MATERIAL CRITICALITY RATING | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-000105 | 076551C-000D-SL-0910-003 | 000-A-INX-50034-001 | BIDDERS LIST FOR BB1 BB2 AND BB3 PUMPS | 0A | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000106 | 076551C-000D-SL-4046-001 | 000-A-INX-50048-001 | BIDDERS LIST FOR DOSING SYSTEM | 0 | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000107 | 076551C-000D-JSS-1300-001 | 000-L-TSP-50001-001 | GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | 0 | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 | CLOSED BY REVISION 0A DTD 10/08/2018 | 2018-08-10 | CLASS 1
CON-BMP-TRA-000107 | 076551C-000D-JSS-1320-001 | 000-L-TSP-50008-001 | JOB SUPPLY SPECIFICATION FOR PIPES | 0 | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 | CLOSED BY REVISION 0A DTD 10/08/2018 | 2018-08-10 | CLASS 1
CON-BMP-TRA-000107 | 076551C-000D-JSS-1330-001 | 000-L-TSP-50010-001 | JOB SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS | 0 | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 | CLOSED BY REVISION 0A DTD 10/08/2018 | 2018-08-10 | CLASS 1
CON-BMP-TRA-000107 | 076551C-000D-JSS-1350-001 | 000-L-TSP-50012-001 | JOB SUPPLY SPECIFICATION FOR FLANGES | 0 | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 | CLOSED BY REVISION 0A DTD 10/08/2018 | 2018-08-10 | CLASS 1
CON-BMP-TRA-000108 | CON-BMP-MOM-000021 | 000-A-MOM-50033-001 | SPI GAP ANALISYS REVIEW | 0 | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000108 | CON-BMP-MOM-000047 | 000-A-MOM-50034-001 | PROJECT CONTROL MEETING N.6 | 0 | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000109 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF MAY 18TH - WEEK 012 | 0G | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000110 | 076551C-000D-PP-502 | 000-A-PRO-50040-001 | CONFIDENTIALITY PLAN | 0A | 2018-05-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-06 |  |  | CLASS 1
CON-BMP-TRA-000111 | 076551C-000D-JSS-1310-001 | 000-L-TSP-50004-001 | JOB SUPPLY SPECIFICATION FOR VALVES (GATE - GLOBE - CHECK) | 0 | 2018-05-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-06 | CLOSED BY REVISION 0A DTD 10/08/2018 | 2018-08-10 | CLASS 1
CON-BMP-TRA-000112 | 076551C-000D-PP-605 | 000-A-PRI-50006-001 | QA QC/INSPECTION AND EXPEDITING REQUIREMENTS FOR VENDORS | 0 | 2018-05-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-06 |  |  | CLASS 2
CON-BMP-TRA-000113 | 076551C-000D-RR-1010 | 000-A-RPT-50010-001 | WEEKLY PROGRESS REPORT N 10 AS OF MAY 18TH 2018 (WEEK 012) | 0 | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000114 | 076551C-000D-PP-810 | 000-A-PRO-50056-001 | SITE INSPECTION COORDINATION PROCEDURE (CONSTRUCTION AND PRECOMMISSIONING) | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-07 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-000115 | 000-L-TCQ-00004-001 | 000-L-TCQ-00004-001 | TECHNICAL QUERY FOR BOLT TENSIONING REQUIREMENT FOR HYDROGEN SERVICE 600 AND GREATER | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000116 | CON-BMP-MOM-000050 | 000-A-MOM-50035-001 | WEEKLY PROGRESS MEETING N 7 | 0 | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000117 | 076551C-000D-PP-557 | 000-A-PRO-50084-001 | EQUIPMENT INSPECTION GUIDELINE | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-000118 | 000-P-TCQ-00001-001 | 000-P-TCQ-00001-001 | TECHNICAL QUERY FOR POWER SUPPLY TO SALVAGE YARD | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000118 | 000-P-TCQ-00002-001 | 000-P-TCQ-00002-001 | TECHNICAL QUERY FOR POWER SUPPLY TO U378 AREA | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000119 | 076551C-000D-SL-8200-015 | 000-A-INX-50039-001 | BIDDERS LIST FOR TEMPORARY CONSTRUCTION FACILITIES | 1 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000120 | 076551C-000D-SL-1700-021 | 000-A-INX-50046-001 | BIDDERS LIST FOR BASIN CIVIL WORKS | 0 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000121 | 076551C-000D-DW-1652-001-001 | 000-P-SYM-50001-001 | SYMBOLOGY FOR SINGLE-LINE AND SCHEMATIC DIAGRAMS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000122 | CON-BMP-MOM-000049 | 000-A-MOM-50036-001 | PROJECT CONTROL MEETING N 7 | 0 | 2018-05-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000122 | CON-BMP-MOM-000052 | 000-A-MOM-50037-001 | WEEKLY PROGRESS MEETING N 8 | 0 | 2018-05-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000123 | 076551C-000D-DW-1600-001-001 | 000-P-PHD-50001-001 | GROUNDING AND LIGHTNING SYSTEM GENERAL PHILOSOPHY | A | 2018-05-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000124 | 076551C-000D-MR-1310-002 | 000-L-MRQ-50002-001 | MATERIAL REQUISITION FOR GATE GLOBE AND CHECK CAST VALVES CS<=600# UPTO24 | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000125 | 076551C-000D-MR-1310-014 | 000-L-MRQ-50007-001 | MATERIAL REQUISITION FOR DUAL PLATE CHECK VALVES | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000126 | 076551C-000D-MR-1310-032 | 000-L-MRQ-50012-001 | MATERIAL REQUISITION FOR GATE GLOBE AND CHECK CAST VALVES CS >600#/SS/AS (UPTO24) | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000127 | 076551C-000D-MR-1310-052 | 000-L-MRQ-50014-001 | MATERIAL REQUISITION FOR GATE GLOBE AND CHECK CAST VALVES CS/SS/AS 26 AND ABOVE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000128 | 076551C-000D-MR-1321-001 | 000-L-MRQ-50018-001 | MATERIAL REQUISITION FOR CARBON STEEL SEAMLESS PIPE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000129 | 076551C-000D-MR-1321-002 | 000-L-MRQ-50019-001 | MATERIAL REQUISITION FOR CARBON STEEL WELDED PIPE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000130 | 076551C-000D-MR-1322-001 | 000-L-MRQ-50020-001 | MATERIAL REQUISITION FOR ALLOY STEEL SEAMLESS PIPE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-000131 | 076551C-000D-MR-1322-002 | 000-L-MRQ-50021-001 | MATERIAL REQUISITION FOR ALLOY STEEL WELDED PIPE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000132 | 076551C-000D-MR-1324-001 | 000-L-MRQ-50022-001 | MATERIAL REQUISTION FOR STAINLESS STEEL SEAMLESS PIPE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000133 | 076551C-000D-MR-1324-002 | 000-L-MRQ-50023-001 | MATERIAL REQUISTION FOR STAINLESS STEEL WELDED PIPE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 |  |  | CLASS 1
CON-BMP-TRA-000134 | 076551C-000D-MR-1325-001 | 000-L-MRQ-50024-001 | MATERIAL REQUISITION FOR NICKEL ALLOY PIPING | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000135 | 076551C-000D-MR-1331-001 | 000-L-MRQ-50029-001 | MATERIAL REQUISITION FOR BUTTWELDING FITTINGS CS | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-000136 | 076551C-000D-MR-1334-001 | 000-L-MRQ-50030-001 | MATERIAL REQUISITION FOR BUTTWELDING FITTINGS SS / AS | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000137 | 076551C-000D-MR-1350-001 | 000-L-MRQ-50033-001 | MATERIAL REQUISITION FOR CS/SS/AS FLANGES BLINDS AND DRIP RINGS | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-000138 | 076551C-000D-MR-1350-002 | 000-L-MRQ-50042-001 | MATERIAL REQUISITION FOR HIGH PRESSURE CLAMPED CONNECTORS | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-000139 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF MAY 25TH - WEEK 013 | 0H | 2018-05-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000141 | 000-K-TCQ-00004-001 | 000-K-TCQ-00004-001 | TECHNICAL QUERY FOR LUBE OIL SYSTEM FOR CENTRIFUGAL PUMPS | 0 | 2018-05-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000142 | 076551C-000D-RR-1011 | 000-A-RPT-50011-001 | WEEKLY PROGRESS REPORT N 11 AS OF MAY 25TH 2018 (WEEK 013) | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000143 | 076551C-000D-SL-0910-001 | 000-A-INX-50054-001 | BIDDERS LIST FOR OH 2 API 610 PUMPS | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000143 | 076551C-000D-SL-0910-002 | 000-A-INX-50053-001 | BIDDERS LIST FOR ASME PUMPS | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000144 | 076551C-000D-SL-4111-001 | 000-A-INX-50049-001 | BIDDERS LIST FOR PSA | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1310-002 | 000-A-INX-50067-001 | BIDDERS LIST FOR GATE GLOBE AND CHECK CAST VALVES CS<=600# UPTO24 | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1310-014 | 000-A-INX-50068-001 | BIDDERS LIST FOR DUAL PLATE CHECK VALVES | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1310-032 | 000-A-INX-50069-001 | BIDDERS LIST FOR GATE GLOBE AND CHECK CAST VALVES CS >600#/SS/AS (UPTO24) | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1310-052 | 000-A-INX-50070-001 | BIDDERS LIST FOR GATE GLOBE AND CHECK CAST VALVES CS/SS/AS 26 AND ABOVE | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1321-001 | 000-A-INX-50055-001 | BIDDERS LIST FOR CARBON STEEL SEAMLESS PIPE | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1321-002 | 000-A-INX-50056-001 | BIDDERS LIST FOR CARBON STEEL WELDED PIPE | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1322-001 | 000-A-INX-50057-001 | BIDDERS LIST FOR ALLOY STEEL SEAMLESS PIPE | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1322-002 | 000-A-INX-50058-001 | BIDDERS LIST FOR ALLOY STEEL WELDED PIPE | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1324-001 | 000-A-INX-50059-001 | BIDDERS LIST FOR STAINLESS STEEL SEAMLESS PIPE | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1324-002 | 000-A-INX-50060-001 | BIDDERS LIST FOR STAINLESS STEEL WELDED PIPE | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1325-001 | 000-A-INX-50071-001 | BIDDERS LIST FOR NICKEL ALLOY PIPING | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1328-001 | 000-A-INX-50066-001 | BIDDERS LIST FOR FIBERGLASS REINFORCED PLASTIC PIPING | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1331-001 | 000-A-INX-50061-001 | BIDDERS LIST FOR BUTTWELDING FITTINGS CS | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1334-001 | 000-A-INX-50062-001 | BIDDERS LIST FOR BUTTWELDING FITTINGS SS / AS | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1340-001 | 000-A-INX-50063-001 | BIDDERS LIST FOR FORGED FITTINGS | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1340-002 | 000-A-INX-50064-001 | BIDDERS LIST FOR OLETS | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000145 | 076551C-000D-SL-1350-001 | 000-A-INX-50065-001 | BIDDERS LIST FOR CS/SS/AS FLANGES BLINDS AND DRIP RINGS | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000146 | 076551C-000D-PP-816 | 000-A-PRI-50017-001 | CONSTRUCTABILITY PROGRAM AND PLAN | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-000147 | 076551C-000D-SL-0910-006 | 000-A-INX-50052-001 | BIDDERS LIST FOR VERTICAL PUMPS | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000147 | 076551C-000D-SL-0910-007 | 000-A-INX-50038-001 | BIDDERS LIST FOR SULPHUR TRANSFER PUMPS | 0A | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000148 | CON-BMP-MOM-000051 | 000-A-MOM-50038-001 | REVIEW OF INSTRUMENTATION ACTIVITIES WORKFLOW AND WIRELESS TECHNOLOGY APPLICATION | 0 | 2018-06-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000149 | 076551C-000D-SL-1691-001 | 000-A-INX-50051-001 | BIDDERS LIST FOR LV MOTORS | 0 | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000150 | 076551C-000D-RR-1012 | 000-A-RPT-50012-001 | WEEKLY PROGRESS REPORT N 12 AS OF JUNE 1ST 2018 (WEEK 014) | 0 | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000151 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF JUNE 1ST (WEEK 014) | 0I | 2018-06-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000152 | 076551C-000D-RR-103 | 000-A-MRS-50003-001 | MONTHLY PROGRESS REPORT N 03 AS OF MAY 25TH 2018 (MONTH 03) | 0 | 2018-06-07 | FOR BAPCO INFORMATION | BMP Project Director | 2018-06-22 |  |  | CLASS 2
CON-BMP-TRA-000153 | 076551C-000D-PP-601 | 000-A-PRO-50045-001 | PROCUREMENT EXECUTION PLAN | B | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 1 - APPROVED | 2018-06-13 | CLASS 2
CON-BMP-TRA-000154 | 076551C-000D-PP-553 | 000-A-PRO-50042-001 | PROJECT ENVIRONMENTAL MANAGEMENT PLAN | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 3 - REVIEWED WITH COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-000155 | 076551C-000D-PP-102 | 000-A-PRO-50002-001 | COORDINATION PROCEDURE BETWEEN THE BAHRAIN PETROLEUM COMPANY B.S.C. (CLOSED) BAPCO AND TTSJV | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-000156 | 076551C-000D-SL-0841-001 | 000-A-INX-50074-001 | BIDDERS LIST FOR FILTERS | 0 | 2018-06-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000156 | 076551C-000D-SL-0841-003 | 000-A-INX-50073-001 | BIDDERS LIST FOR CENTRIFUGAL SEPARATOR | 0 | 2018-06-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000157 | 000-N-TCQ-00001-001 | 000-N-TCQ-00001-001 | TECHNICAL QUERY FOR FINISH CODE FOR BURIED LINES | 0 | 2018-06-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000158 | 000-J-TCQ-00003-001 | 000-J-TCQ-00003-001 | TECHNICAL QUERY FOR BMPS UNITS ASSIGNMENT TO ESD SYSTEMS | 0 | 2018-06-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000159 | 076551C-000D-SL-4111-001 | 000-A-INX-50049-001 | BIDDERS LIST FOR MEMBRANE PACKAGE | 0A | 2018-06-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000160 | 076551C-000D-PP-609 | 000-A-PRO-50013-001 | INSPECTION PROCEDURE | 0 | 2018-06-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-26 | 1 - APPROVED | 2018-06-13 | CLASS 1
CON-BMP-TRA-000160 | 076551C-000D-PP-611 | 000-A-PRO-50074-001 | PROJECT EXPEDITING PROCEDURE | 0 | 2018-06-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-26 | 1 - APPROVED | 2018-06-13 | CLASS 1
CON-BMP-TRA-000161 | 076551C-000D-PP-015 | 000-A-PRI-50011-001 | VENDOR GUIDELINES FOR PREPARATION OF QUALITY CONTROL MANUFACTURING DOSSIER (QCMD) | 0 | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 1 - APPROVED | 2018-06-25 | CLASS 2
CON-BMP-TRA-000162 | 076551C-000D-PP-854 | 000-A-PRO-50060-001 | WASTE MANAGEMENT PROGRAM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 3 - REVIEWED WITH COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-000163 | 076551C-000D-RR-3001 | 000-A-RPT-50013-001 | REPORT FOR EXPORT CREDIT AGENCY (ECA) FINANCING N. 01 | 0 | 2018-06-11 | FOR BAPCO INFORMATION | BMP Project Director | 2018-06-27 |  |  | CLASS 2
CON-BMP-TRA-000164 | CON-BMP-MOM-000054 | 000-A-MOM-50039-001 | BMP SYSTEMS COMPLETION PHASES DELIVERABLES STATUS | 0 | 2018-06-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000164 | CON-BMP-MOM-000055 | 000-A-MOM-50040-001 | PROJECT CONTROL MEETING N 8 | 0 | 2018-06-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000164 | CON-BMP-MOM-000056 | 000-A-MOM-50041-001 | PROCUREMENT WEEKLY MEETING N 8 | 0 | 2018-06-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000165 | 076551C-000D-RR-1013 | 000-A-WRS-50013-001 | WEEKLY PROGRESS REPORT N 13 AS OF JUNE 8TH 2018 (WEEK 015) | 0 | 2018-06-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000166 | 000-L-TCQ-00002-001 | 000-L-TCQ-00002-001 | TECHNICAL QUERY FOR MIMINUM LINE SIZE | 0 | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000167 | 076551C-000D-SL-0610-003 | 000-A-INX-50050-001 | BIDDERS LIST FOR WET H2S AND SPECIAL SERVICE CS SHELL & TUBE HEAT EXCHANGER | 0 | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000167 | 076551C-000D-SL-0811-002 | 000-A-INX-50077-001 | BIDDERS LIST FOR STAINLESS STEEL & CLAD VESSELS | 0 | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000167 | 076551C-000D-SL-0811-003 | 000-A-INX-50078-001 | BIDDERS LIST FOR CS VESSELS 19< MM | 0 | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000167 | 076551C-000D-SL-0811-004 | 000-A-INX-50079-001 | BIDDERS LIST FOR CS VESSELS 19> MM | 0 | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000168 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF JUNE 8TH (WEEK 015) | 0J | 2018-06-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000169-REV.1 | 076551C-000D-PLG-305 | 000-A-SCH-50003-001 | LEVEL 3 EPC SCHEDULE | A | 2018-06-18 | FOR INFORMATION | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-000170 | 076551C-000D-SL-1410-003 | 000-A-INX-50072-001 | BIDDERS LIST FOR UNDERGROUND MAPPING | 0 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000171 | CON-BMP-MOM-000058 | 000-A-MOM-50042-001 | PROJECT CONTROL MEETING N 9 | 0 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000171 | CON-BMP-MOM-000060 | 000-A-MOM-50043-001 | WEEKLY PROGRESS MEETING N 9 | 0 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000171 | CON-BMP-MOM-000061 | 000-A-MOM-50044-001 | PROCUREMENT WEEKLY MEETING N 9 | 0 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000171 | CON-BMP-MOM-000062 | 000-A-MOM-50045-001 | PROCUREMENT WEEKLY MEETING N 10 | 0 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000172 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF JUNE 15TH (WEEK 016) | 0K | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1001 | 000-A-WRS-50001-001 | WEEKLY PROGRESS REPORT N.01 AS OF MARCH 16TH, 2018 (WEEK 03) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1002 | 000-A-WRS-50002-001 | WEEKLY PROGRESS REPORT N.02 AS OF MARCH 23RD, 2018 (WEEK 04) | 2 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1003 | 000-A-WRS-50003-001 | WEEKLY PROGRESS REPORT N.03 AS OF MARCH 30TH, 2018 (WEEK 005) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1004 | 000-A-WRS-50004-001 | WEEKLY PROGRESS REPORT N.04 AS OF APRIL 6TH, 2018 (WEEK 006) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1005 | 000-A-WRS-50005-001 | WEEKLY PROGRESS REPORT N.05 AS OF APRIL 13TH, 2018 (WEEK 007) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1006 | 000-A-WRS-50006-001 | WEEKLY PROGRESS REPORT N.06 AS OF APRIL 20TH, 2018 (WEEK 008) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1007 | 000-A-WRS-50007-001 | WEEKLY PROGRESS REPORT N.07 AS OF APRIL 27TH, 2018 (WEEK 009) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1008 | 000-A-WRS-50008-001 | WEEKLY PROGRESS REPORT N.08 AS OF MAY 4TH, 2018 (WEEK 0010) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1009 | 000-A-WRS-50009-001 | WEEKLY PROGRESS REPORT N 09 AS OF MAY 11TH 2018 (WEEK 011) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1010 | 000-A-WRS-50010-001 | WEEKLY PROGRESS REPORT N 10 AS OF MAY 18TH 2018 (WEEK 012) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1011 | 000-A-WRS-50011-001 | WEEKLY PROGRESS REPORT N 11 AS OF MAY 25TH 2018 (WEEK 013) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000173 | 076551C-000D-RR-1012 | 000-A-WRS-50012-001 | WEEKLY PROGRESS REPORT N 12 AS OF JUNE 1ST 2018 (WEEK 014) | 1 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000174 | 076551C-000D-RR-1014 | 000-A-WRS-50014-001 | WEEKLY PROGRESS REPORT N 14 AS OF JUNE 15TH 2018 (WEEK 016) | 0 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000175 | 076551C-000D-DW-1920-001-001 | 000-P-HAC-50001-001 | TYPICAL FIGURES FOR HAZARDOUS AREA CLASSIFICATION DRAWINGS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-000175 | 076551C-000D-DW-1920-001-002 | 000-P-HAC-50001-002 | TYPICAL FIGURES FOR HAZARDOUS AREA CLASSIFICATION DRAWINGS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-000175 | 076551C-000D-DW-1920-001-003 | 000-P-HAC-50001-003 | TYPICAL FIGURES FOR HAZARDOUS AREA CLASSIFICATION DRAWINGS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-000175 | 076551C-000D-DW-1920-001-004 | 000-P-HAC-50001-004 | TYPICAL FIGURES FOR HAZARDOUS AREA CLASSIFICATION DRAWINGS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-000175 | 076551C-000D-DW-1920-001-005 | 000-P-HAC-50001-005 | TYPICAL FIGURES FOR HAZARDOUS AREA CLASSIFICATION DRAWINGS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-000176 | 076551C-000D-PP-911 | 000-A-PRI-50015-001 | MASTER TRAINING PLAN AND SCHEDULE | A | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-000177 | 076551C-000D-MS-6740-052 | 000-B-MST-50005-001 | JOB SPEC FOR MATERIAL PRESERVATION DURING CONSTRUCTION PRECOMM COMMISSIONING AND START-UP | A | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-000178 | 076551C-000D-SL-0610-005 | 000-A-INX-50080-001 | BIDDERS LIST FOR SULPHUR CONDENSER | 0 | 2018-06-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000179 | 076551C-000D-SL-1700-020 | 000-A-INX-50081-001 | BIDDERS LIST FOR CIVIL WORKS (GREENFIELD/BROWNFIELD) | 0 | 2018-06-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000180 | 076551C-000D-SL-0511-002 | 000-A-INX-50009-001 | BIDDERS LIST FOR CLADDED COLUMNS (LLI) | 0A | 2018-06-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000181 | 000-C-TCQ-00005-001 | 000-C-TCQ-00005-001 | TECHNICAL QUERY FOR INSTRUMENT CONNECTIONS (TG & PG) LOCATION AND TYPE | 0 | 2018-06-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000182 | 000-L-TCQ-00001-001 | 000-L-TCQ-00001-001 | TECHNICAL QUERY FOR PWHT FOR STABILIZED SS GRADES | 0 | 2018-06-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000183 | 000-J-TCQ-00007-001 | 000-J-TCQ-00007-001 | TECHNICAL QUERY FOR INSTRUMENTATION MULTIPAIR/CORE CABLE COMPOSITION | 0 | 2018-06-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000184 | CON-BMP-MOM-000059 | 000-A-MOM-50047-001 | CLARIFICATIONS ON BMPS-L2 | 0 | 2018-06-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000184 | CON-BMP-MOM-000064 | 000-A-MOM-50046-001 | MONTHLY PROGRESS MEETING N. 3 | 0 | 2018-06-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000185 | 076551C-000D-PP-101 | 000-A-PRO-50001-001 | PROJECT EXECUTION PLAN | C | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-000186 | 076551C-000D-ML-303 | 000-A-PLD-50002-001 | BASIS OF SCHEDULE | 0 | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000187 | 076551C-000D-SL-0511-002-A | 000-A-INX-50082-001 | BIDDERS LIST FOR COLUMNS | 0 | 2018-06-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000188 | 076551C-000D-SL-0851-001 | 000-A-INX-50032-001 | BIDDERS LIST FOR VACUUM UNIT PACKAGE | 0A | 2018-06-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000189 | 076551C-000D-SL-1011-001 | 000-A-INX-50003-001 | BIDDERS LIST FOR CENTRIFUGAL COMPRESSORS | 0A | 2018-06-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000190 | 076551C-000D-SL-0610-004 | 000-A-INX-50083-001 | BIDDERS LIST FOR CS SHELL AND TUBE HEAT EXCHANGERS | 0 | 2018-06-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000191 | 076551C-000D-RR-1015 | 000-A-WRS-50015-001 | WEEKLY PROGRESS REPORT N 15 AS OF JUNE 22ND 2018 (WEEK 017) | 0 | 2018-06-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000192 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF JUNE 22TH (WEEK 017) | 0L | 2018-06-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000193 | 000-C-TCQ-00006-001 | 000-C-TCQ-00006-001 | TECHNICAL QUERY FOR THE USE OF SA 516 GR 65 IN SOUR SERVICE | 0 | 2018-06-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000194 | 076551C-000D-SL-0920-001 | 000-A-INX-50086-001 | BIDDERS LIST FOR RECIPROCATING PUMPS | 0 | 2018-06-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000195 | 076551C-000D-QCP-1399-001 | 000-L-PQP-50001-001 | QUALITY CONTROL PLAN FOR WELDERS MANAGEMENT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-000195 | 076551C-000D-QCP-1399-002 | 000-L-PQP-50002-001 | QUALITY CONTROL PLAN FOR PIPING WELDING ACTIVITIES MANAGEMENT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-000196 | 076551C-000D-MS-0000-051 | 000-B-MST-50001-001 | JOB CONSTRUCTION SPECIFICATION FOR WELDERS MANAGEMENT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-000196 | 076551C-000D-MS-0000-053 | 000-B-MST-50003-001 | JOB CONSTRUCTION SPECIFICATION FOR SITE PIPING MATERIAL IDENTIFICATION AND TRACEABILITY | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-000197 | 076551C-000M-TBT-0411-001 | 000-C-TBE-70006-001 | TECHNICAL BID EVALUATIONS FOR REACTORS HCU | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-000197 | 076551C-000R-TBT-0411-001 | 000-C-TBE-60004-001 | TECHNICAL BID EVALUATIONS FOR 2.25CR-1MO-V REACTORS AND INTERNALS | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-000199 | 076551C-000D-PP-909 | 000-A-PRO-50088-001 | SYSTEMS COMPLETION EXECUTION PLAN | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-000200 | CON-BMP-MOM-000065 | 000-A-MOM-50048-001 | PROCUREMENT WEEKLY MEETING N.11 | 0 | 2018-06-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000201 | 076551C-000D-QCP-0000-001 | 000-A-PQP-50001-001 | QUALITY CONTROL PLAN FOR MATERIAL MANAGEMENT AND WAREHOUSE | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000202 | 076551C-000D-PP-601 | 000-A-PRO-50045-001 | PROCUREMENT EXECUTION PLAN | 0 | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 1 - APPROVED | 2018-07-12 | CLASS 2
CON-BMP-TRA-000203 | 076551C-000D-SL-6130-019 | 000-A-INX-50085-001 | BIDDERS LIST FOR SITE SECURITY | 0 | 2018-06-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000204 | 076551C-000R-TBT-0811-001 | 000-C-TBE-60001-001 | TECHNICAL BID EVALUATIONS FOR 2.25CR-1MO-V H.P. SEPARATORS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-000205 | 076551C-000R-RT-1990-001 | 000-A-RSK-60001-001 | JOB SPECIFICATION FOR QUANTITATIVE RISK ASSESSMENT (INCLUDING BUILDING RISK ASSESSMENT) | 0 | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-000206 | 076551C-000M-TBT-0511-001 | 000-C-TBE-70008-001 | TECHNICAL BID EVALUATIONS FOR CS COLUMNS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-000207 | 000-J-TCQ-00009-001 | 000-J-TCQ-00009-001 | TECHNICAL QUERY (TQ) - MOTOR OPERATED VALVE (MOV) TYPICAL | 0 | 2018-07-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000208 | 076551C-000M-TBT-0470-001 | 000-C-TBE-70007-001 | TECHNICAL BID EVALUATIONS FOR 2HCU REACTOR INTERNALS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-000209 | 076551C-000D-SL-0610-003 | 000-A-INX-50050-001 | BIDDERS LIST FOR WET H2S AND SPECIAL SERVICE CS SHELL & TUBE HEAT EXCHANGER | 0A | 2018-07-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000210 | 076551C-000D-PP-610 | 000-A-PRI-50002-001 | VENDOR PRE-QUALIFICATION PROCEDURE | 0 | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-000211 | 076551C-000D-PP-123 | 000-A-PRO-50017-001 | EQUIPMENT AND MATERIAL CRITICALITY RATING | B | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-000212 | 076551C-000D-PP-820 | 000-A-PRO-50093-001 | CAMP MANAGEMENT PLAN | A | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-18 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-000213 | CON-BMP-MOM-000063 | 000-A-MOM-50051-001 | WEEKLY CONSTRUCTION MEETING N. 4 | 0 | 2018-07-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000213 | CON-BMP-MOM-000066 | 000-A-MOM-50049-001 | WEEKLY CONSTRUCTION MEETING N. 5 | 0 | 2018-07-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000214 | 076551C-000D-RR-1016 | 000-A-WRS-50016-001 | WEEKLY PROGRESS REPORT N 16 AS OF JUNE 29TH 2018 (WEEK 018) | 0 | 2018-07-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000215 | 076551C-000D-SL-1700-020 | 000-A-INX-50081-001 | BIDDERS LIST FOR CIVIL WORKS (GREENFIELD/BROWNFIELD) | 0A | 2018-07-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000216 | 076551C-000D-MS-1700-002 | 000-Q-MST-50001-001 | TECHNICAL SPECIFICATION FOR CIVIL WORKS | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-000217 | 076551C-000D-JSD-1700-001 | 000-M-TSP-50001-001 | BASIS OF DESIGN FOUNDATIONS CONCRETE AND STEEL STRUCTURES | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-000218 | 076551C-000D-SL-0910-008 | 000-A-INX-50076-001 | BIDDERS LIST FOR CRYOGENIC VERTICAL PUMPS | 0 | 2018-07-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000218 | 076551C-000D-SL-0910-010 | 000-A-INX-50075-001 | BIDDERS LIST FOR SUBMERSIBLE PUMP | 0 | 2018-07-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000219 | 076551C-000D-SL-0213-001 | 000-A-INX-50092-001 | BIDDERS LIST FOR POLISHING PACKAGE | 0 | 2018-07-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000219 | 076551C-000D-SL-4260-001 | 000-A-INX-50091-001 | BIDDERS LIST FOR MIXER ROTATIVE | 0 | 2018-07-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000219 | 076551C-000D-SL-4263-001 | 000-A-INX-50084-001 | BIDDERS LIST FOR STATIC MIXER | 0 | 2018-07-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000220 | 076551C-000D-SL-0510-001 | 000-A-INX-50087-001 | BIDDERS LIST FOR DEAERATOR | 0 | 2018-07-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000221 | CON-BMP-MOM-000057 | 000-A-MOM-50053-001 | WEEKLY CONSTRUCTION MEETING N. 3 | 0 | 2018-07-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000221 | CON-BMP-MOM-000068 | 000-A-MOM-50052-001 | WEEKLY PROGRESS MEETING N. 10 | 0 | 2018-07-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000222 | CON-BMP-MOM-000053 | 000-A-MOM-50050-001 | WEEKLY CONSTRUCTION MEETING N.2 | 0 | 2018-07-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000223 | 076551C-000D-RR-104 | 000-A-MRS-50004-001 | MONTHLY PROGRESS REPORT N 04 AS OF JUNE 29TH 2018 (MONTH 04) | 0 | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-21 |  |  | CLASS 2
CON-BMP-TRA-000224 | 000-J-TCQ-00005-001 | 000-J-TCQ-00005-001 | TECHNICAL QUERY (TQ) - USAGE OF MINERAL INSULATED CABLE | 0 | 2018-07-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000224 | 000-J-TCQ-00010-001 | 000-J-TCQ-00010-001 | TECHNICAL QUERY (TQ) - MISSING DRAWEINGS IN THE ITB BMPS-J23 | 0 | 2018-07-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000224 | 000-J-TCQ-00011-001 | 000-J-TCQ-00011-001 | TECHNICAL QUERY (TQ) - INSTRUMENT WIRING IDENTIFICATION | 0 | 2018-07-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000225 | 000-L-TCQ-00015-001 | 000-L-TCQ-00015-001 | TECHNICAL QUERY (TQ) - CONFLICT OF BMPS REQUIREMENTS REGARDING DESIGN OF VENT PIPE TO ATMOSPHERE | 0 | 2018-07-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000226 | 000-C-TCQ-00007-001 | 000-C-TCQ-00007-001 | TECHNICAL QUERY FOR REINFORCEMENT OF NOZZLE FOR 098C9804 / 099C904 AND 036V360 / 037V3702 | 0 | 2018-07-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000227 | 076551C-000D-PP-505 | 000-A-PRO-50078-001 | PROJECT AUDIT PROCEDURE | 0 | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 1 - APPROVED | 2018-07-11 | CLASS 2
CON-BMP-TRA-000227 | 076551C-000D-PP-506 | 000-A-PRO-50079-001 | NON CONFORMANCE CONTROL PROCEDURE | 0 | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 1 - APPROVED | 2018-07-11 | CLASS 2
CON-BMP-TRA-000228 | CON-BMP-MOM-000069 | 000-A-MOM-50054-001 | WEEKLY PROGRESS MEETING N. 11 | 0 | 2018-07-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000228 | CON-BMP-MOM-000071 | 000-A-MOM-50055-001 | CLARIFICATION ABOUT PAINTING OF STEEL STRUCTURE AND SYSTEM AT TEMPERATURE ABOVE 400 C | 0 | 2018-07-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000228 | CON-BMP-MOM-000072 | 000-A-MOM-50056-001 | PROCUREMENT WEEKLY MEETING N. 12 | 0 | 2018-07-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000229 | 076551C-000D-PP-402 | 000-A-PRO-50094-001 | INCIDENTAL COST MANAGEMENT PROCEDURE | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-000230 | 076551C-000D-SL-0570-001 | 000-A-INX-50010-001 | BIDDERS LIST FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | 0A | 2018-07-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000230 | 076551C-000D-SL-0610-006 | 000-A-INX-50089-001 | BIDDERS LIST FOR PLATE AND SHELL HEAT EXCHANGER | 0 | 2018-07-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000230 | 076551C-000D-SL-0660-001 | 000-A-INX-50090-001 | BIDDERS LIST FOR PLATE AND FRAME HEAT EXCHANGER | 0 | 2018-07-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000231-REV1 | 076551C-000D-RR-1017 | 000-A-WRS-50017-001 | WEEKLY PROGRESS REPORT N 17 AS OF JULY 6TH 2018 (WEEK 019) | 0 | 2018-07-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000232 | 076551C-000D-QCP-1470-002 | 000-L-PQP-50003-001 | QUALITY CONTROL PLAN NON METALLIC PRESSURE PIPING INSTALLATION (ABOVE AND UNDERGROUND) | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000233 | 076551C-000D-QCP-1430-001 | 000-Q-PQP-50001-001 | QUALITY CONTROL PLAN CIVIL WORKS BORED CAST IN SITU PILES | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000233 | 076551C-000D-QCP-1430-002 | 000-Q-PQP-50002-001 | QUALITY CONTROL PLAN CIVIL WORKS CONTINUOS FLIGHT AUGER PILES | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000233 | 076551C-000D-QCP-1430-003 | 000-Q-PQP-50003-001 | QUALITY CONTROL PLAN CIVIL WORKS CONCRETE PRECAST DRIVEN PILES | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000234 | 076551C-000D-QCP-1420-001 | 000-S-PQP-50001-001 | QUALITY CONTROL PLAN CIVIL WORKS FENCING | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000234 | 076551C-000D-QCP-1433-001 | 000-S-PQP-50002-001 | QUALITY CONTROL PLAN CIVIL WORKS SOIL IMPROVEMENT | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000234 | 076551C-000D-QCP-1440-001 | 000-S-PQP-50003-001 | QUALITY CONTROL PLAN CIVIL WORKS EARTH MOVING | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000234 | 076551C-000D-QCP-1440-008 | 000-S-PQP-50004-001 | QUALITY CONTROL PLAN CIVIL WORKS STORM WATER POND | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000234 | 076551C-000D-QCP-1450-001 | 000-S-PQP-50005-001 | QUALITY CONTROL PLAN CIVIL WORKS ASPHALT ROADS AND YARDS | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000234 | 076551C-000D-QCP-1470-001 | 000-S-PQP-50006-001 | QUALITY CONTROL PLAN U/G CIVIL WORKS SEWERS | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000234 | 076551C-000D-QCP-1490-001 | 000-S-PQP-50007-001 | QUALITY CONTROL PLAN CIVIL WORKS DEMOLITION / DISMANTLING | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000235 | 076551C-000D-SL-2520-001 | 000-A-INX-50097-001 | BIDDERS LIST FOR STORAGE TANKS | 0 | 2018-07-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000236 | 076551C-000D-SL-1040-001 | 000-A-INX-50094-001 | BIDDERS LIST FOR FAN AND BLOWER | 0 | 2018-07-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000237 | 076551C-000D-SL-1800-001 | 000-A-INX-50088-001 | BIDDERS LIST FOR STEEL STRUCTURE | 0 | 2018-07-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000238 | 076551C-000D-PP-108 | 000-A-PRO-50006-001 | HOMOGENIZATION PROCEDURE | B | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-000239 | 076551C-000D-PP-304 | 000-A-PRO-50034-001 | TREND PROCEDURE | 0 | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 |  |  | CLASS 2
CON-BMP-TRA-000239 | 076551C-000D-PP-307 | 000-A-PRO-50036-001 | VARIATION PROCEDURE | 0 | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 |  |  | CLASS 2
CON-BMP-TRA-000240 | 076551C-000D-JSD-2000-001 | 000-R-TSP-50002-001 | DESIGN BASIS FOR BUILDING | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-000241 | 076551C-000D-PP-313 | 000-A-PRO-50096-001 | CONTRACT MANAGEMENT DOCUMENT COST ESTIMATE PROCEDURE OPEN BOOK ESTIMATE | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-000242 | 000-P-TCQ-00003-001 | 000-P-TCQ-00003-001 | TECHNICAL QUERY FOR DIRECT BURIED TRENCH IN SUBSTATIN CABLE ROOMS | 0 | 2018-07-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000242 | 000-P-TCQ-00005-001 | 000-P-TCQ-00005-001 | TECHNICAL QUERY FOR LOCAL OF AC & DC UPS BATTERIES | 0 | 2018-07-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000243 | 000-J-TCQ-00014-001 | 000-J-TCQ-00014-001 | TECHNICAL QUERY FOR PNEUMATIC ACTUATOR PRESSURE SIZING CRITERIA | 0 | 2018-07-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000244 | 000-P-TCQ-00004-001 | 000-P-TCQ-00004-001 | TECHNICAL QUERY FOR LAYER PROPRERTIES FOR DIMENSIONS LINES ON AUTOCAD DRAWINGS | 0 | 2018-07-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000245 | 000-B-TCQ-00008-001 | 000-B-TCQ-00008-001 | TECHNICAL QUERY FOR TEMPERATURE LIMIT FOR COLOUR CODING | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000246 | 076551C-000D-RR-1018 | 000-A-WRS-50018-001 | WEEKLY PROGRESS REPORT N 18 AS OF JULY 13TH 2018 (WEEK 020) | 0 | 2018-07-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000247 | 076551C-000D-SL-1310-260 | 000-A-INX-50103-001 | BIDDERS LIST FOR CS-1310-260 PIPING PRE-FABRICATIN WORKS (GREEN FIELD/BROWN FIELD) | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000248 | CON-BMP-MOM-000077 | 000-A-MOM-50057-001 | WEEKLY PROGRESS MEETING N. 12 | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000248 | CON-BMP-MOM-000078 | 000-A-MOM-50058-001 | PROCUREMENT WEEKLY MEETING N. 14 | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000248 | CON-BMP-MOM-000079 | 000-A-MOM-50059-001 | PROJECT CONTROL MEETING N. 10 | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000249 | 076551C-000D-SL-0841-002 | 000-A-INX-50101-001 | BIDDERS LIST FOR COALESCER | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000249 | 076551C-000D-SL-0848-001 | 000-A-INX-50093-001 | BIDDERS LIST FOR FEED STRINERS | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000249 | 076551C-000D-SL-0852-001 | 000-A-INX-50099-001 | BIDDERS LIST FOR DESUPERHEATER | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000249 | 076551C-000D-SL-0852-002 | 000-A-INX-50100-001 | BIDDERS LIST FOR EJECTOR & EDUCTOR | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000250 | 076551C-000D-SL-2543-001 | 000-A-INX-50095-001 | BIDDERS LIST FOR STORAGE BULLETS | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000251 | 076551C-000D-SL-2000-100 | 000-A-INX-50102-001 | BIDDERS LIST FOR BUILDING WORKS | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000252 | 076551C-000D-PP-908 | 000-A-PRI-50010-001 | INSTRUCTIONS TO VENDORS FOR FILLING-UP OF SPARE PARTS INTERCHANGEABILITY RECORD (SPIR) | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 |  |  | CLASS 2
CON-BMP-TRA-000253 | 076551C-000D-QCP-1710-001 | 000-Q-PQP-50004-001 | QUALITY CONTROL PLAN CIVIL WORKS REINFORCED CONCRETE FOR FOUNDATION/ELEVATION STRUCTURES AND BASINS | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000253 | 076551C-000D-QCP-1710-004 | 000-Q-PQP-50005-001 | QUALITY CONTROL PLAN CIVIL WORKS TANK RINGS FOUNDATIONS | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000253 | 076551C-000D-QCP-1713-001 | 000-Q-PQP-50006-001 | QUALITY CONTROL PLAN CIVIL WORKS RIGID PAVING | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000253 | 076551C-000D-QCP-1760-001 | 000-Q-PQP-50009-001 | QUALITY CONTROL PLAN CIVIL WORKS - GROUTING | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 1 - APPROVED | 2018-07-30 | CLASS 2
CON-BMP-TRA-000253 | 076551C-000D-QCP-1761-001 | 000-Q-PQP-50007-001 | QUALITY CONTROL PLAN CONCRETE PROTECTIVE COATING | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 1 - APPROVED | 2018-07-30 | CLASS 2
CON-BMP-TRA-000253 | 076551C-000D-QCP-1770-001 | 000-Q-PQP-50010-001 | QUALITY CONTROL PLAN CIVIL WORKS REVAMPING OF REINFORCED CONCRETE FOUNDATIONS | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000254 | 076551C-000D-QCP-1714-001 | 000-S-PQP-50013-001 | QUALITY CONTROL PLAN U/G CIVIL WORKS INSTALLATION OF CONCRETE PITS, CABLES. BOX CULVERTS AND LIGHTING POLES | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000254 | 076551C-000D-QCP-1740-001 | 000-S-PQP-50012-001 | QUALITY CONTROL PLAN CIVIL WORKS FIRE PROOFING | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000255 | 076551C-000D-QCP-1710-002 | 000-M-PQP-50002-001 | QUALITY CONTROL PLAN CIVIL WORKS PREFABRICATION OF CONCRETE ELEMENTS | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000255 | 076551C-000D-QCP-1710-003 | 000-M-PQP-50003-001 | QUALITY CONTROL PLAN PRECAST PIPE-RACK ERECTION | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000255 | 076551C-000D-QCP-1710-005 | 000-M-PQP-50004-001 | QUALITY CONTROL PLAN ABOVE GROUND CIVIL WORKS CONCRETE ELEMENTS INSTALLATION | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 1 - APPROVED | 2018-07-30 | CLASS 2
CON-BMP-TRA-000255 | 076551C-000D-QCP-1717-001 | 000-M-PQP-50001-001 | QUALITY CONTROL PLAN CIVIL WORKS CONCRETE STRUCTURE FOR COOLING TOWER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000256 | 076551C-000D-PP-312 | 000-A-PRO-50073-001 | PROGRESS MEASUREMENT AND MILESTONE CERTIFICATE PROCEDURE | C | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 1
CON-BMP-TRA-000257 | 076551C-000D-PP-202 | 000-A-PRO-50020-001 | HAZOP AND SIL DETERMINATION STUDIES PLAN | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 1
CON-BMP-TRA-000258 | 076551C-000D-PP-267 | 000-A-PRO-50095-001 | HUMAN FACTORS ENGINEERING (HFE) IMPLEMENTATION PLAN | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-000259 | 076551C-000D-PP-955 | 000-A-PRI-50022-001 | CRITICALITY ASSESSMENT GUIDELINES | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-000260 | 076551C-000D-JSS-1328-001 | 000-L-TSP-50009-001 | JOB SUPPLY SPECIFICATION FOR GLASS REINFORCED PLASTIC PIPING | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-000261 | 076551C-000D-PP-957 | 000-A-PRI-50021-001 | RELIABILITY & MAINTENANCE EXECUTION PLAN | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-000262 | 076551C-000D-PP-301 | 000-A-PRO-50031-001 | PLANNING AND SCHEDULING PROCEDURE | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-000263 | 076551C-000D-PLG-309 | 000-A-PLD-50003-001 | PROGRESS CONTROL TABLES | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-000264 | 076551C-000D-SL-0841-003-A | 000-A-INX-50105-001 | BIDDERS LIST FOR SULPHUR LOCK | 0 | 2018-07-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000264 | 076551C-000D-SL-4131-001 | 000-A-INX-50109-001 | BIDDERS LIST FOR OIL MIST SYSTEM | 0 | 2018-07-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000265 | 076551C-000D-SL-0630-001 | 000-A-INX-50098-001 | BIDDERS LIST FOR HAIR PIN TYPE HEAT EXCHANGERS | 0 | 2018-07-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000265 | 076551C-000D-SL-0811-002-A | 000-A-INX-50106-001 | BIDDERS LIST FOR CLADDED AND ALLOY SS VESSEL | 0 | 2018-07-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000265 | 076551C-000D-SL-0811-004-A | 000-A-INX-50107-001 | BIDDERS LIST FOR LARGE CARBON STEEL PRESSURE VESSELS | 0 | 2018-07-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000267 | 076551C-000D-NM-110 | 000-A-PLD-50004-001 | LEVEL 4 SCHEDULE - PROJECT DELIVERABLE LIST | A | 2018-07-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-21 | CLASS 1
CON-BMP-TRA-000268 | 076551C-000D-QCP-1300-001 | 000-L-PQP-50004-001 | PRECOMISSIONING/COMMISIONING QUALITY CONTROL PLAN PIPING | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000269 | 076551C-000D-QCP-1500-001 | 000-J-PQP-50001-001 | PRECOMISSIONING/COMMISSIONING QUALITY CONTROL PLAN INTRUMENTATION | A | 2018-07-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-000270 | 076551C-000D-QCP-6800-001 | 000-S-PQP-50014-001 | PRECOMISSIONING/COMMISSIONING QUALITY CONTROL PLAN MECHANICAL | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-000271 | 076551C-000D-QCP-1600-001 | 000-P-PQP-50001-001 | PRECOMISSIONING/COMMISSIONING QUALITY CONTROL PLAN ELECTRICAL | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-000272 | 000-C-TCQ-00010-001 | 000-C-TCQ-00010-001 | TECHNICAL QUERY FOR SLOPE REQUIREMENTS FOR HORIZONTAL VESSEL | 0 | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000273 | 000-L-TCQ-00014-001 | 000-L-TCQ-00014-001 | TECHNICAL QUERY (TQ) - ORIENTATION OF ROOT VALVES FOR AIR AND STEAM | 0 | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000274 | 000-P-TCQ-00006-001 | 000-P-TCQ-00006-001 | TECHNICAL QUERY FOR COVER OF CONCRETE CABLE TRENCHES ON PAVED AREA | 0 | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000275 | 076551C-000D-SL-0610-006 | 000-A-INX-50089-001 | BIDDERS LIST FOR PLATE AND SHELL HEAT EXCHANGER | 0A | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000276 | 076551C-000D-SL-1800-001 | 000-A-INX-50088-001 | BIDDERS LIST FOR STEEL STRUCTURE | 0A | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000277 | 076551C-000D-PLG-102 | 000-A-PMP-50001-001 | WORK BREAKDOWN STRUCTURE | C | 2018-07-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 1
CON-BMP-TRA-000278 | 076551C-000D-PP-800 | 000-A-ORG-50002-001 | SITE ORGANIZATION CHART | 0 | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000279-REV.1 | 076551C-000D-MS-1700-002 | 000-Q-TSP-50001-001 | TECHNICAL SPECIFICATION FOR CIVIL WORKS (EX 000-Q-MST-50001-001) | B | 2018-07-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 1
CON-BMP-TRA-000280 | 076551C-000D-PP-855 | 000-A-PRO-50061-001 | WORK AT HEIGHT PROCEDURE | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 |  |  | CLASS 2
CON-BMP-TRA-000281 | 076551C-000D-RR-1019 | 000-A-WRS-50019-001 | WEEKLY PROGRESS REPORT N 19 AS OF JULY 20TH 2018 (WEEK 021) | 0 | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000282 | 076551C-000D-PP-921 | 000-A-PRI-50020-001 | CONSTRUCTION SKILLS VOCATIONAL TRAINING PLAN | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 |  |  | CLASS 2
CON-BMP-TRA-000283 | CON-BMP-MOM-000080 | 000-A-MOM-50060-001 | DEFINITION OF TAGS FOR BUILDINGS | 0 | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000284 | CON-BMP-MOM-000084 | 000-A-MOM-50061-001 | PROJECT CONTROL MEETING N¿11 | 0 | 2018-07-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000285 | 076551C-000D-JSD-1470-001 | 000-S-TSP-50001-001 | JOB DESIGN SPECIFICATION FOR DRAINAGE SEWER SYSTEMS AND EFFULENT TREATMENT | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-000286 | 000-C-TCQ-00011-001 | 000-C-TCQ-00011-001 | TECHNICAL QUERY FOR SELF-REINFORCING CRITERIA FOR WET H2S SERVICE EQUIPMENT | 0 | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000286 | 000-C-TCQ-00012-001 | 000-C-TCQ-00012-001 | TECHNICAL QUERY FOR PWHT REQUIREMENT ON AIR COOLER HEAT EXCHANGERS | 0 | 2018-07-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000287 | CON-BMP-MOM-000067 | 000-A-MOM-50062-001 | WEEKLY CONSTRUCTION MEETING N. 6 | 0 | 2018-07-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000288 | 076551C-000D-JSS-1800-001 | 000-M-TSP-50002-001 | GENERAL SUPPLY RULES FOR STEEL STRUCTURES | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 |  |  | CLASS 2
CON-BMP-TRA-000289 | CON-BMP-MOM-000070 | 000-A-MOM-50064-001 | WEEKLY CONSTRUCTION MEETING N. 7 | 0 | 2018-07-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000289 | CON-BMP-MOM-000075 | 000-A-MOM-50065-001 | WEEKLY CONSTRUCTION MEETING N. 8 | 0 | 2018-07-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000289 | CON-BMP-MOM-000082 | 000-A-MOM-50066-001 | WEEKLY CONSTRUCTION MEETING N. 9 | 0 | 2018-07-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000289 | CON-BMP-MOM-000085 | 000-A-MOM-50067-001 | WEEKLY CONSTRUCTION MEETING N. 10 | 0 | 2018-07-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000290 | CON-BMP-MOM-000076 | 000-A-MOM-50063-001 | PAINTING SYSTEM FOR STEEL STRUCTURES INSIDE PACKAGES | 0 | 2018-07-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000290 | CON-BMP-MOM-000086 | 000-A-MOM-50068-001 | PROCUREMENT WEEKLY MEETING N. 16 | 0 | 2018-07-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000290 | CON-BMP-MOM-000087 | 000-A-MOM-50069-001 | WEEKLY PROGRESS MEETING N. 13 | 0 | 2018-07-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000291 | 076551C-000D-MS-8200-015 | 000-R-MST-50002-001 | METHOD OF STATEMENTS FOR TEMPORARY CONSTRUCTION FACITLITIES (EX 000R-MS-8200-001/000-R-MST-60001-001) | B | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-000292 | 000-L-TCQ-00020-001 | 000-L-TCQ-00020-001 | TECHNICAL QUERY (TQ) - TANK STAIR ORIENTATION | 0 | 2018-07-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000293 | 076551C-000D-PP-819 | 000-A-PRO-50091-001 | TRAFFIC MANAGEMENT PLAN | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 |  |  | CLASS 2
CON-BMP-TRA-000294 | 076551C-000D-PP-851 | 000-A-PRO-50058-001 | SITE HSE PLAN (LOSS PREVENTION PROGRAM) | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 |  |  | CLASS 2
CON-BMP-TRA-000295 | 076551C-000D-MTO-1311-001 | 000-L-MTO-50002-001 | PIPING STANDARD ASSEMBLY COLLECTION | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 |  |  | CLASS 2
CON-BMP-TRA-000296 | 076551C-000D-SL-1020-002 | 000-A-INX-50096-001 | BIDDERS LIST FOR RECIPROCATING COMPRESSOR (GENERAL SERVICE) | 0 | 2018-07-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000297 | 076551C-000D-SL-4112-001-A | 000-A-INX-50104-001 | BIDDERS LIST FOR NITROGEN GENERATION STORAGE AND VAPORIZATION | 0 | 2018-07-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000298 | CON-BMP-MOM-000083 | 000-A-MOM-50070-001 | MONTHLY MEETING NO. 4 | 0 | 2018-07-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000299 | 076551C-000D-RR-1020 | 000-A-WRS-50020-001 | WEEKLY PROGRESS REPORT N 20 AS OF JULY 27TH 2018 (WEEK 022) | 0 | 2018-07-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000300 | 076551C-000D-JSD-1510-002 | 000-J-TSP-50001-001 | GENERAL DESIGN RULES FOR AUTOMATION SYSTEM AVAILABILITY (ASA) | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 |  |  | CLASS 2
CON-BMP-TRA-000301 | 076551C-000D-JSD-1511-001 | 000-J-TSP-50002-001 | GENERAL DESIGN RULES FOR DCS BASIC CONFIGURATION CRITERIA & PARAMETER DEFINITION | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000302 | 076551C-000D-STC-1890-001-001 | 000-M-STD-50001-001 | STRUCTURAL STEEL WORKS DAVITS ON PLATFORMS TYPICAL DETAILS | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-000302 | 076551C-000D-STC-1890-002-001 | 000-M-STD-50002-001 | STRUCTURAL STEEL WORKS GRATING FASTENING SYSTEM TYPICAL DETAILS | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-000302 | 076551C-000D-STC-1890-002-002 | 000-M-STD-50002-002 | STRUCTURAL STEEL WORKS GRATING FASTENING SYSTEM TYPICAL DETAILS | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-000302 | 076551C-000D-STC-1890-003-001 | 000-M-STD-50003-001 | STRUCTURAL STEEL WORKS GRATING TYPICAL DETAIL | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-000302 | 076551C-000D-STC-1890-003-002 | 000-M-STD-50003-002 | STRUCTURAL STEEL WORKS GRATING TYPICAL DETAIL | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-000302 | 076551C-000D-STC-1890-003-003 | 000-M-STD-50003-003 | STRUCTURAL STEEL WORKS GRATING TYPICAL DETAIL | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-000302 | 076551C-000D-STC-1890-004-001 | 000-M-STD-50004-001 | STRUCTURAL STEEL WORKS MOMENT CONNECTED BEAMS AND VERTICAL BRACINGS CONNECTIONS | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-000303 | 076551C-000D-STC-1790-001-001 | 000-Q-STD-50001-001 | CONCRETE WORKS EMBEDDED PLATES TYPICAL DETAILS | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-000303 | 076551C-000D-STC-1790-002-001 | 000-Q-STD-50002-001 | CONCRETE WORKS SLIDING PLATES TYPICAL DETAILS | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-000304 | 076551C-000D-STC-2000-001-001 | 000-R-STD-50001-001 | BUILDING STANDARD DRAWING INTERNAL FINISH DETAIL | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000304 | 076551C-000D-STC-2000-002-001 | 000-R-STC-50002-001 | BUILDING STANDARD DRAWING INTERNAL FINISH DETAIL | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000304 | 076551C-000D-STC-2000-005-001 | 000-R-STC-50005-001 | BUILDING STANDARD DRAWING FENCE DETAIL | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000304 | 076551C-000D-STC-2000-006-001 | 000-R-STC-50006-001 | BUILDING STANDARD DRAWING CONCRETE MASONRY WALL DETAIL | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000304 | 076551C-000D-STC-2000-007-001 | 000-R-STC-50007-001 | BUILDING STANDARD DRAWING DOOR SCHEDULE | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000304 | 076551C-000D-STC-2000-008-001 | 000-R-STC-50008-001 | BUILDING STANDARD DRAWING DOOR SCHEDULE | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000305 | 076551C-000D-PP-402 | 000-A-PRO-50094-001 | INCIDENTAL COST MANAGEMENT PROCEDURE | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 |  |  | CLASS 2
CON-BMP-TRA-000306 | 076551C-000D-STC-1890-005-001 | 000-M-STD-50005-001 | STRUCTURAL STEEL WORKS SHEAR CONNECTED BEAMS - MEMBER SPLICES AND HOR. BRACINGS CONNECT | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-000307 | 076551C-000D-SL-0811-005 | 000-A-INX-50110-001 | BIDDERS LIST FOR HP CENTRIFUGAL SEPARATOR | 0 | 2018-08-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000308 | 076551C-000D-PLG-305 | 000-A-SCH-50003-001 | LEVEL 3 EPC SCHEDULE | B | 2018-08-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-000309 | 076551C-000D-STC-1490-001-001 | 000-S-STD-50001-001 | STANDARD DRAWING UNDERGROUND TYPICAL DETAILS CATCH BASIN | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000309 | 076551C-000D-STC-1490-002-001 | 000-S-STD-50002-001 | STANDARD DRAWING UNDERGROUND TYPICAL DETAILS CLEAN OUT & FUNNEL | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000309 | 076551C-000D-STC-1490-003-001 | 000-S-STD-50003-001 | STANDARD DRAWING UNDERGROUND TYPICAL DETAILS ONE CHAMBER MANHOLE (MH) | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000309 | 076551C-000D-STC-1490-004-001 | 000-S-STD-50004-001 | STANDARD DRAWING UNDERGROUND TYPICAL DETAILS DOUBLE CHAMBER MANHOLE (CH) | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000309 | 076551C-000D-STC-1490-005-001 | 000-S-STD-50005-001 | STANDARD DRAWING UNDERGROUND TYPICAL DETAILS TRIPLE CHAMBER MANHOLE (CH) | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000309 | 076551C-000D-STC-1490-006-001 | 000-S-STD-50006-001 | STANDARD DRAWING UNDERGROUND TYPICAL DETAILS SOAKAWAY & GHYDRANT FOUNDATION | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000309 | 076551C-000D-STC-1490-007-001 | 000-S-STD-50007-001 | STANDARD DRAWING UNDERGROUND TYPICAL DETAILS SANITARY MANHOLE | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000310 | 076551C-000D-PP-553 | 000-A-PRO-50042-001 | PROJECT ENVIRONMENTAL MANAGEMENT PLAN | B | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 |  |  | CLASS 2
CON-BMP-TRA-000311 | 076551C-000D-PP-610 | 000-A-PRI-50002-001 | VENDOR PRE-QUALIFICATION PROCEDURE | 0A | 2018-08-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-23 | 1 - APPROVED | 2018-08-09 | CLASS 1
CON-BMP-TRA-000312 | 076551C-000D-QCP-1310-001 | 000-L-PQP-50005-001 | QUALITY CONTROL PLAN PIPING PREFABRICATION | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-000312 | 076551C-000D-QCP-1320-001 | 000-L-PQP-50006-001 | QUALITY CONTROL PLAN PIPING ERECTION (ABOVE & UNDERGROUND) | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-000312 | 076551C-000D-QCP-1330-001 | 000-L-PQP-50007-001 | QUALITY CONTROL PLAN STEAM TRACING SYSTEM | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-000312 | 076551C-000D-QCP-1370-001 | 000-L-PQP-50008-001 | QUALITY CONTROL PLAN PIPING TIE-INS | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-000312 | 076551C-000D-QCP-1380-001 | 000-L-PQP-50009-001 | QUALITY CONTROL PLAN PIPING SUPPORT PREFABRICATION | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-000312 | 076551C-000D-QCP-1390-001 | 000-L-PQP-50010-001 | QUALITY CONTROL PLAN PIPING NDE & PWHT MANAGEMENT | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-000313 | 076551C-000D-PP-854 | 000-A-PRO-50060-001 | WASTE MANAGEMENT PROGRAM | B | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 |  |  | CLASS 2
CON-BMP-TRA-000314 | 076551C-000D-MS-1320-051 | 000-L-MST-50001-001 | CONSTRUCTION SPECIFICATION FOR PIPING PREFABRICATION ERECTION AND NON DESTRUCTIVE EXAMINATION | A | 2018-08-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 1
CON-BMP-TRA-000315 | 076551C-000D-QCP-2010-001 | 000-N-PQP-50001-001 | QUALITY CONTROL PLAN BUILDINGS FIRE RATED PANELS INSTALLATION | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-000316 | 076551C-000D-QCP-2000-001 | 000-R-PQP-50001-001 | QUALITY CONTROL PLAN BUILDING (CONCRETE & MASONRY) | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-000316 | 076551C-000D-QCP-2041-001 | 000-R-PQP-50002-001 | QUALITY CONTROL PLAN BUILDINGS HVAC (HEATING VENTILATION AND AIR CONDITIONING) SYSTEM INSTALLATION | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-000316 | 076551C-000D-QCP-2043-001 | 000-R-PQP-50003-001 | QUALITY CONTROL PLAN LIFT INSTALLATION | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-000316 | 076551C-000D-QCP-2045-002 | 000-R-PQP-50004-001 | QUALITY CONTROL PLAN FIRE FIGHTING SYSTEM INSTALLATION | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-000317 | CON-BMP-MOM-000073 | 000-A-MOM-50072-001 | PROCUREMENT WEEKLY MEETING N. 13 | 0 | 2018-08-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000317 | CON-BMP-MOM-000081 | 000-A-MOM-50073-001 | PROCUREMENT WEEKLY MEETING N. 15 | 0 | 2018-08-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000317 | CON-BMP-MOM-000089 | 000-A-MOM-50074-001 | PROCUREMENT WEEKLY MEETING N. 17 | 0 | 2018-08-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000317 | CON-BMP-MOM-000092 | 000-A-MOM-50071-001 | PROCUREMENT WEEKLY MEETING N. 18 | 0 | 2018-08-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000318 | 076551C-000D-STC-2000-003-001 | 000-R-STD-50003-001 | BUILDING STANDARD DRAWING INTERNAL FINISH DETAIL | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-000318 | 076551C-000D-STC-2000-004-001 | 000-R-STD-50004-001 | BUILDING STANDARD DRAWING ROOF WATERPROOFING AND DRAIN DETAIL | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-000319 | CON-BMP-MOM-000088 | 000-A-MOM-50075-001 | WEEKLY CONSTRUCTION MEETING N. 11 | 0 | 2018-08-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000319 | CON-BMP-MOM-000090 | 000-A-MOM-50076-001 | PROJECT CONTROL MEETING N. 12 | 0 | 2018-08-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000319 | CON-BMP-MOM-000091 | 000-A-MOM-50077-001 | WEEKLY PROGRESS MEETING N. 14 | 0 | 2018-08-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000320 | 076551C-000D-PP-859 | 000-A-PRO-50087-001 | SITE SAFE SCAFFOLDING MANAGEMENT | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 |  |  | CLASS 2
CON-BMP-TRA-000321 | 076551C-000D-PLG-309 | 000-A-PLD-50003-001 | PROGRESS CONTROL TABLES | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 |  |  | CLASS 2
CON-BMP-TRA-000322 | 076551C-000D-PP-509 | 000-A-ORG-50005-001 | QA/QC/ ORGANIZATION CHART | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000323 | 076551C-000D-RR-105 | 000-A-MRS-50005-001 | MONTHLY PROGRESS REPORT N 05 AS OF JULY 27TH 2018 (MONTH 05) | 0 | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 |  |  | CLASS 2
CON-BMP-TRA-000324 | 076551C-000D-JSD-1700-001 | 000-M-TSP-50001-001 | JOB DESIGN SPECIFICATION FOR SHALLOW FOUNDATIONS CONCRETE AND STEEL STRUCTURES | 0 | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-28 | CLASS 2
CON-BMP-TRA-000325 | 076551C-000D-RR-1021 | 000-A-WRS-50021-001 | WEEKLY PROGRESS REPORT N 21 AS OF AUGUST 3RD 2018 (WEEK 023) | 0 | 2018-08-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000326 | CON-BMP-MOM-000094 | 000-A-MOM-50078-001 | WEEKLY PROGRESS MEETING N. 15 | 0 | 2018-08-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000327 | CON-BMP-MOM-000095 | 000-A-MOM-50079-001 | CHLORIDE CONTENT WITHIN INSULATION MATERIAL | 0 | 2018-08-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000328 | 076551C-000D-SL-4026-001 | 000-A-INX-50111-001 | BIDDERS LIST FOR MARINE LOADING ARMS | 0 | 2018-08-07 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000329 | 076551C-000D-MS-6740-051 | 000-A-MST-50004-001 | JOB CONSTRUCTION SPECIFICATION FOR MATERIAL RECEIVING AND WAREHOUSING | A | 2018-08-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 1
CON-BMP-TRA-000330 | 076551C-000D-MS-6850-051 | 000-K-MST-50001-001 | JOB CONSTRUCTION SPECIFICATION FOR MACHINERY AND AIR COOLERS INSTALLATION | A | 2018-08-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 |  |  | CLASS 1
CON-BMP-TRA-000331 | 076551C-000D-MS-1500-051 | 000-I-MST-50001-001 | JOB CONSTRUCTION SPECIFICATION FOR INSTRUMENT INSTALLATION | A | 2018-08-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 1
CON-BMP-TRA-000332 | 076551C-000D-PP-864 | 000-A-PRO-50099-001 | HEAT STRESS PREVENTION PROGRAM | A | 2018-08-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 |  |  | CLASS 2
CON-BMP-TRA-000333 | 076551C-000D-STC-1390-000 | 000-L-STD-50001-001 | STRUCTURAL AUXILIARY PIPING SUPPORTS COLLECTION | A | 2018-08-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 |  |  | CLASS 2
CON-BMP-TRA-000334 | 076551C-000D-MS-0000-52 | 000-B-MST-50002-001 | JOB CONSTRUCTION SPECIFICATION FOR WELDING ACTIVITIES MANAGEMENT | A | 2018-08-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 |  |  | CLASS 2
CON-BMP-TRA-000335 | 076551C-000D-MS-6820-051 | 000-C-MST-50001-001 | JOB CONSTRUCTION SPECIFICATION FOR STATIC EQUIPMENT AND TRAYS/INTERNALS INSTALLATION | A | 2018-08-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-000336 | 076551C-000D-MS-1800-001 | 000-M-MST-50001-001 | METHOD OF STATEMENT FOR STEEL STRUCTURES ERECTION | A | 2018-08-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 1
CON-BMP-TRA-000337 | 076551C-000D-JSS-1328-001 | 000-L-TSP-50009-001 | JOB SUPPLY SPECIFICATION FOR GLASS REINFORCED PLASTIC PIPING | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-28 | CLASS 2
CON-BMP-TRA-000338 | 076551C-000D-DL-1328-001 | 000-L-IDL-50025-001 | DEVIATION LIST FOR FIBERGLASS REINFORCED PLASTIC PIPING | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000338 | 076551C-000D-ITP-1328-001 | 000-L-ITP-50025-001 | INSPECTION AND TEST PLAN FOR FIBERGLASS REINFORCED PLASTIC PIPING | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000338 | 076551C-000D-MR-1328-001 | 000-L-MRQ-50025-001 | MATERIAL REQUISTION FOR FIBERGLASS REINFORCED PLASTIC PIPING | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000338 | 076551C-000D-SR-1328-001 | 000-L-SOW-50025-001 | SCOPE OF SUPPLY FOR FIBERGLASS REINFORCED PLASTIC PIPING | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000339 | 076551C-000D-PP-909 | 000-A-PRO-50088-001 | SYSTEMS COMPLETION EXECUTION PLAN | B | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-000341 | CON-BMP-MOM-000074 | 000-A-MOM-50080-001 | CEO MANAGEMENT MEETING N. 1 | 0 | 2018-08-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000342 | CON-BMP-MOM-000093 | 000-A-MOM-50081-001 | WEEKLY CONSTRUCTION MEETING N. 12 | 0 | 2018-08-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000343 | CON-BMP-MOM-000097 | 000-A-MOM-50082-001 | PROJECT CONTROL MEETING N. 13 | 0 | 2018-08-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000344 | 076551C-000D-JSS-1300-001 | 000-L-TSP-50001-001 | GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | 0A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-000344 | 076551C-000D-JSS-1310-001 | 000-L-TSP-50004-001 | JOB SUPPLY SPECIFICATION FOR VALVES (GATE - GLOBE - CHECK) | 0A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-000344 | 076551C-000D-JSS-1320-001 | 000-L-TSP-50008-001 | JOB SUPPLY SPECIFICATION FOR PIPES | 0A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-000344 | 076551C-000D-JSS-1330-001 | 000-L-TSP-50010-001 | JOB SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS | 0A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-000344 | 076551C-000D-JSS-1350-001 | 000-L-TSP-50012-001 | JOB SUPPLY SPECIFICATION FOR FLANGES | 0A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-000345 | 076551C-000D-PP-957 | 000-A-PRI-50021-001 | RELIABILITY & MAINTENANCE GUIDELINES | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-000346 | 076551C-000D-PP-955 | 000-A-PRI-50022-001 | CRITICALITY ASSESSMENT GUIDELINES | 0 | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 1 - APPROVED | 2018-08-24 | CLASS 2
CON-BMP-TRA-000347 | 076551C-000D-PLG-102 | 000-A-PMP-50001-001 | WORK BREAKDOWN STRUCTURE | D | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 | 1 - APPROVED | 2018-08-23 | CLASS 1
CON-BMP-TRA-000348 | 076551C-000D-PP-312 | 000-A-PRO-50073-001 | PROGRESS MEASUREMENT AND MILESTONE CERTIFICATE PROCEDURE | D | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-000349 | 076551C-000D-ML-303 | 000-A-PLD-50002-001 | BASIS OF SCHEDULE | 0A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-000350 | CON-BMP-MOM-000099 | 000-A-MOM-50083-001 | PROJECT CONTROL MEETING N. 14 | 0 | 2018-08-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000352 | 076551C-000D-PP-820 | 000-A-PRO-50093-001 | CAMP MANAGEMENT PLAN | B | 2018-08-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-06 |  |  | CLASS 1
CON-BMP-TRA-000353 | 076551C-000D-SL-4041-001 | 000-A-INX-50112-001 | BIDDERS LIST FOR TRUCK SCALE WEIGHING BRIDGES | 0 | 2018-08-22 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000354 | 076551C-000D-SL-4026-001 | 000-A-INX-50111-001 | BIDDERS LIST FOR MARINE LOADING ARMS | 0A | 2018-08-22 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000355 | 076551C-000D-RR-1022 | 000-A-WRS-50022-001 | WEEKLY PROGRESS REPORT N 22 AS OF AUGUST 17TH 2018 (WEEK 24 AND WEEK 25) | 0 | 2018-08-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000356 | 076551C-000D-DW-1600-002-001 | 000-P-WRD-50002-001 | 6 6 KV PROTECTION DIAGRAM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-000356 | 076551C-000D-DW-1600-002-002 | 000-P-WRD-50002-002 | 6 6 KV PROTECTION DIAGRAM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-000356 | 076551C-000D-DW-1600-002-003 | 000-P-WRD-50002-003 | 6 6 KV PROTECTION DIAGRAM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-000356 | 076551C-000D-DW-1600-002-004 | 000-P-WRD-50002-004 | 6 6 KV PROTECTION DIAGRAM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-000356 | 076551C-000D-DW-1600-002-005 | 000-P-WRD-50002-005 | 6 6 KV PROTECTION DIAGRAM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-000356 | 076551C-000D-DW-1600-002-006 | 000-P-WRD-50002-006 | 6 6 KV PROTECTION DIAGRAM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-000356 | 076551C-000D-DW-1600-002-007 | 000-P-WRD-50002-007 | 6 6 KV PROTECTION DIAGRAM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-000356 | 076551C-000D-DW-1600-002-008 | 000-P-WRD-50002-008 | 6 6 KV PROTECTION DIAGRAM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-000357 | 076551C-000D-MS-1600-051 | 000-P-MST-50001-001 | JOB CONSTRUCTION SPECIFICATION FOR ELECTRICAL INSTALLATION | A | 2018-08-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-07 |  |  | CLASS 1
CON-BMP-TRA-000358 | 076551C-000D-PP-809 | 000-A-PRO-50100-001 | SITE QUALITY CONTROL PLAN | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000358 | 076551C-000D-PP-811 | 000-A-PRO-50101-001 | PREPARATION OF CONSTRUCTION, PRECOMMISSIONING AND COMMISSIONING QUALITY DOSSIER | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000358 | 076551C-000D-PP-813 | 000-A-PRO-50102-001 | PIPING SYSTEM PRESSURE TEST AND TEST PACKAGE MANAGEMENT PROCEDURE | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000359 | 076551C-000D-PP-269 | 000-A-PRO-50104-001 | GUIDELINE FOR 3D MODEL REVIEW | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-000360 | 076551C-000D-PP-804 | 000-A-PRO-50052-001 | CONSTRUCTION EXECUTION PLAN | B | 2018-08-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-07 |  |  | CLASS 1
CON-BMP-TRA-000361 | CON-BMP-MOM-000101 | 000-A-MOM-50084-001 | PROJECT CONTROL MEETING N. 15 | 0 | 2018-08-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000362 | CON-BMP-MOM-000102 | 000-A-MOM-50085-001 | MONTHLY MEETING N. 5 | 0 | 2018-08-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000363 | 076551C-000D-PP-111 | 000-A-PRO-50009-001 | REPORTING PROCEDURE | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000364 | 076551C-000D-MS-0000-051 | 000-B-MST-50001-001 | JOB CONSTRUCTION SPECIFICATION FOR WELDERS MANAGEMENT | B | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-07 |  |  | CLASS 1
CON-BMP-TRA-000365 | 076551C-000D-QCP-6820-001 | 000-C-PQP-50001-001 | QUALITY CONTROL PLAN STATIC EQUIPMENT INSTALLATION | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000365 | 076551C-000D-QCP-6860-001 | 000-C-PQP-50002-001 | QUALITY CONTROL PLAN EQUIPMENT INTERNALS INSTALLATION (TRAYS) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000365 | 076551C-000D-QCP-6860-002 | 000-C-PQP-50003-001 | QUALITY CONTROL PLAN EQUIPMENT INTERNALS INSTALLATION (DISTRIBUTORS GRIDS DEMISTERS ETC) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000366 | 076551C-000D-QCP-6831-001 | 000-F-PQP-50001-001 | QUALITY CONTROL PLAN PACKAGE FURNACE (SITE ASSEMBLED) INSTALLATION | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000366 | 076551C-000D-QCP-6835-001 | 000-F-PQP-50002-001 | QUALITY CONTROL PLAN REFRACTORY INSTALLATION | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-000367 | 076551C-000D-QCP-6833-001 | 000-S-PQP-50015-001 | QUALITY CONTROL PLAN FLARE SYSTEM ERECTION | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000367 | 076551C-000D-QCP-6880-001 | 000-S-PQP-50016-001 | QUALITY CONTROL PLAN PACKAGES INSTALLATION | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000367 | 076551C-000D-QCP-6880-002 | 000-S-PQP-50017-001 | QUALITY CONTROL PLAN SKID MOUNTED PACKAGES | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000367 | 076551C-000D-QCP-6883-001 | 000-S-PQP-50018-001 | QUALITY CONTROL PLAN MISCELLANEA EQUIPMENTS INSTALLATION | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000368 | 076551C-000D-QCP-6850-001 | 000-G-PQP-50001-001 | QUALITY CONTROL PLAN MACHINERY INSTALLATION (CENTRIFUGAL AND ROTARY PUMPS) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000369 | 076551C-000D-QCP-2200-001 | 000-N-PQP-50002-001 | QUALITY CONTROL PLAN INSULATION | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-000370 | 000-C-TCQ-00014-001 | 000-C-TCQ-00014-001 | TECHNICAL QUERY (TQ) - AUSTENITIC STAINLESS STEEL CLADDING FOR PRESSURE EQUIPMENT (HEAT TREATMENT) | 0 | 2018-08-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000371 | 076551C-000D-MS-6740-052 | 000-B-TSP-50005-001 | JOB SPEC FOR MATERIAL PRESERVATION DURING CONSTRUCTION PRECOMM COMMISSIONING AND START-UP (EX 000-B-MST-50005-001) | B | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000372 | 000-L-TCQ-00021-001 | 000-L-TCQ-00021-001 | TECHNICAL QUERY (TQ) - MATERIAL OF STEAM TRACERS | 0 | 2018-08-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000372 | 000-L-TCQ-00023-001 | 000-L-TCQ-00023-001 | TECHNICAL QUERY (TQ) - PWHT FOR CS PIPING (WITH NO SERVICE REQUIREMENTS) | 0 | 2018-08-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000373 | 000-P-TCQ-00007-001 | 000-P-TCQ-00007-001 | TECHNICAL QUERY (TQ) - GROUNDING CABLE FOR UNDERGROUND INSTALLATION | 0 | 2018-08-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000373 | 000-P-TCQ-00008-001 | 000-P-TCQ-00008-001 | TECHNICAL QUERY (TQ) - TYPE OF CONNECTION AND JOIN FOR UNDERGROUND GROUNDING CABLE | 0 | 2018-08-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000373 | 000-P-TCQ-00010-001 | 000-P-TCQ-00010-001 | TECHNICAL QUERY (TQ) - AMBIENT TYPE FOR INDOOR EQUIPMENT | 0 | 2018-08-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000374 | 076551C-000D-PP-915 | 000-A-PRO-50103-001 | OPERABILITY AND MAINTENANCE CONSIDERATIONS GUIDELINE | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000375 | 076551C-000D-DW-1652-002-001 | 000-P-SYM-50002-001 | SYMBOLOGY FOR ELECTRICAL LAYOUT | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-001 | 000-P-WRD-50001-001 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-002 | 000-P-WRD-50001-002 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-003 | 000-P-WRD-50001-003 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-004 | 000-P-WRD-50001-004 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-005 | 000-P-WRD-50001-005 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-006 | 000-P-WRD-50001-006 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-007 | 000-P-WRD-50001-007 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-008 | 000-P-WRD-50001-008 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-009 | 000-P-WRD-50001-009 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-010 | 000-P-WRD-50001-010 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000376 | 076551C-000D-DW-1600-005-011 | 000-P-WRD-50001-011 | 0 4 KV PROTECTION DIAGRAMS | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000377 | 076551C-000D-DL-1800-001 | 000-M-IDL-50003-001 | DEVIATION LIST FOR STEEL STRUCTURES | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000377 | 076551C-000D-ITP-1800-001 | 000-M-ITP-50003-001 | INSPECTION AND TEST PLAN FOR STEEL STRUCTURES | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000377 | 076551C-000D-MR-1800-001 | 000-M-MRQ-50003-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000377 | 076551C-000D-SR-1800-001 | 000-M-SOW-50003-001 | SCOPE OF SUPPLY FOR STEEL STRUCTURES | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-000378 | 076551C-000D-QCP-6850-002 | 000-K-PQP-50001-001 | QUALITY CONTROL PLAN MACHINERY INSTALLATION BLOWERS AND FANS | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000378 | 076551C-000D-QCP-6850-003 | 000-K-PQP-50002-001 | QUALITY CONTROL PLAN MACHINERY INSTALLATION CENTRIFUGAL COMPRESSORS | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000378 | 076551C-000D-QCP-6850-004 | 000-K-PQP-50003-001 | QUALITY CONTROL PLAN MACHINERY INSTALLATION RECIPROCATING COMPRESSORS | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000378 | 076551C-000D-QCP-6850-005 | 000-K-PQP-50004-001 | QUALITY CONTROL PLAN MACHINERY INSTALLATION MIXERS AND AGITATORS | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000378 | 076551C-000D-QCP-6852-001 | 000-K-PQP-50005-001 | QUALITY CONTROL PLAN ELEVATOR INSTALLATION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000378 | 076551C-000D-QCP-6871-001 | 000-K-PQP-50006-001 | QUALITY CONTROL PLAN AIR COOLERS INSTALLATION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000378 | 076551C-000D-QCP-6882-001 | 000-K-PQP-50007-001 | QUALITY CONTROL PLAN BRIDGE CRANE INSTALLATION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000379 | 076551C-000D-QCP-2520-001 | 000-D-PQP-50001-001 | QUALITY CONTROL PLAN FIXED ROOF TANKS ERECTION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000379 | 076551C-000D-QCP-2520-002 | 000-D-PQP-50002-001 | QUALITY CONTROL PLAN FLOATING ROOF TANKS ERECTION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000379 | 076551C-000D-QCP-2520-003 | 000-D-PQP-50003-001 | QUALITY CONTROL PLAN CRYOGENIC TANKS ERECTION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000379 | 076551C-000D-QCP-2530-001 | 000-D-PQP-50004-001 | QUALITY CONTROL PLAN STORAGE SPHERE ERECTION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000379 | 076551C-000D-QCP-2560-001 | 000-D-PQP-50005-001 | QUALITY CONTROL PLAN PARTIALLY PREASSEMBLED SILOS ERECTION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000380 | 076551C-000D-QCP-1812-001 | 000-M-PQP-50005-001 | QUALITY CONTROL PLAN STEEL STRUCTURES ERECTION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000380 | 076551C-000D-QCP-1812-002 | 000-M-PQP-50006-001 | QUALITY CONTROL PLAN SECONDARY STEEL TRUCTURES ERECTION (LADDERS PLATFORMS WALKWAYS HANDRAILS AND GRATINGS) | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000380 | 076551C-000D-QCP-1812-003 | 000-M-PQP-50007-001 | QUALITY CONTROL PLAN STEEL STRUCTURES REVAMPING | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000381 | 076551C-000D-QCP-6872-001 | 000-E-PQP-50001-001 | QUALITY CONTROL PLAN COOLING TOWER MECHANICAL INSTALLATION | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000382 | 076551C-000D-QCP-2300-001 | 000-B-PQP-50001-001 | QUALITY CONTROL PLAN PAINTING | A | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-000383 | 076551C-000D-PP-856 | 000-A-PRO-50075-001 | HSE TRAINING PLAN | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-000384 | 076551C-000D-MS-8400-001 | 000-R-MST-50003-001 | METHOD OF STATEMENTS FOR ACCOMDATION PLAN | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-000385 | CON-BMP-MOM-000100 | 000-A-MOM-50086-001 | WEEKLY CONSTRUCTION MEETING N. 13 | 0 | 2018-08-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000386 | 076551C-000D-RR-1023 | 000-A-WRS-50023-001 | WEEKLY PROGRESS REPORT N 23 AS OF AUGUST 24TH 2018 (WEEK 26) | 0 | 2018-08-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000387 | 000-S-TCQ-00002-001 | 000-S-TCQ-00002-001 | TECHNICAL QUERY FOR ACCEPTANCE FOR ENERSUL'S PREMIUM GRANULAR PRODUCT | 0 | 2018-08-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000388 | 076551C-000D-PP-306 | 000-A-PRO-50035-001 | RISK MANAGEMENT PLAN | A | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-000389 | 076551C-000D-PP-101 | 000-A-PRO-50001-001 | PROJECT EXECUTION PLAN | D | 2018-08-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-13 |  |  | CLASS 1
CON-BMP-TRA-000390 | 076551C-000D-PP-016 | 000-A-PRI-50013-001 | PRESCRIPTIONS FOR PREPARATION OF VENDOR DATA BOOK | A | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-000395 | 076551C-000D-PP-507 | 000-A-PRO-50082-001 | PROJECT AUDIT PLAN AND SCHEDULE | B | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-000396 | 076551C-000D-PP-508 | 000-A-PRO-50083-001 | CORRECTIVE ACTION PROCEDURE | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-000397 | 076551C-000D-PP-124 | 000-A-PRO-50018-001 | TTSJV ENGINEERING MANAGEMENT PLAN | B | 2018-08-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-14 |  |  | CLASS 1
CON-BMP-TRA-000399 | CON-BMP-MOM-000104 | 000-A-MOM-50087-001 | PROCUREMENT WEEKLY MEETING N. 19 | 0 | 2018-08-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000400 | CON-BMP-MOM-000106 | 000-A-MOM-50088-001 | PROJECT CONTROL MEETING N. 16 | 0 | 2018-08-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000401 | 076551C-000D-SL-1641-001 | 000-A-INX-50113-001 | BIDDERS LIST FOR POWER/DISTRIBUTION TRANSFORMERS AND NEUTRAL GROUNDING RESISTORS | 0 | 2018-08-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000401 | 076551C-000D-SL-1652-001 | 000-A-INX-50114-001 | BIDDERS LIST FOR HV SWITCHGEARS | 0 | 2018-08-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000401 | 076551C-000D-SL-1654-001 | 000-A-INX-50115-001 | BIDDERS LIST FOR LV SWITCHGEARS | 0 | 2018-08-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000402 | 076551C-000D-JSD-2000-001 | 000-R-TSP-50002-001 | JOB DESIGN SPECIFICATION FOR BUILDINGS | B | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010001 | 076551C-000R-MS-1410-001 | 000-S-MST-60001-001 | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION REFINERY AREA | A | 2018-03-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-03 | CLASS 2
CON-BMP-TRA-010001 | 076551C-000R-PS-1410-001 | 000-S-BOM-60001-001 | PRICE LIST FOR SOIL INVESTIGATION REFINERY AREA | A | 2018-03-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-03 | CLASS 2
CON-BMP-TRA-010002 | 076551C-079-CN-0007-001 | 079-A-BOD-00001-001 | PROCESS DESIGN BASIS SPENT CAUSTIC TREATING PLANT | A | 2018-03-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-10 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-010003 | 076551C-082-CN-0007-001 | 082-A-BOD-00001-001 | PROCESS DESIGN BASIS 1 FLARE SYSTEM | A | 2018-03-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-10 | 3 - REVIEWED WITH COMMENTS | 2018-04-05 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0051-001-001 | 000-A-PPN-60000-001 | GENERAL PLOT PLAN REFINERY NORTH SIDE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0051-002-001 | 000-A-PPN-60001-001 | GENERAL PLOT PLAN REFINERY SOUTH SIDE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0053-005-001 | 000-A-PPN-60002-001 | OPERATING CENTRAL KEY PLAN NORTH SIDE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0053-006-001 | 000-A-PPN-60003-001 | OPERATING CENTRAL KEY PLAN SOUTH SIDE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0053-009-001 | 000-A-PPN-60005-001 | OVERALL KEY PLAN BMP | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0053-011-001 | 000-A-PPN-60004-001 | OVERALL OPERATING CENTER KEY PLAN | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-001-001 | 018-A-PFD-00001-001 | PROCESS FLOW DIAGRAM FIRST TRAIN REACTION AND SEPARATIONSECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-002-001 | 018-A-PFD-00001-002 | PROCESS FLOW DIAGRAM FIRST TRAIN H2 RECOVERY SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-003-001 | 018-A-PFD-00001-003 | PROCESS FLOW DIAGRAM FIRST TRAIN COMPRESSION SECTION SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-004-001 | 018-A-PFD-00001-004 | PROCESS FLOW DIAGRAM SECOND TRAIN REACTION AND SEPARATION SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-005-001 | 018-A-PFD-00001-005 | PROCESS FLOW DIAGRAM SECOND TRAIN H2 RECOVERY SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-006-001 | 018-A-PFD-00001-006 | PROCESS FLOW DIAGRAM SECOND TRAIN H2 COMPRESSION SECTION SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-007-001 | 018-A-PFD-00001-007 | PROCESS FLOW DIAGRAM SEPARATION & AMINE ABSORBER COMMON SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-008-001 | 018-A-PFD-00001-008 | PROCESS FLOW DIAGRAM ATMOSPHERIC COLUMN SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-009-001 | 018-A-PFD-00001-009 | PROCESS FLOW DIAGRAM VACUUM COLUMN SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-010-001 | 018-A-PFD-00001-010 | PROCESS FLOW DIAGRAM VACUUM TOWER SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-011-001 | 018-A-PFD-00001-011 | PROCESS FLOW DIAGRAM WASH WATER/LEAN AND RICH AMINE/SOUR WATER SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-012-001 | 018-A-PFD-00001-012 | PROCESS FLOW DIAGRAM WASH CATALYST HANDLING SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-013-001 | 018-A-PFD-00001-013 | PROCESS FLOW DIAGRAM CATALYST HANDLING SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-014-001 | 018-A-PFD-00001-014 | PROCESS FLOW DIAGRAM CATALYST HANDLING SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-015-001 | 018-A-PFD-00001-015 | PROCESS FLOW DIAGRAM SHORT CIRCULATION LOOP SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-016-001 | 018-A-PFD-00001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-017-001 | 018-A-PFD-00001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-018-001 | 018-A-PFD-00001-018 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-019-001 | 018-A-PFD-00001-019 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-020-001 | 018-A-PFD-00001-020 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-021-001 | 018-A-PFD-00001-021 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-022-001 | 018-A-PFD-00001-022 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-023-001 | 018-A-PFD-00001-023 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-024-001 | 018-A-PFD-00001-024 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-025-001 | 018-A-PFD-00001-025 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-026-001 | 018-A-PFD-00001-026 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-027-001 | 018-A-PFD-00001-027 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-028-001 | 018-A-PFD-00001-028 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-029-001 | 018-A-PFD-00001-029 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-030-001 | 018-A-PFD-00001-030 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-031-001 | 018-A-PFD-00001-031 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-032-001 | 018-A-PFD-00001-032 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-033-001 | 018-A-PFD-00001-033 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-034-001 | 018-A-PFD-00001-034 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-035-001 | 018-A-PFD-00001-035 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-036-001 | 018-A-PFD-00001-036 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-037-001 | 018-A-PFD-00001-037 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-038-001 | 018-A-PFD-00001-038 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-039-001 | 018-A-PFD-00001-039 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-040-001 | 018-A-PFD-00001-040 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-041-001 | 018-A-PFD-00001-041 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-042-001 | 018-A-PFD-00001-042 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-043-001 | 018-A-PFD-00001-043 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-044-001 | 018-A-PFD-00001-044 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-045-001 | 018-A-PFD-00001-045 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-046-001 | 018-A-PFD-00001-046 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-047-001 | 018-A-PFD-00001-047 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-048-001 | 018-A-PFD-00001-048 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-049-001 | 018-A-PFD-00001-049 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-001-001 | 021-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HIGH PRESSURE LOOP | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-002-001 | 021-A-PFD-00001-002 | PROCESS FLOW DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-003-001 | 021-A-PFD-00001-003 | PROCESS FLOW DIAGRAM AMINE AND SOUR WATER | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-004-001 | 021-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-005-001 | 021-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-006-001 | 021-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-007-001 | 021-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-008-001 | 021-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-009-001 | 021-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-010-001 | 021-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-011-001 | 021-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-012-001 | 021-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-013-001 | 021-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-014-001 | 021-A-PFD-00001-014 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-015-001 | 021-A-PFD-00001-015 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-016-001 | 021-A-PFD-00001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-017-001 | 021-A-PFD-00001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-018-001 | 021-A-PFD-00001-018 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-019-001 | 021-A-PFD-00001-019 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-020-001 | 021-A-PFD-00001-020 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-021-001 | 021-A-PFD-00001-021 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-022-001 | 021-A-PFD-00001-022 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-023-001 | 021-A-PFD-00001-023 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010007 | 076551C-023-CN-0007-001 | 023-A-BOD-00001-001 | BASIS OF DESIGN 1HRU (UNIT 023) HYDROGEN RECOVERY UNIT | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-11 | CLASS 1
CON-BMP-TRA-010008 | 076551C-051-CN-0007-001 | 051-A-BOD-00001-001 | PROCESS DESIGN BASIS REFRIGERATED LPG STORAGE (AT SITRA MARINE TERMINAL) | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010009 | 076551C-056-CN-0007-001 | 056-A-BOD-00001-001 | PROCESS DESIGN BASIS SITRA TANK FARM | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010010 | 076551C-061-CN-0007-001 | 061-A-BOD-00001-001 | PROCESS DESIGN BASIS SITRA WHARF AND ASSOCIATED MARINE FACILITIES | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010011 | 076551C-073-CN-0007-001 | 073-A-BOD-00001-001 | PROCESS DESIGN BASIS LSFO FLARE SYSTEM MODIFICATIONS | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010012 | 076551C-081-CN-0007-001 | 081-A-BOD-00001-001 | PROCESS DESIGN BASIS LSDP FLARE SYSTEM REVAMPING | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010013 | 076551C-907-CN-0007-001 | 907-A-BOD-00001-001 | PROCESS DESIGN BASIS REFINERY TO SITRA TRANSFE LINES | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-010014 | 076551C-000R-PP-100 | 000-A-ORG-60001-001 | ROC PROJECT ORGANIZATION CHART | 0 | 2018-03-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010015 | 076551C-930-DW-1442-002-001 | 930-L-GAD-00001-001 | GENERAL LAYOUT INTERFACE POINT LOCATION AREA 1 | A | 2018-03-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 1
CON-BMP-TRA-010015 | 076551C-930-DW-1442-002-002 | 930-L-GAD-00001-002 | GENERAL LAYOUT INTERFACE POINT LOCATION AREA 2 | A | 2018-03-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 1
CON-BMP-TRA-010015 | 076551C-930-DW-1442-002-003 | 930-L-GAD-00001-003 | GENERAL LAYOUT INTERFACE POINT LOCATION AREA 3 | A | 2018-03-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 1
CON-BMP-TRA-010015 | 076551C-930-DW-1442-002-004 | 930-L-GAD-00001-004 | GENERAL LAYOUT INTERFACE POINT LOCATION AREA 4 | A | 2018-03-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 1
CON-BMP-TRA-010016 | 076551C-000R-DL-0811-001 | 000-C-IDL-60001-001 | DEVIATION LIST FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-000R-ITP-0811-001 | 000-C-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-000R-MR-0811-001 | 000-C-MRQ-60001-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-000R-SP-0811-001 | 000-C-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-000R-SR-0811-001 | 000-C-SOW-60001-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-002-001 | 018-C-GAD-00005-001 | 018V1002 TRAIN 1 INTERSTAGE SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-003-001 | 018-C-GAD-00006-001 | 018V1003 TRAIN 1 HP/HT SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-005-001 | 018-C-GAD-00007-001 | 018V1005 TRAIN 1 HP/MT SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-022-001 | 018-C-GAD-00008-001 | 018V2002 TRAIN 2 INTERSTAGE SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-023-001 | 018-C-GAD-00009-001 | 018V2003 TRAIN 2 HP/HT SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-025-001 | 018-C-GAD-00010-001 | 018V2005 TRAIN 2 HP/MT SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-DL-0411-001 | 000-C-IDL-60004-001 | DEVIATION LIST FOR 2.25CR-1MO-V REACTORS AND INTRNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-ITP-0411-001 | 000-C-ITP-60004-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V REACTORS AND INTRNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-MR-0411-001 | 000-C-MRQ-60004-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-SP-0411-001 | 000-C-GRD-60004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V REACTORS AND INTRNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-SR-0411-001 | 000-C-SOW-60004-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V REACTORS AND INTRNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-018-DW-0410-001-001 | 018-C-GAD-00001-001 | 018C1001R TRAIN 1 1ST REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-018-DW-0410-002-001 | 018-C-GAD-00002-001 | 018C1002R TRAIN 1 2ND REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-018-DW-0410-003-001 | 018-C-GAD-00003-001 | 018C2001R TRAIN 2 1ST REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-018-DW-0410-004-001 | 018-C-GAD-00004-001 | 018C2002R TRAIN 2 2ND REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-021-DW-0410-001-001 | 021-C-GAD-00001-001 | 021C0001R REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 2
CON-BMP-TRA-010018 | 076551C-000R-MS-1410-003 | 000-S-MST-60002-001 | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION TRANSFER LINE SITRA TANK FARAM AND SHARF AREA | A | 2018-03-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-17 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 2
CON-BMP-TRA-010018 | 076551C-000R-PS-1410-003 | 000-S-BOM-60002-001 | PRICE LIST FOR SOIL INVESTIGATION TRANSFER LINE SITRA TANK FARM AND WHARF AREAS | A | 2018-03-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-17 | 3 - REVIEWED WITH COMMENTS | 2018-04-16 | CLASS 2
CON-BMP-TRA-010019 | 076551C-023-PFD-0010-001-001 | 023-A-PFD-00001-001 | PROCESS FLOW DIAGRAM 1HRU HYDROGEN RECOVERY UNIT | A | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-16 | CLASS 1
CON-BMP-TRA-010019 | 076551C-023-PFD-0010-001-002 | 023-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-16 | CLASS 1
CON-BMP-TRA-010019 | 076551C-023-PFD-0010-001-003 | 023-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-16 | CLASS 1
CON-BMP-TRA-010020 | 076551C-000R-MS-1410-004 | 000-S-MST-60003-001 | TECHNICAL SPECIFICATION FOR TOPOGRAPHIC SURVEY FOR REFINERY TANK FARM TRANSFER LINE SITRA TANK FARM & WHARF AREAS | A | 2018-04-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-18 | CLASS 2
CON-BMP-TRA-010021 | 076551C-000R-DL-0960-001 | 000-G-IDL-60002-001 | DEVIATION LIST FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 1 - APPROVED | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-000R-ITP-0960-001 | 000-G-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-000R-MR-0960-001 | 000-G-MRQ-60002-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-000R-SP-0960-001 | 000-G-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-000R-SR-0960-001 | 000-G-SOW-60002-001 | SCOPE OF SUPPLY FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-018-SP-0960-001 | 018-G-DAT-00001-001 | 1ST 2ND REACTOR RECYCLE PUMPS PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010022 | 076551C-000R-PP-102 | 000-A-PRO-60001-001 | COORDINATION PROCEDURE BETWEEN BAPCO IPMT AND ROC | A | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010023 | 076551C-000R-DL-0411-001 | 000-C-IDL-60004-001 | DEVIATION LIST FOR 2.25CR-1MO-V REACTORS AND INTRNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-000R-ITP-0411-001 | 000-C-ITP-60004-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V REACTORS AND INTRNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-000R-MR-0411-001 | 000-C-MRQ-60004-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-000R-SP-0411-001 | 000-C-GRD-60004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V REACTORS AND INTRNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-000R-SR-0411-001 | 000-C-SOW-60004-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V REACTORS AND INTRNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-018-DW-0410-001-001 | 018-C-GAD-00001-001 | 018C1001R TRAIN 1 1ST REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-018-DW-0410-002-001 | 018-C-GAD-00002-001 | 018C1002R TRAIN 1 2ND REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-018-DW-0410-003-001 | 018-C-GAD-00003-001 | 018C2001R TRAIN 2 1ST REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-018-DW-0410-004-001 | 018-C-GAD-00004-001 | 018C2002R TRAIN 2 2ND REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-021-DW-0410-001-001 | 021-C-GAD-00001-001 | 021C0001R REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-DL-0811-001 | 000-C-IDL-60001-001 | DEVIATION LIST FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-ITP-0811-001 | 000-C-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-MR-0811-001 | 000-C-MRQ-60001-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-SP-0811-001 | 000-C-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-SR-0811-001 | 000-C-SOW-60001-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-002-001 | 018-C-GAD-00005-001 | 018V1002 TRAIN 1 INTERSTAGE SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-003-001 | 018-C-GAD-00006-001 | 018V1003 TRAIN 1 HP/HT SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-005-001 | 018-C-GAD-00007-001 | 018V1005 TRAIN 1 HP/MT SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-022-001 | 018-C-GAD-00008-001 | 018V2002 TRAIN 2 INTERSTAGE SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-023-001 | 018-C-GAD-00009-001 | 018V2003 TRAIN 2 HP/HT SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-025-001 | 018-C-GAD-00010-001 | 018V2005 TRAIN 2 HP/MT SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 1 - APPROVED | 2018-07-04 | CLASS 2
CON-BMP-TRA-010025 | 076551C-058-CN-0007-001 | 058-A-BOD-50001-001 | PROCESS DESIGN BASIS FUEL GAS SYSTEM | A | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-DL-0110-001 | 000-F-IDL-60001-001 | DEVIATION LIST 1 RHCU FIRED HEATERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-ITP-0110-001 | 000-F-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) 1 RHCU FIRED HEATERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-MR-0110-001 | 000-F-MRQ-60001-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-SP-0110-001 | 000-F-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 1 RHCU FIRED HEATERS 18F1001/18-F1002/18F2001/18F2002/18F0001/18F0002 | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-SR-0110-001 | 000-F-SOW-60001-001 | SCOPE OF SUPPLY 1 RHCU FIRED HEATERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-018-SP-0110-001 | 018-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1001 /F 018F2001 TRAIN 1&2 - REACTOR FEED FURNACE | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-018-SP-0110-002 | 018-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F0001 ATM COLUMN FEED FURNACE | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-018-SP-0110-003 | 018-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F0002 VACUUM COLUMN FEED FURNACE | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-018-SP-0110-004 | 018-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1002 / 018F2002 TRAIN 1&2 - RECYCLE HYDROGEN FURNACE | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010027 | 076551C-018-DW-0053-003-001 | 018-L-PPN-00002-001 | 3D MODEL WBS DESIGN AREAS KEY-PLAN NO. 1 RHCU RESIDUE HYDROCRACKING UNIT | A | 2018-06-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 1
CON-BMP-TRA-010028 | 076551C-050-CN-0007-001 | 050-A-BOD-50001-001 | PROCESS DESIGN BASIS REFINERY TANK FARM | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-010029 | 076551C-000R-MS-1410-002 | 000-S-MST-60004-001 | TECHNICAL SPECIFICATION FOR TOPOGRAPHIC SURVEY FOR REFINERY AREA | A | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 2
CON-BMP-TRA-010029 | 076551C-000R-PS-1410-002 | 000-S-BOM-60004-001 | PRICE LIST FOR TOPOGRAPHIC SURVEY FOR REFINERY AREA | A | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 2
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-001-001 | 058-A-PFD-00002-001 | PROCESS FLOW DIAGRAM REFINERY GAS SYSTEM | 11A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-002-001 | 058-A-PFD-50001-001 | PROCESS FLOW DIAGRAM HP KHUFF GAS TO 2&3 BAGRU | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-003-001 | 058-A-PFD-50001-002 | PROCESS FLOW DIAGRAM FUEL GAS DISTRIBUTION TO NEW UNIT | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-004-001 | 058-A-PFD-50001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-005-001 | 058-A-PFD-50001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010031 | 076551C-081-PFD-0010-001-001 | 081-A-PFD-50001-001 | PROCESS FLOW DIAGRAM FLARE SYSTEM LSDP HIGH LEVEL FLARE SERIAL | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010031 | 076551C-081-PFD-0010-002-001 | 081-A-PFD-50001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010032 | 076551C-082-PFD-0010-001-001 | 082-A-PFD-00001-001 | PROCESS FLOW DIAGRAM REFINERY SOUTH FLARE SYSTEM FLARE KO DRUM AND RECOVERY | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-010032 | 076551C-082-PFD-0010-002-001 | 082-A-PFD-00001-002 | PROCESS FLOW DIAGRAM REFINERY SOUTH FLARE SYSTEM SEAL DRUM AND FLARE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-010032 | 076551C-082-PFD-0010-003-001 | 082-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-DL-1011-001 | 000-K-IDL-60002-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-ITP-1011-001 | 000-K-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-MR-1011-001 | 000-K-MRQ-60002-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-SP-1011-001 | 000-K-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-SR-1011-001 | 000-K-SOW-60002-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-018-SP-1011-001 | 018-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 018K0002 A/B SOUR GAS COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-021-SP-1011-001 | 021-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 021K0001 RECYCLE GAS COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-021-SP-1012-001 | 021-K-DAT-00002-001 | DATA SHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 021T0001 RECYCLE GAS COMPRESSOR TURBINE | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-023-SP-1011-001 | 023-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 023K0002 A/B PURGE GAS COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-051-SP-1011-001 | 051-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 051K0001 A/B PROPANE COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-DL-0710-002 | 000-E-IDL-60008-001 | DEVIATION LIST FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-ITP-0710-002 | 000-E-ITP-60008-001 | INSPECTION AND TEST PLAN FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-MR-0710-002 | 000-E-MRQ-60008-001 | MATERIAL REQUISITION FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-SP-0710-002 | 000-E-GRD-60008-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-SR-0710-002 | 000-E-SOW-60008-001 | SCOPE OF SUPPLY FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-004 | 018-E-DAT-00007-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0011 - ATM COLUMN OVHD PRODUCT AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-005 | 018-E-DAT-00009-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0015 - DIESEL PRODUCT AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-006 | 018-E-DAT-00008-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0012 A/B - SOUR GAS COMPRESSOR DISCHARGE COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-009 | 018-E-DAT-00010-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0019 - LVGO AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-010 | 018-E-DAT-00011-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0023 - MVGO AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-012 | 018-E-DAT-00012-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0035 -TEMPERED WATER COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-021-SP-0710-003 | 021-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0012 -STRIPPER OVERHEAD AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-021-SP-0710-004 | 021-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0016 -DIESEL PRODUCT COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-DL-1020-001 | 000-K-IDL-60001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 1 - APPROVED | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-ITP-1020-001 | 000-K-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 1 - APPROVED | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-MR-1020-001 | 000-K-MRQ-60001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-SP-1020-001 | 000-K-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-SR-1020-001 | 000-K-SOW-60001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-018-SP-1020-001 | 018-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 018K1001/K1002/K00001/K2001/K2002 MAKE-UP HYDROGEN COMPRESSORS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-023-SP-1020-001 | 023-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 023K0001A/B FEED GAS COMPRESSORS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-DL-0910-004 | 000-G-IDL-60001-001 | DEVIATION LIST FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 1 - APPROVED | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-ITP-0910-004 | 000-G-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-MR-0910-004 | 000-G-MRQ-60001-001 | MATERIAL REQUISITION FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-SP-0910-004 | 000-G-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-SR-0910-004 | 000-G-SOW-60001-001 | SCOPE OF SUPPLY FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-0910-001 | 018-G-DAT-00002-001 | CENTRIFUGAL PUMPS DATA SHEET TRAIN1 & TRAIN2 FEED PUMPS 018P1001A/B & 018P2001A/B | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-0910-002 | 018-G-DAT-00003-001 | CENTRIFUGAL PUMPS DATA SHEET QUENCH OIL PUMPS 018P0001A/B | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-0910-018 | 018-G-DAT-00004-001 | CENTRIFUGAL PUMPS DATA SHEET HP LEAN AMINE PUMPS 018P0019A/B | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-1012-001 | 018-K-DAT-00003-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 018T1001A/018T2001A TRAIN 1 FEED PUMP TURBINE TRAIN 2 FEED PUMP TURBINE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-1012-002 | 018-K-DAT-00004-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 018T0001A QUECH OIL PUMP TURBINE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-021-SP-0910-002 | 021-G-DAT-00001-001 | CENTRIFUGAL PUMP DATA SHEET FOR FEED PUMPS 021P0001 A/B | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010037 | 076551C-907-PFD-0010-001-001 | 907-A-PFD-50001-001 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010037 | 076551C-907-PFD-0010-002-001 | 907-A-PFD-50001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-DL-0846-001 | 000-S-IDL-60002-001 | DEVIATION LIST FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-ITP-0846-001 | 000-S-ITP-60002-001 | INSPECTIONA AND TEST PLAN FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-MR-0846-001 | 000-S-MRQ-60002-001 | MATERIAL REQUISITION FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-SP-0846-001 | 000-S-GRD-60002-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-SR-0846-001 | 000-S-SOW-60002-001 | SCOPE OF SUPPLY FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-021-SP-0841-001 | 021-S-DAT-00001-001 | DATA SHEET FOR 021U0001 FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-03 | CLASS 1
CON-BMP-TRA-010039 | 076551C-000R-DL-0511-001 | 000-C-IDL-60005-001 | DEVIATION LIST FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-000R-ITP-0511-001 | 000-C-ITP-60005-001 | INSPECTION AND TEST PLAN (ITP) FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-000R-MR-0511-001 | 000-C-MRQ-60005-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-000R-SP-0511-001 | 000-C-GRD-60005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-000R-SR-0511-001 | 000-C-SOW-60005-001 | SCOPE OF SUPPLY FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-018-DW-0510-001-001 | 018-C-GAD-00013-001 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-018-DW-0510-002-001 | 018-C-GAD-00011-001 | 018C0001 ATMOSPHERIC COLUMN | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-018-DW-0510-004-001 | 018-C-GAD-00012-001 | 018C0003 VACUUM COLUMN COLUMN | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-018-DW-0510-007-001 | 018-C-GAD-00014-001 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-DL-0570-001 | 000-C-IDL-60007-001 | DEVIATION LIST FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-ITP-0570-001 | 000-C-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-MR-0570-001 | 000-C-MRQ-60007-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-SP-0570-001 | 000-C-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-SR-0570-001 | 000-C-SOW-60007-001 | SCOPE OF SUPPLY FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-001-001 | 051-A-PFD-00001-001 | PROCESS FLOW DIAGRAM REFRIGERATED LPG STORAGE SHIPPING PUMPS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-002-001 | 051-A-PFD-00001-002 | PROCESS FLOW DIAGRAM REFRIGERATION SYSTEM (TRAIN A) | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-003-001 | 051-A-PFD-00001-003 | PROCESS FLOW DIAGRAM REFRIGERATION SYSTEM (TRAIN B) | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-004-001 | 051-A-PFD-00001-004 | PROCESS FLOW DIAGRAM REFRIGERATED LPG STORAGE PACKAGE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-005-001 | 051-A-PFD-00001-005 | PROCESS FLOW DIAGRAM RECYCLE VAPORIZERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-006-001 | 051-A-PFD-00001-006 | PROCESS FLOW DIAGRAM NITROGEN PACKAGE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-007-001 | 051-A-PFD-00001-007 | PROCESS FLOW DIAGRAM INSTRUMENT AIR SYSTEM | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-008-001 | 051-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-009-001 | 051-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-010-001 | 051-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-011-001 | 051-A-PFD-00002-001 | PROCESS FLOW DIAGRAM REFRIGERATED LPG STORAGE FIRE WATER SYSTEM | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-012-001 | 051-A-PFD-00002-002 | PROCESS FLOW DIAGRAM REFRIGERATED LPG STORAGE FIRE WATER SYSTEM | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-013-001 | 051-A-PFD-00002-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE FIRE WATER SYSTEM | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-010042 | 076551C-000R-RT-6200-002 | 000-A-RPT-60001-001 | FEED ESIA IMPLEMENTATION REPORT | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-010042 | 076551C-000R-RT-6200-003 | 000-A-RPT-60002-001 | FEED ESAP IMPLEMENTATION REPORT | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-001-001 | 018-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM FIRST TRAIN REACTION AND SEPARATION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-002-001 | 018-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM FIRST TRAIN H2 RECOVERY SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-003-001 | 018-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM FIRST TRAIN COMPRESSION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-004-001 | 018-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM SECOND TRAIN REACTION AND SEPARATION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-005-001 | 018-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM SECOND TRAIN H2 RECOVERY SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-006-001 | 018-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM SECOND TRAIN H2 COMPRESSION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-007-001 | 018-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM SEPARATION & AMINE ABSORBER COMMON SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-008-001 | 018-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM ATMOSPHERIC COLUMN SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-009-001 | 018-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM VACUUM COLUMN SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-010-001 | 018-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM VACUUM TOWER SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-011-001 | 018-A-MSD-00001-011 | MATERIAL SELECTION DIAGRAM WASH WATER / LEAN AND RICH AMINE / SOUR WATER SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-012-001 | 018-A-MSD-00001-012 | MATERIAL SELECTION DIAGRAM CATALYST HANDLING SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-013-001 | 018-A-MSD-00001-013 | MATERIAL SELECTION DIAGRAM CATALYST HANDLING SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-014-001 | 018-A-MSD-00001-014 | MATERIAL SELECTION DIAGRAM CATALYST HANDLING SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-015-001 | 018-A-MSD-00001-015 | MATERIAL SELECTION DIAGRAM SHORT CIRCULATION LOOP SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-016-001 | 018-A-MSD-00001-016 | MATERIAL SELECTION DIAGRAM FIRST TRAIN REACTION AND SEPARATION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-017-001 | 018-A-MSD-00001-017 | MATERIAL SELECTION DIAGRAM SECOND TRAIN REACTION AND SEPARATION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-018-001 | 018-A-MSD-00001-018 | MATERIAL SELECTION DIAGRAM SEPARATION & AMINE ABSORBER COMMON SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-019-001 | 018-A-MSD-00001-019 | MATERIAL SELECTION DIAGRAM ATMOSPHERIC COLUMN SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-020-001 | 018-A-MSD-00001-020 | MATERIAL SELECTION DIAGRAM VACUUM COLUMN SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-021-001 | 018-A-MSD-00001-021 | MATERIAL SELECTION DIAGRAM GENERAL NOTES | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-001-001 | 061-A-PFD-50001-001 | PROCESS FLOW DIAGRAM WHITE PRODUCTS TO WHARF | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-002-001 | 061-A-PFD-50001-002 | PROCESS FLOW DIAGRAM BLACK PORDUCTS TO WHARF / SLOP TO SITRA | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-003-001 | 061-A-PFD-50001-003 | PROCESS FLOW DIAGRAM BERTH NO. 1 - PRODUCTS MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-004-001 | 061-A-PFD-50001-004 | PROCESS FLOW DIAGRAM BERTH NO. 1 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-005-001 | 061-A-PFD-50001-005 | PROCESS FLOW DIAGRAM BERTH NO. 2 - PRODUCTS MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-006-001 | 061-A-PFD-50001-006 | PROCESS FLOW DIAGRAM BERTH NO. 2 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-007-001 | 061-A-PFD-50001-007 | PROCESS FLOW DIAGRAM BERTH NO. 3 - PRODUCT MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-008-001 | 061-A-PFD-50001-008 | PROCESS FLOW DIAGRAM BERTH NO. 3 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-009-001 | 061-A-PFD-50001-009 | PROCESS FLOW DIAGRAM BERTH NO. 5 - PRODUCTS MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-010-001 | 061-A-PFD-50001-010 | PROCESS FLOW DIAGRAM BERTH NO. 5 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-011-001 | 061-A-PFD-50001-011 | PROCESS FLOW DIAGRAM BERTH NO. 6 - PRODUCT MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-012-001 | 061-A-PFD-50001-012 | PROCESS FLOW DIAGRAM BERTH NO. 6 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-013-001 | 061-A-PFD-50001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-DL-0710-001 | 000-E-IDL-60007-001 | DEVIATION LIST FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-ITP-0710-001 | 000-E-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-MR-0710-001 | 000-E-MRQ-60007-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-SP-0710-001 | 000-E-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-SR-0710-001 | 000-E-SOW-60007-001 | SCOPE OF SUPPLY FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-001 | 018-E-DAT-00005-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E1005 TRAIN 1 - HP/MT FLASH GAS COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-002 | 018-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0006 - HP/MT VAPOR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-003 | 018-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0010 - ATM COLUMN REFLUX AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-007 | 018-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0007 - QUENCH OIL COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-008 | 018-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E2005 - TRAIN 2 - HP/MT FLASH GAS COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-011 | 018-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0030 - CIRCULATION OIL AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-021-SP-0710-001 | 021-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0010 -HHPS VAPOR AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-021-SP-0710-002 | 021-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0011 -HLPS VAPOR AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-DL-0851-001 | 000-H-IDL-60001-001 | DEVIATION LIST FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-ITP-0851-001 | 000-H-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-MR-0851-001 | 000-H-MRQ-60001-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-SP-0851-001 | 000-H-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-SR-0851-001 | 000-H-SOW-60001-001 | SCOPE OF SUPPLY FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-018-SP-0851-001 | 018-H-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 018U0001 VACUUM COLUMN EJECTOR SYSTEM | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-021-SP-0851-001 | 021-H-DAT-00001-001 | VACUUM UNIT (MULTISTAGE EJECTOR) DATA SHEET FOR 021U0002 VACUUM PRODUCING EQUIPMENT | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010047-REV.1 | 076551C-023-SP-4111-001 | 023-S-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 023U0001 PRESSURE SWING ADSORPTION PACKAGE (PSA) | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-001-001 | 021-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-11 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-002-001 | 021-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-11 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-003-001 | 021-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM AMINE AND SOUR WATER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-11 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-004-001 | 021-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-11 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-005-001 | 021-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-11 | CLASS 2
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-001-001 | 056-A-PFD-50001-001 | PROCESS FLOW DIAGRAM 10 PPM DIESEL TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-002-001 | 056-A-PFD-50001-002 | PROCESS FLOW DIAGRAM 10 PPM DIESEL TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-003-001 | 056-A-PFD-50001-003 | PROCESS FLOW DIAGRAM 10 PPM DIESEL TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-004-001 | 056-A-PFD-50001-004 | PROCESS FLOW DIAGRAM (EXISTING SITRA TANK FARM) KERO TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-005-001 | 056-A-PFD-50001-005 | PROCESS FLOW DIAGRAM GASOLINE/MTBE TANK AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-006-001 | 056-A-PFD-50001-006 | PROCESS FLOW DIAGRAM CRUDE OIL IMPORT EXPORT AND FUEL OIL TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-007-001 | 056-A-PFD-50001-007 | PROCESS FLOW DIAGRAM NAPHTHA CRUDE OIL SITRA TANKS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-008-001 | 056-A-PFD-50001-008 | PROCESS FLOW DIAGRAM (EXISTING SITRA TANK FARM) SITRA SLOP TANKS AND PUMP | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-009-001 | 056-A-PFD-50001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-010-001 | 056-A-PFD-50001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-13 | CLASS 1
CON-BMP-TRA-010050 | 076551C-000R-RT-1990-001 | 000-A-RSK-60001-001 | JOB SPECIFICATION FOR QUANTITATIVE RISK ASSESSMENT (INCLUDING BUILDING RISK ASSESSMENT) | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 3 - REVIEWED WITH COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-010051 | ROC-BMR-MOM-000001 | 000-A-MOM-60001-001 | ROC WEEKLY PROGRESS MEETING NO.1 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000002 | 000-A-MOM-60002-001 | ROC WEEKLY PROGRESS MEETING NO.2 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000004 | 000-A-MOM-60003-001 | 050 REFINERY TANK FARM P&ID'S REDLINE REVIEW MEETING | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000005 | 000-A-MOM-60004-001 | UNIT 056 SITRA TANK FARM P&ID'S REDLINE REVIEW MEETING | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000006 | 000-A-MOM-60005-001 | UNIT 061 SITRA WHARF P&ID'S REDLINE REVIEW MEETING | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000007 | 000-A-MOM-60006-001 | ROC BAPCO WEEKLY MEETING INT. U&O 4 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000008 | 000-A-MOM-60007-001 | ROC BAPCO WEEKLY MEETING INT. U&O 5 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000012 | 000-A-MOM-60008-001 | TTSJVROC BAPCO WEEKLY MEETING INT. U&O 6 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000013 | 000-A-MOM-60009-001 | ROC WEEKLY PROGRESS MEETING NO. 3 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010052 | 076551C-023-MSD-0011-001-001 | 023-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM 1HRU HYDROGEN RECOVERY UNIT | A | 2018-05-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-010052 | 076551C-023-MSD-0011-002-001 | 023-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM 1HRU HYDROGEN RECOVERY UNIT | A | 2018-05-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-010053 | 076551C-000R-DL-0110-003 | 000-F-IDL-60002-001 | DEVIATION LIST 3HDU FIRED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-000R-ITP-0110-003 | 000-F-ITP-60002-001 | INSPECTION AND TEST PLAN 3HDU FIRED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-000R-MR-0110-003 | 000-F-MRQ-60002-001 | MATERIAL REQUISITION 3HDU FIRED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-000R-SP-0110-003 | 000-F-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 3HDU FIRED HEATER 021F0001 COMBINED FEED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-000R-SR-0110-003 | 000-F-SOW-60002-001 | SCOPE OF SUPPLY 3HDU FIRED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-021-SP-0110-001 | 021-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 021F0001 COMBINED FEED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-001-001 | 000-R-GAD-60002-001 | TEMPORARY CONSTRUCTION FACILITIES GENERAL LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-001-002 | 000-R-GAD-60002-002 | TEMPORARY CONSTRUCTION FACILITIES GENERAL LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-003-001 | 000-R-GAD-60006-001 | TEMPORARY CONSTRUCTION SATELLITE OFFICE BUILDING | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-003-002 | 000-R-GAD-60006-002 | TEMPORARY CONSTRUCTION SATELLITE OFFICE BUILDING | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-004-001 | 000-R-GAD-60007-001 | TEMPORARY CONSTRUCTION SATELLITE CONTRACTOR MESS HALL LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-005-001 | 000-R-GAD-60008-001 | TEMPORARY CONSTRUCTION SATELLITE GUARD HOUSE LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-006-001 | 000-R-GAD-60009-001 | TEMPORARY CONSTRUCTION FACILITIES FIRST AND LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-007-001 | 000-R-GAD-60010-001 | TEMPORARY CONSTRUCTION FACILITIES SIMPLE MEDICAL FACILITY SMF LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-008-001 | 000-R-GAD-60011-001 | TEMPORARY CONSTRUCTION FACILITIES TRAINING CENTER LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-009-001 | 000-R-GAD-60012-001 | TEMPORARY CONSTRUCTION FACILITIES CF - TWO FLOOR CONTRACTOR OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-009-002 | 000-R-GAD-60012-002 | TEMPORARY CONSTRUCTION FACILITIES CONTRACTOR OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-010-001 | 000-R-GAD-60013-001 | TEMPORARY CONSTRUCTION FACILITIES CONTRACTOR OFFICE BUILDING LAYOUT AT SITRA | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-011-001 | 000-R-GAD-60014-001 | TEMPORARY CONSTRUCTION FACILITIES TWO FLOOR IPTM OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-011-002 | 000-R-GAD-60014-002 | TEMPORARY CONSTRUCTION FACILITIES TWO FLOOR IPTM OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-012-001 | 000-R-GAD-60015-001 | TEMPORARY CONSTRUCTION FACILITIES OWNER OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8240-001-001 | 000-R-GAD-60004-001 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 9.00 SQM-2.000 SQM OF COVERED SHELTER (WITH COLD ROOM & SHELVES LAY.) | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8240-002-001 | 000-R-GAD-60005-001 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3.000 SQM-1.000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8240-002-002 | 000-R-GAD-60005-002 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3.000 SQM-1.000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8240-002-003 | 000-R-GAD-60005-003 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3.000 SQM-1.000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 2
CON-BMP-TRA-010055 | ROC-BMR-MOM-000015 | 000-A-MOM-60010-001 | P&ID'S REDLINE REVIEW MEETING UNIT 371,372,373,375,381,386,930 | 0 | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-001-001 | 050-A-PFD-50001-001 | PROCESS FLOW DIAGRAM NAPHTA TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-002-001 | 050-A-PFD-50001-002 | PROCESS FLOW DIAGRAM KEROSENE TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-003-001 | 050-A-PFD-50001-003 | PROCESS FLOW DIAGRAM 10 PPM DIESEL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-004-001 | 050-A-PFD-50001-004 | PROCESS FLOW DIAGRAM LVGO TANKS AND PUMPS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-005-001 | 050-A-PFD-50001-005 | PROCESS FLOW DIAGRAM HSR NAPHTA SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-006-001 | 050-A-PFD-50001-006 | PROCESS FLOW DIAGRAM DIESEL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-007-001 | 050-A-PFD-50001-007 | PROCESS FLOW DIAGRAM NEW 1RHCU FEED TANKS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-008-001 | 050-A-PFD-50001-008 | PROCESS FLOW DIAGRAM A/B CRUDE OIL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-009-001 | 050-A-PFD-50001-009 | PROCESS FLOW DIAGRAM A/B CRUDE OIL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-010-001 | 050-A-PFD-50001-010 | PROCESS FLOW DIAGRAM FUEL OIL/CRUDE OIL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-011-001 | 050-A-PFD-50001-011 | PROCESS FLOW DIAGRAM UNCONVERTED OIL (UCO)/DIESEL TANKS AND PUMPS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-012-001 | 050-A-PFD-50001-012 | PROCESS FLOW DIAGRAM 2HDU AND 3HDU FEED TANKS AND PUMPS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-013-001 | 050-A-PFD-50001-013 | PROCESS FLOW DIAGRAM 1HCU AND 2HCU GASOIL FEED TANKS AND PUMPS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-014-001 | 050-A-PFD-50001-014 | PROCESS FLOW DIAGRAM KMU FEED TANKS AND KERO INJECTION TANKS (FO BLENDING) | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-015-001 | 050-A-PFD-50001-015 | PROCESS FLOW DIAGRAM LIGHT NAPHTA TANKS AND PUMPS FOR GASOLINE BLENDING | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-016-001 | 050-A-PFD-50001-016 | PROCESS FLOW DIAGRAM PLATFORMATE TANKS AND PUMPS FOR GASOLINE BLENDING | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-017-001 | 050-A-PFD-50001-017 | PROCESS FLOW DIAGRAM EXISTING DIESEL BLENDING SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-018-001 | 050-A-PFD-50001-018 | PROCESS FLOW DIAGRAM EXISTING FUEL OIL BLENDING SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-019-001 | 050-A-PFD-50001-019 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-020-001 | 050-A-PFD-50001-020 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-021-001 | 050-A-PFD-50001-021 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-022-001 | 050-A-PFD-50001-022 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-023-001 | 050-A-PFD-50001-023 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-22 | CLASS 1
CON-BMP-TRA-010057 | 076551C-000R-PP-557 | 000-A-PRO-60003-001 | HSSE REQUIREMENTS FOR WORKING IN THE WHARF AREA | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 2
CON-BMP-TRA-010059 | 076551C-000D-MS-8200-015 | 000-R-MST-60001-001 | TECHNICAL SPECIFICATION FOR TEMPORARY CONSTRUCTION FACITLITIES (EX 000R-MS-8200-001) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-24 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 2
CON-BMP-TRA-010059 | 076551C-000R-PS-8200-001 | 000-R-BOM-60001-001 | PRICE LIST FOR TEMPORARY CONSTRUCTIN FACITLITIES (PREFABRICATED OR MODULARIZED BUILDING) INCLUDING UTILITIES | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 2
CON-BMP-TRA-010060 | 076551C-018-SP-4111-001 | 018-S-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 018U1001/2001 TRAIN 1 & TRAIN 2 MEMBRANE UNITS | A | 2018-05-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-010061 | 076551C-058-MSD-0011-001-001 | 058-A-MSD-00002-001 | MATERIAL SELECTION DIAGRAM REFINERY GAS SYSTEM | 11A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010061 | 076551C-058-MSD-0011-002-001 | 058-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM HP KHUFF GAS TO 2&3 BAGRU | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010061 | 076551C-058-MSD-0011-003-001 | 058-A-MSD-50001-002 | MATERIAL SELECTION DIAGRAM FUEL GAS DISTRIBUTION TO NEW UNITS | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010062 | ROC-BMR-MOM-000016 | 000-A-MOM-60012-001 | ROC WEEKLY PROGRESS MEETING | 0 | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010063 | 076551C-079-PFD-0010-001-001 | 079-A-PFD-00001-001 | PROCESS FLOW DIAGRAM SPEND CAUSTIC TREATING PLANT | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010063 | 076551C-079-PFD-0010-002-001 | 079-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010063 | 076551C-079-PFD-0010-003-001 | 079-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010064 | 076551C-907-MSD-0011-001-001 | 907-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM REFINERY TO SITRA TRANSFER LINES | A | 2018-05-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010065 | 076551C-023-PID-0021-001-001 | 023-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU FEED GAS COMPRESSOR KO DRUM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-002-001 | 023-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU FEED GAS COMPRESSOR A | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-003-001 | 023-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU FEED GAS COMPRESSOR B | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-004-001 | 023-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU OFF GAS AMINE ABSORBER AND LP AMINE PUMPS | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-005-001 | 023-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU PSA UNIT | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-006-001 | 023-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU LEAN AMINE SURGE DRUM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-007-001 | 023-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU RICH AMINE ACCUMULATOR | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-008-001 | 023-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU PSA PURGE GAS COMPRESSOR A | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-009-001 | 023-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU PSA PURGE GAS COMPRESSOR B | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-401-001 | 023-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-402-001 | 023-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU BATTERY LIMIT PROCESS AUXILIARY | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-403-001 | 023-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU BATTERY LIMIT UTILITIES | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-404-001 | 023-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU BATTERY LIMIT UTILITIES | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-501-001 | 023-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU FLARE SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-502-001 | 023-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU COOLING WATER SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-504-001 | 023-A-PID-00016-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU NITROGEN SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-505-001 | 023-A-PID-00017-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU INSTRUMENT AIR SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-506-001 | 023-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU 60 STEAM SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-24 | CLASS 1
CON-BMP-TRA-010066 | 076551C-000R-MS-1410-001 | 000-S-MST-60001-001 | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION REFINERY AREA | 0 | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010066 | 076551C-000R-MS-1410-003 | 000-S-MST-60002-001 | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION TRANSFER LINE SITRA TANK FARM AND WHARF AREA | 0 | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010067 | 076551C-081-MSD-0011-001-001 | 081-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM FLARE SYSTEM LSDP HIGH LEVEL FLARE SERIAL | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010067 | 076551C-082-MSD-0011-001-001 | 082-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM REFINERY SOUTH FLARE SYSTEM FLARE K.O. DRUM AND RECOVERY | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010067 | 076551C-082-MSD-0011-002-001 | 082-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REFINERY SOUTH FLARE SYSTEM SEAL DRUM AND FLARE | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010068 | 076551C-000R-DW-1421-001-001 | 000-S-LSD-60001-001 | SITE PREPARATION ARRANGEMENT (PHASE 1 & 2) WITH F.G.L. DETAILS ROC, SOC, MOC - AREAS | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-010069 | 076551C-180-RT-2000-001 | 180-A-RPT-00001-001 | REFINERY SOUTH CONTROL BUILDINGS (RSCB) CONTROL ROOM STUDY REPORT | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-010070 | 076551C-000R-MR-0610-001 | 000-E-MRQ-60001-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-05-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 1
CON-BMP-TRA-010071 | 076551C-000R-DW-1410-001-001 | 000-A-PPN-60006-001 | PLANT DATUM & COORDINATE SYSTEM GENERAL PLOT PLAN | A | 2018-05-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-010072 | 076551C-000R-MS-3800-001 | 000-A-SOW-60001-001 | SCOPE OF WORKS FOR BMP MARINE FACILITIES INCLUDING UTILITIE | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-31 | CLASS 2
CON-BMP-TRA-010073 | 076551C-930-DW-1452-007-001 | 930-L-GAD-00002-001 | DESALINATION DISCHARGE TO EXISTING OUT-FALL DITCH GENERAL LAYOUT & HYDRAULIC PROFILE | A | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-010074 | 076551C-930-DW-1454-001-001 | 930-Q-GAD-00001-001 | DESALINATION DISCHARGE TO EXISTING OUT-FALL DITCH CONCRETE DITCH SETIONS & DETAILS | A | 2018-05-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-06 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-010075 | 076551C-058-CN-0008-002 | 058-A-BOD-50002-001 | MATERIAL SELECTION BASIS FUEL GAS SYSTEM | A | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 | 3 - REVIEWED WITH COMMENTS | 2018-05-31 | CLASS 1
CON-BMP-TRA-010076 | 076551C-081-CN-0008-002 | 081-A-BOD-50002-001 | MATERIAL SELECTION BASIS LSDP FLARE SYSTEM REVAMPING | A | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-010077 | 076551C-082-CN-0008-002 | 082-A-BOD-00002-001 | MATERIAL SELECTION BASIS REFINERY SOUTH FLARE SYSTEM | A | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-010078 | ROC-BMR-MOM-000010 | 000-A-MOM-60013-001 | F000 INTERCONNETING P&ID'S REDLINE REVIEW MEETING | 0 | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010078 | ROC-BMR-MOM-000017 | 000-A-MOM-60015-001 | ROC WEEKLY PROGRESS MEETING | 0 | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010078 | ROC-BMR-MOM-000018 | 000-A-MOM-60016-001 | TTSJVROC/BAPCO WEEKLY MEETING INT.U&0 #8 | 0 | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010079 | ROC-BMR-MOM-000011 | 000-A-MOM-60018-001 | DESIGN BASIS LSFO FLARE SYSTEM MODIFICATIONS | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010079 | ROC-BMR-MOM-000014 | 000-A-MOM-60017-001 | SPENT CAUSTIC TRATMENT COD OUTLET BASIS | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010079 | ROC-BMR-MOM-000022 | 000-A-MOM-60014-001 | TTSJVROC/BAPCO WEEKLY MEETING INT.U&0 #7 | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-001-001 | 061-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM WHITE PRODUCTS TO WHARF | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-002-001 | 061-A-MSD-50001-002 | MATERIAL SELECTION DIAGRAM BLACK PRODUCTS TO WHARF/SLOP TO SITRA | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-003-001 | 061-A-MSD-50001-003 | MATERIAL SELECTION DIAGRAM BERTH NO. 1 PRODUCTS MANIFOLDS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-004-001 | 061-A-MSD-50001-004 | MATERIAL SELECTION DIAGRAM BERTH NO. 1 LOADING ARMS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-005-001 | 061-A-MSD-50001-005 | MATERIAL SELECTION DIAGRAM BERTH NO. 2 PRODUCTS MANIFOLDS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-006-001 | 061-A-MSD-50001-006 | MATERIAL SELECTION DIAGRAM BERTH NO. 2 LOADING ARMS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-007-001 | 061-A-MSD-50001-007 | MATERIAL SELECTION DIAGRAM BERTH NO. 2 PRODUCTS MANIFOLDS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-008-001 | 061-A-MSD-50001-008 | MATERIAL SELECTION DIAGRAM BERTH NO. 3 LOADING ARMS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-009-001 | 061-A-MSD-50001-009 | MATERIAL SELECTION DIAGRAM BERTH NO. 5 PRODUCTS MANIFOLDS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-010-001 | 061-A-MSD-50001-010 | MATERIAL SELECTION DIAGRAM BERTH NO. 5 LOADING ARMS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-011-001 | 061-A-MSD-50001-011 | MATERIAL SELECTION DIAGRAM BERTH NO. 6 PRODUCTS MANIFOLDS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010080 | 076551C-061-MSD-0011-012-001 | 061-A-MSD-50001-012 | MATERIAL SELECTION DIAGRAM BERTH NO. 6 LOADING ARMS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010081 | ROC-BMR-MOM-000019 | 000-A-MOM-60019-001 | TTSJVROC/BAPCO WEEKLY MEETING INT.U&0 #9 | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010082 | 076551C-058-ML-222 | 058-A-HZR-50001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UBNIT 058 | 0 | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 |  |  | CLASS 2
CON-BMP-TRA-010083 | 076551C-082-ML-222 | 082-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 082 | 0 | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010084 | 076551C-021-DW-0051-002-001 | 021-L-PPN-00001-001 | GENERAL PLOT PLAN NO. 3 HDU-HYDRODESULPHURIZATION UNIT NO.1 HRU-HYDROGEN RECOVERY UNIT | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-010085 | 076551C-018-DW-0510-003-001 | 018-C-GAD-00015-001 | 018C0002 DIESEL STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-003-002 | 018-C-GAD-00015-002 | 018C0002 DIESEL STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-003-003 | 018-C-GAD-00015-003 | 018C0002 DIESEL STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-005-001 | 018-C-GAD-00016-001 | 018C0005 HVGO STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-005-002 | 018-C-GAD-00016-002 | 018C0005 HVGO STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-005-003 | 018-C-GAD-00016-003 | 018C0005 HVGO STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-006-001 | 018-C-GAD-00017-001 | 018C0004 VACUUM GAS SCRUBBER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-006-002 | 018-C-GAD-00017-002 | 018C0004 VACUUM GAS SCRUBBER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-006-003 | 018-C-GAD-00017-003 | 018C0004 VACUUM GAS SCRUBBER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-018-DW-0510-006-004 | 018-C-GAD-00017-004 | 018C0004 VACUUM GAS SCRUBBER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-001-001 | 021-C-GAD-00002-001 | 021C0003 STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-001-002 | 021-C-GAD-00002-002 | 021C0003 STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-001-003 | 021-C-GAD-00002-003 | 021C0003 STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-002-001 | 021-C-GAD-00003-001 | 021C0001 021V0005 HIGH PRESSURE ABSORBER HIGH PRESSURE ABSORBER KO DRUM | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-002-002 | 021-C-GAD-00003-002 | 021C0001 021V0005 HIGH PRESSURE ABSORBER HIGH PRESSURE ABSORBER KO DRUM | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-002-003 | 021-C-GAD-00003-003 | 021C0001 021V0005 HIGH PRESSURE ABSORBER HIGH PRESSURE ABSORBER KO DRUM | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-003-001 | 021-C-GAD-00004-001 | 021C0004 VACUUM DRIER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-003-002 | 021-C-GAD-00004-002 | 021C0004 VACUUM DRIER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-021-DW-0510-003-003 | 021-C-GAD-00004-003 | 021C0004 VACUUM DRIER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-023-DW-0510-001-001 | 023-C-GAD-00001-001 | 023C0001 VACUUM DRIER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-023-DW-0510-001-002 | 023-C-GAD-00001-002 | 023C0001 VACUUM DRIER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010085 | 076551C-023-DW-0510-001-003 | 023-C-GAD-00001-003 | 023C0001 VACUUM DRIER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-010086 | 076551C-018-SP-0510-003 | 018-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018C0002 DIESEL STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010086 | 076551C-018-SP-0510-005 | 018-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018C0005 HVGO STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010086 | 076551C-018-SP-0510-006 | 018-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018C0004 VACUUM GAS SCRUBBER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010086 | 076551C-021-SP-0510-001 | 021-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021C0003 STRIPPER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010086 | 076551C-021-SP-0510-002 | 021-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021C0002 HIGH PRESSURE ABSORBER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010086 | 076551C-021-SP-0510-003 | 021-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021C0004 VACUUM DRIER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010086 | 076551C-021-SP-0810-007 | 021-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0005 HIGH PRESSURE ABSORBER KO DRUM | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010086 | 076551C-023-SP-0510-001 | 023-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 023C0001 OFFGAS AMINE ABSORBER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-005 | 018-E-DAT-00033-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0004 A/B MP/HT VAPOR / ATM COLUMN FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-006 | 018-E-DAT-00032-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0005 MP/HT VAPOR / MP STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-009 | 018-E-DAT-00031-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0009 LT OIL / DIESEL PUMPAROUND EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-011 | 018-E-DAT-00030-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0008 A/B LT OIL / DIESEL EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-022 | 018-E-DAT-00029-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0024 HVGO/FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-023 | 018-E-DAT-00028-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0025 HVGO STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-025 | 018-E-DAT-00027-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0026 A/B VAC. COLUMN BOTTOM/FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-026 | 018-E-DAT-00026-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0027 A/B/C VAC. COLUMN BOTTOM STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010087 | 076551C-018-SP-0610-031 | 018-E-DAT-00025-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0033 SHUTDOWN STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-005-001 | 018-E-GAD-00021-001 | 018E0004AB MP HT VAPOR ATM COLUMN FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-005-002 | 018-E-GAD-00021-002 | 018E0004AB MP HT VAPOR ATM COLUMN FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-005-003 | 018-E-GAD-00021-003 | 018E0004AB MP HT VAPOR ATM COLUMN FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-005-004 | 018-E-GAD-00021-004 | 018E0004AB MP HT VAPOR ATM COLUMN FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-005-005 | 018-E-GAD-00021-005 | 018E0004AB MP HT VAPOR ATM COLUMN FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-006-001 | 018-E-GAD-00020-001 | 018E0005 MP HT VAPOR MP STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-006-002 | 018-E-GAD-00020-002 | 018E0005 MP HT VAPOR MP STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-006-003 | 018-E-GAD-00020-003 | 018E0005 MP HT VAPOR MP STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-006-004 | 018-E-GAD-00020-004 | 018E0005 MP HT VAPOR MP STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-006-005 | 018-E-GAD-00020-005 | 018E0005 MP HT VAPOR MP STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-009-001 | 018-E-GAD-00019-001 | 018E0009 LT OIL DIESEL PUMPAROUND EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-009-002 | 018-E-GAD-00019-002 | 018E0009 LT OIL DIESEL PUMPAROUND EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-009-003 | 018-E-GAD-00019-003 | 018E0009 LT OIL DIESEL PUMPAROUND EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-009-004 | 018-E-GAD-00019-004 | 018E0009 LT OIL DIESEL PUMPAROUND EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-009-005 | 018-E-GAD-00019-005 | 018E0009 LT OIL DIESEL PUMPAROUND EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-011-001 | 018-E-GAD-00018-001 | 018E0008 AB LT OIL DIESEL EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-011-002 | 018-E-GAD-00018-002 | 018E0008 AB LT OIL DIESEL EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-011-003 | 018-E-GAD-00018-003 | 018E0008 AB LT OIL DIESEL EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-011-004 | 018-E-GAD-00018-004 | 018E0008 AB LT OIL DIESEL EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-011-005 | 018-E-GAD-00018-005 | 018E0008 AB LT OIL DIESEL EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-022-001 | 018-E-GAD-00017-001 | 018E0024 HVGO FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-022-002 | 018-E-GAD-00017-002 | 018E0024 HVGO FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-022-003 | 018-E-GAD-00017-003 | 018E0024 HVGO FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-022-004 | 018-E-GAD-00017-004 | 018E0024 HVGO FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-022-005 | 018-E-GAD-00017-005 | 018E0024 HVGO FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-023-001 | 018-E-GAD-00016-001 | 018E0025 HVGO STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-023-002 | 018-E-GAD-00016-002 | 018E0025 HVGO STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-023-003 | 018-E-GAD-00016-003 | 018E0025 HVGO STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-023-004 | 018-E-GAD-00016-004 | 018E0025 HVGO STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-023-005 | 018-E-GAD-00016-005 | 018E0025 HVGO STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-025-001 | 018-E-GAD-00015-001 | 018E0026 VAC COLUMN BOTTOM FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-025-002 | 018-E-GAD-00015-002 | 018E0026 VAC COLUMN BOTTOM FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-025-003 | 018-E-GAD-00015-003 | 018E0026 VAC COLUMN BOTTOM FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-025-004 | 018-E-GAD-00015-004 | 018E0026 VAC COLUMN BOTTOM FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-025-005 | 018-E-GAD-00015-005 | 018E0026 VAC COLUMN BOTTOM FEED EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-026-001 | 018-E-GAD-00014-001 | 018E0027 ABC VAC COLUMN BOTTOM STEAM EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-026-002 | 018-E-GAD-00014-002 | 018E0027 ABC VAC COLUMN BOTTOM STEAM EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-026-003 | 018-E-GAD-00014-003 | 018E0027 ABC VAC COLUMN BOTTOM STEAM EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-026-004 | 018-E-GAD-00014-004 | 018E0027 ABC VAC COLUMN BOTTOM STEAM EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-026-005 | 018-E-GAD-00014-005 | 018E0027 ABC VAC COLUMN BOTTOM STEAM EXCHANGER | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-031-001 | 018-E-GAD-00013-001 | 018E0033 SHUTDOWN STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-031-002 | 018-E-GAD-00013-002 | 018E0033 SHUTDOWN STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-031-003 | 018-E-GAD-00013-003 | 018E0033 SHUTDOWN STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-031-004 | 018-E-GAD-00013-004 | 018E0033 SHUTDOWN STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010088 | 076551C-018-DW-0610-031-005 | 018-E-GAD-00013-005 | 018E0033 SHUTDOWN STEAM GENERATOR | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-010089 | 076551C-021-PID-0021-001-001 | 021-A-PID-00036-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FILTER BACKWASH SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-002-001 | 021-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FEED FILTER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-003-001 | 021-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FEED COALESCER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-004-001 | 021-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FEED EXCHANGER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-005-001 | 021-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FEED SURGE DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-006-001 | 021-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FEED PUMPS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-007-001 | 021-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU COMBINED FEED HEATER INLET | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-007-002 | 021-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU COMBINED FEED HEATER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-008-001 | 021-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU REACTOR | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-009-001 | 021-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU REACTOR EFFLUENT EXCHANGERS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-010-001 | 021-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU HOT HIGH PRESSURE SEPARATOR (HHPS) | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-011-001 | 021-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU HHPS VAPOR EXCHANGERS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-012-001 | 021-A-PID-00019-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU HOT LOW PRESSURE SEPARATOR (HLPS) | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-013-001 | 021-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU HHPS VAPOR AIRCOOLER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-013-002 | 021-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU COLD HIGH PRESSURE SEPARATOR (CHPS) | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-014-001 | 021-A-PID-00020-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU COLD LOW PRESSURE SEPARATOR (CLPS) | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-015-001 | 021-A-PID-00034-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU LEAN AMINE SURGE DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-016-001 | 021-A-PID-00035-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU LEAN AMINE PUMPS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-017-001 | 021-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU HIGH PRESSURE ABSORBER AND KO DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-018-001 | 021-A-PID-00032-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU RICH AMINE FLASH DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-019-001 | 021-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU RECYCKE GAS COMPRESSOR SUCTION DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-020-001 | 021-A-PID-00016-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU RECYCKE GAS COMPRESSOR | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-021-001 | 021-A-PID-00017-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU RECYCLE GAS COMPRESSOR STEAM TURBINE | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010089 | 076551C-021-PID-0021-022-001 | 021-A-PID-00021-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU STRIPPER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-023-001 | 021-A-PID-00024-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU STRIPPER BOTTOMS MP STEAM SUPERHEATER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-023-002 | 021-A-PID-00025-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU STRIPPER BOTTOMS MP STEAM GENERATOR | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-024-001 | 021-A-PID-00022-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU STRIPPER REFLUX DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-025-001 | 021-A-PID-00023-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU STRIPPER REFLUX PUMPS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-026-001 | 021-A-PID-00026-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU DIESEL PRODUCT COALESCER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-027-001 | 021-A-PID-00027-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU VACUUM DRIER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-029-001 | 021-A-PID-00028-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU DIESEL PRODUCT COOLER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-030-001 | 021-A-PID-00029-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU VACUUM PRODUCING EQUIPMENT | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-030-002 | 021-A-PID-00030-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU EJECTOR RECEIVER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-031-001 | 021-A-PID-00031-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU WATER SEAL PLOT | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-032-001 | 021-A-PID-00033-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU SOUR WATER DEGASSING DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-033-001 | 021-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU INJECTION WATER BREAK TANK | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-034-001 | 021-A-PID-00054-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FLUSHING OIL HEADER | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-035-001 | 021-A-PID-00061-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU PHOSPHATE INJECTION SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-036-001 | 021-A-PID-00062-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU ANTISTATIC ADDITIVE SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-037-001 | 021-A-PID-00037-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FUEL GAS KO DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-038-001 | 021-A-PID-00038-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU REACTION SECTION FUEL GAS SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-039-001 | 021-A-PID-00043-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU REACTOR EFFLUENT SAMPLING ARRANGEMENT | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-042-001 | 021-A-PID-00059-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU ANTIFOAM CHEMICAL INJECTION | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010090 | 076551C-021-PID-0021-043-001 | 021-A-PID-00060-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU INHIBITOR INJECTION PACKAGE | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-040-001 | 021-A-PID-00056-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-040-002 | 021-A-PID-00056-002 | PIPING AND INSTRUMENT DIAGRAM - 3HDU BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-040-003 | 021-A-PID-00056-003 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-041-001 | 021-A-PID-00057-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU BATTERY LIMIT PROCESS AUXILIARY | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-501-001 | 021-A-PID-00040-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU RECOVERED PROCESS SLOP OIL SUMP | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-501-002 | 021-A-PID-00040-002 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU SLOP SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-502-001 | 021-A-PID-00041-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU AMINE SUMP TANK | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-502-002 | 021-A-PID-00041-002 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU AMINE CLOSED DRAIN SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-503-001 | 021-A-PID-00042-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU SOUR WATER SUMP | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-503-002 | 021-A-PID-00042-002 | PIPING AND INSTRUMENT DIAGRAM - 3HDU SOUR WATER DRAIN SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-504-001 | 021-A-PID-00044-002 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FLARE KO DRUM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-504-002 | 021-A-PID-00044-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FLARE DISTRIBUTION | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-505-001 | 021-A-PID-00046-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU STEAM BLOWDOWN COLLECTION SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-506-001 | 021-A-PID-00045-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU 60-110-550 STEAM SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-507-001 | 021-A-PID-00048-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU 60-110-550 STEAM CONDENSATE SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-508-001 | 021-A-PID-00049-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU COOLING WATER SYSTEM (MAIN) | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-509-001 | 021-A-PID-00047-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU BOILER FEED WATER SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-510-001 | 021-A-PID-00053-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU NITROGEN SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-511-001 | 021-A-PID-00052-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU INSTRUMENT AIR AND YARD AIR SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-512-001 | 021-A-PID-00050-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU UTILITY WATER SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-513-001 | 021-A-PID-00051-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU DRINKING WATER SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-514-001 | 021-A-PID-00039-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FUEL GAS SYSTEM | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-515-001 | 021-A-PID-00058-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU BATTERY LIMIT UTILITIES | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-515-002 | 021-A-PID-00058-002 | PIPING AND INSTRUMENT DIAGRAM - 3HDU BATTERY LIMIT UTILITIES | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-515-003 | 021-A-PID-00058-003 | PIPING AND INSTRUMENT DIAGRAM - 3HDU BATTERY LIMIT UTILITIES | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010091 | 076551C-021-PID-0031-515-004 | 021-A-PID-00058-004 | PIPING AND INSTRUMENT DIAGRAM - 3HDU/1HRU BATTERY LIMIT UTILITIES | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-001-001 | 082-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM FLARE MAIN KO DRUM | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-002-001 | 082-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM SEAL DRUM | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-003-001 | 082-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM FLARE PACKAGE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-004-001 | 082-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM FLARE GAS RECOVERY PACKAGE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-401-001 | 082-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM BATTERY LIMIT | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-402-001 | 082-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM BATTERY LIMIT | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-403-001 | 082-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM BATTERY LIMIT | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-501-001 | 082-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM UTILITY AND POTABLE WATER | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-502-001 | 082-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM PROCESS GAS AND KHUFF GAS DITRIBUTION | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-503-001 | 082-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM NITRTOGEN AND AIR | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-504-001 | 082-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM 110 STEAM DITRIBUTION | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010092 | 076551C-082-PID-0031-505-001 | 082-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY SOUTH FLARE SYSTEM COOLING WATER DISTRIBUTION | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010093 | 076551C-081-PID-0031-001-001 | 081-A-PID-00001-003 | PIPING AND INSTRUMENT DIAGRAM - LSDP FLARE K.O. DRUM FOR SGP | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-010093 | 076551C-081-PID-0031-002-001 | 081-A-PID-00001-002 | PIPING AND INSTRUMENT DIAGRAM - LSDP FLARE - FLARE STACK LSDP | 2A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-010093 | 076551C-081-PID-0031-003-001 | 081-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - LSDP FLARE KO DRUM LSDP | 2A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-010093 | 076551C-081-PID-0031-401-001 | 081-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - LSDP FLARE LSDP FLARE SYSTEM BATTERY LIMIT | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-111-001 | 018-A-PID-10014-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 HP/HT FLASH GAS COOLERS | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-112-001 | 018-A-PID-10015-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 HP/LT SEPARATOR | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-113-001 | 018-A-PID-10016-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 HP AMINE ABSORBER & HP CENTRIFUGAL SEPARATOR | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-115-001 | 018-A-PID-10018-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 MEMBRANE UNIT | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-116-001 | 018-A-PID-10019-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 MU & RG 1ST STAGE SUCTION DRUM | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-117-001 | 018-A-PID-10020-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 018K1001 MU HYDROGEN COMPRESSOR 1ST STAGE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-118-001 | 018-A-PID-10021-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 018K1001 MU HYDROGEN COMPRESSOR 2ND STAGE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-119-001 | 018-A-PID-10025-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 K1001 MU HYDROGEN COMPRESSOR 3RD STAGE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-120-001 | 018-A-PID-10022-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 018K1002 MU HYDROGEN COMPRESSOR 1ST STAGE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-121-001 | 018-A-PID-10023-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 018K1002 MU HYDROGEN COMPRESSOR 2ND STAGE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-122-001 | 018-A-PID-10026-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 K1002 MU HYDROGEN COMPRESSOR 3RD STAGE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-123-001 | 018-A-PID-10024-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 COMPRESSOR INTERSTAGE PIPING | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-124-001 | 018-A-PID-10033-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 EMERGENCY DEPRESSURING (HRDP) ACTIONS | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-125-001 | 018-A-PID-10031-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 HYDROGEN PURGE GAS SYSTEM (1/2) | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-126-001 | 018-A-PID-10032-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 HYDROGEN PURGE GAS SYSTEM (2/2) | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010094 | 076551C-018-PID-0021-127-001 | 018-A-PID-10027-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 SEAL OIL PUMPS | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-128-001 | 018-A-PID-10028-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 FUEL GAS SYSTEM FURNACE 018F1001 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-129-001 | 018-A-PID-10044-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 THERMAL SLEEVE DETAILS | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-131-001 | 018-A-PID-10035-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 1ST REACTOR TEMPERATURE SURVEILLANCE 1 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-132-001 | 018-A-PID-10036-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 1ST REACTOR TEMPERATURE SURVEILLANCE 2 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-133-001 | 018-A-PID-10037-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 1ST REACTOR TEMPERATURE SURVEILLANCE 3 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-134-001 | 018-A-PID-10038-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 1ST REACTOR TEMPERATURE SURVEILLANCE 4 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-136-001 | 018-A-PID-10040-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 2ND REACTOR TEMPERATURE SURVEILLANCE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-137-001 | 018-A-PID-10041-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 2ND REACTOR TEMPERATURE SURVEILLANCE 2 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-138-001 | 018-A-PID-10042-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 2ND REACTOR TEMPERATURE SURVEILLANCE 3 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-139-001 | 018-A-PID-10043-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 2ND REACTOR TEMPERATURE SURVEILLANCE 4 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010095 | 076551C-018-PID-0021-143-001 | 018-A-PID-10029-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 1 FUEL GAS SYSTEM RECYCLE GAS FURNACE 018F1002 | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-101-001 | 018-A-PID-10001-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 FEED SURGE DRUM | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-102-001 | 018-A-PID-10002-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 VR FEED PUMPS | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-103-001 | 018-A-PID-10003-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 REACTOR FEED FURNACE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-103-002 | 018-A-PID-10004-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 REACTOR FEED FURNACE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-104-001 | 018-A-PID-10006-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 1ST REACTOR | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-105-001 | 018-A-PID-10007-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 INTERSTAGE SEPARATOR | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-106-001 | 018-A-PID-10009-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 2ND REACTOR | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-107-001 | 018-A-PID-10010-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 HP/HT SEPARATOR | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-108-001 | 018-A-PID-10012-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 HP/HT VAPOR COOLING | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-109-001 | 018-A-PID-10011-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 MP / HT SEPARATOR | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-110-001 | 018-A-PID-10013-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 HP/MT SEPARATOR & REACTOR EFFLUENT COOLING | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-114-001 | 018-A-PID-10017-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 MEMBRANE KNOCKOUT DRUM | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-130-001 | 018-A-PID-10034-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 1ST REACTOR - DETAILS | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-135-001 | 018-A-PID-10039-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 2ND REACTOR - DETAILS | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-140-001 | 018-A-PID-10030-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 REACTION FURNACE - STEAM DRUM AND BFW CIRC. SYSTEM | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-141-001 | 018-A-PID-10005-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 RECYCLE HYDROGEN FURNACE | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010096 | 076551C-018-PID-0021-142-001 | 018-A-PID-10008-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 1 INTERSTAGE SEPARATOR VAPOR | A | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010097 | 076551C-018-DW-0051-002-001 | 018-L-PPN-00001-001 | GENERAL PLOT PLAN NO.1 RHCU RESIDUE HYDROCRACKING UNIT | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-010097 | 076551C-018-DW-0051-002-002 | 018-L-PPN-00001-002 | GENERAL PLOT PLAN NO.1 RHCU RESIDUE HYDROCRACKING UNIT | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-010097-REV.1 | 076551C-018-DW-0051-002-001 | 018-L-PPN-00001-001 | GENERAL PLOT PLAN NO.1 RHCU RESIDUE HYDROCRACKING UNIT | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-010097-REV.1 | 076551C-018-DW-0051-002-002 | 018-L-PPN-00001-002 | GENERAL PLOT PLAN NO.1 RHCU RESIDUE HYDROCRACKING UNIT | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-002-001 | 018-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM COMMON MAKE-UP HYDROGEN | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-003-001 | 018-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON 018K0001 MU HYDROGEN COMPRESSOR 1ST STAGE | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-004-001 | 018-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON 018K0001 MU HYDROGEN COMPRESSOR 2ND STAGE | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-005-001 | 018-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON 018K0001 MU HYDROGEN COMPRESSOR 3RD STAGE | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-008-001 | 018-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON MP/HT SEPARATOR FLASH GAS COOLING | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-009-001 | 018-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON MP/MT SEPARATOR | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-011-001 | 018-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON QUENCH OIL COOLER AND DISTRIBUTION | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-013-001 | 018-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON MP/LT VAPOR | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-014-001 | 018-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON LT OIL FLASH DRUM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-022-001 | 018-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. ATMOSPHERIC COLUMN FEED PREHEAT EXCHANGERS | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-025-001 | 018-A-PID-00016-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. CONVECTION SECTION FURNACE 018F0001 | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-033-001 | 018-A-PID-00031-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. DIESEL PUMPAROUND PUMPS | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-034-002 | 018-A-PID-00033-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. DIESEL PA LP STEAM GENERATOR | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-036-001 | 018-A-PID-00023-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. SOUR GAS COMPRESSOR 018K0002A 1ST STAGE SUCTION DRUM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-039-001 | 018-A-PID-00026-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. SOUR GAS COMPRESSOR 018K0001A 2ND STAGE | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-040-001 | 018-A-PID-00027-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. SOUR GAS COMPRESSOR 018K0002B 1ST STAGE SUCTION DRUM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010098 | 076551C-018-PID-0021-043-001 | 018-A-PID-00030-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. SOUR GAS COMPRESSOR 018K0002B 2ND STAGE | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010099 | 076551C-018-PID-0021-075-001 | 018-A-PID-00110-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON SEAL OIL SYSTEM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010099 | 076551C-018-PID-0021-080-001 | 018-A-PID-00107-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010099 | 076551C-018-PID-0021-080-002 | 018-A-PID-00107-002 | PIPING AND INSTRUMENT DIAGRAM 1RHCU BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010099 | 076551C-018-PID-0021-080-003 | 018-A-PID-00107-003 | PIPING AND INSTRUMENT DIAGRAM 1RHCU BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010099 | 076551C-018-PID-0021-081-001 | 018-A-PID-00108-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU BATTERY LIMIT PROCESS AUXILIARY | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010099 | 076551C-018-PID-0031-510-001 | 018-A-PID-00112-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON ANTIFOAM INJECTION SYSTEM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010099 | 076551C-018-PID-0031-524-001 | 018-A-PID-00109-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU BATTERY LIMIT UTILITIES | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010099 | 076551C-018-PID-0031-524-003 | 018-A-PID-00109-003 | PIPING AND INSTRUMENT DIAGRAM 1RHCU BATTERY LIMIT UTILITIES | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-008-002 | 018-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON MP/HT SEPARATOR FLASH GAS COOLING | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-010-001 | 018-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON QUENCH OIL PUMPS | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-012-001 | 018-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON MP/LT SEPARATOR | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-015-001 | 018-A-PID-00081-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON SOUR WATER DEGASSER | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-016-001 | 018-A-PID-00082-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON RICH AMINE FLASH DRUM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-018-001 | 018-A-PID-00079-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON MP WASH WATER PUMPS | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-019-001 | 018-A-PID-00080-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON CONDENSATE INJECTION WATER SYSTEM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-028-001 | 018-A-PID-00021-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU FRACT. ATM COLUMN OVHD PRODUCT SYSTEM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-029-001 | 018-A-PID-00020-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU FRACT. ATM COLUMN REFLUX PUMPS | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-051-001 | 018-A-PID-00048-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON VR FEED PREHEAT EXCHANGERS | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-054-001 | 018-A-PID-00053-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU VACUUM WASH OIL CIRCULATION PUMPS | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-075-002 | 018-A-PID-00111-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON SEAL OIL SYSTEM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0021-077-001 | 018-A-PID-00059-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON CUTTERSTOCK SYSTEM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010100 | 076551C-018-PID-0031-521-001 | 018-A-PID-00113-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON PHOSPHATE INJECTION SYSTEM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010101 | 076551C-018-PID-0021-026-001 | 018-A-PID-00017-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. ATMOSPHERIC COLUMN-TOP SECTION | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010101 | 076551C-018-PID-0021-047-001 | 018-A-PID-00040-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM VACUUM COLUMN - BOTTOM PORTION | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010101 | 076551C-018-PID-0021-062-001 | 018-A-PID-00058-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON VACUUM COLUMN BOTTOMS MP STEAM DRUM AND BFW CIRC. SYST. | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010101 | 076551C-018-PID-0021-065-001 | 018-A-PID-00066-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON CATALYST TRANSFER VESSELS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010101 | 076551C-018-PID-0021-067-001 | 018-A-PID-00062-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON CATALYST INVENTORY HOLDING BINS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010101 | 076551C-018-PID-0021-068-002 | 018-A-PID-00065-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON CATALYST INVENTORY HOLDING BINS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-021-001 | 018-A-PID-00085-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON SHORT CIRCULATION COOLERS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-021-002 | 018-A-PID-00086-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON SHORT CIRCULATION COOLERS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-027-001 | 018-A-PID-00019-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. ATMOSPHERIC COLUMN REFLUX DRUM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-030-001 | 018-A-PID-00022-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. ATM COLUMN OVHD. PRODUCT PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-031-001 | 018-A-PID-00034-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. DIESEL STRIPPER & DIESEL PRODUCT PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-034-001 | 018-A-PID-00032-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. DIESEL PA MP STEAM GENERATOR | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-037-001 | 018-A-PID-00024-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. SOUR GAS COMPRESSOR 018K0002A 1ST STAGE | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-041-001 | 018-A-PID-00028-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. SOUR GAS COMPRESSOR 018K0002B 1ST STAGE | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-042-001 | 018-A-PID-00029-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. SOUR GAS COMPRESSOR 018K0002B DISCHARGE KO DRUM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-045-001 | 018-A-PID-00038-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM VACUUM COLUMN FEED FURNACE | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-046-001 | 018-A-PID-00039-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM CONVECTIVE SECTION FURNACE 018F0002 | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-048-001 | 018-A-PID-00041-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM VACUUM COLUMN - TOP PORTION | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-053-001 | 018-A-PID-00052-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM HVGO STRIPPER AND PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-055-001 | 018-A-PID-00054-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM VACUUM COLUMN BOTTOMS PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-061-001 | 018-A-PID-00044-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM VENT GAS SCRUBBER SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-071-001 | 018-A-PID-00069-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON COOLING OIL CIRCULATION SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-071-002 | 018-A-PID-00070-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON COOLING OIL CIRCULATION SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-072-001 | 018-A-PID-00071-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON CIRCULATION OIL FILTERS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-072-002 | 018-A-PID-00072-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON CATALYST SLOP OIL DRAIN | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010102 | 076551C-018-PID-0021-076-001 | 018-A-PID-00042-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON VACUUM SYSTEM EJECTOR/ CONDENSER | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-006-001 | 018-A-PID-00076-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON LEAN AMINE SURGE DRUM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-020-001 | 018-A-PID-00084-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON SHORT CIRCULATION DRUM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-038-001 | 018-A-PID-00025-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU FRACT. SOUR GAS COMPRESSOR 018K0002A DISCHARGE KO DRUM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-049-001 | 018-A-PID-00045-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM LVGO COOLING SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-050-001 | 018-A-PID-00046-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM MVGO STEAM GENERATOR | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-050-002 | 018-A-PID-00047-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM MVGO PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-052-001 | 018-A-PID-00050-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM HVGO STEAM GENERATOR | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-052-002 | 018-A-PID-00051-001 | PIPING AND INSTRUMENT DIAGRAM 1HRCU VACUUM HVGO PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-059-001 | 018-A-PID-00049-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM MVGO AIR COOLER | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-060-001 | 018-A-PID-00043-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU VACUUM VACUUM COLUMN HOTWELL & PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-066-001 | 018-A-PID-00060-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON FRESH CATALYST TRANSFER POT (FCTP) | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-069-001 | 018-A-PID-00075-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON OIL DRAIN SURGE DRUM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-070-001 | 018-A-PID-00073-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON SPENT CATALYST DE-OILING BINS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0021-070-002 | 018-A-PID-00074-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON SPENT CATALYST DE-OILING BINS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010103 | 076551C-018-PID-0031-524-002 | 018-A-PID-00109-002 | PIPING AND INSTRUMENT DIAGRAM 1RHCU BATTERY LIMIT UTILITIES | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-001-001 | 051-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM REFRIGERATED LPG STORAGE SHIPPING PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-002-001 | 051-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REFRIGERATION SYSTEM (TRAIN A) | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-003-001 | 051-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM REFRIGERATION SYSTEM (TRAIN B) | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-004-001 | 051-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM REFRIGERATED LPG STORAGE PACKAGE | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-005-001 | 051-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM RECYCLE VAPORAIZERS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-006-001 | 051-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM NITROGEN PACKAGE | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-007-001 | 051-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM INSTRUMENT AIR SYSTEM | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-008-001 | 051-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM REFRIGERATED LPG STORAGE AND REFRIGERATION SYSTEM (TRAINS A AND B) | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-011-001 | 051-A-MSD-00002-001 | MATERIAL SELECTION DIAGRAM REFRIGERATED LPG STORAGE FIRE WATER SYSTEM | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010104 | 076551C-051-MSD-0011-012-001 | 051-A-MSD-00002-002 | MATERIAL SELECTION DIAGRAM REFRIGERATED LPG STORAGE FIRE WATER SYSTEM | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010105 | 076551C-018-PID-0021-001-001 | 018-A-PID-00083-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON START-UP HEATER COMMON FEED OILS SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-007-001 | 018-A-PID-00077-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON HIGH PRESSURE LEAN AMINE PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-017-001 | 018-A-PID-00078-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON INJECTION WATER SYSTEM | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-023-001 | 018-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU FRACT. LT / MT OIL SURGE DRUM AND FEED PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-024-001 | 018-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU FRACT. ATM COLUMN FEED FURNACE | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-026-002 | 018-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCUFRACT. ATMOSPHERIC COLUMN - BOTTOM SECTION | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-032-001 | 018-A-PID-00035-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU FRACT. DIESEL PRODUCT COOLING SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-035-001 | 018-A-PID-00036-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU FRACT. ATM COLUMN BOTTOMS PUMPS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-044-001 | 018-A-PID-00037-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU VACUUM VACUUM COLUMN FURNACE FEED SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-056-001 | 018-A-PID-00055-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU VACUUM VACUUM COLUMN BOTTOM / FEED EXCHANGER | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-057-001 | 018-A-PID-00056-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU VACUUM VACUUM COLUMN BOTTOMS STEAM GENERATORS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-058-001 | 018-A-PID-00057-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU VACUUM VACUUM COLUMN BOTTOMS COOLER | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-063-001 | 018-A-PID-00068-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON TRANSPORT OIL SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-064-001 | 018-A-PID-00067-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON TRANSPORT OIL HEADER SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-066-002 | 018-A-PID-00061-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON FRESH CATALYST TRANSFER POT (FCTP) | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-067-002 | 018-A-PID-00063-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON CATALYST INVENTORY HOLDING BINS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-068-001 | 018-A-PID-00064-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON CATALYST INVENTORY HOLDING BINS | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-073-001 | 018-A-PID-00089-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU FRACT. FUEL GAS SYSTEM FURNACE 018F0001 | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0021-074-001 | 018-A-PID-00090-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU VACUUM FUEL GAS SYSTEM FURNACE 018F0002 | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010105 | 076551C-018-PID-0031-509-001 | 018-A-PID-00091-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON TEMPERED WATER SYSTEM | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-010106 | 076551C-021-DW-0053-002-001 | 021-L-PPN-00002-001 | 3D MODEL WBS DESIGN AREAS KEY-PLAN NO. 3 HDU-HYDRODESULPHURIZATION UNIT NO. 1 HRU-HYDROGEN RECOVERY UNIT | A | 2018-06-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 1
CON-BMP-TRA-010107 | ROC-BMR-MOM-000023 | 000-A-MOM-60020-001 | ROC 8 TH WEEKLY PROGRESS MEETING | 0 | 2018-06-05 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010108 | 076551C-000R-DW-1410-001-001 | 000-A-PPN-60006-001 | PLANT DATUM & COORDINATE SYSTEM GENERAL PLOT PLAN | 0 | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-010109 | 076551C-018-SP-4111-001 | 018-S-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 018U1001/2001 TRAIN 1 & TRAIN 2 MEMBRANE UNITS | B | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-010110 | 076551C-023-SP-4111-001 | 023-S-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 023U0001 PRESSURE SWING ADSORPTION PACKAGE (PSA) | B | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-010111 | 076551C-000R-MR-4111-002 | 000-S-MRQ-60008-001 | MATERIAL REQUISITION FOR PSA | A | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-21 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010112 | 076551C-000R-MR-4111-001 | 000-S-MRQ-60006-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | A | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-010113 | 076551C-000R-RT-1990-001 | 000-A-RSK-60001-001 | JOB SPECIFICATION FOR QUANTITATIVE RISK ASSESSMENT (INCLUDING BUILDING RISK ASSESSMENT) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-010114 | 076551C-061-CN-0008-002 | 061-A-BOD-50002-001 | MATERIAL SELECTION BASIS SITRA WHARF AND ASSOCIATES | A | 2018-06-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010115 | ROC-BMR-MOM-000024 | 000-A-MOM-60021-001 | UNIT 023 N 1HRU P AND ID IBD REVIEW MEETING | 0 | 2018-06-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010115 | ROC-BMR-MOM-000026 | 000-A-MOM-60023-001 | ROC 9 TH WEEKLY PROGRESS MEETING | 0 | 2018-06-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010116 | 076551C-056-MSD-0011-001-001 | 056-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM 10 PPM DIESEL TANKS AND SHIPPING PUMPS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010116 | 076551C-056-MSD-0011-002-001 | 056-A-MSD-50001-002 | MATERIAL SELECTION DIAGRAM 10 PPM DIESEL TANKS AND SHIPPING PUMPS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010116 | 076551C-056-MSD-0011-003-001 | 056-A-MSD-50001-003 | MATERIAL SELECTION DIAGRAM NAPHTHA TANKS AND SHIPPING PUMPS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010116 | 076551C-056-MSD-0011-004-001 | 056-A-MSD-50001-004 | MATERIAL SELECTION DIAGRAM (EXISTING SITRA TANK FARM) KERO TANKS AND SHIPPING PUMPS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010116 | 076551C-056-MSD-0011-005-001 | 056-A-MSD-50001-005 | MATERIAL SELECTION DIAGRAM GASOLINE/MTBE TANKS AND SHIPPING PUMPS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010116 | 076551C-056-MSD-0011-006-001 | 056-A-MSD-50001-006 | MATERIAL SELECTION DIAGRAM CRUDE OIL IMPORT/EXPORT AND FUEL OIL TANKS AND SHIPPING PUMPS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010116 | 076551C-056-MSD-0011-007-001 | 056-A-MSD-50001-007 | MATERIAL SELECTION DIAGRAM NAPHTHA/CRUDE OIL SITRA TANKS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010116 | 076551C-056-MSD-0011-008-001 | 056-A-MSD-50001-008 | MATERIAL SELECTION DIAGRAM (EXISTING SITRA TANK FARM) SITRA SLOP TANKS AND PUMP | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010117 | 076551C-000R-MSD-0011-001-001 | 000-A-MSD-60001-001 | MATERIAL SELECTION DIAGRAM GENERAL NOTES | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-001 | 018-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1001 - TRAIN 1 - RG +H2 PREHEAT EXCHANGER NO.2 | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-002 | 018-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1002 - TRAIN 1 - FEED PREHEAT EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-003 | 018-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1003 - TRAIN 1 - RG + H2 PREHEAT EXCHANGER NO.1 | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-004 | 018-E-DAT-00016-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1004 - TRAIN 1 - HP/HT STEAM GENERATOR | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-007 | 018-E-DAT-00017-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1006 - TRAIN 1 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-008 | 018-E-DAT-00018-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1007 - TRAIN 1 - MEMBRANE FEED HEATER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-014 | 018-E-DAT-00019-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2001 - TRAIN 2 - RG + H2 PREHEAT EXCHANGER NO.2 | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-015 | 018-E-DAT-00020-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2002 - TRAIN 2 -FEED PREHEAT EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-016 | 018-E-DAT-00021-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2003 - TRAIN 2 - RG + H2 PREHEAT EXCHANGER NO.1 | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-017 | 018-E-DAT-00022-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2004 - TRAIN 2 - HP/HT STEAM GENERATOR | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-018 | 018-E-DAT-00023-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2006 - TRAIN 2 - HP/MT FLASH GAS TRIM COOLER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-018-SP-0610-019 | 018-E-DAT-00024-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2007 - TRAIN 2 - MEMBRANE FEED HEATER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-021-SP-0610-003 | 021-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0006 A/B REACTOR EFFLUENT/FEED COLD EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-021-SP-0610-004 | 021-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0004 A/B REACTOR EFFLUENT/FEED HOT EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-021-SP-0610-005 | 021-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0003 REACTOR EFFLUENT/RECYCLE GAS HOT EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-021-SP-0610-006 | 021-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0005 REACTOR EFFLUENT/RECYCLE GAS COLD EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-021-SP-0610-007 | 021-E-DAT-00009-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0007 HHPS VAPOR/FEED EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-021-SP-0610-008 | 021-E-DAT-00010-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0008 HHPS VAPOR/RECYCLE GAS EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010118 | 076551C-021-SP-0610-009 | 021-E-DAT-00011-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0009 HHPS VAPOR/STRIPPER FEED EXCHANGER | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-010119 | 076551C-018-PID-0021-201-001 | 018-A-PID-20001-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 FEED SURGE DRUM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-207-001 | 018-A-PID-20010-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 HP/HT SEPARATOR | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-208-001 | 018-A-PID-20012-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 HP/HT VAPOR COOLING | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-209-001 | 018-A-PID-20011-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 MP / HT SEPARATOR | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-212-001 | 018-A-PID-20015-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 HP/LT SEPARATOR | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-224-001 | 018-A-PID-20033-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 EMERGENCY DEPRESSURING (HRDP) ACTIONS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-225-001 | 018-A-PID-20031-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 HYDROGEN PURGE GAS SYSTEM (1/2) | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-226-001 | 018-A-PID-20032-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 HYDROGEN PURGE GAS SYSTEM (2/2) | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-229-001 | 018-A-PID-20044-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 THERMAL SLEEVE DETAILS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-230-001 | 018-A-PID-20034-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 1ST REACTOR - DETAILS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-231-001 | 018-A-PID-20035-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 1ST REACTOR TEMPERATURE SURVEILLANCE 1 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-233-001 | 018-A-PID-20037-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 1ST REACTOR TEMPERATURE SURVEILLANCE 3 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-234-001 | 018-A-PID-20038-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 1ST REACTOR TEMPERATURE SURVEILLANCE 4 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-235-001 | 018-A-PID-20039-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 2ND REACTOR - DETAILS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-236-001 | 018-A-PID-20040-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 2ND REACTOR TEMPERATURE SURVEILLANCE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-237-001 | 018-A-PID-20041-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 2ND REACTOR TEMPERATURE SURVEILLANCE 2 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-238-001 | 018-A-PID-20042-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 2ND REACTOR TEMPERATURE SURVEILLANCE 3 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-239-001 | 018-A-PID-20043-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 2ND REACTOR TEMPERATURE SURVEILLANCE 4 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010119 | 076551C-018-PID-0021-242-001 | 018-A-PID-20008-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 2 INTERSTAGE SEPARATOR | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010120 | 076551C-018-SP-0810-007 | 018-C-DAT-00047-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1007 TRAIN1 HP CENTRIFUGAL SEPARATOR | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010120 | 076551C-018-SP-0810-027 | 018-C-DAT-00046-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2007 TRAIN 2 HP CENTRIFUGAL SEPARATOR | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-010121 | 076551C-018-PID-0031-501-001 | 018-A-PID-00095-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON RECOVERED PROCESS SLOP OIL SYSTEM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010121 | 076551C-018-PID-0031-502-001 | 018-A-PID-00094-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON AMINE CLOSE DRAIN SYSTEM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010121 | 076551C-018-PID-0031-503-001 | 018-A-PID-00093-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON SOUR WATER SUMP | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010121 | 076551C-018-PID-0031-504-001 | 018-A-PID-00088-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON UTILITIES DISTRIBUTION SWEET FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010121 | 076551C-018-PID-0031-504-002 | 018-A-PID-00087-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON UTILITIES DISTRIBUTION SWEET FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010121 | 076551C-018-PID-0031-508-001 | 018-A-PID-00098-001 | PIPING AND INSTRUMENT DIAGRAM 1RHCU COMMON STEAM BLOWDOWN COOLING | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-202-001 | 018-A-PID-20002-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 VR FEED PUMPS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-203-001 | 018-A-PID-20003-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 REACTOR FEED FURNACE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-204-001 | 018-A-PID-20006-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 1ST REACTOR | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-206-001 | 018-A-PID-20009-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 2ND REACTOR | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-210-001 | 018-A-PID-20013-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 HP/MT SEPARATOR & REACTOR EFFLUENT COOLING | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-213-001 | 018-A-PID-20016-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 HP AMINE ABSORBER & HP CENTRIFUGAL SEPARATOR | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-214-001 | 018-A-PID-20017-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 MEMBRANE KNOCKOUT DRUM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-215-001 | 018-A-PID-20018-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 MEMBRANE UNIT | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-216-001 | 018-A-PID-20019-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 MU & RG 1ST STAGE SUCTION DRUM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-217-001 | 018-A-PID-20020-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 018K2001 MU HYDROGEN COMPRESSOR 1ST STAGE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-218-001 | 018-A-PID-20021-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 018K2001 MU HYDROGEN COMPRESSOR 2ND STAGE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-219-001 | 018-A-PID-20025-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 K2001 MU HYDROGEN COMPRESSOR 3RD STAGE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-221-001 | 018-A-PID-20023-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 018K2002 MU HYDROGEN COMPRESSOR 2ND STAGE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-222-001 | 018-A-PID-20026-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 K1002 MU HYDROGEN COMPRESSOR 3RD STAGE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-223-001 | 018-A-PID-20024-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 COMPRESSOR INTERSTAGE PIPING | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-227-001 | 018-A-PID-20027-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 SEAL OIL PUMPS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-232-001 | 018-A-PID-20036-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 1ST REACTOR TEMPERATURE SURVEILLANCE 2 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-240-001 | 018-A-PID-20030-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 REACTION FURNACE - STEAM GENER. STEAM DRUM AND BFW CIRC. SYSTEM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0021-241-001 | 018-A-PID-20005-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 RECYCLE HYDROGEN FURNACE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010122 | 076551C-018-PID-0031-505-002 | 018-A-PID-00096-002 | PIPING AND INSTRUMENT DIAGRAM 1RHCU TRAIN 1 FLARE HEADER | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-010123 | 076551C-018-SP-0610-012 | 018-E-DAT-00055-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0013 DIESEL PUMPAROUND MP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-013 | 018-E-DAT-00054-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0014 DIESEL PUMPAROUND LP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-020 | 018-E-DAT-00053-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0020 A-D MVGO/FEED EXCHANGER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-021 | 018-E-DAT-00052-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0022 MVGO STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-029 | 018-E-DAT-00049-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0032 START-UP STEAM HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-030 | 018-E-DAT-00048-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0034 A-F SHUTDOWN TEMPERED WATER COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-032 | 018-E-DAT-00047-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0031 COOLING OIL HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-035 | 018-E-DAT-00045-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1008 FIRST STAGE INTERCOOLER - TRAIN 1A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-037 | 018-E-DAT-00044-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1010 TRAIN 1 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-038 | 018-E-DAT-00043-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1011 FIRST STAGE INTERCOOLER - TRAIN 1B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-040 | 018-E-DAT-00042-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0002 FIRST STAGE INTERCOOLER - SPARE TRAIN | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-042 | 018-E-DAT-00041-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2008 FIRST STAGE INTERCOOLER - TRAIN 2A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-044 | 018-E-DAT-00040-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2010 TRAIN 2 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010123 | 076551C-018-SP-0610-045 | 018-E-DAT-00039-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2011 FIRST STAGE INTERCOOLER - TRAIN 2B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-020-001 | 018-E-GAD-00036-001 | 018E0020 A-D MVGO / FEED EXCHANGER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-020-002 | 018-E-GAD-00036-002 | 018E0020 A-D MVGO / FEED EXCHANGER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-020-003 | 018-E-GAD-00036-003 | 018E0020 A-D MVGO / FEED EXCHANGER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-020-004 | 018-E-GAD-00036-004 | 018E0020 A-D MVGO / FEED EXCHANGER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-020-005 | 018-E-GAD-00036-005 | 018E0020 A-D MVGO / FEED EXCHANGER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-029-001 | 018-E-GAD-00032-001 | 018E0032 START-UP STEAM HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-029-002 | 018-E-GAD-00032-002 | 018E0032 START-UP STEAM HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-029-003 | 018-E-GAD-00032-003 | 018E0032 START-UP STEAM HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-029-004 | 018-E-GAD-00032-004 | 018E0032 START-UP STEAM HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-029-005 | 018-E-GAD-00032-005 | 018E0032 START-UP STEAM HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-032-001 | 018-E-GAD-00030-001 | 018E0031 COOLING OIL HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-032-002 | 018-E-GAD-00030-002 | 018E0031 COOLING OIL HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-032-003 | 018-E-GAD-00030-003 | 018E0031 COOLING OIL HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-032-004 | 018-E-GAD-00030-004 | 018E0031 COOLING OIL HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010124 | 076551C-018-DW-0610-032-005 | 018-E-GAD-00030-005 | 018E0031 COOLING OIL HEATER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-030-001 | 018-E-GAD-00031-001 | 018E0034 A-F SHUTDOWN TEMPERED WATER COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-030-002 | 018-E-GAD-00031-002 | 018E0034 A-F SHUTDOWN TEMPERED WATER COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-030-003 | 018-E-GAD-00031-003 | 018E0034 A-F SHUTDOWN TEMPERED WATER COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-030-004 | 018-E-GAD-00031-004 | 018E0034 A-F SHUTDOWN TEMPERED WATER COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-030-005 | 018-E-GAD-00031-005 | 018E0034 A-F SHUTDOWN TEMPERED WATER COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-030-006 | 018-E-GAD-00031-006 | 018E0034 A-F SHUTDOWN TEMPERED WATER COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-037-001 | 018-E-GAD-00027-001 | 018E1010 TRAIN 1 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-037-002 | 018-E-GAD-00027-002 | 018E1010 TRAIN 1 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-037-003 | 018-E-GAD-00027-003 | 018E1010 TRAIN 1 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-037-004 | 018-E-GAD-00027-004 | 018E1010 TRAIN 1 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-037-005 | 018-E-GAD-00027-005 | 018E1010 TRAIN 1 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-044-001 | 018-E-GAD-00023-001 | 018E2010 TRAIN 2 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-044-002 | 018-E-GAD-00023-002 | 018E2010 TRAIN 2 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-044-003 | 018-E-GAD-00023-003 | 018E2010 TRAIN 2 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-044-004 | 018-E-GAD-00023-004 | 018E2010 TRAIN 2 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010125 | 076551C-018-DW-0610-044-005 | 018-E-GAD-00023-005 | 018E2010 TRAIN 2 - SPILLBACK COOLER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010126 | 076551C-000R-MR-0610-002 | 000-E-MRQ-60002-001 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010127 | 076551C-018-DW-0610-012-001 | 018-E-GAD-00038-001 | 018E0013 DIESEL PUMPAROUND MP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-012-002 | 018-E-GAD-00038-002 | 018E0013 DIESEL PUMPAROUND MP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-012-003 | 018-E-GAD-00038-003 | 018E0013 DIESEL PUMPAROUND MP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-012-004 | 018-E-GAD-00038-004 | 018E0013 DIESEL PUMPAROUND MP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-012-005 | 018-E-GAD-00038-005 | 018E0013 DIESEL PUMPAROUND MP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-021-001 | 018-E-GAD-00035-001 | 018E0022 MVGO STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-021-002 | 018-E-GAD-00035-002 | 018E0022 MVGO STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-021-003 | 018-E-GAD-00035-003 | 018E0022 MVGO STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-021-004 | 018-E-GAD-00035-004 | 018E0022 MVGO STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-021-005 | 018-E-GAD-00035-005 | 018E0022 MVGO STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-035-001 | 018-E-GAD-00028-001 | 018E1008 FIRST STAGE INTERCOOLER - TRAIN 1A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-035-002 | 018-E-GAD-00028-002 | 018E1008 FIRST STAGE INTERCOOLER - TRAIN 1A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-035-003 | 018-E-GAD-00028-003 | 018E1008 FIRST STAGE INTERCOOLER - TRAIN 1A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-035-004 | 018-E-GAD-00028-004 | 018E1008 FIRST STAGE INTERCOOLER - TRAIN 1A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-035-005 | 018-E-GAD-00028-005 | 018E1008 FIRST STAGE INTERCOOLER - TRAIN 1A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-038-001 | 018-E-GAD-00026-001 | 018E1011 FIRST STAGE INTERCOOLER - TRAIN 1B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-038-002 | 018-E-GAD-00026-002 | 018E1011 FIRST STAGE INTERCOOLER - TRAIN 1B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-038-003 | 018-E-GAD-00026-003 | 018E1011 FIRST STAGE INTERCOOLER - TRAIN 1B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-038-004 | 018-E-GAD-00026-004 | 018E1011 FIRST STAGE INTERCOOLER - TRAIN 1B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010127 | 076551C-018-DW-0610-038-005 | 018-E-GAD-00026-005 | 018E1011 FIRST STAGE INTERCOOLER - TRAIN 1B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-040-001 | 018-E-GAD-00025-001 | 018E0002 FIRST STAGE INTERCOOLER - SPARE TRAIN | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-040-002 | 018-E-GAD-00025-002 | 018E0002 FIRST STAGE INTERCOOLER - SPARE TRAIN | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-040-003 | 018-E-GAD-00025-003 | 018E0002 FIRST STAGE INTERCOOLER - SPARE TRAIN | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-040-004 | 018-E-GAD-00025-004 | 018E0002 FIRST STAGE INTERCOOLER - SPARE TRAIN | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-040-005 | 018-E-GAD-00025-005 | 018E0002 FIRST STAGE INTERCOOLER - SPARE TRAIN | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-042-001 | 018-E-GAD-00024-001 | 018E2008 FIRST STAGE INTERCOOLER - TRAIN 2A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-042-002 | 018-E-GAD-00024-002 | 018E2008 FIRST STAGE INTERCOOLER - TRAIN 2A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-042-003 | 018-E-GAD-00024-003 | 018E2008 FIRST STAGE INTERCOOLER - TRAIN 2A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-042-004 | 018-E-GAD-00024-004 | 018E2008 FIRST STAGE INTERCOOLER - TRAIN 2A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-042-005 | 018-E-GAD-00024-005 | 018E2008 FIRST STAGE INTERCOOLER - TRAIN 2A | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-043-001 | 018-E-GAD-00037-001 | 018E0014 DIESEL PUMPAROUND LP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-043-002 | 018-E-GAD-00037-002 | 018E0014 DIESEL PUMPAROUND LP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-043-003 | 018-E-GAD-00037-003 | 018E0014 DIESEL PUMPAROUND LP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-043-004 | 018-E-GAD-00037-004 | 018E0014 DIESEL PUMPAROUND LP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-043-005 | 018-E-GAD-00037-005 | 018E0014 DIESEL PUMPAROUND LP STEAM GENERATOR | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-045-001 | 018-E-GAD-00022-001 | 018E2001 FIRST STAGE INTERCOOLER - TRAIN 2B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-045-002 | 018-E-GAD-00022-002 | 018E2001 FIRST STAGE INTERCOOLER - TRAIN 2B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-045-003 | 018-E-GAD-00022-003 | 018E2001 FIRST STAGE INTERCOOLER - TRAIN 2B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-045-004 | 018-E-GAD-00022-004 | 018E2001 FIRST STAGE INTERCOOLER - TRAIN 2B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010128 | 076551C-018-DW-0610-045-005 | 018-E-GAD-00022-005 | 018E2001 FIRST STAGE INTERCOOLER - TRAIN 2B | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010129 | 076551C-018-PID-0021-203-002 | 018-A-PID-20004-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 REACTOR FEED FURNACE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-010129 | 076551C-018-PID-0021-205-001 | 018-A-PID-20007-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 INTERSTAGE SEPARATOR | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-010129 | 076551C-018-PID-0021-220-001 | 018-A-PID-20022-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 018K1002 MU HYDROGEN COMPRESSOR 1ST STAGE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-010129 | 076551C-018-PID-0021-228-001 | 018-A-PID-20028-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 FUEL GAS SYSTEM FURNACE 018F2001 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-010129 | 076551C-018-PID-0021-243-001 | 018-A-PID-20029-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 FUEL GAS SYSTEM RECYCLE GAS FURNACE 018F2002 | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-010130 | 076551C-000R-MR-0570-002 | 000-C-MRQ-60012-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010131 | 076551C-000R-MR-0511-002 | 000-C-MRQ-60006-001 | MATERIAL REQUISITION FOR COLUMNS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010132 | 076551C-056-PID-0021-001-001 | 056-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - STK NAPHTA SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-002-001 | 056-A-PID-00010-002 | PIPING AND INSTRUMENT DIAGRAM - STK NAPHTA SYSTEM SITRA TANKS | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-003-001 | 056-A-PID-00010-003 | PIPING AND INSTRUMENT DIAGRAM - STK NAPHTA SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-010-001 | 056-A-PID-00011-002 | PIPING AND INSTRUMENT DIAGRAM - STK JET A-1 CALTEX (JP-5) | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-018-001 | 056-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - STK GASOLINE SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-019-001 | 056-A-PID-00013-002 | PIPING AND INSTRUMENT DIAGRAM - STK GASOLINE SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-020-001 | 056-A-PID-00013-003 | PIPING AND INSTRUMENT DIAGRAM - STK GASOLINE SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-035-001 | 056-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - STK KEROSENE SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-036-001 | 056-A-PID-00014-002 | PIPING AND INSTRUMENT DIAGRAM - STK KEROSENE SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-155-001 | 056-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - STK 4 PUMP HOUSE SITRA TANKS | 5A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-156-001 | 056-A-PID-00003-002 | PIPING AND INSTRUMENT DIAGRAM - STK MTBE PUMPS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-170-001 | 056-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - STK DIESEL TRANSFER PUMP 056P2952X 4 PUMP HOUSE | 2A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-185-001 | 056-A-PID-00014-003 | PIPING AND INSTRUMENT DIAGRAM - STK NEW NAPHTA / KERO TANK | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-210-001 | 056-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - STK STORAGE TANKS HEATING | 12A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-215-001 | 056-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - STK BUTANE INJECTION SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010132 | 076551C-056-PID-0021-216-001 | 056-A-PID-00009-002 | PIPING AND INSTRUMENT DIAGRAM - STK BUTANE INJECTION SYSTEM | 4A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-038-001 | 056-A-PID-00015-008 | PIPING AND INSTRUMENT DIAGRAM - STK 2 PUMP HOUSE SITRA TANKS | A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-052-001 | 056-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - STK DIESEL, FUEL OIL AND BUNKER SYSTEMS | 6A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-053-001 | 056-A-PID-00015-002 | PIPING AND INSTRUMENT DIAGRAM - STK DIESEL, FUEL OIL AND BUNKER SYSTEMS | 6A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-054-001 | 056-A-PID-00015-003 | PIPING AND INSTRUMENT DIAGRAM - STK DIESEL, FUEL OIL AND BUNKER SYSTEMS SITRA TANKS | 6A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-055-001 | 056-A-PID-00015-004 | PIPING AND INSTRUMENT DIAGRAM - STK DIESEL, FUEL OIL AND BUNKER SYSTEMS SITRA TANKS | 6A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-056-001 | 056-A-PID-00015-005 | PIPING AND INSTRUMENT DIAGRAM - STK DIESEL, FUEL OIL AND BUNKER SYSTEMS SITRA TANKS | 6A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-058-001 | 056-A-PID-00015-007 | PIPING AND INSTRUMENT DIAGRAM - STK KEROSENE SITRA TANK | 6A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-070-001 | 056-A-PID-00016-001 | PIPING AND INSTRUMENT DIAGRAM - STK SLOP SYSTEM | A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-085-001 | 056-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM - STK 2 PUMP HOUSE SITRA TANKS | 5A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-086-001 | 056-A-PID-00018-003 | PIPING AND INSTRUMENT DIAGRAM - STK 2 PUMP HOUSE SITRA TANKS | 5A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-102-001 | 056-A-PID-00019-001 | PIPING AND INSTRUMENT DIAGRAM - STK NO. 3 PUMP HOUSE | 4A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-103-001 | 056-A-PID-00019-002 | PIPING AND INSTRUMENT DIAGRAM - STK 3 PUMP HOUSE NEW NAPHTA/KERO/CRUDE OIL SHIPPING PUMPS | A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-113-001 | 056-A-PID-00020-001 | PIPING AND INSTRUMENT DIAGRAM - STK SEALINES SITRA TANKS | 4A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-125-001 | 056-A-PID-00021-001 | PIPING AND INSTRUMENT DIAGRAM - STK 1 PUMP HOUSE (NORTH MANIFOLD) SITRA TANKS | 4A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-140-001 | 056-A-PID-00023-001 | PIPING AND INSTRUMENT DIAGRAM - STK FOR NO. 1 PUMP HOUSE (EAST MANIFOLD) SITRA TANKS | 4A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010133 | 076551C-056-PID-0021-201-001 | 056-A-PID-00017-001 | PIPING AND INSTRUMENT DIAGRAM - STK SLOP SYSTEM | 5A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-010134 | 076551C-018-SP-0110-001 | 018-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1001 /F 018F2001 TRAIN 1&2 - REACTOR FEED FURNACE | B | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-004 | 018-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1004 TRAIN1 MP/HT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-006 | 018-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1006 TRAIN1 HP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-008 | 018-C-DAT-00008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0003 MP/MT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-009 | 018-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0004 MP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-024 | 018-C-DAT-00010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2004 TRAIN 2 MP/HT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-026 | 018-C-DAT-00011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2006 TRAIN 2 HP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-035 | 018-C-DAT-00012-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0006 LT OIL FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-036 | 018-C-DAT-00013-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0027 SOUR WATER DEGASSER | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-037 | 018-C-DAT-00014-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0028 RICH AMINE FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-046 | 018-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0037 CATALYST TRANSFER VESSEL | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-047 | 018-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0038 CATALYST TRANSFER VESSEL | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-048 | 018-C-DAT-00015-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0039 TRANSPORT OIL SURGE DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-050 | 018-C-DAT-00016-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0041 CATALYST SLOP OIL DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-056 | 018-C-DAT-00017-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0065 SEAL OIL RESERVOIR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010135 | 076551C-018-SP-0810-061 | 018-C-DAT-00018-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0050 SHORT CIRCULATION DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010136 | 076551C-021-SP-0810-003 | 021-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0003 HOT HIGH PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010136 | 076551C-021-SP-0810-004 | 021-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0008 HOT LOW PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010136 | 076551C-021-SP-0810-005 | 021-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0004 COLD HIGH PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010136 | 076551C-021-SP-0810-006 | 021-C-DAT-00008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0009 COLD LOW PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010136 | 076551C-021-SP-0810-012 | 021-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0015 RICH AMINE FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010136 | 076551C-023-SP-0810-004 | 023-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 023V0005 RICH AMINE ACCUMULATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010137 | ROC-BMR-MOM-000025 | 000-A-MOM-60022-001 | EBULLATING PUMPS 000-G-MRQ-60002-001 BAPCO TPFMC FLOWSERVE TECHNICAL MEETING | 0 | 2018-06-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010138 | 076551C-018-DW-0810-004-001 | 018-C-GAD-00020-001 | 018V1004 TRAIN 1 MP/HT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-004-002 | 018-C-GAD-00020-002 | 018V1004 TRAIN 1 MP/HT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-004-003 | 018-C-GAD-00020-003 | 018V1004 TRAIN 1 MP/HT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-006-001 | 018-C-GAD-00021-001 | 018V1006 TRAIN 1 HP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-006-002 | 018-C-GAD-00021-002 | 018V1006 TRAIN 1 HP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-006-003 | 018-C-GAD-00021-003 | 018V1006 TRAIN 1 HP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-008-001 | 018-C-GAD-00022-001 | 018V0003 MP/MT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-008-002 | 018-C-GAD-00022-002 | 018V0003 MP/MT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-008-003 | 018-C-GAD-00022-003 | 018V0003 MP/MT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-046-001 | 018-C-GAD-00018-001 | 018V0037 CATALYST TRANSFER VESSEL | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-046-002 | 018-C-GAD-00018-002 | 018V0037 CATALYST TRANSFER VESSEL | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-046-003 | 018-C-GAD-00018-003 | 018V0037 CATALYST TRANSFER VESSEL | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-047-001 | 018-C-GAD-00019-001 | 018V0038 CATALYST TRANSFER VESSEL | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-047-002 | 018-C-GAD-00019-002 | 018V0038 CATALYST TRANSFER VESSEL | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010138 | 076551C-018-DW-0810-047-003 | 018-C-GAD-00019-003 | 018V0038 CATALYST TRANSFER VESSEL | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-009-001 | 018-C-GAD-00023-001 | 018V0004 MP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-009-002 | 018-C-GAD-00023-002 | 018V0004 MP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-009-003 | 018-C-GAD-00023-003 | 018V0004 MP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-024-001 | 018-C-GAD-00024-001 | 018V2004 TRAIN 2 MP/HT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-024-002 | 018-C-GAD-00024-002 | 018V2004 TRAIN 2 MP/HT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-024-003 | 018-C-GAD-00024-003 | 018V2004 TRAIN 2 MP/HT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-026-001 | 018-C-GAD-00025-001 | 018V2006 TRAIN 2 HP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-026-002 | 018-C-GAD-00025-002 | 018V2006 TRAIN 2 HP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-026-003 | 018-C-GAD-00025-003 | 018V2006 TRAIN 2 HP/LT SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-035-001 | 018-C-GAD-00026-001 | 018V0006 LT OIL FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-035-002 | 018-C-GAD-00026-002 | 018V0006 LT OIL FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-035-003 | 018-C-GAD-00026-003 | 018V0006 LT OIL FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-036-001 | 018-C-GAD-00027-001 | 018V0027 SOUR WATER DEGASSER | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-036-002 | 018-C-GAD-00027-002 | 018V0027 SOUR WATER DEGASSER | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010139 | 076551C-018-DW-0810-036-003 | 018-C-GAD-00027-003 | 018V0027 SOUR WATER DEGASSER | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-037-001 | 018-C-GAD-00028-001 | 018V0028 RICH AMINE FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-037-002 | 018-C-GAD-00028-002 | 018V0028 RICH AMINE FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-037-003 | 018-C-GAD-00028-003 | 018V0028 RICH AMINE FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-048-001 | 018-C-GAD-00029-001 | 018V0039 TRANSPORT OIL SURGE DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-048-002 | 018-C-GAD-00029-002 | 018V0039 TRANSPORT OIL SURGE DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-048-003 | 018-C-GAD-00029-003 | 018V0039 TRANSPORT OIL SURGE DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-050-001 | 018-C-GAD-00030-001 | 018V0041 CATALYST SLOP OIL DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-050-002 | 018-C-GAD-00030-002 | 018V0041 CATALYST SLOP OIL DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-050-003 | 018-C-GAD-00030-003 | 018V0041 CATALYST SLOP OIL DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-056-001 | 018-C-GAD-00031-001 | 018V0065 SEAL OIL RESERVOIR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-056-002 | 018-C-GAD-00031-002 | 018V0065 SEAL OIL RESERVOIR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-056-003 | 018-C-GAD-00031-003 | 018V0065 SEAL OIL RESERVOIR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-061-001 | 018-C-GAD-00032-001 | 018V0050 SHORT CIRCULATION DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-061-002 | 018-C-GAD-00032-002 | 018V0050 SHORT CIRCULATION DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010140 | 076551C-018-DW-0810-061-003 | 018-C-GAD-00032-003 | 018V0050 SHORT CIRCULATION DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-003-001 | 021-C-GAD-00032-001 | 021V0003 HOT HIGH PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-003-002 | 021-C-GAD-00032-002 | 021V0003 HOT HIGH PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-003-003 | 021-C-GAD-00032-003 | 021V0003 HOT HIGH PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-004-001 | 021-C-GAD-00007-001 | 021V0008 HOT LOW PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-004-002 | 021-C-GAD-00007-002 | 021V0008 HOT LOW PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-004-003 | 021-C-GAD-00007-003 | 021V0008 HOT LOW PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-005-001 | 021-C-GAD-00008-001 | 021V0004 COLD HIGH PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-005-002 | 021-C-GAD-00008-002 | 021V0004 COLD HIGH PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-005-003 | 021-C-GAD-00008-003 | 021V0004 COLD HIGH PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-006-001 | 021-C-GAD-00009-001 | 021V0009 COLD LOW PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-006-002 | 021-C-GAD-00009-002 | 021V0009 COLD LOW PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-006-003 | 021-C-GAD-00009-003 | 021V0009 COLD LOW PRESSURE SEPARATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-012-001 | 021-C-GAD-00010-001 | 021V0015 RICH AMINE FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-012-002 | 021-C-GAD-00010-002 | 021V0015 RICH AMINE FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-021-DW-0810-012-003 | 021-C-GAD-00010-003 | 021V0015 RICH AMINE FLASH DRUM | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-023-DW-0810-004-001 | 023-C-GAD-00002-001 | 023V0005 RICH AMINE ACCUMULATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-023-DW-0810-004-002 | 023-C-GAD-00002-002 | 023V0005 RICH AMINE ACCUMULATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010141 | 076551C-023-DW-0810-004-003 | 023-C-GAD-00002-003 | 023V0005 RICH AMINE ACCUMULATOR | A | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010142 | 076551C-000R-RT-2500-001 | 000-D-RPT-60001-001 | SUMMARY DESCRIPTION, ACTION PLAN AND EXECUTION STRATEGY FOR THE REVAMPING ACTIVITIES OF TANKS UNIT 050 - 056 - 372 | A | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-010143 | 076551C-061-PID-0021-040-001 | 061-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - WRF SEALINES - SITRA TANKS / WHARF MANIFOLD SITRAWHARF | 6A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-055-001 | 061-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - WRF MANIFOLD SITRA WHARF | 6A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-056-001 | 061-A-PID-00004-002 | PIPING AND INSTRUMENT DIAGRAM - WRF SITRA WHARF | 5A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-071-001 | 061-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - WRF 'T' HEAD INTERCONNECTING LINES SITRA WHARF | 5A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-072-001 | 061-A-PID-00005-003 | PIPING AND INSTRUMENT DIAGRAM - WRF 'T' HEAD INTERCONNECTING LINES SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-086-001 | 061-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - WRF BERTHS 1 & 3 - 'T' HEAD SITRA WHARF | 5A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-087-001 | 061-A-PID-00006-002 | PIPING AND INSTRUMENT DIAGRAM - WRF BERTHS 1 & 3 - 'T' HEAD SITRA WHARF | 4A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-103-001 | 061-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - WRF BERTHS 2 & 4 - 'T' HEAD SITRA WHARF | 5A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-104-001 | 061-A-PID-00007-002 | PIPING AND INSTRUMENT DIAGRAM - WRF BERTHS 2 & 4 - 'T' HEAD SITRA WHARF | 4A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-105-001 | 061-A-PID-00007-003 | PIPING AND INSTRUMENT DIAGRAM - WRF BERTHS 2 & 4 - 'T' HEAD SITRA WHARF | 4A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-106-001 | 061-A-PID-00007-004 | PIPING AND INSTRUMENT DIAGRAM - WRF BERTHS 2 & 4 - 'T' HEAD SITRA WHARF | 4A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-121-001 | 061-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - WRF ISLAND SITRA WHARF | 4A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-122-001 | 061-A-PID-00008-002 | PIPING AND INSTRUMENT DIAGRAM - WRF ISLAND SITRA WHARF | 4A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-130-001 | 061-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - WRF ISLAND SITRA WHARF | 5A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-131-001 | 061-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - WRF AIA AND DCI-4A INJECTION SITRA WHARF MANIFOLD | 4A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010143 | 076551C-061-PID-0021-132-001 | 061-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - WRF DYE INJECTION SITRA WHARF MANIFOLD | 1A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-001-001 | 061-A-PID-50001-001 | PIPING AND INSTRUMENT DIAGRAM - WRF NAPHTHA/KERO/10PPM DIESEL PROPANE AND BUTANE SITRA WHARF NORTH OF MANIFORL | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-002-001 | 061-A-PID-50002-001 | PIPING AND INSTRUMENT DIAGRAM - WRF LOADING LINE WHARF NO. 182 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-003-001 | 061-A-PID-50003-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING MANIFOLDS AT BERTH 1 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-004-001 | 061-A-PID-50004-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING ARMS AT BERTH 1 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-005-001 | 061-A-PID-50005-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING MANIFOLDS AT BERTH 2 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-006-001 | 061-A-PID-50006-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING ARMS AT BERTH 2 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-007-001 | 061-A-PID-50007-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING MANIFOLDS AT BERTH 3 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-008-001 | 061-A-PID-50008-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING ARMS AT BERTH 3 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-009-001 | 061-A-PID-50009-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING MANIFOLDS AT BERTH 5 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-010-001 | 061-A-PID-50010-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING ARMS AT BERTH 5 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-011-001 | 061-A-PID-50011-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING MANIFOLDS AT BRTH 6 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-012-001 | 061-A-PID-50012-001 | PIPING AND INSTRUMENT DIAGRAM - WRF WHITE AND BLACK PRODUCTS LOADING ARMS AT BERTH 6 | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010144 | 076551C-061-PID-0021-013-001 | 061-A-PID-50013-001 | PIPING AND INSTRUMENT DIAGRAM - WRF LPG LOADING FACILITIES AT BERTH 1 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0021-014-001 | 061-A-PID-50014-001 | PIPING AND INSTRUMENT DIAGRAM - WRF LPG LOADING FACILITIES AT BERTH 2 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0021-015-001 | 061-A-PID-50015-001 | PIPING AND INSTRUMENT DIAGRAM - WRF C3/C4 BLOW DRUM DRUM SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0021-026-001 | 061-A-PID-50016-001 | PIPING AND INSTRUMENT DIAGRAM - WRF SLOP VESSEL AT BERTH 1 AND 3 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0021-027-001 | 061-A-PID-50017-001 | PIPING AND INSTRUMENT DIAGRAM - WRF SLOP VESSEL AT BERTH 2 AND 4 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0021-028-001 | 061-A-PID-50018-001 | PIPING AND INSTRUMENT DIAGRAM - WRF SLOP VESSEL AT BERTH 5 AND 6 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0021-029-001 | 061-A-PID-50019-001 | PIPING AND INSTRUMENT DIAGRAM - WRF SLOP VESSEL AT BERTH 1 AND 3 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0021-030-001 | 061-A-PID-50020-001 | PIPING AND INSTRUMENT DIAGRAM - WRF SLOP VESSEL AT BERTH 2 AND 4 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0021-031-001 | 061-A-PID-50021-001 | PIPING AND INSTRUMENT DIAGRAM - WRF SLOP VESSEL AT BERTH 5 AND 6 SITRA WHARF | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0031-500-001 | 061-A-PID-50022-001 | PIPING AND INSTRUMENT DIAGRAM - WRF BATTERY LIMIT UTILITIES | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0031-504-001 | 061-A-PID-50023-001 | PIPING AND INSTRUMENT DIAGRAM - WRF NITROGEN SYSTEM - T-HEAD | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0031-504-002 | 061-A-PID-50024-001 | PIPING AND INSTRUMENT DIAGRAM - WRF NITROGEN SYSTEM - ISLAND | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0031-505-001 | 061-A-PID-50025-001 | PIPING AND INSTRUMENT DIAGRAM - WRF INSTRUMENT AIR SYSTEM - T-HEAD | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010145 | 076551C-061-PID-0031-505-002 | 061-A-PID-50026-001 | PIPING AND INSTRUMENT DIAGRAM - WRF INSTRUMENT AIR SYSTEM - ISLAND | A | 2018-06-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010146 | 076551C-018-DW-0610-024-001 | 018-E-GAD-00034-001 | 018E0021 MVGO BFW PREHEATER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-024-002 | 018-E-GAD-00034-002 | 018E0021 MVGO BFW PREHEATER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-024-003 | 018-E-GAD-00034-003 | 018E0021 MVGO BFW PREHEATER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-024-004 | 018-E-GAD-00034-004 | 018E0021 MVGO BFW PREHEATER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-024-005 | 018-E-GAD-00034-005 | 018E0021 MVGO BFW PREHEATER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-027-001 | 018-E-GAD-00033-001 | 018E0028 A-H & J-M VAC. COLUMN BOTTOM TEMPERED WATER EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-027-002 | 018-E-GAD-00033-002 | 018E0028 A-H & J-M VAC. COLUMN BOTTOM TEMPERED WATER EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-027-003 | 018-E-GAD-00033-003 | 018E0028 A-H & J-M VAC. COLUMN BOTTOM TEMPERED WATER EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-027-004 | 018-E-GAD-00033-004 | 018E0028 A-H & J-M VAC. COLUMN BOTTOM TEMPERED WATER EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-027-005 | 018-E-GAD-00033-005 | 018E0028 A-H & J-M VAC. COLUMN BOTTOM TEMPERED WATER EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-027-006 | 018-E-GAD-00033-006 | 018E0028 A-H & J-M VAC. COLUMN BOTTOM TEMPERED WATER EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-034-001 | 018-E-GAD-00029-001 | 018E0001 MAKE-UP HYDROGEN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-034-002 | 018-E-GAD-00029-002 | 018E0001 MAKE-UP HYDROGEN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-034-003 | 018-E-GAD-00029-003 | 018E0001 MAKE-UP HYDROGEN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-034-004 | 018-E-GAD-00029-004 | 018E0001 MAKE-UP HYDROGEN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010146 | 076551C-018-DW-0610-034-005 | 018-E-GAD-00029-005 | 018E0001 MAKE-UP HYDROGEN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-001-001 | 021-E-GAD-00012-001 | 021E0001 VACUUM DRIER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-001-002 | 021-E-GAD-00012-002 | 021E0001 VACUUM DRIER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-001-003 | 021-E-GAD-00012-003 | 021E0001 VACUUM DRIER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-001-004 | 021-E-GAD-00012-004 | 021E0001 VACUUM DRIER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-001-005 | 021-E-GAD-00012-005 | 021E0001 VACUUM DRIER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-002-001 | 021-E-GAD-00011-001 | 021E0002 A/B/C STRIPPER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-002-002 | 021-E-GAD-00011-002 | 021E0002 A/B/C STRIPPER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-002-003 | 021-E-GAD-00011-003 | 021E0002 A/B/C STRIPPER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-002-004 | 021-E-GAD-00011-004 | 021E0002 A/B/C STRIPPER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010147 | 076551C-021-DW-0610-002-005 | 021-E-GAD-00011-005 | 021E0002 A/B/C STRIPPER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-010-001 | 021-E-GAD-00010-001 | 021E0013 STRIPPER FEED / BOTTOMS EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-010-002 | 021-E-GAD-00010-002 | 021E0013 STRIPPER FEED / BOTTOMS EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-010-003 | 021-E-GAD-00010-003 | 021E0013 STRIPPER FEED / BOTTOMS EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-010-004 | 021-E-GAD-00010-004 | 021E0013 STRIPPER FEED / BOTTOMS EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-010-005 | 021-E-GAD-00010-005 | 021E0013 STRIPPER FEED / BOTTOMS EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-011-001 | 021-E-GAD-00009-001 | 021E0015 STRIPPER BOTTOMS / MP STEAM GENERATOR | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-011-002 | 021-E-GAD-00009-002 | 021E0015 STRIPPER BOTTOMS / MP STEAM GENERATOR | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-011-003 | 021-E-GAD-00009-003 | 021E0015 STRIPPER BOTTOMS / MP STEAM GENERATOR | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-011-004 | 021-E-GAD-00009-004 | 021E0015 STRIPPER BOTTOMS / MP STEAM GENERATOR | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-011-005 | 021-E-GAD-00009-005 | 021E0015 STRIPPER BOTTOMS / MP STEAM GENERATOR | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-012-001 | 021-E-GAD-00008-001 | 021E0017 DIESEL PRODUCT TRIM COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-012-002 | 021-E-GAD-00008-002 | 021E0017 DIESEL PRODUCT TRIM COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-012-003 | 021-E-GAD-00008-003 | 021E0017 DIESEL PRODUCT TRIM COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-012-004 | 021-E-GAD-00008-004 | 021E0017 DIESEL PRODUCT TRIM COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010148 | 076551C-021-DW-0610-012-005 | 021-E-GAD-00008-005 | 021E0017 DIESEL PRODUCT TRIM COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010149 | 076551C-373-PID-0031-100-001 | 373-A-PID-00026-001 | PIPING AND INSTRUMENT DIAGRAM - IIAS GAS TURBINE | 4A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010150 | 076551C-018-SP-0610-024 | 018-E-DAT-00051-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0021 MVGO/BFW PREHEATER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010150 | 076551C-018-SP-0610-027 | 018-E-DAT-00050-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0028 A-L VAC. COLUMN BOTTOM TEMPERED WATER EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010150 | 076551C-018-SP-0610-034 | 018-E-DAT-00046-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0001 MAKE-UP HYDROGEN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010151 | 076551C-021-SP-0610-001 | 021-E-DAT-00016-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0001 VACUUM DRIER BOTTOMS/FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010151 | 076551C-021-SP-0610-002 | 021-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0002 A/B/C STRIPPER BOTTOMS / FEED EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010151 | 076551C-021-SP-0610-010 | 021-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0013 STRIPPER FEED / BOTTOMS EXCHANGER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010151 | 076551C-021-SP-0610-011 | 021-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0015 STRIPPER BOTTOMS / MP STEAM GENERATOR | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010151 | 076551C-021-SP-0610-012 | 021-E-DAT-00012-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0017 DIESEL PRODUCT TRIM COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010152 | 076551C-018-SP-0630-001 | 018-E-DAT-00057-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0037 A HP/MP BLOWDOWN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 1 - APPROVED | 2018-07-10 | CLASS 2
CON-BMP-TRA-010152 | 076551C-018-SP-0630-002 | 018-E-DAT-00056-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0037 B LP BLOWDOWN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 1 - APPROVED | 2018-07-10 | CLASS 2
CON-BMP-TRA-010152 | 076551C-018-SP-0630-003 | 018-E-DAT-00058-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0029 LEAN AMINE SCRUBBER COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 1 - APPROVED | 2018-07-10 | CLASS 2
CON-BMP-TRA-010153 | 076551C-021-SP-0630-001 | 021-E-DAT-00018-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0014 STRIPPER BOTTOMS /MP STEAM SUPERHEATER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010153 | 076551C-021-SP-0630-002 | 021-E-DAT-00017-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0019 STEAM BLOWDOWN COOLER | A | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-010154 | 076551C-018-PID-0021-211-001 | 018-A-PID-20014-001 | PIPING AND INSTRUMENT DIAGRAM TRAIN 2 HP/HT FLASH GAS COOLERS | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010155 | 076551C-018-PID-0031-505-004 | 018-A-PID-00096-004 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 2 FLARE HEADER | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010155 | 076551C-018-PID-0031-505-005 | 018-A-PID-00096-005 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU TRAIN 2 FLARE HEADER | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010155 | 076551C-018-PID-0031-505-006 | 018-A-PID-00096-006 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON FLARE HEADER | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010155 | 076551C-018-PID-0031-505-007 | 018-A-PID-00096-007 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON FLARE HEADER | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010155 | 076551C-018-PID-0031-505-008 | 018-A-PID-00096-008 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON FLARE HEADER | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010155 | 076551C-018-PID-0031-506-001 | 018-A-PID-00097-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON 60 STEAM SYSTEM | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010155 | 076551C-018-PID-0031-506-002 | 018-A-PID-00097-002 | PIPING AND INSTRUMENT DIAGRAM - COMMON 550 / 110 STEAM SYSTEM | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010155 | 076551C-018-PID-0031-515-001 | 018-A-PID-00099-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON BOILER FEED WATER SYSTEM | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010156 | 076551C-907-PID-0021-001-001 | 907-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - TRF REFINERY TO SITRA TRANSFER LINES | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-010157 | 076551C-023-CN-0007-001 | 023-A-BOD-00001-001 | BASIS OF DESIGN 1HRU (UNIT 023) HYDROGEN RECOVERY UNIT | B | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-010158 | 076551C-018-PID-0031-502-002 | 018-A-PID-00094-002 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU AMINE CLOSED DRAIN SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010158 | 076551C-018-PID-0031-503-002 | 018-A-PID-00093-002 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU SOUR WATER CLOSED DRAIN SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010158 | 076551C-018-PID-0031-507-002 | 018-A-PID-00102-002 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON COOLING WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010158 | 076551C-018-PID-0031-507-003 | 018-A-PID-00102-003 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON COOLING WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010158 | 076551C-018-PID-0031-511-001 | 018-A-PID-00101-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON CONDENSATE SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010158 | 076551C-018-PID-0031-513-001 | 018-A-PID-00103-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON INSTRUMENT AIR AND YARD AIR SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010159 | 076551C-386-PID-0031-001-001 | 386-A-PID-00001-040 | PIPING AND INSTRUMENT DIAGRAM - WWTP EMERGENCY POND | 2A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010159 | 076551C-386-PID-0031-002-001 | 386-A-PID-00001-002 | PIPING AND INSTRUMENT DIAGRAM - EQUALIZATION TANK 386D002A | 2A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010159 | 076551C-386-PID-0031-003-001 | 386-A-PID-00001-003 | PIPING AND INSTRUMENT DIAGRAM - EQUALIZATION TANK 386D002B | 2A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 1
CON-BMP-TRA-010160 | 076551C-021-EL-001 | 021-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO.3 HYDRODESULPHURIZATION UNIT (3HDU) | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-010160 | 076551C-023-EL-001 | 023-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO.1 HYDROGEN RECOVERY UNIT (1HRU) | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-010161 | 076551C-018-SP-0910-003 | 018-G-DAT-00026-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN FEED PUMPS 018P0002A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-004 | 018-G-DAT-00011-001 | CENTRIFUGAL PUMPS DATA SHEET 1ST ATM COLUMN WATER PUMPS 018P0004A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-005 | 018-G-DAT-00008-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN REFLUX PUMPS 018P0003A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-006 | 018-G-DAT-00017-001 | CENTRIFUGAL PUMPS DATA SHEET 2ND ATM COLUMN WATER PUMPS 018P0006A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-007 | 018-G-DAT-00010-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN OVHD PRODUCT PUMPS 018P0005A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-011 | 018-G-DAT-00007-001 | CENTRIFUGAL PUMPS DATA SHEET LVGO PUMPS 018P0012A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-013 | 018-G-DAT-00006-001 | CENTRIFUGAL PUMPS DATA SHEET HVGO PUMPAROUND PUMPS 018P0014A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-014 | 018-G-DAT-00009-001 | CENTRIFUGAL PUMPS DATA SHEET WASH OIL CIRCULATION PUMPS 018P0016A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-016 | 018-G-DAT-00019-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM COLUMN SLOP OIL PUMPS 018P0010A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-017 | 018-G-DAT-00014-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM COLUMN SOUR WATER PUMPS 018P0011A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-023 | 018-G-DAT-00015-001 | CENTRIFUGAL PUMPS DATA SHEET CATALYST SLOP OIL PUMPS 018P0026A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-025 | 018-G-DAT-00032-001 | CENTRIFUGAL PUMPS DATA SHEET VENT GAS SCRUBBER BOTTOM PUMPS 018P0020A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-029 | 018-G-DAT-00016-001 | CENTRIFUGAL PUMPS DATA SHEET FLARE KO DRUM PUMPS 018P0033A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-031 | 018-G-DAT-00012-001 | CENTRIFUGAL PUMPS DATA SHEET TRAIN 1 BFW CIRCULATION PUMPS 018P1007A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-018-SP-0910-032 | 018-G-DAT-00013-001 | CENTRIFUGAL PUMPS DATA SHEET TRAIN 2 BFW CIRCULATION PUMPS 018P2007A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-021-SP-0910-003 | 021-G-DAT-00005-001 | CENTRIFUGAL PUMP DATA SHEET FOR STRIPPER REFLUX PUMPS 021P0003A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-021-SP-0910-013 | 021-G-DAT-00004-001 | CENTRIFUGAL PUMP DATA SHEET FOR FLARE KO DRUM PUMPS 021P0012A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010161 | 076551C-023-SP-0910-001 | 023-G-DAT-00001-001 | CENTRIFUGAL PUMP DATA SHEET FOR RECOVERY HC CONDENSATE PUMPS 023P0001A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010162 | 076551C-050-SP-0910-001 | 050-G-DAT-50001-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA TRANSFER PUMP 050P5030 | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010162 | 076551C-050-SP-0910-004 | 050-G-DAT-50002-001 | CENTRIFUGAL PUMPS DATA SHEET BAHRAIN / RUBBLE CRUDE OIL INJECTION /TRANSFER PUMP 050P5033A/B/C | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010162 | 076551C-050-SP-0910-009 | 050-G-DAT-50003-001 | CENTRIFUGAL PUMPS DATA SHEET SLOP OIL PUMPS 050P5038A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010162 | 076551C-079-SP-0910-002 | 079-G-DAT-00002-001 | CENTRIFUGAL PUMPS DATA SHEET SPENT CAUSTIC PUMPS 079P0002 A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010162 | 076551C-081-SP-0910-001 | 081-G-DAT-00001-001 | CENTRIFUGAL PUMPS DATA SHEET LSDP FLARE KO DRUM FOR BMP UNITS PUMPS 081P8102 A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010162 | 076551C-082-SP-0910-001 | 082-G-DAT-00001-001 | CENTRIFUGAL PUMP DATA SHEET REFINERY SOUTH FLARE MAIN KO DRUM PUMPS 082P0001 A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010162 | 076551C-082-SP-0910-002 | 082-G-DAT-00002-001 | CENTRIFUGAL PUMP DATA SHEET REFINERY SOUTH FLARE SEAL DRUM PUMPS 082P0002 A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-001-001 | 050-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM NAPHTA TRANSFER SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-002-001 | 050-A-MSD-50001-002 | MATERIAL SELECTION DIAGRAM KEROSENE TRANSFER SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-003-001 | 050-A-MSD-50001-003 | MATERIAL SELECTION DIAGRAM 10 PPM DIESEL TRANSFER SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-004-001 | 050-A-MSD-50001-004 | MATERIAL SELECTION DIAGRAM LVGO TANKS AND PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-005-001 | 050-A-MSD-50001-005 | MATERIAL SELECTION DIAGRAM HSR NAPHTA SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-006-001 | 050-A-MSD-50001-006 | MATERIAL SELECTION DIAGRAM DIESEL TRANSFER SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-007-001 | 050-A-MSD-50001-007 | MATERIAL SELECTION DIAGRAM NEW 1RHCU FEED TANKS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-008-001 | 050-A-MSD-50001-008 | MATERIAL SELECTION DIAGRAM A/B CRUDE OIL TRANSFER SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-009-001 | 050-A-MSD-50001-009 | MATERIAL SELECTION DIAGRAM A/B CRUDE OIL TRANSFER SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-010-001 | 050-A-MSD-50001-010 | MATERIAL SELECTION DIAGRAM FUEL OIL/CRUDE OIL TRANSFER SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-011-001 | 050-A-MSD-50001-011 | MATERIAL SELECTION DIAGRAM UNCONVERTED OIL (UCO)/DIESEL TANKS AND PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-012-001 | 050-A-MSD-50001-012 | MATERIAL SELECTION DIAGRAM 2HDU AND 3HDU FEED TANKS AND PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-013-001 | 050-A-MSD-50001-013 | MATERIAL SELECTION DIAGRAM 1HCU AND 2HCU GASOIL FEED TANKS AND PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-014-001 | 050-A-MSD-50001-014 | MATERIAL SELECTION DIAGRAM KMU FEED TANKS AND KERO INJECTION TANKS (FO BLENDING) | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-015-001 | 050-A-MSD-50001-015 | MATERIAL SELECTION DIAGRAM LIGHT NAPHTA TANKS AND PUMPS FOR GASOLINE BLENDING | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-016-001 | 050-A-MSD-50001-016 | MATERIAL SELECTION DIAGRAM PLATFORMATE TANKS AND PUMPS FOR GASOLINE BLENDING | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-017-001 | 050-A-MSD-50001-017 | MATERIAL SELECTION DIAGRAM EXISTING DIESEL BLENDING SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010163 | 076551C-050-MSD-0011-018-001 | 050-A-MSD-50001-018 | MATERIAL SELECTION DIAGRAM EXISTING FUEL OIL BLENDING SYSTEM | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 1 - APPROVED | 2018-07-07 | CLASS 2
CON-BMP-TRA-010164 | 076551C-079-MSD-0011-001-001 | 079-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM SPENT CAUSTIC TRATING PLANT | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-010165 | 076551C-050-ML-222 | 050-A-HZR-50001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 050 | 0 | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 |  |  | CLASS 2
CON-BMP-TRA-010166 | 076551C-056-ML-222 | 056-A-HZR-50001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 056 | 0 | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 |  |  | CLASS 2
CON-BMP-TRA-010167 | 076551C-061-ML-222 | 061-A-HZR-50001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 061 | 0 | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 |  |  | CLASS 2
CON-BMP-TRA-010168 | 076551C-907-ML-222 | 907-A-HZR-50001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 907 | 0 | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 |  |  | CLASS 2
CON-BMP-TRA-010169 | 076551C-018-PID-0031-507-001 | 018-A-PID-00102-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON COOLING WATER SYSTEM | A | 2018-06-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010169 | 076551C-018-PID-0031-512-001 | 018-A-PID-00100-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON WATER / FED SYSTEM (DRINKING WATER) | A | 2018-06-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010169 | 076551C-018-PID-0031-514-001 | 018-A-PID-00104-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON NITROGEN SYSTEM | A | 2018-06-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010170 | 076551C-375-PID-0031-001-001 | 375-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - DWS TREATMENT PLANT DRINKING WATER SYSTEM | 3A | 2018-06-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010170 | 076551C-375-PID-0031-002-001 | 375-A-PID-00001-006 | PIPING AND INSTRUMENT DIAGRAM - DWS DRINKING WATER DISTRIBUTION SYSTEM REFINERY | 3A | 2018-06-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010170 | 076551C-375-PID-0031-003-001 | 375-A-PID-00001-004 | PIPING AND INSTRUMENT DIAGRAM - DWS DRINKING WATER DISTR. SYS. REFINERY | 2A | 2018-06-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010171 | 076551C-018-SP-0910-008 | 018-G-DAT-00024-001 | CENTRIFUGAL PUMPS DATA SHEET DIESEL PUMPAROUND PUMPS 018P0007A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010171 | 076551C-018-SP-0910-009 | 018-G-DAT-00021-001 | CENTRIFUGAL PUMPS DATA SHEET DIESEL PRODUCT PUMPS 018P0008A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010171 | 076551C-018-SP-0910-010 | 018-G-DAT-00018-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN BOTTOMS PUMPS 018P0009A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010171 | 076551C-018-SP-0910-012 | 018-G-DAT-00033-001 | CENTRIFUGAL PUMPS DATA SHEET MVGO PUMPS 018P0013A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010171 | 076551C-018-SP-0910-015 | 018-G-DAT-00023-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM COLUMN BOTTOMS PUMPS 018P0017A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010171 | 076551C-018-SP-0910-021 | 018-G-DAT-00020-001 | CENTRIFUGAL PUMPS DATA SHEET SHORT CIRCULATION PUMPS 018P0027A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010171 | 076551C-018-SP-0910-022 | 018-G-DAT-00022-001 | CENTRIFUGAL PUMPS DATA SHEET COOLING OIL CIRCULATION PUMPS 018P0025A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010171 | 076551C-018-SP-0910-030 | 018-G-DAT-00025-001 | CENTRIFUGAL PUMPS DATA SHEET TEMPERED WATER PUMPS 018P0028A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010171 | 076551C-018-SP-0910-033 | 018-G-DAT-00027-001 | CENTRIFUGAL PUMPS DATA SHEET CUTTER STOCK PUMPS 018P0018A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010172 | 076551C-021-SP-0910-004 | 021-G-DAT-00006-001 | CENTRIFUGAL PUMP DATA SHEET FOR VACUUM DRIER BOTTOMS PUMP 021P0004A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010172 | 076551C-021-SP-0910-007 | 021-G-DAT-00007-001 | CENTRIFUGAL PUMP DATA SHEET FOR LEAN AMINE PUMPS 021P0007A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010172 | 076551C-023-SP-0910-002 | 023-G-DAT-00002-001 | CENTRIFUGAL PUMP DATA SHEET FOR LEAN AMINE PUMPS 023P0002A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010173 | 076551C-021-SP-0910-001 | 021-G-DAT-00003-001 | CENTRIFUGAL PUMP DATA SHEET FOR BACKWASH PUMP 021-P0008A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010173 | 076551C-021-SP-0910-005 | 021-G-DAT-00002-001 | CENTRIFUGAL PUMP DATA SHEET FOR EJECTOR RECEIVER OIL PUMPS 021P0005A/B | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-010174 | 076551C-018-EL-001 | 018-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO.1 RESIDUE HYDROCRACKING UNIT (1HRCU) | A | 2018-06-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-001-001 | 020-A-PID-00027-001 | PIPING AND INSTRUMENT DIAGRAM - STM G&D STEAM DISTRIBUTION SYSTEM DESALINATION PLANTS | 4A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-005-001 | 371-A-PID-50001-001 | PIPING AND INSTRUMENT DIAGRAM - STM G&D20 PSIG EXCESS STEAM CONDENSATE SYSTEM | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-006-001 | 371-A-PID-50002-001 | PIPING AND INSTRUMENT DIAGRAM - STM G&D SOUTH CLCW 550/110 PSIG LETDOWN STATION | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-007-014 | 371-A-PID-50003-001 | PIPING AND INSTRUMENT DIAGRAM - STM G&D SOUTH CLCW 110/60 PSIG LETDOWN STATION | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-008-001 | 020-A-PID-00051-001 | PIPING AND INSTRUMENT DIAGRAM - STM G&D L.P. BOILER UTILITY SYSTEM 2 POWER PLANT | 5A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-009-001 | 020-A-PID-00027-002 | PIPING AND INSTRUMENT DIAGRAM - STM G&D REFINERY STEAM DISTRIBUTION SYSTEM | 8A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-010-001 | 371-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - STM G&D 550 STEAM SYSTEM | 3A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-011-001 | 382-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - STM G&D DRAINAGE SYSTEM L.G. / H.G. CONDENSATE / OILY WATER | 4A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-012-001 | 020-A-PID-00027-003 | PIPING AND INSTRUMENT DIAGRAM - STM G&D REFINERY STEAM DISTRIBUTION SYSTEM - 3CDU | 4A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-013-001 | 020-A-PID-00027-004 | PIPING AND INSTRUMENT DIAGRAM - STM G&D REFINERY STEAM DISTRIBUTION SYSTEM - GCRU/1CDU/2CDU | 4A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010175 | 076551C-371-PID-0031-014-001 | 371-A-PID-00027-007 | PIPING AND INSTRUMENT DIAGRAM - STM G&D REFINERY STEAM DISTRIBUTION SYSTEM - 1VBU/KERO RERUN/LSFO | 4A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010176 | 076551C-050-SP-0910-002 | 050-G-DAT-50004-001 | CENTRIFUGAL PUMPS DATA SHEET KEROSENE PUMP 050P5031 | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010176 | 076551C-056-SP-0910-004 | 056-G-DAT-50001-001 | CENTRIFUGAL PUMPS DATA SHEET DIESEL SHIPPING PUMP 056P5606 | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010177 | 076551C-073-PID-0021-001-001 | 062-A-PID-00023-001 | PIPING AND INSTRUMENT DIAGRAM - LSFO LSFO ON PLOT FLARE HEADER | 18A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-010178 | 076551C-000R-RT-201 | 000-A-RPT-60003-001 | DIESEL RUNDOWN PROCESS STUDY | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-010179 | 076551C-018-PID-0031-501-002 | 018-A-PID-00095-002 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU RECOVERED PROCESS SLOP OIL SYSTEM | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-501-003 | 018-A-PID-00095-003 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU RECOVERED PROCESS SLOP OIL SYSTEM | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-516-001 | 018-A-PID-00105-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON FLUSHING OIL | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-516-002 | 018-A-PID-00105-002 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU DIESEL HEADER | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-516-003 | 018-A-PID-00105-003 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COLD HVGO | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-516-004 | 018-A-PID-00105-004 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU HOT HVGO | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-516-005 | 018-A-PID-00105-005 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON FLUSHING OIL | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-517-001 | 018-A-PID-00092-001 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON HOT PURGING OIL | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-517-002 | 018-A-PID-00092-002 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON COLD PURGING OIL | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-517-003 | 018-A-PID-00092-003 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON PURGING OIL SYSTEM - TRAIN 1 | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-517-004 | 018-A-PID-00092-004 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON PURGING OIL SYSTEM - TRAIN 2 | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-517-005 | 018-A-PID-00092-005 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU COMMON SECTION PURGING OIL SYSTEM | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-517-006 | 018-A-PID-00092-006 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU PURGE LIST | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010179 | 076551C-018-PID-0031-517-007 | 018-A-PID-00092-007 | PIPING AND INSTRUMENT DIAGRAM - 1RHCU PURGE LIST | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-010180 | 076551C-371-CN-0007-001 | 371-A-BOD-50001-001 | PROCESS DESIGN BASIS STEAM GENERATION & DISTRIBUTION | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-001-001 | 000-R-GAD-60002-001 | TEMPORARY CONSTRUCTION FACILITIES GENERAL LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-001-002 | 000-R-GAD-60002-002 | TEMPORARY CONSTRUCTION FACILITIES GENERAL LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-003-001 | 000-R-GAD-60006-001 | TEMPORARY CONSTRUCTION SATELLITE OFFICE BUILDING | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-003-002 | 000-R-GAD-60006-002 | TEMPORARY CONSTRUCTION SATELLITE OFFICE BUILDING | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-005-001 | 000-R-GAD-60008-001 | TEMPORARY CONSTRUCTION SATELLITE GUARD HOUSE LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-006-001 | 000-R-GAD-60009-001 | TEMPORARY CONSTRUCTION FACILITIES FIRST AND LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-007-001 | 000-R-GAD-60010-001 | TEMPORARY CONSTRUCTION FACILITIES SIMPLE MEDICAL FACILITY SMF LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-008-001 | 000-R-GAD-60011-001 | TEMPORARY CONSTRUCTION FACILITIES TRAINING CENTER LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-009-001 | 000-R-GAD-60012-001 | TEMPORARY CONSTRUCTION FACILITIES CF - TWO FLOOR CONTRACTOR OFFICE BUILDING LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-009-002 | 000-R-GAD-60012-002 | TEMPORARY CONSTRUCTION FACILITIES CF - TWO FLOOR CONTRACTOR OFFICE BUILDING LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-011-001 | 000-R-GAD-60014-001 | TEMPORARY CONSTRUCTION FACILITIES TWO FLOOR IPMT OFFICE BUILDING LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-011-002 | 000-R-GAD-60014-002 | TEMPORARY CONSTRUCTION FACILITIES TWO FLOOR IPMT OFFICE BUILDING LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-012-001 | 000-R-GAD-60015-001 | TEMPORARY CONSTRUCTION FACILITIES OWNER OFFICE BUILDING LAYOUT | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-013-001 | 000-R-GAD-60016-001 | TEMPORARY CONSTRUCTION FACILITIES SOUTH AREA | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-014-001 | 000-R-GAD-60018-001 | TEMPORARY CONSTRUCTION FACILITIES NOGA 1 | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-015-001 | 000-R-GAD-60017-001 | TEMPORARY CONSTRUCTION FACILITIES ONE FLOOR CONTRACTOR OFFICE BUILDING LAYOUT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-015-002 | 000-R-GAD-60017-002 | TEMPORARY CONSTRUCTION FACILITIES ONE FLOOR CONTRACTOR OFFICE BUILDING LAYOUT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-016-001 | 000-R-GAD-60021-001 | TEMPORARY CONSTRUCTION FACILITIES IPMT OFFICE A BUILDING LAYOUT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-016-002 | 000-R-GAD-60021-002 | TEMPORARY CONSTRUCTION FACILITIES IPMT OFFICE A BUILDING LAYOUT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-017-001 | 000-R-GAD-60019-001 | TEMPORARY CONSTRUCTION FACILITIES CONTRACTOR CANTEEN LAYOUT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8210-018-001 | 000-R-GAD-60020-001 | TEMPORARY CONSTRUCTION FACILITIES NOGA1 - CONTRACTOR OFFICE BUILDING LAYOUT | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8240-001-001 | 000-R-GAD-60004-001 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 9 00 SQM-2 000 SQM OF COVERED SHELTER (WITH COLD ROOM & SHELVES LAY) | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8240-002-001 | 000-R-GAD-60005-001 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3 000 SQM-1 000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8240-002-002 | 000-R-GAD-60005-002 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3 000 SQM-1 000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-010181 | 076551C-000R-DW-8240-002-003 | 000-R-GAD-60005-003 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3 000 SQM-1 000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | B | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-19 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-001 | 061-S-DAT-50001-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6111 1 WHITE PRODUCT LOADING ARM AT BERTH 1 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-002 | 061-S-DAT-50002-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6112 2 WHITE PRODUCT LOADING ARM AT BERTH 1 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-003 | 061-S-DAT-50003-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6113 BLACK PRODUCT LOADING ARM AT BERTH 1 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-004 | 061-S-DAT-50004-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6114 PROPANE/BUTANE LIQUID NEW LOADING ARM AT BERTH 1 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-005 | 061-S-DAT-50005-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6115 PROPANE/BUTANE VAPOUR RECOVERY LOADING ARM AT BERTH 1 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-006 | 061-S-DAT-50006-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6121 1 WHITE PRODUCT LOADING ARM AT BERTH 2 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-007 | 061-S-DAT-50007-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6122 2 WHITE PRODUCT LOADING ARM AT BERTH 2 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-008 | 061-S-DAT-50008-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6123 BLACK PRODUCT LOADING ARM AT BERTH 2 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-009 | 061-S-DAT-50009-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6124 PROPANE/BUTANE LIQUID NEW LOADING ARM AT BERTH 2 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-010 | 061-S-DAT-50010-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6125 PROPANE/BUTANE VAPOUR RECOVERY LOADING ARM AT BERTH 2 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-011 | 061-S-DAT-50011-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6131 1 WHITE PRODUCT LOAIDNG ARM AT BERTH 3 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-012 | 061-S-DAT-50012-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6132 2 WHITE PRODUCT LOADING ARM AT BERTH 3 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-013 | 061-S-DAT-50013-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6133 BLACK PRODUCT LOADING ARM AT BERTH 3 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-014 | 061-S-DAT-50014-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6151 1 WHITE PRODUCT LOADING ARM AT BERTH 5 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-015 | 061-S-DAT-50015-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6152 2 WHITE PRODUCT LOADING ARM AT BERTH 5 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-016 | 061-S-DAT-50016-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6153 BLACK PRODUCT LOADING ARM AT BERTH 5 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-017 | 061-S-DAT-50017-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6161 1 WHITE PRODUCT LOADING AT BERTH 6 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-018 | 061-S-DAT-50018-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6162 2 WHITE PRODUCT LOADING ARM AT BERTH 6 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010182 | 076551C-061-SP-4026-019 | 061-S-DAT-50019-001 | LOADING ARM DESIGN SPECIFICATION SHEET FOR 061LA6163 BLACK PRODUCT LOADING ARM AT BERTH 6 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010183 | 076551C-000R-MS-1410-002 | 000-S-MST-60004-001 | TECHNICAL SPECIFICATION FOR TOPOGRAPHIC SURVEY FOR REFINERY AREA | 0 | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-010183 | 076551C-000R-MS-1410-004 | 000-S-MST-60003-001 | TECHNICAL SPECIFICATION FOR TOPOGRAPHIC SURVEY FOR REFINERY TANK FARM TRANSFER LINE SITRA TANK FARM & WHARF AREAS | 0 | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-010184 | ROC-BMR-MOM-000027 | 000-A-MOM-60024-001 | ROC 10 TH WEEKLY PROGRESS MEETING | 0 | 2018-06-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010184 | ROC-BMR-MOM-000029 | 000-A-MOM-60025-001 | ROC 11 TH WEEKLY PROGRESS MEETING | 0 | 2018-06-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010185 | 076551C-079-PID-0021-001-001 | 079-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU UTILITIES AND AUXILIARES SPENT CAUSTIC STORAGE TANK | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-002-001 | 079-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU SPENT CAUSTIC PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-003-001 | 079-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU SPENT CAUSTIC TREATING PACKAGE FEED DRUM | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-004-001 | 079-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU SPENT CAUSTIC CLOSED DRAIN | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-005-001 | 079-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU SPENT TREATMENT PACKAGE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-401-001 | 079-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU PROCESS BATTERY LIMIT | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-402-001 | 079-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU STEAM CONDENSATE AND BFW BATTERY LIMIT | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-403-001 | 079-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU COOLING WATER AND UTILITY WATER BATTERY LIMIT | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-404-001 | 079-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU FUEL GAS - INSTRUMENT AIR - YARD AIR AND NITROGEN BATTERY LIMIT | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-501-001 | 079-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU STEAM CONDENSATE AND BFW DISTRIBUTION | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-502-001 | 079-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU COOLING WATER SUPPLY AND RETURN AND UTILITY WATER DISTRIBUTION | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010185 | 076551C-079-PID-0021-503-001 | 079-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - SCTU NITROGEN - YARD AIR AND INSTRUMENT AIR DISTRIBUTION | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-001-001 | 372-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND HOTWELL FACILITIES 2 POWER PLANT | 4A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-002-001 | 372-A-PID-00003-002 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND HOTWELL FACILITIES 2 POWER PLANT | 4A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-003-001 | 372-A-PID-50001-001 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND HG CONDENSATE DRUM AND PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-004-001 | 020-A-PID-00052-001 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND OIL SEPARATOR TANKS | 3A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-005-001 | 372-A-PID-50002-001 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND LG CONDENSATE TRANSFER PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-006-001 | 020-A-PID-00053-001 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND OIL REMOVAL FILTERS AND PUMPS - 2 POWER PLANT | 3A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-007-001 | 372-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND FED STORAGE FACILITIES | 5A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-008-001 | 372-A-PID-00004-002 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND FED STORAGE FACILITIES | 5A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-066-001 | 372-A-PID-00001-003 | PIPING AND INSTRUMENT DIAGRAM - REFINERY CONDENSATE KRU/VBU/NRC/2POLY/GCU | 2A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010186 | 076551C-372-PID-0031-066-002 | 372-A-PID-00001-006 | PIPING AND INSTRUMENT DIAGRAM - 2BFW AND COND REFINERY CONDENSATE 1CDU/2CDU/3CDU/NORTH PUMP HOUSE | 4A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-001-001 | 371-A-PFD-50001-001 | PROCESS FLOW DIAGRAM STEAM DISTRIBUTION | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-002-001 | 371-A-PFD-50001-002 | PROCESS FLOW DIAGRAM STEAM DISTRIBUTION | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-003-001 | 371-A-PFD-50001-003 | PROCESS FLOW DIAGRAM 20 PSIG EXCESS STEAM SYSTEM | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-004-001 | 371-A-PFD-50001-004 | PROCESS FLOW DIAGRAM 60 PSIG EXCESS STEAM SYSTEM | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-005-001 | 371-A-PFD-50001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-006-001 | 371-A-PFD-50001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-007-001 | 371-A-PFD-50001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-008-001 | 371-A-PFD-50001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-009-001 | 371-A-PFD-50001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-010-001 | 371-A-PFD-50001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-011-001 | 371-A-PFD-50001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010187 | 076551C-371-PFD-0010-012-001 | 371-A-PFD-50001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 1 - APPROVED | 2018-07-24 | CLASS 1
CON-BMP-TRA-010188 | 076551C-018-SP-0910-020 | 018-G-DAT-00035-001 | CENTRIFUGAL PUMPS DATA SHEET MP WASH WATER PUMPS 018P0022A/B | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-010188 | 076551C-018-SP-0910-024 | 018-G-DAT-00028-001 | CENTRIFUGAL PUMPS DATA SHEET HVGO PRODUCT PUMPS 018P0015A/B | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-010188 | 076551C-018-SP-0910-034 | 018-G-DAT-00005-001 | CENTRIFUGAL PUMPS DATA SHEET HP WASH WATER PUMPS 018P0021A/B | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-010188 | 076551C-018-SP-0910-035 | 018-G-DAT-00036-001 | CENTRIFUGAL PUMPS DATA SHEET CONDENSATE PUMPS 018P0023A/B | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-010189 | 076551C-005-PID-0021-023-001 | 005-A-PID-00002-001 | PIPING AND INSTRUMENTATION DIAGRAM LPG PUMP DISCHARGE HORTON SPHERES | 9A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-010189 | 076551C-005-PID-0021-030-001 | 005-A-PID-00003-001 | PIPING AND INSTRUMENTATION DIAGRAM LPG STORAGE AREA HORTON SPHERES 80/81/82 | 8A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-010189 | 076551C-005-PID-0021-040-001 | 005-A-PID-00004-001 | PIPING AND INSTRUMENTATION DIAGRAM LPG STORAGE AREA HORTON SPHERES 83/84/85 | 9A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-010189 | 076551C-005-PID-0021-041-001 | 005-A-PID-00001-001 | PIPING AND INSTRUMENTATION DIAGRAM LPG PUMP SUCTION | 9A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-010190 | 076551C-021-SP-0910-006 | 021-G-DAT-00011-001 | CENTRIFUGAL PUMP DATA SHEET FOR INJECTION WATER PUMPS 021P0002A/B | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-010191 | ROC-BMR-MOM-000030 | 000-A-MOM-60026-001 | TTJSVROC BAPCO WEEKLY MEETING INT U AND O N. 10 | 0 | 2018-07-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010192 | 076551C-000R-RT-6200-003 | 000-A-RPT-60002-001 | BMP ESAP IMPLEMENTATION REPORT | B | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-010193 | 076551C-051-CN-0008-002 | 051-A-BOD-00002-001 | MATERIAL SELECTION BASIS REFRIGERATED LPG STORAGE (AT SITRA MARINE TERMINAL) | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010194 | 076551C-056-CN-0008-002 | 056-A-BOD-50002-001 | MATERIAL SELECTION BASIS SITRA TANK FARM | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010195 | 076551C-021-SP-0910-008 | 021-G-DAT-00012-001 | CENTRIFUGAL PUMP DATA SHEET FOR EJECTOR RECEIVER WATER PUMP 021P0006A/B | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010196 | 076551C-371-SP-0910-001 | 371-G-DAT-50001-001 | CENTRIFUGAL PUMP DATA SHEET 20 PSIG EXCESS STEAM CONDENSATE PUMPS 371P3701 A/B | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010197 | 076551C-018-DW-1442-001-001 | 018-S-GAD-00001-001 | GENERAL UNDERGROUND NETWORKS MAJOR U/G FOR 018-1RHCU UNIT | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-010197 | 076551C-021-DW-1442-001-001 | 021-S-GAD-00001-001 | GENERAL UNDERGROUND NETWORKS MAJOR U/G FOR 021 3HDU AND 023-2PSA UNITS | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-010198 | 076551C-018-DW-1451-001-001 | 018-A-PPN-00001-001 | 3D MODEL CIVIL AREAS KEY-PLAN NO. 1 RHCU RESIDUE HYDROCRAKING UNIT | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 1
CON-BMP-TRA-010198 | 076551C-021-DW-1451-001-001 | 021-A-PPN-00001-001 | 3D MODEL CIVIL AREAS KEY-PLAN NO. 3 HDU-HYDROGDESULPHURIZATION UNIT NO. 1 HRU HYDROGEN RECOVERY UNIT | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-001-001 | 050-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - RTK CRUDE FEED ROUNDOWN SYSTEM REFINERY TANKS | 8A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-002-001 | 050-A-PID-00001-002 | PIPING AND INSTRUMENT DIAGRAM - RTK CRUDE FEED ROUNDOWN SYSTEM REFINERY TANKS | 8A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-003-001 | 050-A-PID-00001-003 | PIPING AND INSTRUMENT DIAGRAM - RTK CRUDE FEED ROUNDOWN SYSTEM REFINERY TANKS | 8A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-020-001 | 050-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - RTK STRAINGHT RUN NAPHTHA | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-021-001 | 050-A-PID-00002-002 | PIPING AND INSTRUMENT DIAGRAM - RTK STRAINGHT RUN NAPHTHA | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-026-001 | 050-A-PID-00002-007 | PIPING AND INSTRUMENT DIAGRAM - RTK STRAINGHT RUN NAPHTHA | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-043-001 | 050-A-PID-00004-004 | PIPING AND INSTRUMENT DIAGRAM - RTK GASOLINE SYSTEM | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-044-001 | 050-A-PID-00004-005 | PIPING AND INSTRUMENT DIAGRAM - RTK GASOLINE SYSTEM | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-060-001 | 050-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - RTK KEROSENE SYSTEM REFINERY TANKS | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-062-001 | 050-A-PID-00005-003 | PIPING AND INSTRUMENT DIAGRAM - RTK KEROSENE SYSTEM REFINERY TANKS | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-063-001 | 050-A-PID-00005-004 | PIPING AND INSTRUMENT DIAGRAM - RTK KEROSENE SYSTEM REFINERY TANKS | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-080-001 | 050-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL RUNDOWN SYSTEM REFINERY TANKS | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-081-001 | 050-A-PID-00006-002 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL RUNDOWN SYSTEM REFINERY TANKS | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-083-001 | 050-A-PID-00006-004 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL RUNDOWN SYSTEM REFINERY TANKS | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-086-001 | 050-A-PID-00006-007 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL RUNDOWN SYSTEM REFINERY TANKS | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-088-001 | 050-A-PID-00006-010 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL RUNDOWN SYSTEM REFINERY TANKS | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-099-001 | 050-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL FEED SYSTEM | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-100-001 | 050-A-PID-00007-002 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL FEED SYSTEM | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010199 | 076551C-050-PID-0021-119-001 | 050-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - RTK FUEL OIL RUNDOWN SYSTEM | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-121-001 | 050-A-PID-00008-003 | PIPING AND INSTRUMENT DIAGRAM - RTK FUEL OIL RUNDOWN SYSTEM | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-123-001 | 050-A-PID-00008-005 | PIPING AND INSTRUMENT DIAGRAM - RTK FUEL OIL RUNDOWN SYSTEM | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-137-001 | 050-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - RTK RESID / ASPHALT SYSTEM REFINERY TANKS | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-138-001 | 050-A-PID-00009-002 | PIPING AND INSTRUMENT DIAGRAM - RTK RESID / ASPHALT SYSTEM REFINERY TANKS | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-154-001 | 050-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - RTK UN LEADED SLOP SYSTEM REFINERY TANKS | 6A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-191-001 | 050-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - RTK GASOLINE - SYSTEM 300 SWEET MCN BLENDER PUMPS 050P5021A&B | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-194-001 | 050-A-PID-00012-004 | PIPING AND INSTRUMENT DIAGRAM - RTK GASOLINE - SYSTEM 300 POLYMER BLENDER PUMPS 050P-5025A&B | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-196-001 | 050-A-PID-00012-006 | PIPING AND INSTRUMENT DIAGRAM - RTK GASOLINE - SYSTEM 300 SWEET LLCN BLENDER PUMPS 050P5023A/B | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-198-001 | 050-A-PID-00012-008 | PIPING AND INSTRUMENT DIAGRAM - RTK GASOLINE - SYSTEM 300 BLENDER MANIFOLD BOOSTER PUMPS 050P5027A&B | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-204-001 | 050-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - RTK FUEL OIL-SYSTEM 200 UNTREATED KEROSENE BLENDER PUMPS 050P-5004A&B / P-5005 | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-207-001 | 050-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL - SYSTEM 400 LVGO BLENDER PUMPS 050P5062A&B | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-212-001 | 050-A-PID-00014-006 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL - SYSTEM 400 LVGO BLENDER PUMPS 050P5061 | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-214-001 | 050-A-PID-00014-010 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL - SYSTEM 400 BLENDER MANIFOLD BOOSTER PUMPS 050P-5070 A&B | 5A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-230-001 | 050-A-PID-00030-001 | PIPING AND INSTRUMENT DIAGRAM - RTK MONO-ACID ADDITIVE SYSTEM | 1A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-231-001 | 050-A-PID-00031-001 | PIPING AND INSTRUMENT DIAGRAM - RTK MONO-ACID ADDITIVE SYSTEM | 1A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010200 | 076551C-050-PID-0021-232-001 | 050-A-PID-00032-001 | PIPING AND INSTRUMENT DIAGRAM - RTK CFPP ADDITIVE SYSTEM | 1A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-006-001 | 050-A-PID-50001-001 | PIPING AND INSTRUMENT DIAGRAM - RTK CRUDE FEED RUNDOWN SYSTEM REFINERY TANK INJECTION PUMPS | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-010-001 | 050-A-PID-50002-001 | PIPING AND INSTRUMENT DIAGRAM - RTK CRUDE FEED RUNDOWN SYSTEM REFINERY TANK INJECTION PUMPS | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-028-001 | 050-A-PID-50004-001 | PIPING AND INSTRUMENT DIAGRAM - RTK LSR AND HSR NAPHTHA MANIFOLD | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-032-001 | 050-A-PID-50003-001 | PIPING AND INSTRUMENT DIAGRAM - RTK STRAIGHT RUN NAPHTHA REFINERY TANKS | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-064-001 | 050-A-PID-50005-001 | PIPING AND INSTRUMENT DIAGRAM - RTK KEROSENE SYSTEM REFINERY TANKS | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-090-001 | 050-A-PID-50006-001 | PIPING AND INSTRUMENT DIAGRAM - RTK DIESEL -RUNDOWN SYSTEM REFINERY TANK | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-105-001 | 050-A-PID-50011-001 | PIPING AND INSTRUMENT DIAGRAM - RTK REFINERY TANKS NITROGEN BLANKETING SYSTEM | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-106-001 | 050-A-PID-50012-001 | PIPING AND INSTRUMENT DIAGRAM - RTK REFINERY TANKS NITROGEN BLANKETING SYSTEM AND INSTRUMENT / YARD AIR | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-125-001 | 050-A-PID-50007-001 | PIPING AND INSTRUMENT DIAGRAM - RTK FUEL OIL RUNDOWN SYSTEM | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-126-001 | 050-A-PID-50008-001 | PIPING AND INSTRUMENT DIAGRAM - RTK 1HCU AND 2HDU DIESEL RUNDOWN AND NEW BOOSTER PUMPS | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-127-001 | 050-A-PID-50009-001 | PIPING AND INSTRUMENT DIAGRAM - REFINERY TO TRANSFER LINE (NEW LINES) | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010201 | 076551C-050-PID-0021-233-001 | 050-A-PID-50010-001 | PIPING AND INSTRUMENT DIAGRAM - RTK CFPP ADDITIVE SYSTEM | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-010202 | 076551C-082-DW-0051-002-001 | 082-A-PPN-00001-001 | GENERAL PLOT PLAN 082 NO.1 BMP-FLARE 081-LSDP FLARE | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010203 | 076551C-018-SP-0810-007 | 018-C-DAT-00047-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1007 TRAIN1 HP CENTRIFUGAL SEPARATOR | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-010203 | 076551C-018-SP-0810-027 | 018-C-DAT-00046-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2007 TRAIN 2 HP CENTRIFUGAL SEPARATOR | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-010204 | 076551C-082-DW-1442-001-001 | 082-S-GAD-00001-001 | GENERAL UNDERGROUND NETWORKS MAJOR U/G FOR 082-BMP FLARE | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-21 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-010205 | 076551C-000R-DL-0811-005 | 000-C-IDL-60011-001 | DEVIATION LIST FOR HP CENTRIFUGAL SEPARATOR | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010205 | 076551C-000R-ITP-0811-005 | 000-C-ITP-60011-001 | INSPECTION AND TEST PLAN FOR HP CENTRIFUGAL SEPARATOR | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010205 | 076551C-000R-MR-0811-005 | 000-C-MRQ-60011-001 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010205 | 076551C-000R-SP-0811-005 | 000-C-GRD-60011-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HP CENTRIFUGAL SEPARATOR | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010205 | 076551C-000R-SR-0811-005 | 000-C-SOW-60011-001 | SCOPE OF SUPPLY FOR HP CENTRIFUGAL SEPARATOR | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010206 | 076551C-000R-IDL-0610-004 | 000-E-IDL-60004-001 | DEVIATION LIST FOR CS SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-010206 | 076551C-000R-ITP-0610-004 | 000-E-ITP-60004-001 | INSPECTION AND TEST PLAN FOR CS SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-010206 | 076551C-000R-MR-0610-004 | 000-E-MRQ-60004-001 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-010206 | 076551C-000R-SP-0610-004 | 000-E-GRD-60004-001 | PARTICULAR TACHNICAL SPECIFICATION FOR CS SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-010206 | 076551C-000R-SR-0610-004 | 000-E-SOW-60004-001 | SCOPE OF SUPPLY FOR CS SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-010207 | 076551C-051-SP-0710-001 | 051-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 051E0001A/B PROPANE CONDENSERS | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-010208 | 076551C-371-SP-0710-001 | 371-E-DAT-50002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 371E0001 20 PSIG EXCESS STEAM CONDENSATE AIR COOLER | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010209 | 076551C-933-PID-0021-001-001 | 933-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING PROCESS | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-001-002 | 933-A-PID-00001-002 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING PROCESS AUXILIARIES | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-002-001 | 933-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - DRINKING WATER AND UTILITY WATER INTERCONNECTING | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-003-001 | 933-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - CONDENSATES INTERCONNECTING | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-004-001 | 933-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - HP LP BFW FED WATER DEMIN WATER BLOWDOWN BACKWASH AND WASTE WATER SANITARY | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-005-001 | 933-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - STEAM DISTRIBUTION | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-006-001 | 933-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - COOLING WATER INTERCONNECTING | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-007-001 | 933-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - FUEL GAS INTERCONNECTING | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-008-001 | 933-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - INSTRUMENT AIR YARD AIR NITROGEN INTERCONNECTING | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-009-001 | 933-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - FLARE NETWORK | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010209 | 076551C-933-PID-0021-010-001 | 058-A-PID-00001-010 | PIPING AND INSTRUMENT DIAGRAM - GCU FCCU 4ACDU 5VDU AND PLATFORMER AREAS | 7A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-001-001 | 792-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - RGS ALBA DISTRIBUTION POINT | 13A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-002-001 | 058-A-PID-50001-001 | PIPING AND INSTRUMENT DIAGRAM - RGS ALBA PIG LAUNCHER | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-002-002 | 058-A-PID-50001-002 | PIPING AND INSTRUMENT DIAGRAM - RGS ALBA PIG RECEIVER | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-003-001 | 058-A-PID-50002-001 | PIPING AND INSTRUMENT DIAGRAM - RGS ALBA CUSTODY METERING | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-004-001 | 743-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - RGS RIFFA DISTRIBUTION POINT - RDP | 6A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-005-001 | 058-A-PID-50003-001 | PIPING AND INSTRUMENT DIAGRAM - RGS RIFFA PIG LAUNCHER | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-005-002 | 058-A-PID-50003-002 | PIPING AND INSTRUMENT DIAGRAM - RGS RIFFA PIG RECEIVER | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-006-001 | 058-A-PID-50004-001 | PIPING AND INSTRUMENT DIAGRAM - RGS RIFFA CUSTODY METERING | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-007-001 | 000-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - RGS PITCH POND MICROSCRUBBERS | 7A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-008-001 | 058-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - RGS PITCH POND MICRO SCRUBBER LSDP | 4A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-009-001 | 058-A-PID-50005-001 | PIPING AND INSTRUMENT DIAGRAM - RGS BMP MICROSCRUBBER | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-010-001 | 058-A-PID-50005-002 | PIPING AND INSTRUMENT DIAGRAM - RGS BMP MICROSCRUBBER | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-011-001 | 058-A-PID-50006-001 | PIPING AND INSTRUMENT DIAGRAM - RGS FUEL SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-012-001 | 058-A-PID-50007-001 | PIPING AND INSTRUMENT DIAGRAM - RGS FUEL SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-013-001 | 000-A-PID-00001-008 | PIPING AND INSTRUMENT DIAGRAM - RGS KHUFF GAS K.O. VESSEL AND GAS DRIP DRUMS AT KRU | 7A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-014-001 | 000-A-PID-00001-007 | PIPING AND INSTRUMENT DIAGRAM - RGS GAS SWEETENING PLANT AT KRU | 7A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-015-001 | 000-A-PID-00001-005 | PIPING AND INSTRUMENT DIAGRAM - RGS SOUTH MICROSCRUBBER AND L/D STATION | 7A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-401-001 | 058-A-PID-50008-001 | PIPING AND INSTRUMENT DIAGRAM - RGS BATTERY LIMIT | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010210 | 076551C-058-PID-0021-401-002 | 058-A-PID-50008-002 | PIPING AND INSTRUMENT DIAGRAM - RGS BATTERY LIMIT | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010211 | 076551C-018-SP-0910-026 | 018-G-DAT-00030-001 | CENTRIFUGAL PUMPS DATA SHEET AMINE SUMP PUMPS 018P0031A/B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010211 | 076551C-018-SP-0910-027 | 018-G-DAT-00031-001 | CENTRIFUGAL PUMPS DATA SHEET SOUR WATER SUMP PUMPS 018P0030A/B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010211 | 076551C-018-SP-0910-028 | 018-G-DAT-00029-001 | CENTRIFUGAL PUMPS DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMPS 018P0032A/B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010211 | 076551C-018-SP-0920-003 | 018-G-DAT-00034-001 | RECIPROCATING PUMPS DATA SHEET CATALYST TRANSPORT OIL PUMPS 018P0024A/B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010211 | 076551C-018-SP-0920-004 | 018-G-DAT-00037-001 | RECIPROCATING PUMPS DATA SHEET HOT PURGE OIL PUMPS 018P0029A/B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010212 | 076551C-021-SP-0910-009 | 021-G-DAT-00008-001 | CENTRIFUGAL PUMP DATA SHEET FOR RECOVERED PROCESS OIL SUMP PUMPS 021P0009A/B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010212 | 076551C-021-SP-0910-010 | 021-G-DAT-00009-001 | CENTRIFUGAL PUMP DATA SHEET FOR AMINE SUMP PUMPS 021P0010A/B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010212 | 076551C-021-SP-0910-012 | 021-G-DAT-00010-001 | CENTRIFUGAL PUMP DATA SHEET FOR SOUR WATER SUMP PUMPS 021P0011A/B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010213 | 076551C-018-SP-0610-036 | 018-E-DAT-00038-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1009 SECOND STAGE INTERCOOLER - TRAIN 1A | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010213 | 076551C-018-SP-0610-039 | 018-E-DAT-00037-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E1012 SECOND STAGE INTERCOOLER - TRAIN 1B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010213 | 076551C-018-SP-0610-041 | 018-E-DAT-00036-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E0003 SECOND STAGE INTERCOOLER - SPARE TRAIN | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010213 | 076551C-018-SP-0610-043 | 018-E-DAT-00035-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2009 SECOND STAGE INTERCOOLER - TRAIN 2A | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010213 | 076551C-018-SP-0610-046 | 018-E-DAT-00034-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 018E2012 SECOND STAGE INTERCOOLER - TRAIN 2B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010214 | 076551C-021-SP-0610-013 | 021-E-DAT-00019-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0018A/B SOUR WATER COOLER | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010215 | 076551C-058-PID-0031-501-001 | 058-A-PID-50010-001 | PIPING AND INSTRUMENT DIAGRAM - RGS FUEL GAS SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010215 | 076551C-058-PID-0031-502-001 | 058-A-PID-50009-001 | PIPING AND INSTRUMENT DIAGRAM - RGS BATTERY LIMIT UTILITIES | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010215 | 076551C-058-PID-0031-502-002 | 058-A-PID-50009-002 | PIPING AND INSTRUMENT DIAGRAM - RGS BATTERY LIMIT UTILITIES | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010215 | 076551C-058-PID-0031-503-001 | 058-A-PID-50011-001 | PIPING AND INSTRUMENT DIAGRAM - RGS UTILITIES SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010216 | 076551C-023-SP-0610-001 | 023-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 023E0001 FEED GAS COOLER | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010216 | 076551C-023-SP-0610-002 | 023-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 023E0002 COMPRESSED GAS TRIM COOLER | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010216 | 076551C-023-SP-0610-003 | 023-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 023E0005 A/B 1ST STAGE GAS TRIM COOLER | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010216 | 076551C-023-SP-0610-004 | 023-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 023E0004 PSA INLET COOLER | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010216 | 076551C-023-SP-0610-005 | 023-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 023E0003 LEAN AMINE COOLER | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010216 | 076551C-023-SP-0610-006 | 023-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 023E0006 A/B K0002A/B SPILLBACK COOLER | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010217 | 076551C-050-SP-0910-010 | 050-G-DAT-50005-001 | CENTRIFUGAL PUMPS DATA SHEET 10PPM DIESEL BOOSTER PUMPS ITEM 050P5034A/B | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-036-001 | 018-E-GAD-00043-001 | 018E1009 SECOND STAGE INTERCOOLER - TRAIN 1A | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-036-002 | 018-E-GAD-00043-002 | 018E1009 SECOND STAGE INTERCOOLER - TRAIN 1A | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-036-003 | 018-E-GAD-00043-003 | 018E1009 SECOND STAGE INTERCOOLER - TRAIN 1A | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-036-004 | 018-E-GAD-00043-004 | 018E1009 SECOND STAGE INTERCOOLER - TRAIN 1A | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-036-005 | 018-E-GAD-00043-005 | 018E1009 SECOND STAGE INTERCOOLER - TRAIN 1A | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-039-001 | 018-E-GAD-00042-001 | 018E1012 SECOND STAGE INTERCOOLER - TRAIN 1B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-039-002 | 018-E-GAD-00042-002 | 018E1012 SECOND STAGE INTERCOOLER - TRAIN 1B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-039-003 | 018-E-GAD-00042-003 | 018E1012 SECOND STAGE INTERCOOLER - TRAIN 1B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-039-004 | 018-E-GAD-00042-004 | 018E1012 SECOND STAGE INTERCOOLER - TRAIN 1B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-039-005 | 018-E-GAD-00042-005 | 018E1012 SECOND STAGE INTERCOOLER - TRAIN 1B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-041-001 | 018-E-GAD-00041-001 | 018E0003 SECOND STAGE INTERCOOLER - SPARE TRAIN | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-041-002 | 018-E-GAD-00041-002 | 018E0003 SECOND STAGE INTERCOOLER - SPARE TRAIN | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-041-003 | 018-E-GAD-00041-003 | 018E0003 SECOND STAGE INTERCOOLER - SPARE TRAIN | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-041-004 | 018-E-GAD-00041-004 | 018E0003 SECOND STAGE INTERCOOLER - SPARE TRAIN | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-041-005 | 018-E-GAD-00041-005 | 018E0003 SECOND STAGE INTERCOOLER - SPARE TRAIN | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-046-001 | 018-E-GAD-00039-001 | 018E2012 SECOND STAGE INTERCOOLER - TRAIN 2B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-046-002 | 018-E-GAD-00039-002 | 018E2012 SECOND STAGE INTERCOOLER - TRAIN 2B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-046-003 | 018-E-GAD-00039-003 | 018E2012 SECOND STAGE INTERCOOLER - TRAIN 2B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-046-004 | 018-E-GAD-00039-004 | 018E2012 SECOND STAGE INTERCOOLER - TRAIN 2B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010218 | 076551C-018-DW-0610-046-005 | 018-E-GAD-00039-005 | 018E2012 SECOND STAGE INTERCOOLER - TRAIN 2B | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-22 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-001-001 | 023-E-GAD-00007-001 | 023E0001 FEED GAS COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-001-002 | 023-E-GAD-00007-002 | 023E0001 FEED GAS COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-001-003 | 023-E-GAD-00007-003 | 023E0001 FEED GAS COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-001-004 | 023-E-GAD-00007-004 | 023E0001 FEED GAS COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-001-005 | 023-E-GAD-00007-005 | 023E0001 FEED GAS COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-002-001 | 023-E-GAD-00006-001 | 023E0002 COMPRESSED GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-002-002 | 023-E-GAD-00006-002 | 023E0002 COMPRESSED GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-002-003 | 023-E-GAD-00006-003 | 023E0002 COMPRESSED GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-002-004 | 023-E-GAD-00006-004 | 023E0002 COMPRESSED GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-002-005 | 023-E-GAD-00006-005 | 023E0002 COMPRESSED GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-003-001 | 023-E-GAD-00004-001 | 023E0005 A/B 1ST STAGE GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-003-002 | 023-E-GAD-00004-002 | 023E0005 A/B 1ST STAGE GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-003-003 | 023-E-GAD-00004-003 | 023E0005 A/B 1ST STAGE GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-003-004 | 023-E-GAD-00004-004 | 023E0005 A/B 1ST STAGE GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010219 | 076551C-023-DW-0610-003-005 | 023-E-GAD-00004-005 | 023E0005 A/B 1ST STAGE GAS TRIM COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-004-001 | 023-E-GAD-00005-001 | 023E0004 PSA INLET COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-004-002 | 023-E-GAD-00005-002 | 023E0004 PSA INLET COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-004-003 | 023-E-GAD-00005-003 | 023E0004 PSA INLET COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-004-004 | 023-E-GAD-00005-004 | 023E0004 PSA INLET COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-004-005 | 023-E-GAD-00005-005 | 023E0004 PSA INLET COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-005-001 | 023-E-GAD-00002-001 | 023E0003 LEAN AMINE COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-005-002 | 023-E-GAD-00002-002 | 023E0003 LEAN AMINE COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-005-003 | 023-E-GAD-00002-003 | 023E0003 LEAN AMINE COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-005-004 | 023-E-GAD-00002-004 | 023E0003 LEAN AMINE COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-005-005 | 023-E-GAD-00002-005 | 023E0003 LEAN AMINE COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-006-001 | 023-E-GAD-00003-001 | 023E0006 A/B K0002A/B SPILLBACK COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-006-002 | 023-E-GAD-00003-002 | 023E0006 A/B K0002A/B SPILLBACK COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-006-003 | 023-E-GAD-00003-003 | 023E0006 A/B K0002A/B SPILLBACK COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-006-004 | 023-E-GAD-00003-004 | 023E0006 A/B K0002A/B SPILLBACK COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010220 | 076551C-023-DW-0610-006-005 | 023-E-GAD-00003-005 | 023E0006 A/B K0002A/B SPILLBACK COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010221 | 076551C-056-SP-0910-001 | 056-G-DAT-50004-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA SHIPPING PUMP 056P5603 | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010221 | 076551C-056-SP-0910-002 | 056-G-DAT-50002-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA KERO CRUDE SHIPPING PUMP 056P5605 | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010221 | 076551C-056-SP-0910-003 | 056-G-DAT-50003-001 | CENTRIFUGAL PUMPS DATA SHEET KERO SHIPPING PUMP 056P5604 | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010221 | 076551C-079-SP-0910-001 | 079-G-DAT-00001-001 | CENTRIFUGAL PUMPS DATA SHEET SPENT CAUSTIC CLOSED DRAIN PUMPS 079P0001 A/B | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010221 | 076551C-372-SP-0910-001 | 372-G-DAT-50002-001 | CENTRIFUGAL PUMP DATA SHEET HG CONDENSATE TRANSFER PUMPS 372P0045 A/B | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010221 | 076551C-372-SP-0910-002 | 372-G-DAT-50001-001 | CENTRIFUGAL PUMP DATA SHEET HG CONDENSATE TRANSFER PUMPS 372P0033 A/B | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010222 | 076551C-021-DW-0610-013-001 | 021-E-GAD-00013-001 | 021E0018 A/B SOUR WATER COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010222 | 076551C-021-DW-0610-013-002 | 021-E-GAD-00013-002 | 021E0018 A/B SOUR WATER COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010222 | 076551C-021-DW-0610-013-003 | 021-E-GAD-00013-003 | 021E0018 A/B SOUR WATER COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010222 | 076551C-021-DW-0610-013-004 | 021-E-GAD-00013-004 | 021E0018 A/B SOUR WATER COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010222 | 076551C-021-DW-0610-013-005 | 021-E-GAD-00013-005 | 021E0018 A/B SOUR WATER COOLER | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010223 | 076551C-018-DW-0610-047-001 | 018-E-GAD-00040-001 | 018E2009 SECOND STAGE INTERCOOLER - TRAIN 2A | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010223 | 076551C-018-DW-0610-047-002 | 018-E-GAD-00040-002 | 018E2009 SECOND STAGE INTERCOOLER - TRAIN 2A | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010223 | 076551C-018-DW-0610-047-003 | 018-E-GAD-00040-003 | 018E2009 SECOND STAGE INTERCOOLER - TRAIN 2A | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010223 | 076551C-018-DW-0610-047-004 | 018-E-GAD-00040-004 | 018E2009 SECOND STAGE INTERCOOLER - TRAIN 2A | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010223 | 076551C-018-DW-0610-047-005 | 018-E-GAD-00040-005 | 018E2009 SECOND STAGE INTERCOOLER - TRAIN 2A | A | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 2
CON-BMP-TRA-010224 | 076551C-062-PID-0021-001-001 | 062-A-PID-00002-002 | PIPING AND INSTRUMENT DIAGRAM - 062 SEPARATION AND HP ABSORPTION SECTION 2HDU | 26A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010224 | 076551C-062-PID-0021-003-001 | 062-A-PID-00003-002 | PIPING AND INSTRUMENT DIAGRAM - 062 PRODUCT STRIPPING PRODUCT STRIPPER OVHD SYSTEM-2HDU | 26A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010224 | 076551C-062-PID-0021-004-001 | 062-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - SLOP SYSTEM 2HDU | 25A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010224 | 076551C-062-PID-0021-005-001 | 062-A-PID-00021-001 | PIPING AND INSTRUMENT DIAGRAM - 062 LP ABSORPTION SECTION DEA UNIT 2HDU | 26A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-001-001 | 930-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS INTERCONNECTING PROCESS | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-001-002 | 930-A-PID-00001-002 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS INTERCONNECTING PROCESS | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-001-003 | 930-A-PID-00001-003 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS INTERCONNECTING PROCESS | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-001-004 | 930-A-PID-00001-004 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS INTERCONNECTING PROCESS - AUXILIARIES | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-001-005 | 930-A-PID-00001-005 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS INTERCONNECTING PROCESS - AUXILIARIES | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-002-001 | 930-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FUEL GAS INTERCONNECTING (FUEL GAS DISTRIBUTION) | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-003-001 | 930-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS DRINKING WATER & UTILITTY WATER INTERCONNECTING | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-004-001 | 930-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS CONDENSATES INTERCONNECTING | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-005-001 | 930-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCON. FOR BMP NEW UNITS HP LP BFW FED WATER DEMIN. WATER BLOWDOWN BACKWASH & W.W. | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-006-001 | 930-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS BMP FLARE NETWORK | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-007-001 | 930-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS 550 STEAM INTERCONNECTING | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-007-002 | 930-A-PID-00007-002 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS 110 STEAM INTERCONNECTING | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-007-003 | 930-A-PID-00007-003 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS 60 STEAM INTRCONNECTING | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-008-001 | 930-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS CLOSED LOOP COOLING WATER (MAIN DISTRIBUTION SYSTEM) | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-009-001 | 930-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS CLOSED LOOP COOLING WATER (SECONDARY DISTRIB. SYSTEM) | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-010-001 | 930-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS INSTRUMENT AIR YARD AIR NITROGEN INTERCONNECTING | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-011-001 | 930-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS SANITARY WATER INTERCONNECTING | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0021-012-001 | 930-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS CHILLED WATER INTERCONNECTING | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010225 | 076551C-930-PID-0031-001-001 | 930-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - BMP SEWERS CLCW TOILET SANITARY BASIN | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010226 | 076551C-062-PID-0021-006-001 | 063-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - 062 2HDU PRODUCT STABILIZATION DIESEL PRODUCT RUNDOWN-2HDU | 21A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010227 | 076551C-018-NM-120 | 018-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 018 - NO 1 RESIDUE HYDROCRACKING UNIT CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010228 | 076551C-021-NM-120 | 021-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 021 - NO 3 HYDRODESULPHURIZATION UNIT CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010229 | 076551C-023-NM-120 | 023-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 023 - NO 1 HYDROGEN RECOVERY UNIT CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010230 | 076551C-050-NM-120 | 050-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 050 - REFINERY TANK FARM CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010231 | 076551C-051-NM-120 | 051-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 051 - C3/C4 LPG STORAGE FACILITY AT WHARF CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010232 | 076551C-056-NM-120 | 056-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 056 - SITRA TANK FARM CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010233 | 076551C-058-NM-120 | 058-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 058 - REFINERY GAS SYSTEM CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-010234 | 076551C-061-NM-120 | 061-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 061 - SITRA WHARF NOS 1 AND 2 CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010235 | 076551C-079-NM-120 | 079-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 079 - SPENT CAUSTIC REGENERATION PACKAGE CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010236 | 076551C-081-NM-120 | 081-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 081 - LOW SULPHUR DIESEL PRODUCTION FLARE - LSDP CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010237 | 076551C-082-NM-120 | 082-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 082 - NO 1 BMP FLARE CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010238 | 076551C-371-NM-120 | 371-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 371 - STEAM DISTRIBUTION CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010239 | 076551C-372-NM-120 | 372-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 372 - BFW AND CONDENSATE DISTRIBUTION CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010240 | 076551C-381-NM-120 | 381-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 381 - AC PLANT (PLANT NO 381) CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-010241 | 076551C-180-NM-120 | 180-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 180 - REFINERY CENTRAL CONTROL BUILDING CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010242 | 076551C-930-NM-120 | 930-A-STS-00001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 930 - ITERCONNECTING FOR BMP NEW UNIT CALCULATION SHEET | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-010243 | 076551C-000R-DW-1512-004-001 | 000-J-BLD-60004-001 | OS&E CTRL & SAFETY SYSTEM BLOCK DIAGRAM FOR BMP | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010243 | 076551C-000R-DW-1512-004-002 | 000-J-BLD-60004-002 | OS&E CTRL & SAFETY SYSTEM BLOCK DIAGRAM FOR BMP | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010243 | 076551C-000R-DW-1512-004-003 | 000-J-BLD-60004-003 | OS&E CTRL & SAFETY SYSTEM BLOCK DIAGRAM FOR BMP | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010244 | 076551C-018-SP-0810-001 | 018-C-DAT-00029-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1001 TRAIN1 FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-010 | 018-C-DAT-00030-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0007 LT/MT OIL SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-012 | 018-C-DAT-00028-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0009 ATM COLUMN OVHD PRODUCT DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-015 | 018-C-DAT-00027-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0010A/B SOUR GAS COMPRESSOR 1ST STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-016 | 018-C-DAT-00026-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0011A/B SOUR GAS COMPRESSOR DISCHARGE KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-021 | 018-C-DAT-00031-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2001 TRAIN 2 FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-031 | 018-C-DAT-00053-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0023 VACUUM COLUMN BTMS MP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-033 | 018-C-DAT-00019-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0029 INJECTION WATER DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-034 | 018-C-DAT-00034-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0057 SOUR WATER SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-039 | 018-C-DAT-00035-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0059 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-041 | 018-C-DAT-00052-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0031 FCTP LIQUID OVERFLOW POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-049 | 018-C-DAT-00024-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0040 COOLING OIL SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-051 | 018-C-DAT-00023-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0042 SPENT CATALYST DE-OILING BIN | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-052 | 018-C-DAT-00022-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0043 SPENT CATALYST DE-OILING BIN | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-053 | 018-C-DAT-00021-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0044 OIL DRAIN SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-057 | 018-C-DAT-00036 -001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0053 SWEET FUEL GAS KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-058 | 018-C-DAT-00066-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1010 FIRST STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-059 | 018-C-DAT-00065-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1011 SECOND STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-060 | 018-C-DAT-00064-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1012 THIRD STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010244 | 076551C-018-SP-0810-062 | 018-C-DAT-00063-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1013 SECOND STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-063 | 018-C-DAT-00062-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1014 THIRD STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-064 | 018-C-DAT-00068-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0001 SECOND STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-065 | 018-C-DAT-00067-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0002 THIRD STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-066 | 018-C-DAT-00060-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2010 FIRST STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-067 | 018-C-DAT-00059-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2011 SECOND STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-068 | 018-C-DAT-00058-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2012 THIRD STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-069 | 018-C-DAT-00051-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0049 START-UP STEAM HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-070 | 018-C-DAT-00049-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1009 TRAIN 1 MEMBRANE FEED HEATER CONDENSATE TOP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-071 | 018-C-DAT-00057-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2013 SECOND STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-072 | 018-C-DAT-00056-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2014 THIRD STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-073 | 018-C-DAT-00025-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0030 CONDENSATE SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-074 | 018-C-DAT-00037-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0054 PROCESS FUEL GAS KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-076 | 018-C-DAT-00048-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2009 TRAIN 2 MEMBRANE FEED HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-077 | 018-C-DAT-00020-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0055 TEMPERED WATER DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-078 | 018-C-DAT-00050-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0058 AMINE SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-079 | 018-C-DAT-00061-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1018 TRAIN 1 HP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010245 | 076551C-018-SP-0810-080 | 018-C-DAT-00055-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2018 TRAIN 2 HP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-001-001 | 018-C-GAD-00043-001 | 018V1001 TRAIN 1 FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-001-002 | 018-C-GAD-00043-002 | 018V1001 TRAIN 1 FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-001-003 | 018-C-GAD-00043-003 | 018V1001 TRAIN 1 FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-010-001 | 018-C-GAD-00044-001 | 018V0007 LT/MT OIL SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-010-002 | 018-C-GAD-00044-002 | 018V0007 LT/MT OIL SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-010-003 | 018-C-GAD-00044-003 | 018V0007 LT/MT OIL SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-012-001 | 018-C-GAD-00042-001 | 018V0009 ATM COLUMN OVHD PRODUCT DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-012-002 | 018-C-GAD-00042-002 | 018V0009 ATM COLUMN OVHD PRODUCT DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-012-003 | 018-C-GAD-00042-003 | 018V0009 ATM COLUMN OVHD PRODUCT DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-015-001 | 018-C-GAD-00041-001 | 018V0010 A/B SOUR GAS COMPRESSOR 1ST STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-015-002 | 018-C-GAD-00041-002 | 018V0010 A/B SOUR GAS COMPRESSOR 1ST STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-015-003 | 018-C-GAD-00041-003 | 018V0010 A/B SOUR GAS COMPRESSOR 1ST STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-016-001 | 018-C-GAD-00040-001 | 018V0011 A/B SOUR GAS COMPRESSOR DISCHARGE KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-016-002 | 018-C-GAD-00040-002 | 018V0011 A/B SOUR GAS COMPRESSOR DISCHARGE KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-016-003 | 018-C-GAD-00040-003 | 018V0011 A/B SOUR GAS COMPRESSOR DISCHARGE KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-021-001 | 018-C-GAD-00045-001 | 018V2001 TRAIN 2 FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-021-002 | 018-C-GAD-00045-002 | 018V2001 TRAIN 2 FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010246 | 076551C-018-DW-0810-021-003 | 018-C-GAD-00045-003 | 018V2001 TRAIN 2 FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-031-001 | 018-C-GAD-00065-001 | 018V0023 VACUUM COLUMN BTMS MP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-031-002 | 018-C-GAD-00065-002 | 018V0023 VACUUM COLUMN BTMS MP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-031-003 | 018-C-GAD-00065-003 | 018V0023 VACUUM COLUMN BTMS MP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-033-001 | 018-C-GAD-00033-001 | 018V0029 INJECTION WATER DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-033-002 | 018-C-GAD-00033-002 | 018V0029 INJECTION WATER DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-033-003 | 018-C-GAD-00033-003 | 018V0029 INJECTION WATER DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-034-001 | 018-C-GAD-00048-001 | 018V0057 SOUR WATER SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-034-002 | 018-C-GAD-00048-002 | 018V0057 SOUR WATER SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-034-003 | 018-C-GAD-00048-003 | 018V0057 SOUR WATER SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-039-001 | 018-C-GAD-00049-001 | 018V0059 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-039-002 | 018-C-GAD-00049-002 | 018V0059 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-039-003 | 018-C-GAD-00049-003 | 018V0059 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-041-001 | 018-C-GAD-00064-001 | 018V0031 FCTP LIQUID OVERFLOW POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-041-002 | 018-C-GAD-00064-002 | 018V0031 FCTP LIQUID OVERFLOW POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-041-003 | 018-C-GAD-00064-003 | 018V0031 FCTP LIQUID OVERFLOW POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-049-001 | 018-C-GAD-00038-001 | 018V0040 COOLING OIL SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-049-002 | 018-C-GAD-00038-002 | 018V0040 COOLING OIL SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010247 | 076551C-018-DW-0810-049-003 | 018-C-GAD-00038-003 | 018V0040 COOLING OIL SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-051-001 | 018-C-GAD-00037-001 | 018V0042 SPENT CATALYST DE-OILING BIN | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-051-002 | 018-C-GAD-00037-002 | 018V0042 SPENT CATALYST DE-OILING BIN | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-051-003 | 018-C-GAD-00037-003 | 018V0042 SPENT CATALYST DE-OILING BIN | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-052-001 | 018-C-GAD-00036-001 | 018V0043 SPENT CATALYST DE-OILING BIN | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-052-002 | 018-C-GAD-00036-002 | 018V0043 SPENT CATALYST DE-OILING BIN | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-052-003 | 018-C-GAD-00036-003 | 018V0043 SPENT CATALYST DE-OILING BIN | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-053-001 | 018-C-GAD-00035-001 | 018V0044 OIL DRAIN SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-053-002 | 018-C-GAD-00035-002 | 018V0044 OIL DRAIN SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-053-003 | 018-C-GAD-00035-003 | 018V0044 OIL DRAIN SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-057-001 | 018-C-GAD-00050-001 | 018V0053 SWEET FUEL GAS KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-057-002 | 018-C-GAD-00050-002 | 018V0053 SWEET FUEL GAS KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-057-003 | 018-C-GAD-00050-003 | 018V0053 SWEET FUEL GAS KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-058-001 | 018-C-GAD-00078-001 | 018V1010 FIRST-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-058-002 | 018-C-GAD-00078-002 | 018V1010 FIRST-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-058-003 | 018-C-GAD-00078-003 | 018V1010 FIRST-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-059-001 | 018-C-GAD-00077-001 | 018V1011 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-059-002 | 018-C-GAD-00077-002 | 018V1011 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010248 | 076551C-018-DW-0810-059-003 | 018-C-GAD-00077-003 | 018V1011 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-060-001 | 018-C-GAD-00076-001 | 018V1012 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-060-002 | 018-C-GAD-00076-002 | 018V1012 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-060-003 | 018-C-GAD-00076-003 | 018V1012 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-062-001 | 018-C-GAD-00075-001 | 018V1013 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-062-002 | 018-C-GAD-00075-002 | 018V1013 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-062-003 | 018-C-GAD-00075-003 | 018V1013 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-063-001 | 018-C-GAD-00074-001 | 018V1014 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-063-002 | 018-C-GAD-00074-002 | 018V1014 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-063-003 | 018-C-GAD-00074-003 | 018V1014 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-064-001 | 018-C-GAD-00080-001 | 018V0001 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-064-002 | 018-C-GAD-00080-002 | 018V0001 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-064-003 | 018-C-GAD-00080-003 | 018V0001 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-065-001 | 018-C-GAD-00079-001 | 018V0002 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-065-002 | 018-C-GAD-00079-002 | 018V0002 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-065-003 | 018-C-GAD-00079-003 | 018V0002 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-066-001 | 018-C-GAD-00072-001 | 018V2010 FIRST-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-066-002 | 018-C-GAD-00072-002 | 018V2010 FIRST-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010249 | 076551C-018-DW-0810-066-003 | 018-C-GAD-00072-003 | 018V2010 FIRST-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-067-001 | 018-C-GAD-00071-001 | 018V2011 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-067-002 | 018-C-GAD-00071-002 | 018V2011 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-067-003 | 018-C-GAD-00071-003 | 018V2011 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-068-001 | 018-C-GAD-00070-001 | 018V2012 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-068-002 | 018-C-GAD-00070-002 | 018V2012 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-068-003 | 018-C-GAD-00070-003 | 018V2012 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-069-001 | 018-C-GAD-00063-001 | 018V0049 START-UP STEAM HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-069-002 | 018-C-GAD-00063-002 | 018V0049 START-UP STEAM HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-069-003 | 018-C-GAD-00063-003 | 018V0049 START-UP STEAM HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-070-001 | 018-C-GAD-00061-001 | 018V1009 TRAIN 1 MEMBRANE FEED HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-070-002 | 018-C-GAD-00061-002 | 018V1009 TRAIN 1 MEMBRANE FEED HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-070-003 | 018-C-GAD-00061-003 | 018V1009 TRAIN 1 MEMBRANE FEED HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-071-001 | 018-C-GAD-00069-001 | 018V2013 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-071-002 | 018-C-GAD-00069-002 | 018V2013 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-071-003 | 018-C-GAD-00069-003 | 018V2013 SECOND-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-072-001 | 018-C-GAD-00068-001 | 018V2014 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-072-002 | 018-C-GAD-00068-002 | 018V2014 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010250 | 076551C-018-DW-0810-072-003 | 018-C-GAD-00068-003 | 018V2014 THIRD-STAGE SUCTION DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-073-001 | 018-C-GAD-00039-001 | 018V0030 CONDENSATE SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-073-002 | 018-C-GAD-00039-002 | 018V0030 CONDENSATE SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-073-003 | 018-C-GAD-00039-003 | 018V0030 CONDENSATE SURGE DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-074-001 | 018-C-GAD-00051-001 | 018V0054 PROCESS FUEL GAS KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-074-002 | 018-C-GAD-00051-002 | 018V0054 PROCESS FUEL GAS KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-074-003 | 018-C-GAD-00051-003 | 018V0054 PROCESS FUEL GAS KO DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-076-001 | 018-C-GAD-00060-001 | 018V2009 TRAIN 2 MEMBRANE FEED HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-076-002 | 018-C-GAD-00060-002 | 018V2009 TRAIN 2 MEMBRANE FEED HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-076-003 | 018-C-GAD-00060-003 | 018V2009 TRAIN 2 MEMBRANE FEED HEATER CONDENSATE POT | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-077-001 | 018-C-GAD-00034-001 | 018V0055 TEMPERED WATER DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-077-002 | 018-C-GAD-00034-002 | 018V0055 TEMPERED WATER DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010251 | 076551C-018-DW-0810-077-003 | 018-C-GAD-00034-003 | 018V0055 TEMPERED WATER DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-078-001 | 018-C-GAD-00062-001 | 018V0058 AMINE SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-078-002 | 018-C-GAD-00062-002 | 018V0058 AMINE SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-078-003 | 018-C-GAD-00062-003 | 018V0058 AMINE SUMP | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-079-001 | 018-C-GAD-00073-001 | 018V1018 TRAIN 1 HP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-079-002 | 018-C-GAD-00073-002 | 018V1018 TRAIN 1 HP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-079-003 | 018-C-GAD-00073-003 | 018V1018 TRAIN 1 HP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-080-001 | 018-C-GAD-00067-001 | 018V2018 TRAIN 2 HP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-080-002 | 018-C-GAD-00067-002 | 018V2018 TRAIN 2 HP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010252 | 076551C-018-DW-0810-080-003 | 018-C-GAD-00067-003 | 018V2018 TRAIN 2 HP STEAM DRUM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-010253 | 076551C-000R-PID-0021-010-001 | 022-A-PID-00001-011 | PIPING AND INSTRUMENT DIAGRAM 022/024 4ACDU PREFALSH OVERHEAT VESSEL (022V0001) & STABILIZER FEED SYSTEM - 4ACDU | 9A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010253 | 076551C-000R-PID-0021-011-001 | 022-A-PID-00001-021 | PIPING AND INSTRUMENT DIAGRAMS WSR & PRODUCT SYSTEM 4ACDU | 9A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010253 | 076551C-000R-PID-0021-012-001 | 022-A-PID-00001-023 | PIPING AND INSTRUMENT DIAGRAM 022/024 4ACDU FUEL GAS SYSTEM 4ACDU 4ACDU | 9A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010254 | 076551C-007-PID-0021-001-001 | 007-A-PID-00001-003 | PIPING AND INSTRUMENT DIAGRAM 5CDU | 12A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010254 | 076551C-007-PID-0021-002-001 | 007-A-PID-00001-008 | PIPING AND INSTRUMENT DIAGRAM 5CDU | 12A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010254 | 076551C-007-PID-0021-003-001 | 007-A-PID-00001-005 | PIPING AND INSTRUMENT DIAGRAM 5CDU | 12A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010255 | 076551C-022-PID-0021-002-001 | 022-A-PID-00001-012 | PIPING AND INSTRUMENT DIAGRAM 022/024 4ACDU STAB COLUMN 22C4 / STAB O/H VESSEL 22V3 & FG DRIP VESSEL 22V15 - 4ACDU | 9A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010255 | 076551C-022-PID-0021-003-001 | 022-A-PID-00001-020 | PIPING AND INSTRUMENT DIAGRAM MSR & HSR SYSTEM 4ACDU | 9A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010256 | 076551C-038-PID-0021-001-001 | 038-A-PID-00001-005 | PIPING AND INSTRUMENT DIAGRAM 038 UNFINER / PLATFORM | 11A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010256 | 076551C-038-PID-0021-002-001 | 038-A-PID-00001-006 | PIPING AND INSTRUMENT DIAGRAM 038 UNFINER / PLATFORM | 11A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010256 | 076551C-038-PID-0021-003-001 | 038-A-PID-00001-019 | PIPING AND INSTRUMENT DIAGRAM 038 UNFINER / PLATFORM | 11A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010256 | 076551C-038-PID-0021-004-001 | 038-A-PID-00001-030 | PIPING AND INSTRUMENT DIAGRAM HYDROGEN/UNIFINER / PLATFORMER | 11A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-010257 | 076551C-070-PID-0021-001-001 | 070-A-PID-00005-002 | PIPING AND INSTRUMENT DIAGRAM 070 STEAM GENERATOR 6VDU | 31A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010258 | 076551C-076-PID-0021-001-001 | 076-A-PID-00001-019 | PIPING AND INSTRUMENT DIAGRAM 076 M/U H2 COMPRESSOR SUCTION KO DRUM NO 2 HYDROGEN PLANT | 6A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010258 | 076551C-076-PID-0021-002-001 | 076-A-PID-00001-023 | PIPING AND INSTRUMENT DIAGRAM 076 M/U H2 COMPRESSOR DISCHARGE MANIFOLD NO 2 HYDROGEN PLANT | 6A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010258 | 076551C-076-PID-0021-003-001 | 076-A-PID-00003-002 | PIPING AND INSTRUMENT DIAGRAM 076 FLARE SYSTEM NO 2 HYDROGEN PLANT | 6A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010258 | 076551C-076-PID-0021-004-001 | 076-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM NITROGEN PACKAGE NITROGEN STORAGE DRUM 076V7616A/B NO 2 HYDROGEN PLANT | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010258 | 076551C-076-PID-0021-005-001 | 076-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM UTILITY INSTRUMENT AIR / YARD AIR / NITROGEN SYSTEMS NO 2 HYDROGEN PLANT | 6A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010259 | 076551C-077-PID-0021-001-001 | 077-A-PID-00001-038 | PIPING AND INSTRUMENT DIAGRAM 077 UNCONVERTED OIL COOLING FRACTIONATION SECTION 1 HYDROCRACKING | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010259 | 076551C-077-PID-0021-002-001 | 077-A-PID-00001-040 | PIPING AND INSTRUMENT DIAGRAM 077 STRIPPER REFLUX DRUM & PUMP FRACTIONATIN SECTION PRODUCT 1 HYDROCRACKING UNIT | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010259 | 076551C-077-PID-0021-003-001 | 077-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM SUPPLY / RETURN SYSTEM SW COOLING WATER 1 HYDROCRACKING | 4A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010259 | 076551C-077-PID-0021-004-001 | 077-A-PID-00001-037 | PIPING AND INSTRUMENT DIAGRAM FRACTIONATION SECTION PRODUCT RUNDOWN 1 HYDROCRACKING | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010260 | 076551C-078-PID-0021-001-001 | 078-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM 078 ACID GAS KO DRUM SRU-TRAINS 1AND2 | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010260 | 076551C-078-PID-0021-002-001 | 078-A-PID-00001-002 | PIPING AND INSTRUMENT DIAGRAM 078 SOUR WATER STRIPPER GAS KO DRUM SRU-TRAINS 1AND2 | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010260 | 076551C-078-PID-0021-003-001 | 078-A-PID-00001-023 | PIPING AND INSTRUMENT DIAGRAM SULPHUR DEGASSING / STORAGE PIT SRU TRAIN 2 | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010260 | 076551C-078-PID-0021-004-001 | 078-A-PID-00001-037 | PIPING AND INSTRUMENT DIAGRAM 078 DEGASSING DRUM 1 SWS | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010260 | 076551C-078-PID-0021-005-001 | 078-A-PID-00001-048 | PIPING AND INSTRUMENT DIAGRAM 078 ABSORBER BAGRU | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010260 | 076551C-078-PID-0021-006-001 | 078-A-PID-00001-053 | PIPING AND INSTRUMENT DIAGRAM 078 LP ABSORGBER 1 ARU | 5A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010261 | 076551C-180-PID-0031-001-001 | 180-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM BMP SEWERS OPERATION AND NEW CONTROL BUILDING SANITARY BASIN | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010262-REV.1 | 076551C-381-PID-0021-004-001 | 000-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM 8 ACP DRINKING / FED / REUSED / CHILLED WATERS LSDP - UTILITIES | 3A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010263-REV.1 | 076551C-933-PID-0021-011-001 | 000-A-PID-00005-002 | PIPING AND INSTRUMENT DIAGRAM 078 CAUSTIC SYSTEM | 3A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010263-REV.1 | 076551C-933-PID-0021-012-001 | 000-A-PID-00020-002 | PIPING AND INSTRUMENT DIAGRAM OSBL SOUR WATER STRIPPER 3-4 SOUR WATER HEADERS | 3A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010264 | 076551C-021-SP-0630-002 | 021-E-DAT-00017-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 021E0019 STEAM BLOWDOWN COOLER | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-29 | CLASS 2
CON-BMP-TRA-010265 | 076551C-000R-DL-0630-001 | 000-E-IDL-60005-001 | DEVIATION LIST FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-010265 | 076551C-000R-ITP-0630-001 | 000-E-ITP-60005-001 | INSPECTION AND TEST PLAN (ITP) FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-010265 | 076551C-000R-MR-0630-001 | 000-E-MRQ-60005-001 | MATERIAL REQUISITION FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-010265 | 076551C-000R-SP-0630-001 | 000-E-GRD-60005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-010265 | 076551C-000R-SR-0630-001 | 000-E-SOW-60005-001 | SCOPE OF SUPPLY FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-010266 | 076551C-015-PID-0021-001-001 | 015-A-PID-00001-015 | PIPING AND INSTRUMENT DIAGRAM GTU / MEROX PLANT CAUSTIC TRANKS | 5A | 2018-07-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-010267 | 076551C-087-PID-0031-502-001 | 087-A-PID-00002-010 | PIPING AND INSTRUMENT DIAGRAM L.P. SEPARATOR 1 HDU | 8A | 2018-07-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010268 | 076551C-093-PID-0021-001-001 | 006-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM FCCU FLARE SYSTEM OFF-PLOT K.O. DRUM | 8A | 2018-07-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-010269 | 076551C-000R-DL-0811-002 | 000-C-IDL-60002-001 | DEVIATION LIST FOR CLADDED AND ALLOY/SS VESSEL | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-010269 | 076551C-000R-ITP-0811-002 | 000-C-ITP-60002-001 | INSPECTION AND TEST PLAN FOR CLADDED AND ALLOY/SS VESSEL | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-010269 | 076551C-000R-MR-0811-002 | 000-C-MRQ-60002-001 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-010269 | 076551C-000R-SP-0811-002 | 000-C-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CLADDED AND ALLOY/SS VESSEL | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-010269 | 076551C-000R-SR-0811-002 | 000-C-SOW-60002-001 | SCOPE OF SUPPLY FOR CLADDED AND ALLOY/SS VESSEL | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-010270 | 076551C-021-NM-1920-001 | 021-P-INX-00004-001 | HAZARDOUS SOURCE OF RELEASE LIST NO 3 HYDRODESULPHURIZATION UNIT (3HDU) | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-29 | CLASS 2
CON-BMP-TRA-010271 | 076551C-023-NM-1920-001 | 023-P-INX-00004-001 | HAZARDOUS SOURCE OF RELEASE LIST NO 1 HYDROGEN RECOVERY UNIT (UNIT 023) | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-29 | CLASS 2
CON-BMP-TRA-010272 | 076551C-023-NM-1300-012 | 023-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-29 | CLASS 2
CON-BMP-TRA-010273 | 076551C-051-ML-222 | 051-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 051 | 0 | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 |  |  | CLASS 2
CON-BMP-TRA-010274 | 076551C-018-CN-0007-001 | 018-A-BOD-00001-001 | BASIS OF DESIGN 1RHCU (UNIT 018) RESIDUE HYDROCRACKING UNIT | A | 2018-07-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-010275 | 076551C-021-CN-0007-001 | 021-A-BOD-00001-001 | BASIS OF DESIGN 3HDU (UNIT 021) HYDRO DESULPHURIZATIN UNIT | A | 2018-07-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010276 | 076551C-050-CN-0008-002 | 050-A-BOD-50002-001 | MATERIAL SELECTION BASIS REFINERY TANK FARM | A | 2018-07-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010277 | 076551C-018-NM-1920-001 | 018-P-INX-00004-001 | HAZARDOUS SOURCE OF RELEASE LIST NO. 1 RESIDUE HYDROCRACKING UNIT (1RHCU) | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010278 | 076551C-061-EL-001 | 061-A-EQL-50001-001 | ITEM INDEX (EQUIPMENT LIST) NO.1 HYDROGEN RECOVERY UNIT (1HRU) | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-010279 | 076551C-000R-MS-1300-001 | 000-L-MST-60001-001 | TECHNICAL SPECIFICATION FOR LASER SCAN SURVEY | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-001-001 | 051-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3 REFRIGERATED STORAGE TANK | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-002-001 | 051-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3 REFRIGERATED STORAGE TANK (INSTRUMENTATION AND CONTROL DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-003-001 | 051-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3 REFRIGERATED STORAGE TANK (SAFETY DEVICE DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-004-001 | 051-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3 REFRIGERATED STORAGE TANK (SHIPPING PUMPS DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-005-001 | 051-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C4 REFRIGERATED STORAGE TANK | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-006-001 | 051-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C4 REFRIGERATED STORAGE TANK (INSTRUMENTATION AND CONTROL DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-007-001 | 051-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C4 REFRIGERATED STORAGE TANK (SAFETY DEVICE DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-008-001 | 051-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C4 REFRIGERATED STORAGE TANK (SHIPPING PUMPS DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-009-001 | 051-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3/C4 REFRIGERATION STORAGE TANK | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-010-001 | 051-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3/C4 REFRIGERATION STORAGE TANK (INSTR. AND CONTROL DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-011-001 | 051-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3/C4 REFRIGERATION STORAGE TANK (SAFETY DEVICE DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-012-001 | 051-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3/C4 REFRIGERATION STORAGE TANK (SHIPPING PUMPS DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-013-001 | 051-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3/C4 STORAGE AREA INTERCONNECTIONG | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-014-001 | 051-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE RECYCLE VAPORIZER | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-015-001 | 051-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG BUTANE RECYCLE VAPORIZER | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-016-001 | 051-A-PID-00016-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG NITROGEN PACKAGE | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-017-001 | 051-A-PID-00017-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG COMPRESSED AIR PACKAGES | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-018-001 | 051-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG REFRIGERATED LPG STORAGE FLARE PACKAGE | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-019-001 | 051-A-PID-00019-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE/BUTANE RECYCLE VAPORIZER | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010280 | 076551C-051-PID-0021-020-001 | 051-A-PID-00020-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE COMPRESSOR 1ST STAGE SUCTION DRUM (TRAIN A) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-021-001 | 051-A-PID-00021-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE RUNDOWN PUMP (TRAIN A) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-022-001 | 051-A-PID-00022-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE COMPRESSOR (TRAIN A) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-023-001 | 051-A-PID-00023-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE COMPRESSOR 2ND STAGE SUCTION DRUM (TRAIN A) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-024-001 | 051-A-PID-00024-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE COMPRESSOR 2ND STAGE (TRAIN A) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-025-001 | 051-A-PID-00025-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE CONDENSER (TRAIN A) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-026-001 | 051-A-PID-00026-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE CONDENSER ACCUMULATOR (TRAIN A) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-027-001 | 051-A-PID-00027-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG BUTANE PRODUCT COOLER (TRAIN A) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-028-001 | 051-A-PID-00028-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE COMPRESSOR 1ST STAGE SUCTION DRUM (TRAIN B) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-029-001 | 051-A-PID-00029-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE RUNDOWN PUMP (TRAIN B) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-030-001 | 051-A-PID-00030-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE COMPRESSOR (TRAIN B) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-031-001 | 051-A-PID-00031-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE COMPRESSOR 2ND STAGE SUCTION DRUM (TRAIN B) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-032-001 | 051-A-PID-00032-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE COMPRESSOR 2ND STAGE (TRAIN B) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-033-001 | 051-A-PID-00033-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE CONDENSER (TRAIN B) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-034-001 | 051-A-PID-00034-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG PROPANE CONDENSER ACCUMULATOR (TRAIN B) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-035-001 | 051-A-PID-00035-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG BUTANE PRODUCT COOLER (TRAIN B) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-036-001 | 051-A-PID-00036-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3 REFRIGERATED STORAGE (C3 RECYCLE PUMPS DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-037-001 | 051-A-PID-00037-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C4 REFRIGERATED STORAGE (C4 RECYCLE PUMPS DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010281 | 076551C-051-PID-0021-038-001 | 051-A-PID-00038-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG C3/C4 REFRIGERATED STORAGE (C3/C4 RECYCLE PUMPS DETAILS) | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010282 | 076551C-051-PID-0021-100-001 | 051-A-PID-00039-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG FIRE WATER PUMPS AND BASIN | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010282 | 076551C-051-PID-0021-101-001 | 051-A-PID-00039-002 | PIPING AND INSTRUMENT DIAGRAM - WLPG FIRE WATER PUMPS AND BASIN | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010282 | 076551C-051-PID-0021-102-001 | 051-A-PID-00039-003 | PIPING AND INSTRUMENT DIAGRAM - WLPG FIRE WATER PUMPS AND BASIN | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010282 | 076551C-051-PID-0021-103-001 | 051-A-PID-00039-004 | PIPING AND INSTRUMENT DIAGRAM - WLPG FIRE WATER PUMPS AND BASIN | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010282 | 076551C-051-PID-0021-104-001 | 051-A-PID-00040-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG SEA WATER JOCKEY PUMP AND BASIN | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010282 | 076551C-051-PID-0021-105-001 | 051-A-PID-00041-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG SWEET WATER JOCKEY STORAGE TANK AND PUMPS | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010282 | 076551C-051-PID-0021-106-001 | 051-A-PID-00042-001 | PIPING AND INSTRUMENT DIAGRAM - WLPG NACIO SOLUTION DOSING PACKAGE | A | 2018-07-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-010283 | 076551C-058-EL-001 | 058-A-EQL-50001-001 | ITEM INDEX REFINERY GAS SYSTEM UNIT 058 | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-010284 | 076551C-079-EL-001 | 079-A-EQL-00001-001 | ITEM INDEX SPENT CAUSTIC REGENERATION PACKAGE UNIT 079 | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 1 - APPROVED | 2018-08-01 | CLASS 2
CON-BMP-TRA-010285 | 076551C-081-EL-001 | 081-A-EQL-50001-001 | ITEM INDEX LSDP FLARE UNIT 081 | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 1 - APPROVED | 2018-07-31 | CLASS 2
CON-BMP-TRA-010286 | 076551C-082-EL-001 | 082-A-EQL-00001-001 | ITEM INDEX NO 1 BMP FLARE UNIT 082 | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-010287 | 076551C-180-EL-001 | 180-A-EQL-00001-001 | ITEM INDEX REFINERY CENTRAL CONTROL BUILDING UNIT 180 | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-010288 | 076551C-371-EL-001 | 371-A-EQL-50001-001 | ITEM INDEX REVAMPED STEAM DISTRIBUTION UNIT 371 | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010289 | 076551C-372-EL-001 | 372-A-EQL-50001-001 | ITEM INDEX BOILER FEED WATER AND CONDENSATE DISTRIBUTION UNIT 372 | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-010290 | 076551C-930-EL-001 | 930-A-EQL-00001-001 | ITEM INDEX INTERCONNECTING FOR BMP NEW UNIT - UNIT 930 | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-010291 | 076551C-021-NM-1300-012 | 021-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-010292 | 076551C-386-NM-1300-012 | 386-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010293 | 076551C-021-CN-1901-004 | 021-A-CAL-00001-001 | FIREPROOFING SCHEDULE NO. 3 HYDRODESULPHURIZATION UNIT - 3HDU | A | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-010294 | 076551C-023-CN-1901-004 | 023-A-CAL-00001-001 | FIREPROOFING SCHEDULE NO. 1 HYDROGEN RECOVERY UNIT - 1HRU | A | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010295 | 076551C-051-PID-0031-107-001 | 051-A-PID-00043-001 | PIPING AND INSTRUMENT DIAGRAM - REFRIGERATE C3/C4 STORAGE OILY WATER BASIN | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 1
CON-BMP-TRA-010295 | 076551C-051-PID-0031-108-001 | 051-A-PID-00044-001 | PIPING AND INSTRUMENT DIAGRAM - REFRIGERATE C3/C4 STORAGE CONTAMINATED STORM WATER SURGE BASIN | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 1
CON-BMP-TRA-010295 | 076551C-051-PID-0031-109-001 | 051-A-PID-00045-001 | PIPING AND INSTRUMENT DIAGRAM - REFRIGERATE C3/C4 STORAGE CONTAMINATED STORM WATER SURGE BASIN | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 1
CON-BMP-TRA-010295 | 076551C-051-PID-0031-110-001 | 051-A-PID-00046-001 | PIPING AND INSTRUMENT DIAGRAM - REFRIGERATE C3/C4 STORAGE SANITARY BASIN | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 1
CON-BMP-TRA-010296 | 076551C-000R-PP-014 | 000-A-PRI-60001-001 | INSTRUCTION FOR THE EXCHANGE OF DOCUMENTS BETWEEN TECHNIP ITALY S.P.A. AND VENDORS | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 |  |  | CLASS 2
CON-BMP-TRA-010297 | 076551C-000R-DW-1512-002-001 | 000-J-BLD-60002-001 | CTRL & SAFETY SYSTEM WIRING PRINCIPLE | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010298 | 076551C-021-DW-1933-001-001 | 021-S-GAD-00002-001 | FIREFIGHTING LAYOUT 021 - NO 3 HYDRODESULPHURIZATION UNIT 023 - NO 1 HYDROGEN RECOVERY UNIT | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010299 | 076551C-081-NM-1300-012 | 081-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010300 | 076551C-082-NM-1300-012 | 082-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010301 | 076551C-371-NM-1300-012 | 371-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010302 | 076551C-372-NM-1300-012 | 372-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010303 | 076551C-373-NM-1300-012 | 373-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010304 | 076551C-375-NM-1300-012 | 375-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-001 | 021-C-DAT-00018-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0018 BACKWASH SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-008 | 021-C-DAT-00025-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0006 RECYCLE GAS COMPRESSOR SUCTION DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-009 | 021-C-DAT-00023-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0010 STRIPPER REFLUX DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-010 | 021-C-DAT-00022-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0013 EJECTOR RECEIVER | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-011 | 021-C-DAT-00019-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0017 LEAN AMINE SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-013 | 021-C-DAT-00024-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0007 INJECTION WATER BREAK TANK | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-014 | 021-C-DAT-00020-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0016 SOUR WATER DEGASSING DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-015 | 021-C-DAT-00021-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0014 WATER SEAL POT | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-019 | 021-C-DAT-00015-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0021 AMINE SUMP TANK | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-022 | 021-C-DAT-00013-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0024 STEAM BLOWDOWN DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-023 | 021-C-DAT-00017-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0019 FUEL GAS KO DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010305 | 076551C-021-SP-0810-024 | 021-C-DAT-00016-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0020 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010306 | 076551C-018-SP-0810-013 | 018-C-DAT-00074-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0013 VACUUM COLUMN HOTWELL | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010306 | 076551C-018-SP-0810-017 | 018-C-DAT-00071-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0056 HOT PURGE OIL SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010306 | 076551C-018-SP-0810-032 | 018-C-DAT-00033-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0025 LEAN AMINE SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010306 | 076551C-018-SP-0810-075 | 018-C-DAT-00070-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0061 A HP/MP BLOWDOWN FLASH DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010306 | 076551C-018-SP-0810-081 | 018-C-DAT-00069-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0061 B LP BLOWDOWN FLASH DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-013-001 | 018-C-GAD-00085-001 | 018V0013 VACUUM COLUMN HOTWELL | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-013-002 | 018-C-GAD-00085-002 | 018V0013 VACUUM COLUMN HOTWELL | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-013-003 | 018-C-GAD-00085-003 | 018V0013 VACUUM COLUMN HOTWELL | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-017-001 | 018-C-GAD-00082-001 | 018V0056 HOT PURGE OIL SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-017-002 | 018-C-GAD-00082-002 | 018V0056 HOT PURGE OIL SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-017-003 | 018-C-GAD-00082-003 | 018V0056 HOT PURGE OIL SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-032-001 | 018-C-GAD-00047-001 | 018V0025 LEAN AMINE SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-032-002 | 018-C-GAD-00047-002 | 018V0025 LEAN AMINE SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-032-003 | 018-C-GAD-00047-003 | 018V0025 LEAN AMINE SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-075-001 | 018-C-GAD-00081-001 | 018V0061A HP/MP BLOWDOWN FLASH DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-075-002 | 018-C-GAD-00081-002 | 018V0061A HP/MP BLOWDOWN FLASH DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-075-003 | 018-C-GAD-00081-003 | 018V0061A HP/MP BLOWDOWN FLASH DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-081-001 | 018-C-GAD-00086-001 | 018V0061B LP BLOWDOWN FLASH DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-081-002 | 018-C-GAD-00086-002 | 018V0061B LP BLOWDOWN FLASH DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010307 | 076551C-018-DW-0810-081-003 | 018-C-GAD-00086-003 | 018V0061B LP BLOWDOWN FLASH DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010308 | 076551C-051-DW-0810-002-001 | 051-C-GAD-00002-001 | 051V0002 A/B PROPANE COMPRESSOR 1ST STAGE SUCTION DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010308 | 076551C-051-DW-0810-002-002 | 051-C-GAD-00002-002 | 051V0002 A/B PROPANE COMPRESSOR 1ST STAGE SUCTION DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010308 | 076551C-051-DW-0810-002-003 | 051-C-GAD-00002-003 | 051V0002 A/B PROPANE COMPRESSOR 1ST STAGE SUCTION DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010309 | 076551C-058-DW-0810-002-001 | 058-C-GAD-50001-001 | 058V5817 PROCESS GAS MIXING DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 1 - APPROVED | 2018-08-03 | CLASS 2
CON-BMP-TRA-010309 | 076551C-058-DW-0810-002-002 | 058-C-GAD-50001-002 | 058V5817 PROCESS GAS MIXING DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010309 | 076551C-058-DW-0810-002-003 | 058-C-GAD-50001-003 | 058V5817 PROCESS GAS MIXING DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010309 | 076551C-058-DW-0810-003-001 | 058-C-GAD-50002-001 | 058V5820 SWEET KHUFF GAS KO DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 1 - APPROVED | 2018-08-03 | CLASS 2
CON-BMP-TRA-010309 | 076551C-058-DW-0810-003-002 | 058-C-GAD-50002-002 | 058V5820 SWEET KHUFF GAS KO DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010309 | 076551C-058-DW-0810-003-003 | 058-C-GAD-50002-003 | 058V5820 SWEET KHUFF GAS KO DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010310 | 076551C-051-SP-0810-002 | 051-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 051V0002A/B PROPANE COMPRESSOR 1ST STAGE SUCTION DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-010311 | 076551C-058-SP-0810-002 | 058-C-DAT-50001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 058V5817 PROCESS GAS MIXING DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010311 | 076551C-058-SP-0810-003 | 058-C-DAT-50002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 058V5820 SWEET KHUFF GAS KO DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-001-001 | 021-C-GAD-00018-001 | 021V0018 BACKWASH SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-001-002 | 021-C-GAD-00018-002 | 021V0018 BACKWASH SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-001-003 | 021-C-GAD-00018-003 | 021V0018 BACKWASH SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-008-001 | 021-C-GAD-00025-001 | 021V0006 RECYCLE GAS COMPRESSOR SUCTION DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-008-002 | 021-C-GAD-00025-002 | 021V0006 RECYCLE GAS COMPRESSOR SUCTION DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-008-003 | 021-C-GAD-00025-003 | 021V0006 RECYCLE GAS COMPRESSOR SUCTION DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-009-001 | 021-C-GAD-00023-001 | 021V0010 STRIPPER REFLUX DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-009-002 | 021-C-GAD-00023-002 | 021V0010 STRIPPER REFLUX DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-009-003 | 021-C-GAD-00023-003 | 021V0010 STRIPPER REFLUX DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-010-001 | 021-C-GAD-00022-001 | 021V0013 EJECTOR RECEIVER | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-010-002 | 021-C-GAD-00022-002 | 021V0013 EJECTOR RECEIVER | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-010-003 | 021-C-GAD-00022-003 | 021V0013 EJECTOR RECEIVER | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-011-001 | 021-C-GAD-00019-001 | 021V0017 LEAN AMINE SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-011-002 | 021-C-GAD-00019-002 | 021V0017 LEAN AMINE SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-011-003 | 021-C-GAD-00019-003 | 021V0017 LEAN AMINE SURGE DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-013-001 | 021-C-GAD-00024-001 | 021V0007 INJECTION WATER BREAK TANK | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-013-002 | 021-C-GAD-00024-002 | 021V0007 INJECTION WATER BREAK TANK | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010312 | 076551C-021-DW-0810-013-003 | 021-C-GAD-00024-003 | 021V0007 INJECTION WATER BREAK TANK | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-014-001 | 021-C-GAD-00020-001 | 021V0016 SOUR WATER DEGASSING DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-014-002 | 021-C-GAD-00020-002 | 021V0016 SOUR WATER DEGASSING DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-014-003 | 021-C-GAD-00020-003 | 021V0016 SOUR WATER DEGASSING DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-015-001 | 021-C-GAD-00021-001 | 021V0014 WATER SEAL POT | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-015-002 | 021-C-GAD-00021-002 | 021V0014 WATER SEAL POT | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-015-003 | 021-C-GAD-00021-003 | 021V0014 WATER SEAL POT | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-019-001 | 021-C-GAD-00015-001 | 021V0021 AMINE SUMP TANK | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-019-002 | 021-C-GAD-00015-002 | 021V0021 AMINE SUMP TANK | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-019-003 | 021-C-GAD-00015-003 | 021V0021 AMINE SUMP TANK | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-022-001 | 021-C-GAD-00013-001 | 021V0024 STEAM BLOWDOWN DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-022-002 | 021-C-GAD-00013-002 | 021V0024 STEAM BLOWDOWN DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-022-003 | 021-C-GAD-00013-003 | 021V0024 STEAM BLOWDOWN DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-023-001 | 021-C-GAD-00017-001 | 021V0019 FUEL GAS KO DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-023-002 | 021-C-GAD-00017-002 | 021V0019 FUEL GAS KO DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-023-003 | 021-C-GAD-00017-003 | 021V0019 FUEL GAS KO DRUM | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-024-001 | 021-C-GAD-00016-001 | 021V0020 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-024-002 | 021-C-GAD-00016-002 | 021V0020 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010313 | 076551C-021-DW-0810-024-003 | 021-C-GAD-00016-003 | 021V0020 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-010314 | 076551C-050-EL-001 | 050-A-EQL-50001-001 | ITEM INDEX (EQUIPMENT LIST) REFINERY TANK FARM (UNIT 050) | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-010315 | 076551C-051-EL-001 | 051-A-EQL-50001-001 | ITEM INDEX (EQUIPMENT LIST) C3/C4 LPG STORAGE FACILITY AT WHARF (UNIT 051) | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010316 | 076551C-056-EL-001 | 056-A-EQL-50001-001 | ITEM INDEX (EQUIPMENT LIST) SITRA TANK FARM (UNIT 056) | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010317 | 076551C-018-DW-1980-001-001 | 018-A-GAD-00001-001 | FIRE EXPOSED ENVELOPE AND FIREPROOFING LIMITS NO.1 RHCU | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010317 | 076551C-018-DW-1980-001-002 | 018-A-GAD-00001-002 | FIRE EXPOSED ENVELOPE AND FIREPROOFING LIMITS NO.1 RHCU | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010318 | 076551C-021-DW-1980-001-001 | 021-A-GAD-00001-001 | FIRE EXPOSED ENVELOPE AND FIREPROOFING LIMITS NO.3 HDU NO.1 HRU | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010318 | 076551C-021-DW-1980-001-002 | 021-A-GAD-00001-002 | FIRE EXPOSED ENVELOPE AND FIREPROOFING LIMITS NO.3 HDU NO.1 HRU | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010319 | 076551C-371-MSD-0011-001-001 | 371-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM STEAM DISTRIBUTION | A | 2018-07-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 1
CON-BMP-TRA-010319 | 076551C-371-MSD-0011-002-001 | 371-A-MSD-50001-002 | MATERIAL SELECTION DIAGRAM STEAM DISTRIBUTION | A | 2018-07-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 1
CON-BMP-TRA-010319 | 076551C-371-MSD-0011-003-001 | 371-A-MSD-50001-003 | MATERIAL SELECTION DIAGRAM 20 PSIG EXCESS STEAM SYSTEM | A | 2018-07-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-08 | 1 - APPROVED | 2018-08-08 | CLASS 1
CON-BMP-TRA-010319 | 076551C-371-MSD-0011-004-001 | 371-A-MSD-50001-004 | MATERIAL SELECTION DIAGRAM 60 PSIG EXCESS STEAM SYSTEM | A | 2018-07-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-08 | 1 - APPROVED | 2018-08-08 | CLASS 1
CON-BMP-TRA-010320 | 076551C-907-DW-0051-002-001 | 907-A-PPN-50002-001 | GENERAL PLOT PLAN 907 - TRANSFER LINE | A | 2018-07-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 1
CON-BMP-TRA-010321 | 076551C-056-NM-0003-001 | 056-A-CAL-50002-001 | UTILITY CONSUMTION SUMMARY UNIT 056 - SITRA TANK FARM | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010322 | 076551C-062-EL-001 | 062-A-EQL-50001-001 | ITEM INDEX (EQUIPMENT LIST) NO.2 HYDRODESULPHURIZATION UNIT (2HU) | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010323 | 076551C-077-EL-001 | 077-A-EQL-50001-001 | ITEM INDEX (EQUIPMENT LIST) NO.1 HYDROCRACKING UNIT (1HCU) | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010324 | 076551C-062-NM-120 | 062-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 062 - 2HDU (NO.2 HYDRODESULPHURIZATION UNIT) CALCULATION SHEET | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-010325 | 076551C-077-NM-120 | 077-A-STS-50001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL UNIT 077 - 1HDU (NO.1 HYDROCRACKING UNIT) CALCULATION SHEET | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010326 | 076551C-050-DW-0051-001-001 | 050-A-PPN-50001-001 | OVERALL PLOT PLAN 050 - REFINERY TANK FARM | A | 2018-07-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-09 |  |  | CLASS 1
CON-BMP-TRA-010327 | 076551C-018-SP-0410-001 | 018-C-DAT-00078-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018C1001R TRAIN1 1ST REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-08 | CLASS 2
CON-BMP-TRA-010327 | 076551C-018-SP-0410-002 | 018-C-DAT-00077-001 | UNFIRED PRESSURE VESSSEL DESIGN SPECIFICATION SHEET FOR 018C1002R TRAIN1 2ND REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-08 | CLASS 2
CON-BMP-TRA-010327 | 076551C-018-SP-0410-003 | 018-C-DAT-00076-001 | UNFIRED PRESSURE VESSSEL DESIGN SPECIFICATION SHEET FOR 018C2001R TRAIN1 1ST REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-08 | CLASS 2
CON-BMP-TRA-010327 | 076551C-018-SP-0410-004 | 018-C-DAT-00075-001 | UNFIRED PRESSURE VESSSEL DESIGN SPECIFICATION SHEET FOR 018C2002R TRAIN2 2ND REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-08 | CLASS 2
CON-BMP-TRA-010328 | 076551C-021-SP-4230-001 | 021-C-DAT-00026-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0001 FEED COALESCER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010328 | 076551C-021-SP-4230-002 | 021-C-DAT-00027-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0012 DIESEL PRODUCT COALESCER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010328 | 076551C-021-SP-4250-001 | 021-C-DAT-00028-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0011 STEAM SEPARATOR | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010329 | 076551C-051-SP-0910-007 | 051-G-DAT-00001-001 | CENTRIFUGAL PUMPS DATA SHEET PROPANE RUNDOWN PUMP 051P0004A/B | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010330 | 076551C-061-SP-0910-001 | 061-G-DAT-50001-001 | CENTRIFUGAL PUMPS DATA SHEET SLOP DRAIN PUMP 061P6111A/B - 061P6112A/B - 061P6113A/B | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010331 | 076551C-021-SP-0410-001 | 021-C-DAT-00012-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021C0001R REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-001-001 | 018-C-GAD-00001-001 | 018C1001R TRAIN 1 1ST REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-001-002 | 018-C-GAD-00001-002 | 018C1001R TRAIN 1 1ST REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-001-003 | 018-C-GAD-00001-003 | 018C1001R TRAIN 1 1ST REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-002-001 | 018-C-GAD-00002-001 | 018C1002R TRAIN 1 2ND REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-002-002 | 018-C-GAD-00002-002 | 018C1002R TRAIN 1 2ND REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-002-003 | 018-C-GAD-00002-003 | 018C1002R TRAIN 1 2ND REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-003-001 | 018-C-GAD-00003-001 | 018C2001R TRAIN 2 1ST REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-003-002 | 018-C-GAD-00003-002 | 018C2001R TRAIN 2 1ST REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-003-003 | 018-C-GAD-00003-003 | 018C2001R TRAIN 2 1ST REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-004-001 | 018-C-GAD-00004-001 | 018C2002R TRAIN 2 2ND REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-004-002 | 018-C-GAD-00004-002 | 018C2002R TRAIN 2 2ND REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010332 | 076551C-018-DW-0410-004-003 | 018-C-GAD-00004-003 | 018C2002R TRAIN 2 2ND REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010333 | 076551C-021-DW-0410-001-001 | 021-C-GAD-00001-001 | 021C0001R REACTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010334 | 076551C-018-SP-0810-002 | 018-C-DAT-00084-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1002 TRAIN1 INTERSTAGE SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010334 | 076551C-018-SP-0810-003 | 018-C-DAT-00083-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1003 TRAIN1 HP/HT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010334 | 076551C-018-SP-0810-005 | 018-C-DAT-00082-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1005 TRAIN1 HP/MT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010334 | 076551C-018-SP-0810-022 | 018-C-DAT-00081-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2002 TRAIN2 INTERSTAGE SEPARTOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010334 | 076551C-018-SP-0810-023 | 018-C-DAT-00080-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2003 TRAIN2 HP/HT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010334 | 076551C-018-SP-0810-025 | 018-C-DAT-00079-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2005 TRAIN2 HP/MT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-002-001 | 018-C-GAD-00005-001 | 018V1002 TRAIN 1 INTERSTAGE SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-002-002 | 018-C-GAD-00005-002 | 018V1002 TRAIN 1 INTERSTAGE SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-002-003 | 018-C-GAD-00005-003 | 018V1002 TRAIN 1 INTERSTAGE SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-003-001 | 018-C-GAD-00006-001 | 018V1003 TRAIN 1 HP/HT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-003-002 | 018-C-GAD-00006-002 | 018V1003 TRAIN 1 HP/HT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-003-003 | 018-C-GAD-00006-003 | 018V1003 TRAIN 1 HP/HT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-005-001 | 018-C-GAD-00007-001 | 018V1005 TRAIN 1 HP/MT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-005-002 | 018-C-GAD-00007-002 | 018V1005 TRAIN 1 HP/MT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-005-003 | 018-C-GAD-00007-003 | 018V1005 TRAIN 1 HP/MT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-022-001 | 018-C-GAD-00008-001 | 018V2002 TRAIN 2 INTERSTAGE SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-022-002 | 018-C-GAD-00008-002 | 018V2002 TRAIN 2 INTERSTAGE SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-022-003 | 018-C-GAD-00008-003 | 018V2002 TRAIN 2 INTERSTAGE SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-023-001 | 018-C-GAD-00009-001 | 018V2003 TRAIN 2 HP/HT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-023-002 | 018-C-GAD-00009-002 | 018V2003 TRAIN 2 HP/HT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-023-003 | 018-C-GAD-00009-003 | 018V2003 TRAIN 2 HP/HT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-025-001 | 018-C-GAD-00010-001 | 018V2005 TRAIN 2 HP/MT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-025-002 | 018-C-GAD-00010-002 | 018V2005 TRAIN 2 HP/MT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010335 | 076551C-018-DW-0810-025-003 | 018-C-GAD-00010-003 | 018V2005 TRAIN 2 HP/MT SEPARATOR | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010336 | 076551C-000R-ITP-0811-001 | 000-C-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V H.P. VESSELS | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010336 | 076551C-000R-MR-0811-001 | 000-C-MRQ-60001-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010336 | 076551C-000R-SP-0811-001 | 000-C-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V H.P. VESSELS | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010336 | 076551C-000R-SR-0811-001 | 000-C-SOW-60001-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V H.P. VESSELS | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010337 | 076551C-000R-ITP-0411-001 | 000-C-ITP-60004-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V REACTORS AND INTRNALS | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-09 | CLASS 2
CON-BMP-TRA-010337 | 076551C-000R-MR-0411-001 | 000-C-MRQ-60004-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-09 | CLASS 2
CON-BMP-TRA-010337 | 076551C-000R-SP-0411-001 | 000-C-GRD-60004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V REACTORS AND INTRNALS | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-09 | CLASS 2
CON-BMP-TRA-010337 | 076551C-000R-SR-0411-001 | 000-C-SOW-60004-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V REACTORS AND INTRNALS | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-09 | CLASS 2
CON-BMP-TRA-010337 | 076551C-O6866 | 000-C-MPO-50001-001 | PURCHASE ORDER RELEVANT TO 000R-MR-0411-001 FOR 2.25CR-1MO-V H.P. VESSELS | 0 | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 4 - NOT APPROVED | 2018-08-09 | CLASS 2
CON-BMP-TRA-010338 | 076551C-051-CN-1901-004 | 051-A-CAL-00001-001 | FIREPROOFING SCHEDULE REFRIGERATED LPG C3/C4 STORAGE FACILITY AT WHARF | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010339 | 076551C-058-CN-1901-004 | 058-A-CAL-50001-001 | FIREPROOFING SCHEDULE REFINERY GAS SYSTEM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010340 | 076551C-079-CN-1901-004 | 079-A-CAL-00001-001 | FIREPROOFING SCHEDULE SPENT CAUSTIC TREATMENT UNIT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010341 | 076551C-081-CN-1901-004 | 081-A-CAL-50001-001 | FIREPROOFING SCHEDULE LSDP FLARE AREA | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010342 | 076551C-082-CN-1901-004 | 082-A-CAL-00001-001 | FIREPROOFING SCHEDULE REFINERY SOUTH FLARE | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 1 - APPROVED | 2018-08-19 | CLASS 2
CON-BMP-TRA-010343 | 076551C-056-DW-0051-001-001 | 056-A-PPN-50001-001 | OVERALL PLOT PLAN SITRA TANK FARM | A | 2018-07-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 1
CON-BMP-TRA-010344 | 076551C-907-DW-1452-001-001 | 907-S-GAD-50001-001 | TRANSFER LINES REFINERY / SITRA GRADING & UNDERGROUND INSTALL. DWGS SHEET "1" | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010344 | 076551C-907-DW-1452-001-002 | 907-S-GAD-50001-002 | TRANSFER LINES REFINERY / SITRA GRADING & UNDERGROUND INSTALL. DWGS SHEET "2" | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010344 | 076551C-907-DW-1452-001-003 | 907-S-GAD-50001-003 | TRANSFER LINES REFINERY / SITRA GRADING & UNDERGROUND INSTALL. DWGS SHEET "3" | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-19 | CLASS 2
CON-BMP-TRA-010345 | 076551C-933-DW-0051-002-001 | 933-A-PPN-00001-001 | GENERAL PLOT PLAN 933-INTERCON. FOR REVAMPING AREA | A | 2018-07-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 1
CON-BMP-TRA-010346 | 076551C-018-NM-1300-012 | 018-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-001-001 | 051-C-GAD-00001-001 | 051V0001 A/B INSTRUMENT AIR HOLD-UP RECEIVER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-001-002 | 051-C-GAD-00001-002 | 051V0001 A/B INSTRUMENT AIR HOLD-UP RECEIVER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-001-003 | 051-C-GAD-00001-003 | 051V0001 A/B INSTRUMENT AIR HOLD-UP RECEIVER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-003-001 | 051-C-GAD-00003-001 | 051V0003 A/B PROPANE COMPRESSOR 2ND STAGE SUCTION DRUMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-003-002 | 051-C-GAD-00003-002 | 051V0003 A/B PROPANE COMPRESSOR 2ND STAGE SUCTION DRUMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-003-003 | 051-C-GAD-00003-003 | 051V0003 A/B PROPANE COMPRESSOR 2ND STAGE SUCTION DRUMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-004-001 | 051-C-GAD-00004-001 | 051V0004 A/B PROPANE CONDENSER ACCUMULATORS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-004-002 | 051-C-GAD-00004-002 | 051V0004 A/B PROPANE CONDENSER ACCUMULATORS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010347 | 076551C-051-DW-0810-004-003 | 051-C-GAD-00004-003 | 051V0004 A/B PROPANE CONDENSER ACCUMULATORS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010348 | 076551C-079-DW-0810-001-001 | 079-C-GAD-00001-001 | 079V0001 SPENT CAUSTIC CLOSED DRAIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010348 | 076551C-079-DW-0810-001-002 | 079-C-GAD-00001-002 | 079V0001 SPENT CAUSTIC CLOSED DRAIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010348 | 076551C-079-DW-0810-001-003 | 079-C-GAD-00001-003 | 079V0001 SPENT CAUSTIC CLOSED DRAIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010348 | 076551C-079-DW-0810-002-001 | 079-C-GAD-00002-001 | 079V0002 SPENT CAUSTIC FEED DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010348 | 076551C-079-DW-0810-002-002 | 079-C-GAD-00002-002 | 079V0002 SPENT CAUSTIC FEED DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010348 | 076551C-079-DW-0810-002-003 | 079-C-GAD-00002-003 | 079V0002 SPENT CAUSTIC FEED DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010349 | 076551C-000R-DL-4026-001 | 000-S-IDL-60003-001 | DEVIATION LIST FOR MARINE LOADING ARMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010349 | 076551C-000R-ITP-4026-001 | 000-S-ITP-60003-001 | INSPECTION AND TEST PLAN (ITP) FOR MARINE LOADING ARMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010349 | 076551C-000R-MR-4026-001 | 000-S-MRQ-60003-001 | MATERIAL REQUISITION FOR MARINE LOADING ARMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010349 | 076551C-000R-SP-4026-001 | 000-S-GRD-60003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR MARINE LOADING ARMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010349 | 076551C-000R-SR-4026-001 | 000-S-SOW-60003-001 | SCOPE OF SUPPLY FOR MARINE LOADING ARMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010350 | 076551C-371-DW-0810-001-001 | 371-C-GAD-50001-001 | 371V0005 20 PSIG EXCESS STEAM CONDENSATE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010350 | 076551C-371-DW-0810-001-002 | 371-C-GAD-50001-002 | 371V0005 20 PSIG EXCESS STEAM CONDENSATE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010350 | 076551C-371-DW-0810-001-003 | 371-C-GAD-50001-003 | 371V0005 20 PSIG EXCESS STEAM CONDENSATE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010351 | 076551C-018-DW-1920-001-001 | 018-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION PLAN NO. 1 RESIDUE HYDROCRACKING UNIT 1RHCU | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010351 | 076551C-018-DW-1920-001-002 | 018-P-HAC-00001-002 | HAZARDOUS AREA CLASSIFICATION ELEVATION NO. 1 RESIDUE HYDROCRACKING UNIT 1RHCU | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010351 | 076551C-018-DW-1920-001-003 | 018-P-HAC-00001-003 | HAZARDOUS AREA CLASSIFICATION ELEVATION NO. 1 RESIDUE HYDROCRACKING UNIT 1RHCU | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010351 | 076551C-018-DW-1920-002-001 | 018-P-HAC-00002-001 | HAZARDOUS AREA CLASSIFICATION SECTION NO. 1 RESIDUE HYDROCRACKING UNIT 1RHCU | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010352 | 076551C-021-DW-1920-001-001 | 021-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION PLAN NO. 3 HYDRODESULPHURIZATION UNIT - 3HDU NO. 1 HYDROGEN RECOVERY UNIT - 1RHU | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010352 | 076551C-021-DW-1920-001-002 | 021-P-HAC-00001-002 | HAZARDOUS AREA CLASSIFICATION ELEVATION NO. 3 HYDRODESULPHURIZATION UNIT - 3HDU NO. 1 HYDROGEN RECOVERY UNIT - 1RHU | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010352 | 076551C-021-DW-1920-002-001 | 021-P-HAC-00002-001 | HAZARDOUS AREA CLASSIFICATION SECTION NO. 3 HYDRODESULPHURIZATION UNIT - 3HDU NO. 1 HYDROGEN RECOVERY UNIT - 1RHU | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010353 | 076551C-081-DW-0810-001-001 | 081-C-GAD-50001-001 | 081V8104 LSDP FLARE K O DRUM FOR BMP UNITS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010353 | 076551C-081-DW-0810-001-002 | 081-C-GAD-50001-002 | 081V8104 LSDP FLARE K O DRUM FOR BMP UNITS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010353 | 076551C-081-DW-0810-001-003 | 081-C-GAD-50001-003 | 081V8104 LSDP FLARE K O DRUM FOR BMP UNITS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010354 | 076551C-372-DW-0810-001-001 | 372-C-GAD-50001-001 | 372V003 HG CONDENSATE FLASH DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010354 | 076551C-372-DW-0810-001-002 | 372-C-GAD-50001-002 | 372V003 HG CONDENSATE FLASH DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010354 | 076551C-372-DW-0810-001-003 | 372-C-GAD-50001-003 | 372V003 HG CONDENSATE FLASH DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010355 | 076551C-061-DW-0810-001-001 | 061-C-GAD-50001-001 | 061V6110AB 061V6120AB 061V6130 SLOP DRUMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010355 | 076551C-061-DW-0810-001-002 | 061-C-GAD-50001-002 | 061V6110AB 061V6120AB 061V6130 SLOP DRUMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010355 | 076551C-061-DW-0810-001-003 | 061-C-GAD-50001-003 | 061V6110AB 061V6120AB 061V6130 SLOP DRUMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010355 | 076551C-061-DW-0810-002-001 | 061-C-GAD-50002-001 | 061V6140 PROPANE/BUTANE (C3/C4) BLOW DOWN DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010355 | 076551C-061-DW-0810-002-002 | 061-C-GAD-50002-002 | 061V6140 PROPANE/BUTANE (C3/C4) BLOW DOWN DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010355 | 076551C-061-DW-0810-002-003 | 061-C-GAD-50002-003 | 061V6140 PROPANE/BUTANE (C3/C4) BLOW DOWN DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010356 | 076551C-082-DW-0810-001-001 | 082-C-GAD-00001-001 | 082V0001A/B REFINERY SOUTH FLARE MAIN K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010356 | 076551C-082-DW-0810-001-002 | 082-C-GAD-00001-002 | 082V0001A/B REFINERY SOUTH FLARE MAIN K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010356 | 076551C-082-DW-0810-001-003 | 082-C-GAD-00001-003 | 082V0001A/B REFINERY SOUTH FLARE MAIN K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010357 | 076551C-058-DW-0810-001-001 | 058-C-GAD-50003-001 | 058C5807/058C5808 KHUFF GAS MICROSCRUBBER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010357 | 076551C-058-DW-0810-001-002 | 058-C-GAD-50003-002 | 058C5807/058C5808 KHUFF GAS MICROSCRUBBER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010357 | 076551C-058-DW-0810-001-003 | 058-C-GAD-50003-003 | 058C5807/058C5808 KHUFF GAS MICROSCRUBBER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-001-001 | 023-C-GAD-00006-001 | 023V0001 FEED GAS K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-001-002 | 023-C-GAD-00006-002 | 023V0001 FEED GAS K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-001-003 | 023-C-GAD-00006-003 | 023V0001 FEED GAS K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-002-001 | 023-C-GAD-00005-001 | 023V0002 COMPRESSED GAS K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-002-002 | 023-C-GAD-00005-002 | 023V0002 COMPRESSED GAS K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-002-003 | 023-C-GAD-00005-003 | 023V0002 COMPRESSED GAS K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-003-001 | 023-C-GAD-00004-001 | 023V0003 LEAN AMINE SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-003-002 | 023-C-GAD-00004-002 | 023V0003 LEAN AMINE SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-003-003 | 023-C-GAD-00004-003 | 023V0003 LEAN AMINE SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-005-001 | 023-C-GAD-00003-001 | 023V0004 PSA FEED K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-005-002 | 023-C-GAD-00003-002 | 023V0004 PSA FEED K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010358 | 076551C-023-DW-0810-005-003 | 023-C-GAD-00003-003 | 023V0004 PSA FEED K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010359 | 076551C-000R-IDL-0610-003 | 000-E-IDL-60003-001 | DEVIATION LIST FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010359 | 076551C-000R-MR-0610-003 | 000-E-MRQ-60003-001 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010359 | 076551C-000R-SP-0610-003 | 000-E-GRD-60003-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010359 | 076551C-000R-SR-0610-003 | 000-E-SOW-60003-001 | SCOPE OF SUPPLY FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-011 | 018-C-DAT-00045-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0008 ATM COLUMN REFLUX DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-014 | 018-C-DAT-00073-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0014 HOTWELL VAPOR WATER SEAL DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12
CON-BMP-TRA-010360 | 076551C-018-SP-0810-018 | 018-C-DAT-00039-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V1008 TRAIN 1 MEMBRANE K.O. DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-028 | 018-C-DAT-00038-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V2008 TRAIN 2 MEMBRANE K.O. DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-030 | 018-C-DAT-00032-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0024 CUTTER STOCK SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12
CON-BMP-TRA-010360 | 076551C-018-SP-0810-040 | 018-C-DAT-00044-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0032 FRESH CATALYST TRANSPORT POT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-042 | 018-C-DAT-00043-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0033 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-043 | 018-C-DAT-00042-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0034 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-044 | 018-C-DAT-00041-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0035 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-045 | 018-C-DAT-00040-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0036 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-054 | 018-C-DAT-00054-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0060 FLARE KO DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010360 | 076551C-018-SP-0810-055 | 018-C-DAT-00072-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018V0047 COOLING OIL HEATER CONDENSATE POT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12
CON-BMP-TRA-010361 | 076551C-021-SP-0810-002 | 021-C-DAT-00011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0002 FEED SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010361 | 076551C-021-SP-0810-020 | 021-C-DAT-00010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0023 FLARE KO DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010361 | 076551C-021-SP-0810-021 | 021-C-DAT-00014-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 021V0022 SOUR WATER SUMP | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010362 | 076551C-023-NM-0051-001 | 023-L-INX-00002-001 | BATTERY LIMIT INTERFACE TABLE | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010363 | 076551C-021-NM-0051-001 | 021-L-INX-00002-001 | BATTERY LIMIT INTERFACE TABLE | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-018-001 | 018-C-GAD-00053-001 | 018V1008 TRAIN 1 MEMBRANE K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-018-002 | 018-C-GAD-00053-002 | 018V1008 TRAIN 1 MEMBRANE K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-018-003 | 018-C-GAD-00053-003 | 018V1008 TRAIN 1 MEMBRANE K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-028-001 | 018-C-GAD-00052-001 | 0182008 TRAIN 2 MEMBRANE K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-028-002 | 018-C-GAD-00052-002 | 0182008 TRAIN 2 MEMBRANE K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-028-003 | 018-C-GAD-00052-003 | 0182008 TRAIN 2 MEMBRANE K O DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-030-001 | 018-C-GAD-00046-001 | 018V0024 CUTTER STOCK SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-030-002 | 018-C-GAD-00046-002 | 018V0024 CUTTER STOCK SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-030-003 | 018-C-GAD-00046-003 | 018V0024 CUTTER STOCK SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-043-001 | 018-C-GAD-00056-001 | 018V0034 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-043-002 | 018-C-GAD-00056-002 | 018V0034 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-043-003 | 018-C-GAD-00056-003 | 018V0034 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-044-001 | 018-C-GAD-00055-001 | 018V0035 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-044-002 | 018-C-GAD-00055-002 | 018V0035 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-044-003 | 018-C-GAD-00055-003 | 018V0035 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-045-001 | 018-C-GAD-00054-001 | 018V0036 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-045-002 | 018-C-GAD-00054-002 | 018V0036 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010364 | 076551C-018-DW-0810-045-003 | 018-C-GAD-00054-003 | 018V0036 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-011-001 | 018-C-GAD-00059-001 | 018V0008 ATM COLUMN REFLUX DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-011-002 | 018-C-GAD-00059-002 | 018V0008 ATM COLUMN REFLUX DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-011-003 | 018-C-GAD-00059-003 | 018V0008 ATM COLUMN REFLUX DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-014-001 | 018-C-GAD-00084-001 | 018V0014 HOTWELL VAPOR WATER SEAL DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-014-002 | 018-C-GAD-00084-002 | 018V0014 HOTWELL VAPOR WATER SEAL DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-014-003 | 018-C-GAD-00084-003 | 018V0014 HOTWELL VAPOR WATER SEAL DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-040-001 | 018-C-GAD-00058-001 | 018V0032 FRESH CATALYST TRANSPORT POT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-040-002 | 018-C-GAD-00058-002 | 018V0032 FRESH CATALYST TRANSPORT POT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-040-003 | 018-C-GAD-00058-003 | 018V0032 FRESH CATALYST TRANSPORT POT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-042-001 | 018-C-GAD-00057-001 | 018V0033 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-042-002 | 018-C-GAD-00057-002 | 018V0033 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-042-003 | 018-C-GAD-00057-003 | 018V0033 CATALYST INVENTORY HOLDING BIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-054-001 | 018-C-GAD-00066-001 | 018V0060 FLARE KO DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-054-002 | 018-C-GAD-00066-002 | 018V0060 FLARE KO DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-054-003 | 018-C-GAD-00066-003 | 018V0060 FLARE KO DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-055-001 | 018-C-GAD-00083-001 | 018V0047 COOLING OIL HEATER CONDENSATE POT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-055-002 | 018-C-GAD-00083-002 | 018V0047 COOLING OIL HEATER CONDENSATE POT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010365 | 076551C-018-DW-0810-055-003 | 018-C-GAD-00083-003 | 018V0047 COOLING OIL HEATER CONDENSATE POT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010366 | 076551C-023-SP-0810-001 | 023-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 023V0001 FEED GAS KO DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010366 | 076551C-023-SP-0810-002 | 023-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 023V0002 COMPRESSED GAS KO DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010366 | 076551C-023-SP-0810-003 | 023-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 023V0003 LEAN AMINE SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010366 | 076551C-023-SP-0810-005 | 023-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 023V0004 PSA FEED K.O. DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010367 | 076551C-021-DW-0810-002-001 | 021-C-GAD-00012-001 | 021V0002 FEED SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010367 | 076551C-021-DW-0810-002-002 | 021-C-GAD-00012-002 | 021V0002 FEED SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010367 | 076551C-021-DW-0810-002-003 | 021-C-GAD-00012-003 | 021V0002 FEED SURGE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010368 | 076551C-082-SP-0810-001 | 082-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 082V0001A AND 082V0001B REFINERY SOUTH FLARE MAIN K.O. DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010369 | 076551C-061-SP-0810-001 | 061-C-DAT-50001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 061V6110A/B 061V6120A/B 061V6130A/B SLOP DRUMS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010369 | 076551C-061-SP-0810-002 | 061-C-DAT-50002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 061V6140 PROPANE/BUTANE (C3/C4) BLOW DOWN DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010370 | 076551C-051-SP-0810-001 | 051-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 051V0001A/B INSTRUMENT AIR HOLD UP RECEIVER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010370 | 076551C-051-SP-0810-003 | 051-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 051V0003A/B PROPANE COMPRESSOR 2ND STAGE SUCTION DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010370 | 076551C-051-SP-0810-004 | 051-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 051V0004A/B PROPANE COMPRESSOR ACCUMULATORS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010371 | 076551C-021-ML-222 | 021-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 021 3HDU | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 |  |  | CLASS 2
CON-BMP-TRA-010372 | 076551C-023-ML-222 | 023-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 023 1HRU | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 |  |  | CLASS 2
CON-BMP-TRA-010373 | 076551C-058-SP-0810-001 | 058-C-DAT-50003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 058C5807/058C5808 KHUFF GAS MICROSCRUBBER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010374 | 076551C-930-DW-1622-001-001 | 930-P-CRD-00001-001 | MAIN CABLE ROUTING PROPOSED 33KV EWA TO BMP (CONCEPTUAL) | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010375 | 076551C-081-SP-0810-001 | 081-C-DAT-50001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 081V8104 LSDP FLARE KO DRUM FOR BMP UNITS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010376 | 076551C-372-SP-0810-001 | 372-C-DAT-50001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 372V0035 HG CONDENSATE FLASH DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010377 | 076551C-371-SP-0810-001 | 371-C-DAT-50001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 371V0005 20 PSIG EXCESS STEAM CONDENSATE DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010378 | 076551C-079-SP-0810-001 | 079-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 079V0001 SPENT CAUSTIC CLOSED DRAIN | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010378 | 076551C-079-SP-0810-002 | 079-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 079V0002 SPENT CAUSTIC FEED DRUM | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010379 | ROC-BMR-MOM-000033 | 000-A-MOM-60029-001 | UNIT 82 REFINERY SOUTH FLARE PID IBD REVIEW MEETING (DATE OF MEETING 16 JULY 2018) | 0 | 2018-07-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010379 | ROC-BMR-MOM-000034 | 000-A-MOM-60028-001 | UNIT 005 -073 -081 - HORTON SPHERES LSFO AND FLARES PID IBD REVIEW MEETING (DATE OF MEETING 17 JULY 2018) | 0 | 2018-07-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010379 | ROC-BMR-MOM-000035 | 000-A-MOM-60030-001 | MODIFICATION TO EXISTING UNIT - PID IBD REVIEW MEETING (DATE OF MEETING 18-19 JULY 2018) | 0 | 2018-07-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010379 | ROC-BMR-MOM-000036 | 000-A-MOM-60027-001 | UTILITIES UNITS PID IBD REVIEW MEETING (DATE OF MEETING 20-23 JULY 2018) | 0 | 2018-07-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010380 | 076551C-021-DW-0810-020-001 | 021-C-GAD-00011-001 | 021V0023 FLARE KO DRUM | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010380 | 076551C-021-DW-0810-020-002 | 021-C-GAD-00011-002 | 021V0023 FLARE KO DRUM | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010380 | 076551C-021-DW-0810-020-003 | 021-C-GAD-00011-003 | 021V0023 FLARE KO DRUM | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010380 | 076551C-021-DW-0810-021-001 | 021-C-GAD-00014-001 | 021V0022 SOUR WATER SUMP | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010380 | 076551C-021-DW-0810-021-002 | 021-C-GAD-00014-002 | 021V0022 SOUR WATER SUMP | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010380 | 076551C-021-DW-0810-021-003 | 021-C-GAD-00014-003 | 021V0022 SOUR WATER SUMP | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-010381 | 076551C-056-CN-0022-001 | 056-J-CAL-50001-001 | HYDRAULIC CALCULATION NOTES SITRA TANK FARM UNIT 056 | A | 2018-07-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010382 | 076551C-082-SP-0810-002 | 082-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 082V8202 REFINERY SOUTH FLARE SEAL DRUM | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010383 | 076551C-082-DW-0810-002-001 | 082-C-GAD-00002-001 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010383 | 076551C-082-DW-0810-002-002 | 082-C-GAD-00002-002 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010383 | 076551C-082-DW-0810-002-003 | 082-C-GAD-00002-003 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010384 | 076551C-018-SP-0910-020 | 018-G-DAT-00035-001 | CENTRIFUGAL PUMPS DATA SHEET MP WASH WATER PUMPS 018P0022A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010384 | 076551C-018-SP-0910-024 | 018-G-DAT-00028-001 | CENTRIFUGAL PUMPS DATA SHEET HVGO PRODUCT PUMPS 018P0015A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010384 | 076551C-018-SP-0910-034 | 018-G-DAT-00005-001 | CENTRIFUGAL PUMPS DATA SHEET HP WASH WATER PUMPS 018P0021A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010384 | 076551C-018-SP-0910-035 | 018-G-DAT-00036-001 | CENTRIFUGAL PUMPS DATA SHEET CONDENSATE PUMPS 018P0023A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010385 | 076551C-021-SP-0910-006 | 021-G-DAT-00011-001 | CENTRIFUGAL PUMP DATA SHEET FOR INJECTION WATER PUMPS 021P0002A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010386 | 076551C-000R-DL-0910-005 | 000-G-IDL-60006-001 | DEVIATION LIST FOR HIGH SPEED API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010386 | 076551C-000R-ITP-0910-005 | 000-G-ITP-60006-001 | INSPECTION AND TEST PLAN FOR HIGH SPEED API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010386 | 076551C-000R-MR-0910-005 | 000-G-MRQ-60006-001 | MATERIAL REQUISITION FOR HIGH SPEED API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010386 | 076551C-000R-SP-0910-005 | 000-G-GRD-60006-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HIGH SPEED API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010386 | 076551C-000R-SR-0910-005 | 000-G-SOW-60006-001 | SCOPE OF SUPPLY FOR HIGH SPEED API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-003 | 018-G-DAT-00026-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN FEED PUMPS 018P0002A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-004 | 018-G-DAT-00011-001 | CENTRIFUGAL PUMPS DATA SHEET 1ST ATM COLUMN WATER PUMPS 018P0004A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-005 | 018-G-DAT-00008-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN REFLUX PUMPS 018P0003A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-006 | 018-G-DAT-00017-001 | CENTRIFUGAL PUMPS DATA SHEET 2ND ATM COLUMN WATER PUMPS 018P0006A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-007 | 018-G-DAT-00010-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN OVHD PRODUCT PUMPS 018P0005A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-011 | 018-G-DAT-00007-001 | CENTRIFUGAL PUMPS DATA SHEET LVGO PUMPS 018P0012A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-013 | 018-G-DAT-00006-001 | CENTRIFUGAL PUMPS DATA SHEET HVGO PUMPAROUND PUMPS 018P0014A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-014 | 018-G-DAT-00009-001 | CENTRIFUGAL PUMPS DATA SHEET WASH OIL CIRCULATION PUMPS 018P0016A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-016 | 018-G-DAT-00019-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM COLUMN SLOP OIL PUMPS 018P0010A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-017 | 018-G-DAT-00014-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM COLUMN SOUR WATER PUMPS 018P0011A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-023 | 018-G-DAT-00015-001 | CENTRIFUGAL PUMPS DATA SHEET CATALYST SLOP OIL PUMPS 018P0026A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-025 | 018-G-DAT-00032-001 | CENTRIFUGAL PUMPS DATA SHEET VENT GAS SCRUBBER BOTTOM PUMPS 018P0020A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-029 | 018-G-DAT-00016-001 | CENTRIFUGAL PUMPS DATA SHEET FLARE KO DRUM PUMPS 018P0033A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-031 | 018-G-DAT-00012-001 | CENTRIFUGAL PUMPS DATA SHEET TRAIN 1 BFW CIRCULATION PUMPS 018P1007A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010387 | 076551C-018-SP-0910-032 | 018-G-DAT-00013-001 | CENTRIFUGAL PUMPS DATA SHEET TRAIN 2 BFW CIRCULATION PUMPS 018P2007A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010388 | 076551C-021-SP-0910-001 | 021-G-DAT-00003-001 | CENTRIFUGAL PUMP DATA SHEET FOR BACKWASH PUMP 021-P0008A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010388 | 076551C-021-SP-0910-003 | 021-G-DAT-00005-001 | CENTRIFUGAL PUMP DATA SHEET FOR STRIPPER REFLUX PUMPS 021P0003A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010388 | 076551C-021-SP-0910-005 | 021-G-DAT-00002-001 | CENTRIFUGAL PUMP DATA SHEET FOR EJECTOR RECEIVER OIL PUMPS 021P0005A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010388 | 076551C-021-SP-0910-008 | 021-G-DAT-00012-001 | CENTRIFUGAL PUMP DATA SHEET FOR EJECTOR RECEIVER WATER PUMP 021P0006A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010388 | 076551C-021-SP-0910-013 | 021-G-DAT-00004-001 | CENTRIFUGAL PUMP DATA SHEET FOR FLARE KO DRUM PUMPS 021P0012A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010389 | 076551C-023-SP-0910-001 | 023-G-DAT-00001-001 | CENTRIFUGAL PUMP DATA SHEET FOR RECOVERY HC CONDENSATE PUMPS 023P0001A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-010390 | 076551C-050-SP-0910-001 | 050-G-DAT-50001-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA TRANSFER PUMP 050P5030 | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010390 | 076551C-050-SP-0910-004 | 050-G-DAT-50002-001 | CENTRIFUGAL PUMPS DATA SHEET BAHRAIN / RUBBLE CRUDE OIL INJECTION /TRANSFER PUMP 050P5033A/B/C | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010390 | 076551C-050-SP-0910-009 | 050-G-DAT-50003-001 | CENTRIFUGAL PUMPS DATA SHEET SLOP OIL PUMPS 050P5038A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010391 | 076551C-081-SP-0910-001 | 081-G-DAT-50001-001 | CENTRIFUGAL PUMPS DATA SHEET LSDP FLARE KO DRUM FOR BMP UNITS PUMPS 081P8102 A/B (EX 081-G-DAT-00001-001) | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010392 | 076551C-082-SP-0910-001 | 082-G-DAT-00001-001 | CENTRIFUGAL PUMP DATA SHEET REFINERY SOUTH FLARE MAIN KO DRUM PUMPS 082P0001 A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010392 | 076551C-082-SP-0910-002 | 082-G-DAT-00002-001 | CENTRIFUGAL PUMP DATA SHEET REFINERY SOUTH FLARE SEAL DRUM PUMPS 082P0002 A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010393 | 076551C-079-SP-0910-002 | 079-G-DAT-00002-001 | CENTRIFUGAL PUMPS DATA SHEET SPENT CAUSTIC PUMPS 079P0002 A/B | B | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010394 | 076551C-000R-DL-0910-001 | 000-G-IDL-60003-001 | SCOPE OF SUPPLY FOR OH2 API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010394 | 076551C-000R-ITP-0910-001 | 000-G-ITP-60003-001 | INSPECTION AND TEST PLAN FOR OH2 API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010394 | 076551C-000R-MR-0910-001 | 000-G-MRQ-60003-001 | MATERIAL REQUISITION FOR OH2 API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010394 | 076551C-000R-SP-0910-001 | 000-G-GRD-60003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR OH2 API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010394 | 076551C-000R-SR-0910-001 | 000-G-SOW-60003-001 | SCOPE OF SUPPLY FOR OH2 API 610 PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-008 | 018-G-DAT-00024-001 | CENTRIFUGAL PUMPS DATA SHEET DIESEL PUMPAROUND PUMPS 018P0007A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-009 | 018-G-DAT-00021-001 | CENTRIFUGAL PUMPS DATA SHEET DIESEL PRODUCT PUMPS 018P0008A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-010 | 018-G-DAT-00018-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN BOTTOMS PUMPS 018P0009A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-012 | 018-G-DAT-00033-001 | CENTRIFUGAL PUMPS DATA SHEET MVGO PUMPS 018P0013A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-015 | 018-G-DAT-00023-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM COLUMN BOTTOMS PUMPS 018P0017A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-021 | 018-G-DAT-00020-001 | CENTRIFUGAL PUMPS DATA SHEET SHORT CIRCULATION PUMPS 018P0027A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-022 | 018-G-DAT-00022-001 | CENTRIFUGAL PUMPS DATA SHEET COOLING OIL CIRCULATION PUMPS 018P0025A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-030 | 018-G-DAT-00025-001 | CENTRIFUGAL PUMPS DATA SHEET TEMPERED WATER PUMPS 018P0028A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010395 | 076551C-018-SP-0910-033 | 018-G-DAT-00027-001 | CENTRIFUGAL PUMPS DATA SHEET CUTTER STOCK PUMPS 018P0018A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010396 | 076551C-021-SP-0910-004 | 021-G-DAT-00006-001 | CENTRIFUGAL PUMP DATA SHEET FOR VACUUM DRIER BOTTOMS PUMP 021P0004A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010396 | 076551C-021-SP-0910-007 | 021-G-DAT-00007-001 | CENTRIFUGAL PUMP DATA SHEET FOR LEAN AMINE PUMPS 021P0007A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010397 | 076551C-023-SP-0910-002 | 023-G-DAT-00002-001 | CENTRIFUGAL PUMP DATA SHEET FOR LEAN AMINE PUMPS 023P0002A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010398 | 076551C-050-SP-0910-002 | 050-G-DAT-50004-001 | CENTRIFUGAL PUMPS DATA SHEET KEROSENE PUMP 050P5031 | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010398 | 076551C-050-SP-0910-010 | 050-G-DAT-50005-001 | CENTRIFUGAL PUMPS DATA SHEET 10PPM DIESEL BOOSTER PUMPS ITEM 050P5034A/B | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010399 | 076551C-056-SP-0910-004 | 056-G-DAT-50001-001 | CENTRIFUGAL PUMPS DATA SHEET DIESEL SHIPPING PUMP 056P5606 | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010400 | 076551C-079-CN-0008-002 | 079-A-BOD-00002-001 | MATERIAL SELECTION BASIS SPENT CAUSTIC TREATING UNIT (SCTU) | A | 2018-08-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 1
CON-BMP-TRA-010401 | 076551C-000R-DW-1512-003-001 | 000-J-BLD-60003-001 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW UTILITIES CONTROL BUILDING) | A | 2018-08-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 1
CON-BMP-TRA-010401 | 076551C-000R-DW-1512-003-002 | 000-J-BLD-60003-002 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW UTILITIES CONTROL BUILDING) | A | 2018-08-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 1
CON-BMP-TRA-010401 | 076551C-000R-DW-1512-003-003 | 000-J-BLD-60003-003 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW UTILITIES CONTROL BUILDING) | A | 2018-08-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 1
CON-BMP-TRA-010402 | 076551C-061-CN-0022-001 | 061-J-CAL-50001-001 | HYDRAULIC CALCULATION NOTES SITRA WHARF NOS. 1 AND 2 - UNIT 061 | A | 2018-08-01 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010403 | 076551C-000R-DL-0910-003 | 000-G-IDL-60005-001 | DEVIATION LIST FOR FOR BB1 BB2 AND BB3 PUMPS | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010403 | 076551C-000R-ITP-0910-003 | 000-G-ITP-60005-001 | INSPECTION AND TEST PLAN FOR FOR BB1 BB2 AND BB3 PUMPS | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010403 | 076551C-000R-MR-0910-003 | 000-G-MRQ-60005-001 | MATERIAL REQUISITION FOR BB1 BB2 AND BB3 PUMPS | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010403 | 076551C-000R-SP-0910-003 | 000-G-GRD-60005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FOR BB1 BB2 AND BB3 PUMPS | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010403 | 076551C-000R-SR-0910-003 | 000-G-SOW-60005-001 | SCOPE OF SUPPLY FOR FOR BB1 BB2 AND BB3 PUMPS | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-010404 | 076551C-000R-TBT-0110-003 | 000-F-TBE-60002-001 | TECHNICAL BID EVALUATION FOR 3HDU FIRED HEATER 021F0001 COMBINED FEED HEATER | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director |  | 1 - APPROVED | 2018-08-10 | CLASS 2
CON-BMP-TRA-010405 | 076551C-000R-TBT-0846-001 | 000-S-TBE-60002-001 | TECHNICAL BID EVALUATION FOR FEED FILTERS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010406 | 076551C-000R-TBT-0960-001 | 000-G-TBE-60002-001 | TECHNICAL BID EVALUATION FOR EBULLATING PUMPS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-010407 | ROC-BMR-MOM-000043 | 000-A-MOM-60031-001 | ROC 15 TH WEEKLY PROGRESS MEETING | 0 | 2018-07-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010408 | 076551C-051-DW-0051-002-001 | 051-A-PPN-00001-001 | GENERAL PLOT PLAN 051 C3 C4 LPG STORAGE FACILITY AT WHARF | A | 2018-08-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 1
CON-BMP-TRA-010408 | 076551C-051-DW-0051-002-002 | 051-A-PPN-00001-002 | GENERAL PLOT PLAN 051 C3 C4 LPG STORAGE FACILITY AT WHARF | A | 2018-08-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 1
CON-BMP-TRA-010409 | ROC-BMR-MOM-000009 | 000-A-MOM-60032-001 | UNIT C021 - 3HDU AND UNIT C023 - 1HRU P&IDS REVIEW MEETING | 1 | 2018-08-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010410 | 076551C-018-SP-0910-026 | 018-G-DAT-00030-001 | CENTRIFUGAL PUMPS DATA SHEET AMINE SUMP PUMPS 018P0031A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010410 | 076551C-018-SP-0910-027 | 018-G-DAT-00031-001 | CENTRIFUGAL PUMPS DATA SHEET SOUR WATER SUMP PUMPS 018P0030A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010410 | 076551C-018-SP-0910-028 | 018-G-DAT-00029-001 | CENTRIFUGAL PUMPS DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMPS 018P0032A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010411 | 076551C-021-SP-0910-009 | 021-G-DAT-00008-001 | CENTRIFUGAL PUMP DATA SHEET FOR RECOVERED PROCESS OIL SUMP PUMPS 021P0009A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010411 | 076551C-021-SP-0910-010 | 021-G-DAT-00009-001 | CENTRIFUGAL PUMP DATA SHEET FOR AMINE SUMP PUMPS 021P0010A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010411 | 076551C-021-SP-0910-012 | 021-G-DAT-00010-001 | CENTRIFUGAL PUMP DATA SHEET FOR SOUR WATER SUMP PUMPS 021P0011A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-010412 | 076551C-051-SP-0910-007 | 051-G-DAT-00001-001 | CENTRIFUGAL PUMPS DATA SHEET PROPANE RUNDOWN PUMP 051P0004A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010413 | 076551C-056-SP-0910-001 | 056-G-DAT-50004-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA SHIPPING PUMP 056P5603 | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010413 | 076551C-056-SP-0910-002 | 056-G-DAT-50002-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA KERO CRUDE SHIPPING PUMP 056P5605 | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010413 | 076551C-056-SP-0910-003 | 056-G-DAT-50003-001 | CENTRIFUGAL PUMPS DATA SHEET KERO SHIPPING PUMP 056P5604 | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010414 | 076551C-061-SP-0910-001 | 061-G-DAT-50001-001 | CENTRIFUGAL PUMPS DATA SHEET SLOP DRAIN PUMP 061P6111A/B - 061P6112A/B - 061P6113A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010415 | 076551C-079-SP-0910-001 | 079-G-DAT-00001-001 | CENTRIFUGAL PUMPS DATA SHEET SPENT CAUSTIC CLOSED DRAIN PUMPS 079P0001 A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010416 | 076551C-372-SP-0910-001 | 372-G-DAT-50002-001 | CENTRIFUGAL PUMP DATA SHEET HG CONDENSATE TRANSFER PUMPS 372P3745 A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010416 | 076551C-372-SP-0910-002 | 372-G-DAT-50001-001 | CENTRIFUGAL PUMP DATA SHEET LG CONDENSATE TRANSFER PUMPS 372P3733 A/B | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010417 | 076551C-005-NM-1300-012 | 005-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010418 | 076551C-056-NM-1300-012 | 056-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010419 | 076551C-058-NM-1300-012 | 058-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010420 | 076551C-079-NM-1300-012 | 079-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010421 | 076551C-930-NM-1300-012 | 930-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010422 | 076551C-933-NM-1300-012 | 933-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010423 | 076551C-000R-DL-0910-006 | 000-G-IDL-60007-001 | DEVIATION LIST FOR VERTICAL PUMPS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010423 | 076551C-000R-ITP-0910-006 | 000-G-ITP-60007-001 | INSPECTION AND TEST PLAN FOR VERTICAL PUMPS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010423 | 076551C-000R-MR-0910-006 | 000-G-MRQ-60007-001 | MATERIAL REQUISITION FOR VERTICAL PUMPS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010423 | 076551C-000R-SP-0910-006 | 000-G-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR VERTICAL PUMPS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010423 | 076551C-000R-SR-0910-006 | 000-G-SOW-60007-001 | SCOPE OF SUPPLY FOR VERTICAL PUMPS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010424 | 076551C-050-NM-0004-001 | 050-T-CAL-50001-001 | CATALYST & CHEMICAL COMPTION SUMMARY - UNIT 050 - REFINERY TANK FARM | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010425 | 076551C-930-DW-0053-003-001 | 930-A-PPN-00003-001 | 3D MODEL WBS DESIGN AREAS KEY PLAN UNIT930 PIPE RACK INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010425 | 076551C-930-DW-0053-003-002 | 930-A-PPN-00003-002 | 3D MODEL WBS DESIGN AREAS KEY PLAN UNIT930 PIPE RACK INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010425 | 076551C-930-DW-0053-004-001 | 930-A-PPN-00002-001 | 3D MODEL WBS DESIGN AREAS KEY PLAN UNIT930 INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010426 | 076551C-050-NM-0003-001 | 050-A-CAL-50001-001 | UTILITY CONSUMTION SUMMARY (16) UNIT 050 - REFINERY TANK FARM | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010427 | 076551C-933-DW-0053-003-001 | 933-A-PPN-00003-001 | 3D MODEL WBS DESIGN AREAS KEY PLAN UNIT933 INTERCONNECTING FOR REVAMPING AREA | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010428 | 076551C-000R-DL-0811-004 | 000-C-IDL-60010-001 | DEVIATION LIST FOR LARGE CARBON STEEL PRESSURE VESSELS | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010428 | 076551C-000R-ITP-0811-004 | 000-C-ITP-60010-001 | INSPECTION AND TEST PLAN (ITP) FOR LARGE CARBON STEEL PRESSURE VESSELS | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010428 | 076551C-000R-MR-0811-004 | 000-C-MRQ-60010-001 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010428 | 076551C-000R-SP-0811-004 | 000-C-GRD-60010-001 | PARTICULAR TECHNICAL SPECIFICATION FOR LARGE CARBON STEEL PRESSURE VESSELS | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010428 | 076551C-000R-SR-0811-004 | 000-C-SOW-60010-001 | SCOPE OF SUPPLY FOR LARGE CARBON STEEL PRESSURE VESSELS | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-010429 | 076551C-000R-TBT-4111-002 | 000-S-TBE-60008-001 | TECHNICAL BID EVALUATION FOR PSA PACKAGE | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-010430 | 076551C-371-SP-0910-001 | 371-G-DAT-50001-001 | CENTRIFUGAL PUMP DATA SHEET 20 PSIG EXCESS STEAM CONDENSATE PUMPS 371P3701 A/B | B | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010431 | 076551C-000R-DL-0910-002 | 000-G-IDL-60004-001 | DEVIATION LIST FOR ASME PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010431 | 076551C-000R-ITP-0910-002 | 000-G-ITP-60004-001 | INSPECTION AND TEST PLAN FOR ASME PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010431 | 076551C-000R-MR-0910-002 | 000-G-MRQ-60004-001 | MATERIAL REQUISITION FOR ASME PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010431 | 076551C-000R-SP-0910-002 | 000-G-GRD-60004-001 | PARTICULA TECHNICAL SPECIFICATION FOR ASME PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010431 | 076551C-000R-SR-0910-002 | 000-G-SOW-60004-001 | SCOPE OF SUPPLY FOR ASME PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010432 | 076551C-058-NM-0003-001 | 058-A-CAL-50002-001 | UTILITY CONSUMPTION SUMMARY UNIT 058 - FUEL GAS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010433 | 076551C-018-NM-0051-001 | 018-L-INX-00002-001 | BATTERY LIMIT INTERFACE TABLE | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-010434 | 076551C-023-NM-0003-001 | 023-A-CAL-00003-001 | UTILITY CONSUMPTION SUMMARY | A | 2018-08-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-23 | CLASS 1
CON-BMP-TRA-010435 | 076551C-000R-DL-0811-003 | 000-C-IDL-60003-001 | DEVIATION LIST FOR CARBON STEEL PRESSURE VESSELS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-28 | CLASS 2
CON-BMP-TRA-010435 | 076551C-000R-ITP-0811-003 | 000-C-ITP-60003-001 | INSPECTION AND TEST PLAN FOR CARBON STEEL PRESSURE VESSELS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-28 | CLASS 2
CON-BMP-TRA-010435 | 076551C-000R-MR-0811-003 | 000-C-MRQ-60003-001 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-28 | CLASS 2
CON-BMP-TRA-010435 | 076551C-000R-SP-0811-003 | 000-C-GRD-60003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CARBON STEEL PRESSURE VESSELS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-28 | CLASS 2
CON-BMP-TRA-010435 | 076551C-000R-SR-0811-003 | 000-C-SOW-60003-001 | SCOPE OF SUPPLY FOR CARBON STEEL PRESSURE VESSELS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-28 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-001 | 018-C-DAT-00090-001 | DATA SHEET FOR 018V0045A/B CIRCULATION OIL FILTERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-002 | 018-C-DAT-00091-001 | DATA SHEET FOR 018V0048A/B CATALYST SLOP OIL FILTERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-003 | 018-C-DAT-00092-001 | DATA SHEET FOR 018V0046 EMERGENCY QUENCH OIL FILTER | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-004 | 018-C-DAT-00093-001 | DATA SHEET FOR 018V1015A/B TRAIN 1 FEED PUMP STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-005 | 018-C-DAT-00094-001 | DATA SHEET FOR 018V1019A/B TRAIN 1 PURGE HYDROGEN FILTERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-006 | 018-C-DAT-00095-001 | DATA SHEET FOR 018V0051A/B SHORT CIRCULATION FILTERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-009 | 018-C-DAT-00096-001 | DATA SHEET FOR 018V0012A/B ATMOSPHERIC COLUMN BOTTOMS STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-010 | 018-C-DAT-00097-001 | DATA SHEET FOR 018V0016A/B MVGO CIRCULATING REFLUX STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-011 | 018-C-DAT-00098-001 | DATA SHEET FOR 018V0017A/B MVGO PUMPBACK STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-012 | 018-C-DAT-00099-001 | DATA SHEET FOR 018V0019A/B SECOND STAGE WASH OIL STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-013 | 018-C-DAT-00100-001 | DATA SHEET FOR 018V0020A/B FIRST STAGE WASH OIL STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-014 | 018-C-DAT-00101-001 | DATA SHEET FOR 018V0021A/B WASH OIL PUMP SUCTION STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-015 | 018-C-DAT-00102-001 | DATA SHEET FOR 018V0022A/B VACUUM COLUMN BOTTOMS STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-016 | 018-C-DAT-00103-001 | DATA SHEET FOR 018V0025A/B TRAIN 2 FEED PUMP STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-017 | 018-C-DAT-00104-001 | DATA SHEET FOR 018V2019A/B TRAIN 2 PURGE HYDROGEN FILTERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-020 | 018-C-DAT-00105-001 | DATA SHEET FOR 018V0005A/B QUENCH OIL PUMP STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-021 | 018-C-DAT-00106-001 | DATA SHEET FOR 018V0026A/B LEAN AMINE PUMP STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-022 | 018-C-DAT-00107-001 | DATA SHEET FOR 018V0015A/B LVGO CIRCULATING REFLUX STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-023 | 018-C-DAT-00108-001 | DATA SHEET FOR 018V0018A/B HVGO CIRCULATING REFLUX STRAINERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010436 | 076551C-018-SP-0841-025 | 018-C-DAT-00109-001 | DATA SHEET FOR 018V0062 FLUSHING OIL FILTER | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010437 | 076551C-079-SP-0910-002 | 079-G-DAT-00002-001 | CENTRIFUGAL PUMPS DATA SHEET SPENT CAUSTIC PUMPS 079P0002A/B | C | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010438 | 076551C-023-SP-0841-001 | 023-C-DAT-00007-01 | DATA SHEET FOR 023V0006 1HRU PSA PRODUCT FILTER | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-28 | CLASS 2
CON-BMP-TRA-010439 | 076551C-056-SP-0841-001 | 056-C-DAT-50001-001 | DATA SHEET FOR 056V5601A/B KEROSENE FILTERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010440 | 076551C-061-SP-0841-001 | 061-C-DAT-50003-001 | DATA SHEET FOR 061V6101A/B KEROSENE SEALINE FILTERS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010441 | 076551C-021-DW-0051-002-001 | 021-A-PPN-00002-001 | GENERAL PLOT PLAN NO. 3 HDU-HYDRODESULPHURIZATION UNIT NO.1 HRU-HYDROGEN RECOVERY UNIT (EX 021-L-PPN-00001-001) | B | 2018-08-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 1
CON-BMP-TRA-010442 | 076551C-018-SP-0920-003 | 018-G-DAT-00034-001 | RECIPROCATING PUMPS DATA SHEET CATALYST TRANSPORT OIL PUMPS 018P0024A/B | B | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-010442 | 076551C-018-SP-0920-004 | 018-G-DAT-00037-001 | RECIPROCATING PUMPS DATA SHEET HOT PURGE OIL PUMPS 018P0029A/B | B | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-010443 | 076551C-371-CN-0008-002 | 371-A-BOD-50002-001 | MATERIAL SELECTION BASIS STEAM GENERATION AND DISTRIBUTION | A | 2018-08-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 1
CON-BMP-TRA-010444 | 076551C-000R-DL-0920-001 | 000-G-IDL-60011-001 | DEVIATION LIST FOR RECIPROCATING PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010444 | 076551C-000R-ITP-0920-001 | 000-G-ITP-60011-001 | INSPECTION AND TEST PLAN FOR RECIPROCATING PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010444 | 076551C-000R-MR-0920-001 | 000-G-MRQ-60011-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010444 | 076551C-000R-SP-0920-001 | 000-G-GRD-60011-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010444 | 076551C-000R-SR-0920-001 | 000-G-SOW-60011-001 | SCOPE OF SUPPLY FOR RECIPROCATING PUMPS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010445 | 076551C-021-NM-1551-001 | 021-J-INX-00001-001 | INSTRUMENT INDEX REPORT UNIT 021 | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-28 | CLASS 1
CON-BMP-TRA-010446 | 076551C-023-NM-1551-001 | 023-J-INX-00001-001 | INSTRUMENT INDEX REPORT UNIT 023 | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-29 | CLASS 1
CON-BMP-TRA-010448 | 076551C-058-DW-0051-002-001 | 058-A-PPN-50001-001 | GENERAL PLOT PLAN REFINERY FUEL GAS SYSTEM | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-26 | CLASS 1
CON-BMP-TRA-010449 | 076551C-930-DW-0051-002-001 | 930-A-PPN-00001-001 | GENERAL PLOT PLAN UNIT 930 INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 4 - NOT APPROVED | 2018-08-23 | CLASS 1
CON-BMP-TRA-010449 | 076551C-930-DW-0051-002-002 | 930-A-PPN-00001-002 | GENERAL PLOT PLAN UNIT 930 INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 4 - NOT APPROVED | 2018-08-23 | CLASS 1
CON-BMP-TRA-010449 | 076551C-930-DW-0051-002-003 | 930-A-PPN-00001-003 | GENERAL PLOT PLAN UNIT 930 INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 4 - NOT APPROVED | 2018-08-23 | CLASS 1
CON-BMP-TRA-010449-REV.1 | 076551C-930-DW-0051-002-001 | 930-A-PPN-00001-001 | GENERAL PLOT PLAN UNIT 930 INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-010449-REV.1 | 076551C-930-DW-0051-002-002 | 930-A-PPN-00001-002 | GENERAL PLOT PLAN UNIT 930 INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-010449-REV.1 | 076551C-930-DW-0051-002-003 | 930-A-PPN-00001-003 | GENERAL PLOT PLAN UNIT 930 INTERCONNECTING FOR BMP NEW UNIT | A | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-010450 | 076551C-018-DW-0051-002-001 | 018-A-PPN-00005-001 | GENERAL PLOT PLAN NO.1 RHCU RESIDUE HYDROCRACKING UNIT (EX-018-L-PPN-00001-001) | B | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 1
CON-BMP-TRA-010450 | 076551C-018-DW-0051-002-002 | 018-A-PPN-00005-002 | GENERAL PLOT PLAN NO.1 RHCU RESIDUE HYDROCRACKING UNIT (EX 018-L-PPN-00001-002) | B | 2018-08-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 1
CON-BMP-TRA-010451 | 076551C-000R-TBT-0110-001 | 000-F-TBE-60001-001 | TECHNICAL BID EVALUATION FOR 1RHCU FIRED HEATERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-001 | 930-S-GAD-00001-001 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 1 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-002 | 930-S-GAD-00001-002 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 2 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-003 | 930-S-GAD-00001-003 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 3 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-004 | 930-S-GAD-00001-004 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 4 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-005 | 930-S-GAD-00001-005 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 5 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-006 | 930-S-GAD-00001-006 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 6 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-007 | 930-S-GAD-00001-007 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 7 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-008 | 930-S-GAD-00001-008 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 8 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010452 | 076551C-930-DW-1442-001-009 | 930-S-GAD-00001-009 | GENERAL UNDER GROUND SERVICES INTERCONNECTING SYSTEMS AREA 9 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-010453 | 076551C-023-NM-1511-001 | 023-J-INX-00002-001 | IN/OUT LIST SUMMARY UNIT 023 | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-19 | CLASS 1
CON-BMP-TRA-010454 | 076551C-058-NM-1511-001 | 058-J-INX-50002-001 | IN/OUT LIST SUMMARY UNIT 058 | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 1
CON-BMP-TRA-010455 | 076551C-005-NM-1551-001 | 005-J-INX-50001-001 | INSTRUMENT INDEX REPORT UNIT 005 | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 1
CON-BMP-TRA-010456 | 076551C-056-NM-1551-001 | 056-J-INX-50001-001 | INSTRUMENT INDEX REPORT UNIT 005 | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 1
CON-BMP-TRA-010457 | 076551C-058-NM-1551-001 | 058-J-INX-50001-001 | INSTRUMENT INDEX REPORT UNIT 058 | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 1
CON-BMP-TRA-010458 | 076551C-051-DW-1442-001-001 | 051-S-GAD-00001-001 | GENERAL UNDERGROUND NETWORKS 051 - C3/C4 LPG STORAGE FACILITY MAJOR U/G | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010459 | 076551C-021-PID-1931-515-001 | 021-A-PID-00055-001 | PIPING AND INSTRUMENT DIAGRAM - 3HDU FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010460 | 076551C-930-PID-1931-501-001 | 930-A-PID-01001-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010460 | 076551C-930-PID-1931-502-001 | 930-A-PID-01002-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010460 | 076551C-930-PID-1931-503-001 | 930-A-PID-01003-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010460 | 076551C-930-PID-1931-504-001 | 930-A-PID-01004-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010460 | 076551C-930-PID-1931-505-001 | 930-A-PID-01005-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010460 | 076551C-930-PID-1931-506-001 | 930-A-PID-01006-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010460 | 076551C-930-PID-1931-507-001 | 930-A-PID-01007-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010460-REV.1 | 076551C-930-PID-1931-501-001 | 930-A-PID-01001-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-010460-REV.1 | 076551C-930-PID-1931-502-001 | 930-A-PID-01002-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-010460-REV.1 | 076551C-930-PID-1931-503-001 | 930-A-PID-01003-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-010460-REV.1 | 076551C-930-PID-1931-504-001 | 930-A-PID-01004-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-010460-REV.1 | 076551C-930-PID-1931-505-001 | 930-A-PID-01005-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-010460-REV.1 | 076551C-930-PID-1931-506-001 | 930-A-PID-01006-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-010460-REV.1 | 076551C-930-PID-1931-507-001 | 930-A-PID-01007-001 | PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING FOR BMP NEW UNITS FIRE FIGHTING SYSTEM | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-010461 | 076551C-018-DW-1933-001-001 | 018-S-GAD-00002-001 | FIREFIGHTING LAYOUT 018 - NO. 1 RESIDUE HYDROCRACKING UNIT | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 |  |  | CLASS 2
CON-BMP-TRA-010461 | 076551C-018-DW-1933-001-002 | 018-S-GAD-00002-002 | FIREFIGHTING LAYOUT 018 - NO. 1 RESIDUE HYDROCRACKING UNIT | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 |  |  | CLASS 2
CON-BMP-TRA-010462 | 076551C-021-NM-0003-001 | 021-A-CAL-00003-001 | UTILITY CONSUMPTION SUMMARY | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-31 |  |  | CLASS 1
CON-BMP-TRA-010463 | 076551C-005-NM-1511-001 | 005-J-INX-50002-001 | IN/OUT LIST SUMMARY UNIT 005 | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 1
CON-BMP-TRA-010464 | 076551C-056-NM-1511-001 | 056-J-INX-50002-001 | IN/OUT LIST SUMMARY UNIT 056 | A | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 1
CON-BMP-TRA-010465 | 076551C-018-DW-1572-001-001 | 018-J-CRD-00001-001 | INSTRUMENT MAIN CABLE ROUTING NO. 1 RESIDUE HYDROCRATING UNIT - 1RHCU | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010465 | 076551C-018-DW-1572-001-002 | 018-J-CRD-00001-002 | INSTRUMENT MAIN CABLE ROUTING NO. 1 RESIDUE HYDROCRATING UNIT - 1RHCU | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010466 | 076551C-021-DW-1572-001-001 | 021-J-CRD-00001-001 | INSTRUMENT MAIN CABLE ROUTING NO. 3 HYDROGEN RECOVERY UINT - 3HDU NO.1 HYDOGEN RECOVERY UNIT - 1HRU | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010467 | 076551C-007-NM-1300-012 | 007-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010468 | 076551C-038-NM-1300-012 | 038-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010469 | 076551C-050-NM-1300-012 | 050-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010470 | 076551C-062-NM-1300-012 | 062-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010471 | 076551C-070-NM-1300-012 | 070-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010472 | 076551C-073-NM-1300-012 | 073-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010473 | 076551C-076-NM-1300-012 | 076-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010474 | 076551C-077-NM-1300-012 | 077-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010475 | 076551C-078-NM-1300-012 | 078-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010476 | 076551C-087-NM-1300-012 | 087-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010477 | 076551C-093-NM-1300-012 | 093-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-26 | CLASS 2
CON-BMP-TRA-010478 | 076551C-180-NM-1300-012 | 180-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010479 | 076551C-907-NM-1300-012 | 907-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010480 | 076551C-050-NM-1601-001 | 050-P-INX-50001-001 | ELECTRICAL CONSUMERS LIST UNIT 050 REFINERY TANK FARM | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010481 | 076551C-930-CN-1441-001 | 930-S-CAL-00001-001 | HYDRAULIC CALCULATION FOR CONTAMINATED STORM WATER SEWER SYSTEM (CSS) UNIT 930 INTERCONNECTING SYSTEMS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-010482 | 076551C-018-SP-0410-001 | 018-C-DAT-00078-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 018C1001R TRAIN1 1ST REACTOR | 0A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-010483 | 076551C-000R-TBT-0570-001 | 000-C-TBE-60007-001 | TECHNICAL BID EVALUATIONS FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-01 |  |  | CLASS 2
CON-BMP-TRA-010484 | 076551C-021-DW-1652-002-001 | 021-P-SLD-00001-001 | SINGLE LINE DIAGRAM NO 3 HDU/NO 1 HRU SUBSTATION 021SSTR01 | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-010485 | 076551C-018-DW-1652-002-001 | 018-P-SLD-00001-001 | SINGLE LINE DIAGRAM 1RHCU SUBSTATION 018SSTR01 | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-010486 | 076551C-021-DW-1622-001-001 | 021-P-CRD-00001-001 | ELECTRICALCABLES TRENCH LAYOUT NO 3 HYDRODESULPHURIZATION UNIT 3HDU NO 1 HYDROGEN RECOVERY UNIT 1HRU | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-010487 | 076551C-021-DW-1625-001-001 | 021-P-GAD-00300-001 | SUBSTATION EQUIPMENT LAYOUT UNIT 021 NO 3 HDU / UNIT 23 NO 1 HRUSUBSTATION 021SSTR1 | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-010488 | 076551C-051-DW-1933-001-001 | 051-S-GAD-00002-001 | FIREFIGHTING LAYOUT 051 - REFRIGERATED LPG C3/C4 STORAGE FACILITY AT WHARF | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-001 | 000-J-BLD-60001-001 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-002 | 000-J-BLD-60001-002 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-003 | 000-J-BLD-60001-003 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-004 | 000-J-BLD-60001-004 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-005 | 000-J-BLD-60001-005 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-006 | 000-J-BLD-60001-006 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-007 | 000-J-BLD-60001-007 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-008 | 000-J-BLD-60001-008 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-009 | 000-J-BLD-60001-009 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-010 | 000-J-BLD-60001-0010 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010489 | 076551C-000R-DW-1512-001-011 | 000-J-BLD-60001-0011 | INSTRUMENT BLOCK DIAGRAM CTRL AND SAFETY SYSTEM BLOCK DIAGRAM (NEW REFINERY SOUTH CTRL BUILDING) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010490 | ROC-BMR-MOM-000028 | 000-A-MOM-60033-001 | UNIT 021 - NO. 3 HYDRODESULPHURIZATION UNIT - 3HDU P&IDS IBD REVIEW MEETING | 0 | 2018-08-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010491 | 076551C-000R-RT-6200-002 | 000-A-RPT-60001-001 | FEED ESIA IMPLEMENTATION REPORT | B | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-010492 | 076551C-018-NM-0003-001 | 018-A-CAL-00002-001 | UTILITY CONSUMPTION SUMMARY - 018 - NO. 1 RESIDUE HYDROCRACKING UNIT (1RHCU) | A | 2018-08-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-05 |  |  | CLASS 1
CON-BMP-TRA-010493 | 076551C-056-NM-1601-001 | 056-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST SITRA TANK FARM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-010494 | 076551C-000R-TBT-0851-001 | 000-H-TBE-60001-001 | TECHNICAL BID EVALUATIONS FOR VACUUM UNIT PACKAGE | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-010495 | 076551C-018-CN-1901-004 | 018-A-CAL-00001-001 | FIREPROOFING SCHEDULE NO 1 RESIDUE HYDROCRACKING UNIT - 1RHCU | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-010496 | 076551C-021-SP-4046-001 | 021-S-DAT-00005-001 | DESIGN SPECIFICATION SHEET FOR 021U0005 PHOSPHATE INJECTION PACKAGE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-010496 | 076551C-021-SP-4046-002 | 021-S-DAT-00004-001 | DESIGN SPECIFICATION SHEET FOR 021U0004 INHIBITOR INJECTION PACKAGE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-010496 | 076551C-021-SP-4046-003 | 021-S-DAT-00003-001 | DESIGN SPECIFICATION SHEET FOR 021U0006 ANTISTATIC ADDITIVE PACKAGE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-010496 | 076551C-021-SP-4046-004 | 021-S-DAT-00002-001 | DESIGN SPECIFICATION SHEET FOR 021U0003 ANTIFOAM INJECTION PACKAGE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-010497 | 076551C-051-SP-1030-001 | 051-K-DAT-00002-001 | DATA SHEET FOR ROTARY-TYPE POSITIVE-DISPLACEMENT COMPRESSOR FOR 051U0003AB COMPRESSED AIR PACKAGES | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-010498 | ROC-BMR-MOM-000041 | 000-A-MOM-60034-001 | UNIT 056 - SITRA TANK FARM P&IDS IBD REVIEW MEETING | 0 | 2018-08-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010499 | ROC-BMR-MOM-000042 | 000-A-MOM-60035-001 | UNIT 061 - SITRA WHARF P&IDS IBD REVIEW MEETING | 0 | 2018-08-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010500 | 076551C-907-CN-1735-001 | 907-Q-CAL-50001-001 | FOUNDATION CALCULATION REPORT FOR BOX CULVERT N 1 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-010501 | 076551C-907-DW-1745-001 | 907-Q-GAD-50001-001 | BOX CULVERT N 1 PLAN AND VIEW FORMWORK AND REINFORCEMENT | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-010502 | 076551C-018-NM-1551-001 | 018-J-INX-00001-001 | INSTRUMENT INDEX REPORT UNIT 018 | A | 2018-08-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-07 |  |  | CLASS 1
CON-BMP-TRA-010503 | 076551C-050-DW-1572-001-001 | 050-J-CRD-50001-001 | INSTRUMENT MAIN CABLE ROUTING 050 - REFINERY TANK FARM | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-010504 | 076551C-018-DW-1625-001-001 | 018-P-GAD-00300-001 | SUBSTATION EQUIPMENT LAYOUT 018 NO 1 RESIDUE HYDROCRACKING UNIT SUBSTATION 018SSTR1 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-010505 | 076551C-000R-DW-1431-003-001 | 000-Q-PED-60001-001 | TRIAL PILES TO GEOTECHNICAL FAILURE TEST LOADS AND PILES LOCATION | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-010506 | 076551C-018-NM-1601-001 | 018-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST NO 1 RESIDUE HYDROCRACKING UNIT - 1RHCU | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-010507 | 076551C-021-NM-1601-001 | 021-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST NO 3 HYDRODESULPHURIZATION UNIT - 3HDU | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-010508 | 076551C-023-NM-1601-001 | 023-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST NO 1 HYDROGEN RECOVERY UNIT - 1HRU | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-010509 | 076551C-018-PID-1931-518-001 | 018-A-PID-00106-001 | P AND ID - 1RHCU FIRE FIGHTING SYSTEM | A | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-010510 | 076551C-058-DW-1980-001-001 | 058-A-GAD-50001-001 | FIRE EXPOSED ENVELOPE AND FIREPROOFING LIMITS 058 REFINERY GAS SYSTEM | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-010511 | 076551C-082-DW-1980-001-001 | 082-A-GAD-00001-001 | FIRE EXPOSED ENVELOPE AND FIREPROOFING LIMITS 082 REFINERY SOUTH FLARE 081 LSDP FLARE AREA | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-010512 | 076551C-051-DW-1980-001-001 | 051-A-GAD-00001-001 | FIRE EXPOSED ENVELOPE AND FIREPROOFING LIMITS 051 REFRIGERATED LPG C3/C4 STORAGE FACILITY AT WHARF | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-010512 | 076551C-051-DW-1980-001-002 | 051-A-GAD-00001-002 | FIRE EXPOSED ENVELOPE AND FIREPROOFING LIMITS 051 REFRIGERATED LPG C3/C4 STORAGE FACILITY AT WHARF | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-010513 | 076551C-371-CN-0007-001 | 371-A-BOD-50001-001 | PROCESS DESIGN BASIS STEAM GENERATION & DISTRIBUTION | B | 2018-08-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-11 |  |  | CLASS 1
CON-BMP-TRA-010514 | ROC-BMR-MOM-000049 | 000-A-MOM-60036-001 | TTSJV/BAPCO E&S PLANS STATUS REVIEW | 0 | 2018-08-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010515 | 076551C-018-DW-1622-001-001 | 018-P-CRD-00001-001 | ELECTRICAL MAIN CABLE ROUTING NO 1 RESIDUE HYDROCRACKING UNIT 1RHCU | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-010515 | 076551C-018-DW-1622-001-002 | 018-P-CRD-00001-002 | ELECTRICAL MAIN CABLE ROUTING NO 1 RESIDUE HYDROCRACKING UNIT 1RHCU | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-010516 | 076551C-058-DW-1442-001-001 | 058-S-GAD-50002-001 | GENERAL UNDERGROUND SERVICES | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-010517 | 076551C-061-RT-201 | 061-A-RPT-50001-001 | WHARF INTERIM PERIOD CONCEPTUAL STUDY | A | 2018-08-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-12 |  |  | CLASS 1
CON-BMP-TRA-010518 | 076551C-018-NM-1511-001 | 018-J-INX-00002-001 | IN/OUT LIST SUMMARY UNIT 018 | A | 2018-08-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-12 |  |  | CLASS 1
CON-BMP-TRA-010519 | 076551C-000R-RT-6200-004 | 000-A-RPT-60004-001 | SOCIAL IMPACT ASSESSMENT (SIA) REPORT | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-010519 | 076551C-000R-RT-6200-006 | 000-A-RPT-60006-001 | DETERMINATION OF CRITICAL HABITATS REPORT | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-010519 | 076551C-000R-RT-6200-007 | 000-A-RPT-60007-001 | CRITICAL HABITATS ASSESSMENT (CHA) REPORT | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-010520 | 076551C-022-NM-1300-012 | 022-L-INX-50002-001 | CONSTRUCTION LINE LIST | A | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-010521 | 076551C-015-NM-1300-012 | 015-L-INX-50002-001 | CONSTRUCTION LINE LIST | A | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-010522 | 076551C-051-NM-1300-012 | 051-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-010523 | 076551C-061-NM-1300-012 | 061-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-010524 | ROC-BMR-MOM-000037 | 000-A-MOM-60037-001 | UNIT 079 SPENT CAUSTIC TREATING UNIT - P&IDS IBD REVIEW MEETING | 0 | 2018-08-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010525 | ROC-BMR-MOM-000046 | 000-A-MOM-60038-001 | TTSJVROC/BAPCO WEEKLY MEETING INT. U&O 11 | 0 | 2018-08-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010525 | ROC-BMR-MOM-000047 | 000-A-MOM-60039-001 | TTSJVROC/BAPCO WEEKLY MEETING INT. U&O 12 | 0 | 2018-08-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010525 | ROC-BMR-MOM-000048 | 000-A-MOM-60040-001 | TTSJVROC/BAPCO WEEKLY MEETING INT. U&O 13 | 0 | 2018-08-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010525 | ROC-BMR-MOM-000050 | 000-A-MOM-60041-001 | TTSJVROC/BAPCO WEEKLY MEETING INT. U&O 14 | 0 | 2018-08-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010526 | 076551C-018-ML-222 | 018-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) UNIT 018 1RHCU | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-010527 | 076551C-058-DW-1452-001-001 | 058-S-GAD-50003-001 | GRADING AND UNDERGROUD AND FOUND PLAN AREA-1 (OSBL KHUFF - GAS AREA) | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-010528 | 076551C-058-DW-1745-004-001 | 058-Q-GAD-50001-001 | BOX CULVERT N 1 PLAN AND VIEW FORMWORK AND REINFORCEMENT | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-010529 | 076551C-051-SP-0180-001 | 051-F-DAT-00001-001 | DATA SHEET FOR FLARE PACKAGE 051U00001 A/B REFRIGERATED LPG STORAGE FLARE PACKAGE | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-010530 | 076551C-018-CN-0007-001 | 018-A-BOD-00001-001 | BASIS OF DESIGN 1RHCU (UNIT 018) RESIDUE HYDROCRACKING UNIT | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-14 |  |  | CLASS 1
CON-BMP-TRA-010531 | 076551C-021-CN-0007-001 | 021-A-BOD-00001-001 | BASIS OF DESIGN 3HDU (UNIT 021) HYDRODESULPHURIZATIN UNIT | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-14 |  |  | CLASS 1
CON-BMP-TRA-010532 | 076551C-051-DW-1920-001-001 | 051-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION PLAN REFRIGERATED LPG C3/C4 STORAGE FACILITY | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010532 | 076551C-051-DW-1920-002-001 | 051-P-HAC-00002-001 | HAZARDOUS AREA CLASSIFICATION SECTION REFRIGERATED LPG C3/C4 STORAGE FACILITY | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010533 | 076551C-061-DW-0051-002-001 | 061-A-PPN-50001-001 | GENERAL PLOT PLAN SITRA WHARF TRASFER LINE | A | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-010533 | 076551C-061-DW-0051-002-002 | 061-A-PPN-50001-002 | GENERAL PLOT PLAN SITRA WHARF TRASFER LINE | A | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-010533 | 076551C-061-DW-0051-002-003 | 061-A-PPN-50001-003 | GENERAL PLOT PLAN SITRA WHARF TRASFER LINE | A | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-010533 | 076551C-061-DW-0051-002-004 | 061-A-PPN-50001-004 | GENERAL PLOT PLAN SITRA WHARF TRASFER LINE | A | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-010534 | 076551C-000R-DL-0841-002 | 000-C-IDL-60009-001 | DEVIATION LIST FOR COALESCERS | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010534 | 076551C-000R-ITP-0841-002 | 000-C-ITP-60009-001 | INSPECTION AND TEST PLAN FOR COALESCERS | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010534 | 076551C-000R-MR-0841-002 | 000-C-MRQ-60009-001 | MATERIAL REQUISITION FOR COALESCERS | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010534 | 076551C-000R-SP-0841-002 | 000-C-GRD-60009-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR COALESCERS | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010534 | 076551C-000R-SR-0841-002 | 000-C-SOW-60009-001 | SCOPE OF SUPPLY FOR COALESCERS | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010535 | 076551C-018-SP-4046-001 | 018-S-DAT-00002-001 | DESIGN SPECIFICATION SHEET FOR 018U0003 ANTIFOAM INJECTION PACKAGE | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010535 | 076551C-018-SP-4046-002 | 018-S-DAT-00003-001 | DESIGN SPECIFICATION SHEET FOR 018U0004 PHOSPHATE INJECTION PACKAGE | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010536 | 076551C-018-CN-0009-003 | 018-A-BOD-00002-001 | SEQUENCE AND SPECIAL CONTROL NO 1 RESIDUE HYDROCRACKING UNIT (1RHCU) | A | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-010537 | 076551C-907-CN-0022-001 | 907-J-CAL-50001-001 | HYDRAULIC CALCULATION NOTES REFINERY TO SITRA TRANSFER LINES - UNIT 907 | A | 2018-08-31 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010538 | 076551C-058-DW-1933-001-001 | 058-S-GAD-50001-001 | FIREFIGHTING LAYOUT 058 REFINERY GAS SYSTEM | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-010552 | 076551C-082-DW-1933-001-001 | 082-S-GAD-00002-001 | FIREFIGHTING LAYOUT 082 REFINERY SOUTH FLARE 081 LSDP FLARE AREA | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040001 | 019-C-GAD-10001-001 | 019-C-GAD-10001-001 | 019C0001R 1ST STAGE REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 019-C-GAD-10002-001 | 019-C-GAD-10002-001 | 019C0002R 2ND STAGE REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-DL-0470-001 | 000-C-IDL-70007-001 | DEVIATION LIST FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-ITP-0470-001 | 000-C-ITP-70007-001 | INSPECTION AND TEST PLAN FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-MR-0470-001 | 000-C-MRQ-70007-001 | MATERIAL REQUISITION FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-SP-0470-001 | 000-C-GRD-70007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-SR-0470-001 | 000-C-SOW-70007-001 | SCOPE OF SUPPLY FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 2
CON-BMP-TRA-040002 | 010-C-GAD-10004-001 | 010-C-GAD-10004-001 | STABILIZER - ITEM 010C0004 EX 010C0005/010-C-GAD-10005-001 AS PER CLIENT COMMENTS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 010-C-GAD-10005-001 | 010-C-GAD-10005-001 | NAPHTHA SPLITTER - ITEM 010C0005 EX 010C0006/010-C-GAD-10006-001 AS PER CLIENT COMMENTS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 019-C-GAD-10006-001 | 019-C-GAD-10006-001 | KEROSENE STRIPPER - ITEM 019C0006 | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 019-C-GAD-10010-001 | 019-C-GAD-10010-001 | NAPHTHA SPLITTER - ITEM 019C0010 | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-DL-0511-001 | 000-C-IDL-70008-001 | DEVIATION LIST FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 1 - APPROVED | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-ITP-0511-001 | 000-C-ITP-70008-001 | INSPECTION AND TEST PLAN FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-MR-0511-001 | 000-C-MRQ-70008-001 | MATERIAL REQUISITION FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-SP-0511-001 | 000-C-GRD-70008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-SR-0511-001 | 000-C-SOW-70008-001 | SCOPE OF SUPPLY FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 1 - APPROVED | 2018-04-11 | CLASS 2
CON-BMP-TRA-040003 | 019-E-DAT-00001-001 | 019-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0003 A/B 1ST STAGE REACTOR EFFLUENT / FRESH FEED EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00002-001 | 019-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0004 A/B 1ST STAGE REACTOR EFFLUENT / EFFLUENT EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00003-001 | 019-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0005 A/B 1ST STAGE REACTOR EFFLUENT / FRACTIONATOR FEED EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00004-001 | 019-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0006 A/B 1ST STAGE HHPS VAPOR / RECYCLE GAS EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00005-001 | 019-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0008 A/B 2ND STAGE HHPS VAPOR /CLPS LIQUID EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00006-001 | 019-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0011 A/B 2ND STAGE REACTOR FEED /EFFLUENT EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00007-001 | 019-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0012 2ND STAGE REACTOR EFFLUENT / RECYCLE GAS EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00013-001 | 019-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0062 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00014-001 | 019-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0072 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00015-001 | 019-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0074 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-DL-0610-001 | 000-E-IDL-70001-001 | DEVIATION LIST FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-ITP-0610-001 | 000-E-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-MR-0610-001 | 000-E-MRQ-70001-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-SP-0610-001 | 000-E-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-SR-0610-001 | 000-E-SOW-70001-001 | SCOPE OF SUPPLY FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-06 | CLASS 1
CON-BMP-TRA-040004 | 010-F-DAT-00001-001 | 010-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS - 010F0001 ATMOSPHERIC COLUMN HEATER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 011-F-DAT-00001-001 | 011-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS - 011F0001 VACUUM COLUMN HEATER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-DL-0110-002 | 000-F-IDL-70002-001 | DEVIATION LIST FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-ITP-0110-002 | 000-F-ITP-70002-001 | INSPECTION AND TEST PLAN FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-MR-0110-002 | 000-F-MRQ-70002-001 | MATERIAL REQUISITION FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-SP-0110-002 | 000-F-GRD-70002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-SR-0110-002 | 000-F-SOW-70002-001 | SCOPE OF SUPPLY FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-040005 | 019-S-DAT-00005-001 | 019-S-DAT-00005-001 | MECHANICAL DATA SHEET FEED FILTER 019U0001 | AP | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 3 - REVIEWED WITH COMMENTS | 2018-04-19 | CLASS 2
CON-BMP-TRA-040006 | 085-E-DAT-00001-001 | 085-E-DAT-00001-001 | MECHANICAL DATA SHEET BMP MAIN COOLING TOWER 085CWT0001 | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-20 | CLASS 2
CON-BMP-TRA-040006 | 085-E-DAT-00002-001 | 085-E-DAT-00002-001 | MECHANICAL DATA SHEET BMP SECONDARY COOLING TOWER 085CWT0002 | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-20 | CLASS 2
CON-BMP-TRA-040007 | 019-E-GAD-00026-001 | 019-E-GAD-00026-001 | SETTING PLAN 019E0061 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | AP | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-19 | CLASS 2
CON-BMP-TRA-040007 | 019-E-GAD-00027-001 | 019-E-GAD-00027-001 | SETTING PLAN 019E0071 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | AP | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-19 | CLASS 2
CON-BMP-TRA-040007 | 019-E-GAD-00028-001 | 019-E-GAD-00028-001 | SETTING PLAN 019E0073 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | AP | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 | 3 - REVIEWED WITH COMMENTS | 2018-04-19 | CLASS 2
CON-BMP-TRA-040008 | 010-E-DAT-00030-001 | 010-E-DAT-00030-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0030 KERO AIR COOLER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-20 | CLASS 2
CON-BMP-TRA-040008 | 010-E-DAT-00032-001 | 010-E-DAT-00032-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0033 NAPHTA SPLITTER OVERHEAD AIR COOLER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-20 | CLASS 2
CON-BMP-TRA-040009 | 011-G-DAT-00001-001 | 011-G-DAT-00001-001 | MECHANICAL DATA SHEET - HVGO PUMPS 011P0003AB | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-20 | CLASS 2
CON-BMP-TRA-040010 | 010-A-PFD-00001-001 | 010-A-PFD-00001-001 | PROCESS FLOW DIAGRAM CRUDE PREHEAT 1 DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-002 | 010-A-PFD-00001-002 | PROCESS FLOW DIAGRAM CRUDE PREHEAT 2 DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-003 | 010-A-PFD-00001-003 | PROCESS FLOW DIAGRAM CRUDE DISTILLATION DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-004 | 010-A-PFD-00001-004 | PROCESS FLOW DIAGRAM GAS COMPRESSION SECTION DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-005 | 010-A-PFD-00001-005 | PROCESS FLOW DIAGRAM NAPHTHA STABILIZER / SPLITTER DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-006 | 010-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-007 | 010-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-008 | 010-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-009 | 010-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-010 | 010-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-011 | 010-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-001 | 011-A-PFD-00001-001 | PROCESS FLOW DIAGRAM VACUUM DISTILLATION DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-002 | 011-A-PFD-00001-002 | PROCESS FLOW DIAGRAM STEAM GENERATION & PRODUCTS COOLING DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-003 | 011-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-004 | 011-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-005 | 011-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-001 | 085-A-PFD-00001-001 | PROCESS FLOW DIAGRAM CALCITE BEDS PACKAGE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-002 | 085-A-PFD-00001-002 | PROCESS FLOW DIAGRAM CALCITE BEDS PACKAGE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-003 | 085-A-PFD-00001-003 | PROCESS FLOW DIAGRAM BMP MAIN COOLING WATER SYSTEM | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-004 | 085-A-PFD-00001-004 | PROCESS FLOW DIAGRAM BMP SECONDARY COOLING WATER SYSTEM | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-005 | 085-A-PFD-00001-005 | PROCESS FLOW DIAGRAM SIDE STREAM FILTER PACKAGES | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-006 | 085-A-PFD-00001-006 | PROCESS FLOW DIAGRAM CW CHEMICAL TREATMENT | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-007 | 085-A-PFD-00001-007 | PROCESS FLOW DIAGRAM BMP MAIN COOLING WATER DISTRIBUTION | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-008 | 085-A-PFD-00001-008 | PROCESS FLOW DIAGRAM BMP SECONDARY COOLING WATER DISTRIBUTION | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-009 | 085-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-010 | 085-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-011 | 085-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-012 | 085-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-013 | 085-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040013 | 019-G-DAT-00001-001 | 019-G-DAT-00001-001 | MECHANICAL DATA SHEET 1ST STAGE REACTOR FEED PUMP 019P0002A/B | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 019-G-DAT-00002-001 | 019-G-DAT-00002-001 | MECHANICAL DATA SHEET 2ND STAGE REACTOR FEED PUMP 019P0003A/B | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 019-G-DAT-00003-001 | 019-G-DAT-00003-001 | MECHANICAL DATA SHEET HIGH PRESSURE LEAN AMINE PUMP 019P0021A/B | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-DL-0910-004 | 000-G-IDL-70001-001 | DEVIATION LIST FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-ITP-0910-004 | 000-G-ITP-70001-001 | INSPECTION AND TEST PLAN FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-MR-0910-004 | 000-G-MRQ-70001-001 | MATERIAL REQUISITION FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-SP-0910-004 | 000-G-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-SR-0910-004 | 000-G-SOW-70001-001 | SCOPE OF SUPPLY FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040014 | 019-C-GAD-30001-001 | 019-C-GAD-30001-001 | GENERAL ARRANGEMENT 019C0001R 1ST STAGE REACTOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 019-C-GAD-30002-001 | 019-C-GAD-30002-001 | GENERAL ARRANGEMENT 019C0002R 2ND STAGE REACTOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-DL-0411-001 | 000-C-IDL-70006-001 | DEVIATION LIST FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 1 - APPROVED | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-ITP-0411-001 | 000-C-ITP-70006-001 | INSPECTION AND TEST PLAN FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-MR-0411-001 | 000-C-MRQ-70006-001 | MATERIAL REQUISITION FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-SP-0411-001 | 000-C-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-SR-0411-001 | 000-C-SOW-70006-001 | SCOPE OF SUPPLY FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 019-C-GAD-00003-001 | 019-C-GAD-00003-001 | GENERAL ARRANGEMENT 019V0003 1ST STAGE HOT HIGH PRESSURE SEPARATOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 019-C-GAD-00008-001 | 019-C-GAD-00008-001 | GENERAL ARRANGEMENT 019V0008 2ND STAGE HOT HIGH PRESSURE SEPARATOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 019-C-GAD-00010-001 | 019-C-GAD-00010-001 | GENERAL ARRANGEMENT 019V0010 HOT LOW PRESSURE SEPARATOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-DL-0411-002 | 000-C-IDL-70004-001 | DEVIATION LIST FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-ITP-0411-002 | 000-C-ITP-70004-001 | INSPECTION AND TEST PLAN FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-MR-0411-002 | 000-C-MRQ-70004-001 | MATERIAL REQUISITION FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-SP-0411-002 | 000-C-GRD-70004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-SR-0411-002 | 000-C-SOW-70004-001 | SCOPE OF SUPPLY FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 2
CON-BMP-TRA-040016 | 011-H-DAT-00001-001 | 011-H-DAT-00001-001 | MECHANICAL DATA SHEET FOR VACUUM PACKAGE 011U0001 | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 019-H-DAT-00001-001 | 019-H-DAT-00001-001 | MECHANICAL DATA SHEET FOR VACUUM DRYER EJECTOR SYSTEM 019U0002 | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-DL-0851-001 | 000-H-IDL-70001-001 | DEVIATION LIST FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 1 - APPROVED | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-ITP-0851-001 | 000-H-ITP-70001-001 | INSPECTION AND TEST PLAN FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-MR-0851-001 | 000-H-MRQ-70001-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-SP-0851-001 | 000-H-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-SR-0851-001 | 000-H-SOW-70001-001 | SCOPE OF SUPPLY FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-040017 | 010-K-DAT-00001-001 | 010-K-DAT-00001-001 | MECHANICAL DATA SHEET CDU OVERHEAD VAPOR COMPRESSOR 010K0001 A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040017 | 019-K-DAT-00002-001 | 019-K-DAT-00002-001 | MECHANICAL DATA SHEET MAKE-UP HYDROGEN COMPRESSORS 19K0002 19K0003 19K0004 | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00001-001 | 010-G-DAT-00001-001 | MECHANICAL DATA SHEET CRUDE FEED PUMPS 010-P0001A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00002-001 | 010-G-DAT-00002-001 | MECHANICAL DATA SHEET DESALTED CRUDE PUMPS 010P0002 A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00003-001 | 010-G-DAT-00003-001 | MECHANICAL DATA SHEET PREFLASHED DRUM BOTTOM PUMPS 010P0029A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00004-001 | 010-G-DAT-00004-001 | MECHANICAL DATA SHEET KERO PA PUMPS 010P0007A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00005-001 | 010-G-DAT-00005-001 | MECHANICAL DATA SHEET DIESEL PA PUMPS 010P0010A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00006-001 | 010-G-DAT-00006-001 | MECHANICAL DATA SHEET UNSTABILIZED NAPHTA PUMPS 010P0019A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00008-001 | 010-G-DAT-00008-001 | MECHANICAL DATA SHEET DIESEL PRODUCT PUMPS 010P0012A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040019 | 019-G-DAT-00005-001 | 019-G-DAT-00005-001 | MECHANICAL DATA SHEET PRODUCT STRIPPER BOTTOM PUMPS 019P0005A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040019 | 019-G-DAT-00006-001 | 019-G-DAT-00006-001 | MECHANICAL DATA SHEET FRACTIONATOR BOTTOM PUMPS 019P0017A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040020 | 085-G-DAT-00001-001 | 085-G-DAT-00001-001 | MECHANICAL DATA SHEET MAIN COOLING WATER CIRCULATING PUMPS 085P0001 A/B/C/D/E | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-05-03 | CLASS 2
CON-BMP-TRA-040020 | 085-G-DAT-00002-001 | 085-G-DAT-00002-001 | MECHANICAL DATA SHEET SECONDARY COOLING WATER CIRCULATING PUMPS 085P0002A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-05-03 | CLASS 2
CON-BMP-TRA-040021 | 010-E-GAD-00004-001 | 010-E-GAD-00004-001 | SETTING PLAN 010E0010 A/B FLASHED CRUDE DIESEL PA EXCHANGER | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040021 | 019-C-GAD-00011-001 | 019-C-GAD-00011-001 | GENERAL ARRANGEMENT 019V0011 COLD LOW PRESSURE SEPARATOR | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040021 | 019-C-GAD-00014-001 | 019-C-GAD-00014-001 | GENERAL ARRANGEMENT 019V0014 NAPHTHA STABILIZER REFLUX DRUM | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040021 | 019-C-GAD-00028-001 | 019-C-GAD-00028-001 | GENERAL ARRANGEMENT 019V0028 RICH AMINE FLASH DRUM | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040021 | 019-C-GAD-00029-001 | 019-C-GAD-00029-001 | GENERAL ARRANGEMENT 019V0029 SOUR WATER FLASH DRUM | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040022 | 010-E-DAT-00004-001 | 010-E-DAT-00004-001 | SHEEL AND TUBE HEAT EXCHANGER DATA SHEET FOR 010E0010 A/B FLASHED CRUDE/DIESEL PA EXCHANGER | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 2
CON-BMP-TRA-040022 | 019-E-DAT-00041-001 | 019-E-DAT-00041-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0029 HEAVY DIESEL ARI COOLER | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 2
CON-BMP-TRA-040022 | 019-E-DAT-00047-001 | 019-E-DAT-00047-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0025 DIESEL PRODUCT AIR COOLER | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 2
CON-BMP-TRA-040023 | 010-C-DAT-00001-001 | 010-C-DAT-00001-001 | MECHANICAL DATA SHEET CRUDE OIL DESALTER 010U0001 | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 2
CON-BMP-TRA-040024 | 019-A-PFD-00001-001 | 019-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HIGH PRESSURE LOOP DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-002 | 019-A-PFD-00001-002 | PROCESS FLOW DIAGRAM LP SEPARATION AND PRODUCT STRIPPING DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-003 | 019-A-PFD-00001-003 | PROCESS FLOW DIAGRAM FRACTIONATION DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-004 | 019-A-PFD-00001-004 | PROCESS FLOW DIAGRAM NAPHTA PRODUCT SECTION DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-005 | 019-A-PFD-00001-005 | PROCESS FLOW DIAGRAM FEED AND PRODUCT RUNDOWN DESIGN CAE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-006 | 019-A-PFD-00001-006 | PROCESS FLOW DIAGRAM MAKE-UP HYDROGEN COMPRESSION SECTION DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-007 | 019-A-PFD-00001-007 | PROCESS FLOW DIAGRAM AMINE AND SOUR WATER SYSTEM DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-008 | 019-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-009 | 019-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-010 | 019-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-011 | 019-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-012 | 019-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-013 | 019-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-014 | 019-A-PFD-00001-014 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-015 | 019-A-PFD-00001-015 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-016 | 019-A-PFD-00001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-017 | 019-A-PFD-00001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-018 | 019-A-PFD-00001-018 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-019 | 019-A-PFD-00001-019 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-020 | 019-A-PFD-00001-020 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-021 | 019-A-PFD-00001-021 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-022 | 019-A-PFD-00001-022 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-023 | 019-A-PFD-00001-023 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-024 | 019-A-PFD-00001-024 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-025 | 019-A-PFD-00001-025 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-026 | 019-A-PFD-00001-026 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-027 | 019-A-PFD-00001-027 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-028 | 019-A-PFD-00001-028 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-029 | 019-A-PFD-00001-029 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-030 | 019-A-PFD-00001-030 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-031 | 019-A-PFD-00001-031 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-032 | 019-A-PFD-00001-032 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-033 | 019-A-PFD-00001-033 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-034 | 019-A-PFD-00001-034 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-035 | 019-A-PFD-00001-035 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-036 | 019-A-PFD-00001-036 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-037 | 019-A-PFD-00001-037 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-038 | 019-A-PFD-00001-038 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-039 | 019-A-PFD-00001-039 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-040 | 019-A-PFD-00001-040 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-041 | 019-A-PFD-00001-041 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-042 | 019-A-PFD-00001-042 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-043 | 019-A-PFD-00001-043 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-044 | 019-A-PFD-00001-044 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-045 | 019-A-PFD-00001-045 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-046 | 019-A-PFD-00001-046 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-047 | 019-A-PFD-00001-047 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-048 | 019-A-PFD-00001-048 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-049 | 019-A-PFD-00001-049 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-050 | 019-A-PFD-00001-050 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-051 | 019-A-PFD-00001-051 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-052 | 019-A-PFD-00001-052 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-053 | 019-A-PFD-00001-053 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-054 | 019-A-PFD-00001-054 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-055 | 019-A-PFD-00001-055 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-056 | 019-A-PFD-00001-056 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-057 | 019-A-PFD-00001-057 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-058 | 019-A-PFD-00001-058 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-059 | 019-A-PFD-00001-059 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1 - APPROVED | 2018-04-25 | CLASS 1
CON-BMP-TRA-040025 | 011-H-DAT-00001-001 | 011-H-DAT-00001-001 | MECHANICAL DATA SHEET VACUUM PACKAGE 011U0001 | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-040025 | 019-H-DAT-00001-001 | 019-H-DAT-00001-001 | MECHANICAL DATA SHEET VACUUM DRYER EJECTOR SYSTEM 019U0002 | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-040026 | 019-G-DAT-00009-001 | 019-G-DAT-00009-001 | MECHANICAL DATA SHEET HEAVY NAPHTHA PRODUCT PUMPS 019P0020A/B/C | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040026 | 019-G-DAT-00010-001 | 019-G-DAT-00010-001 | MECHANICAL DATA SHEET HEAVY DIESEL PUMP AROUND PUMP 019P0012A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040026 | 019-G-DAT-00028-001 | 019-G-DAT-00028-001 | MECHANICAL DATA SHEET LIGHT DIESEL PRODUCT PUMP 019P0011A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040026 | 019-K-DAT-00001-001 | 019-K-DAT-00001-001 | MECHANICAL DATA SHEET RECYCLE GAS COMPRESSOR | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040026 | 019-K-DAT-00003-001 | 019-K-DAT-00003-001 | MECHANICAL DATA SHEET RECYCLE GAS COMPRESSOR TURBINE | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 2
CON-BMP-TRA-040027 | 076551C-000M-DL-1020-001 | 000-K-IDL-70001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040027 | 076551C-000M-ITP-1020-001 | 000-K-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040027 | 076551C-000M-MR-1020-001 | 000-K-MRQ-70001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040027 | 076551C-000M-SP-1020-001 | 000-K-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040027 | 076551C-000M-SR-1020-001 | 000-K-SOW-70001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-DL-4141-001 | 000-S-IDL-70009-001 | DEVIATION LIST FOR DESALTER PACKAGE | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-ITP-4141-001 | 000-S-ITP-70009-001 | INSPECTION AND TEST PLAN FOR DESALTER PACKAGE | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-MR-4141-001 | 000-S-MRQ-70009-001 | MATERIAL REQUISITION FOR DESALTER PACKAGER | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-SP-4141-001 | 000-S-GRD-70009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR DESALTER PACKAGE | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-SR-4141-001 | 000-S-SOW-70009-001 | SCOPE OF SUPPLY FOR DESALTER PACKAGE | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-DL-1011-001 | 000-K-IDL-70002-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-ITP-1011-001 | 000-K-ITP-70002-001 | INSPECTION AND TEST PLAN (ITP) FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-MR-1011-001 | 000-K-MRQ-70002-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-SP-1011-001 | 000-K-GRD-70002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-SR-1011-001 | 000-K-SOW-70002-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-DL-0846-001 | 000-S-IDL-70003-001 | DEVIATION LIST FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-ITP-0846-001 | 000-S-ITP-70003-001 | INSPECTION AND TEST PLAN FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-MR-0846-001 | 000-S-MRQ-70003-001 | MATERIAL REQUISITION FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-SP-0846-001 | 000-S-GRD-70003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-SR-0846-001 | 000-S-SOW-70003-001 | SCOPE OF SUPPLY FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-29 | CLASS 1
CON-BMP-TRA-040031 | 019-G-DAT-00004-001 | 019-G-DAT-00004-001 | MECHANICAL DATA SHEET INJECTION WATER PUMPS 019P0022 AB | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-DL-0910-005 | 000-G-IDL-70005-001 | DEVIATION LIST FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 1 - APPROVED | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-ITP-0910-005 | 000-G-ITP-70005-001 | INSPECTION AND TEST PLAN FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-MR-0910-005 | 000-G-MRQ-70005-001 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-SP-0910-005 | 000-G-GRD-70005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-SR-0910-005 | 000-G-SOW-70005-001 | SCOPE OF SUPPLY FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 1
CON-BMP-TRA-040032 | 019-G-DAT-00007-001 | 019-G-DAT-00007-001 | MECHANICAL DATA SHEET LIGHT DIESEL P/A PUMO 019P0010 A/B | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 019-G-DAT-00008-001 | 019-G-DAT-00008-001 | MECHANICAL DATA SHEET FRACTIONATOR NAPHTA PUMPS 019P0006 A/B | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 050-G-DAT-55001-001 | 050-G-DAT-55001-001 | MECHANICAL DATA SHEET 1RHCU FEED PUMPS 050P0037 A/B | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-DL-0910-003 | 000-G-IDL-70004-001 | DEVIATION LIST FOR BB1 BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-ITP-0910-003 | 000-G-ITP-70004-001 | INSPECTION AND TEST PLAN FOR BB1 BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-MR-0910-003 | 000-G-MRQ-70004-001 | MATERIAL REQUISITION FOR BB1 BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-SP-0910-003 | 000-G-GRD-70004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB1 BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-SR-0910-003 | 000-G-SOW-70004-001 | SCOPE OF SUPPLY FOR BB1 BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 372-G-DAT-57001-001 | 372-G-DAT-57001-001 | MECHANICAL DATA SHEET FED WATER PUMPS 372P0030 A/B/C | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 372-G-DAT-57002-001 | 372-G-DAT-57002-001 | MECHANICAL DATA SHEET COOLING WATER MAKE-UP PUMPS 372P0031 A/B/C | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040033 | 085-S-DAT-00012-001 | 085-S-DAT-00012-001 | MECHANICAL DATA SHEET BMP MAIN CALCITE BEDS PACKAGE 085U0001 | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040033 | 085-S-DAT-00013-001 | 085-S-DAT-00013-001 | MECHANICAL DATA SHEET BMP SECONDARY CALCITE BEDS PACKAGE 085U0010 | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040033 | 085-S-DAT-00014-001 | 085-S-DAT-00014-001 | MECHANICAL DATA SHEET BMP MAIN CW SIDE STREAM FILTERS PACKAGE 085U0002 | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040033 | 085-S-DAT-00015-001 | 085-S-DAT-00015-001 | MECHANICAL DATA SHEET BMP SECONDARY CW SIDE STREAM FILTERS PACKAGE 085U0003 | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040034 | 019-E-DAT-00045-001 | 019-E-DAT-00045-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR NAPHTA SPLITTER OVERHEAD AIR COOLER 019E0038 | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040034 | 019-E-DAT-00046-001 | 019-E-DAT-00046-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR HEAVY NAPHTA PRODUCT AIR COOLER 019E0041 | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 019-F-DAT-00001-001 | 019-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F-0001 1ST STAGE REACTOR FEED FURNACE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 019-F-DAT-00002-001 | 019-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F-0002 2ND STAGE REACTOR FEED FURNACE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 019-F-DAT-00003-001 | 019-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F-0003 FRACTIONATOR FEED FURNACE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-DL-0110-001 | 000-F-IDL-70001-001 | DEVIATION LIST FOR HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-ITP-0110-001 | 000-F-ITP-70001-001 | INSPECTION AND TEST PLANT (ITP) FOR HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-MR-0110-001 | 000-F-MRQ-70001-001 | MATERIAL REQUISITION HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-SP-0110-001 | 000-F-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-SR-0110-001 | 000-F-SOW-70001-001 | SCOPE OF SUPPLY FOR HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 1
CON-BMP-TRA-040036 | 019-C-GAD-00004-001 | 019-C-GAD-00004-001 | GENERAL ARRANGEMENT 019V0004 1ST STAGE COLD HIGH PRESSURE SEPARATOR | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 019-C-GAD-00006-001 | 019-C-GAD-00006-001 | GENERAL ARRANGEMENT 019V0006 RECYCLE GAS K.O. DRUM | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 019-C-GAD-00009-001 | 019-C-GAD-00009-001 | GENERAL ARRANGEMENT 019V0009 2ND STAGE COLD HIGH PRESSURE SEPARATOR | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 019-C-GAD-10003-001 | 019-C-GAD-10003-001 | GENERAL ARRANGEMENT 019V0009 2ND STAGE COLD HIGH PRESSURE SEPARATOR | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-DL-0811-002 | 000-C-IDL-70001-001 | DEVIATION LIST FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-ITP-0811-002 | 000-C-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-MR-0811-002 | 000-C-MRQ-70001-001 | MATERIAL REQUISITION FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-SP-0811-002 | 000-C-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-SR-0811-002 | 000-C-SOW-70001-001 | SCOPE OF SUPPLY FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-DL-0811-001 | 000-C-IDL-70003-001 | DEVIATION LIST FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-ITP-0811-001 | 000-C-ITP-70003-001 | INSPECTION AND TEST PLAN (ITP) FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-MR-0811-001 | 000-C-MRQ-70003-001 | MATERIAL REQUISITION FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-SP-0811-001 | 000-C-GRD-70003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-SR-0811-001 | 000-C-SOW-70003-001 | SCOPE OF SUPPLY FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-02 | CLASS 2
CON-BMP-TRA-040038 | 010-C-GAD-10001-001 | 010-C-GAD-10001-001 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 010-C-GAD-10002-001 | 010-C-GAD-10002-001 | GENERAL ARRANGEMENT 010C0002 KERO STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 010-C-GAD-10003-001 | 010-C-GAD-10003-001 | GENERAL ARRANGEMENT 010C0003 DIESEL STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 011-C-GAD-10001-001 | 011-C-GAD-10001-001 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 011-C-GAD-10002-001 | 011-C-GAD-10002-001 | GENERAL ARRANGEMENT 011C0002 TAL GAS ABSORBER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10004-001 | 019-C-GAD-10004-001 | GENERAL ARRANGEMENT 019C0004 PRODUCT STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10005-001 | 019-C-GAD-10005-001 | GENERAL ARRANGEMENT 019C0005 PRODUCT FRACTIONATOR | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10007-001 | 019-C-GAD-10007-001 | GENERAL ARRANGEMENT 019C0007 LIGHT DIESEL STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10008-001 | 019-C-GAD-10008-001 | GENERAL ARRANGEMENT 019C0008 HEAVY DIESEL STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10009-001 | 019-C-GAD-10009-001 | GENERAL ARRANGEMENT 019C0009 NAPHTHA STABILIZER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-DL-0511-002 | 000-C-IDL-70009-001 | DEVIATION LIST FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 1 - APPROVED | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-ITP-0511-002 | 000-C-ITP-70009-001 | INSPECTION AND TEST PLAN (ITP) FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-MR-0511-002 | 000-C-MRQ-70009-001 | MATERIAL REQUISITION FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-SP-0511-002 | 000-C-GRD-70009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-SR-0511-002 | 000-C-SOW-70009-001 | SCOPE OF SUPPLY FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 2
CON-BMP-TRA-040039 | 076551C-000M-DL-0310-001 | 000-E-IDL-70006-001 | DEVIATION LIST FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-040039 | 076551C-000M-ITP-0310-001 | 000-E-ITP-70006-001 | INSPECTION AND TEST PLAN FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-040039 | 076551C-000M-MR-0310-001 | 000-E-MRQ-70006-001 | MATERIAL REQUISITION FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-040039 | 076551C-000M-SP-0310-001 | 000-E-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-040039 | 076551C-000M-SR-0310-001 | 000-E-SOW-70006-001 | SCOPE OF SUPPLY FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-040040 | 076551C-000M-DL-0570-001 | 000-C-IDL-70010-001 | DEVIATION LIST FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 1 - APPROVED | 2018-05-07 | CLASS 2
CON-BMP-TRA-040040 | 076551C-000M-ITP-0570-001 | 000-C-ITP-70010-001 | INSPECTION AND TEST PLAN (ITP) FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-040040 | 076551C-000M-MR-0570-001 | 000-C-MRQ-70010-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-040040 | 076551C-000M-SP-0570-001 | 000-C-GRD-70010-001 | PARTICULAR TECHNICAL SPECIFICATION FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-040040 | 076551C-000M-SR-0570-001 | 000-C-SOW-70010-001 | SCOPE OF SUPPLY FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-07 | CLASS 2
CON-BMP-TRA-040041 | 076551C-000M-DL-0840-002 | 000-S-IDL-70001-001 | DEVIATION LIST FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-040041 | 076551C-000M-ITP-0840-002 | 000-S-ITP-70001-001 | INSPECTION AND TEST PLAN FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-040041 | 076551C-000M-MR-0840-002 | 000-S-MRQ-70001-001 | MATERIAL REQUISITION FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-040041 | 076551C-000M-SP-0840-002 | 000-S-GRD-70001-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-040041 | 076551C-000M-SR-0840-002 | 000-S-SOW-70001-001 | SCOPE OF SUPPLY FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3 - REVIEWED WITH COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-040042 | 010-E-DAT-00031-001 | 010-E-DAT-00031-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0023 DIESEL AIR COOLER | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040042 | 010-E-DAT-00034-001 | 010-E-DAT-00034-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0034 BRINE AIR COOLER | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-DAT-00008-001 | 019-E-DAT-00008-001 | AIR COOLED HEX DATA SHEET FOR 1ST STAGE HHPS VAPOR 019E0008 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-DAT-00009-001 | 019-E-DAT-00009-001 | AIR COOLED HEX DATA SHEET FOR 2ND STAGE HHPS VAPOR AIR COOLER 019E0012 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-DAT-00010-001 | 019-E-DAT-00010-001 | AIR COOLED HEX DATA SHEET FOR HLPS VAPOR AIR COOLER 019E0013 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-GAD-00013-001 | 019-E-GAD-00013-001 | SETTING PLAN FOR MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER 019E0044 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-GAD-00014-001 | 019-E-GAD-00014-001 | SETTING PLAN FOR MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER 019E0047 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-GAD-00015-001 | 019-E-GAD-00015-001 | SETTING PLAN FOR MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER 019E0049 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-DL-0710-001 | 000-E-IDL-70007-001 | DEVIATION LIST FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-ITP-0710-001 | 000-E-ITP-70007-001 | INSPECTION AND TEST PLAN FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-MR-0710-001 | 000-E-MRQ-70007-001 | MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-SP-0710-001 | 000-E-GRD-70007-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-SR-0710-001 | 000-E-SOW-70007-001 | SCOPE OF SUPPLY FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-040045 | 076551C-000M-PP-102 | 000-A-PRO-70001-001 | COORDINATION PROCEDURE BETWEEN BAPCO IMPT AND MOC | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-040046 | 019-A-BOD-00001-001 | 019-A-BOD-00001-001 | PROCESS BASIS OF DESIGN 2HCU (UNIT C019) HYDROCRACKER UNIT | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-040047 | 076551C-000M-PP-100 | 000-A-ORG-70001-001 | MOC PROJECT ORGANIZATION CHART | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040048 | 010-A-EQL-00001-001 | 010-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 7 CRUDE DISTILLATION UNIT (7CDU) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 011-A-EQL-00001-001 | 011-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 7 VACUUM DISTILLATION UNIT (7 VDU) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 012-A-EQL-00001-001 | 012-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 1 SATURATED GAS PLANT- 1SGP | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 017-A-EQL-00001-001 | 017-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 2 SATURATED GAS PLANT - 2SGP | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 019-A-EQL-00001-001 | 019-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - HYDROCRACKER UNIT (2 HCU) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 085-A-EQL-00001-001 | 085-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - COOLING WATER TOWER - CWT | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-040049 | 050-A-EQL-55001-001 | 050-A-EQL-55001-001 | ITEM INDEX (EQUIPMENT LIST) - REFINERY TANK FARM (PLANT N F050) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-040049 | 372-A-EQL-57001-001 | 372-A-EQL-57001-001 | ITEM INDEX (EQUIPMENT LIST) - BOILER FEED WATER AND CONDENSATE DISTRIBUTION (PLANT N U372) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 1
CON-BMP-TRA-040050 | 076551C-000M-PP-124 | 000-A-PRO-70002-001 | MOC ENGINEERING MANAGEMENT PLAN | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 3 - REVIEWED WITH COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-001 | 019-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-002 | 019-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-003 | 019-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM FRACTIONATION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-004 | 019-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM NAPHTHA PRODUCT SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-005 | 019-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM FEED AND RUNDOWN | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-006 | 019-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM HYDROGEN COMPRESSION SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-007 | 019-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM AMINE AND SOUR WATER SYSTEM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-008 | 019-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-009 | 019-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM FRACTIONATION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-010 | 019-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM NAPHTHA PRODUCT SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-011 | 019-A-MSD-00001-011 | MATERIAL SELECTION DIAGRAM FEED AND RUNDOWN | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-012 | 019-A-MSD-00001-012 | MATERIAL SELECTION DIAGRAM NAPHTHA PRODUCT SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-013 | 019-A-MSD-00001-013 | MATERIAL SELECTION DIAGRAM FEED FILTER SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-014 | 019-A-MSD-00001-014 | MATERIAL SELECTION DIAGRAM STEAM GENERATION SYSTEM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-015 | 019-A-MSD-00001-015 | MATERIAL SELECTION DIAGRAM PHOSPHATE INJECTION PACKAGE | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-016 | 019-A-MSD-00001-016 | MATERIAL SELECTION DIAGRAM STEAM BLOWDOWN COLLECTION SYSTEM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-017 | 019-A-MSD-00001-017 | MATERIAL SELECTION DIAGRAM FUEL GAS KO DRUM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-018 | 019-A-MSD-00001-018 | MATERIAL SELECTION DIAGRAM FLARE KO DRUM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-019 | 019-A-MSD-00001-019 | MATERIAL SELECTION DIAGRAM SOUR WATER SLOPS AND AMINE | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-15 | CLASS 2
CON-BMP-TRA-040052 | 076551C-000M-DL-0848-002 | 000-S-IDL-70004-001 | DEVIATION LIST FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 076551C-000M-ITP-0848-002 | 000-S-ITP-70004-001 | INSPECTION AND TEST PLAN FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 076551C-000M-MR-0848-002 | 000-S-MRQ-70004-001 | MATERIAL REQUISITION FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 076551C-000M-SP-0848-002 | 000-S-GRD-70004-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 076551C-000M-SR-0848-002 | 000-S-SOW-70004-001 | SCOPE OF SUPPLY FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 085-S-DAT-00012-001 | 085-S-DAT-00012-001 | MECHANICAL DATA SHEET BMP MAIN CALCITE BEDS PACKAGE 085U0001 | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 085-S-DAT-00013-001 | 085-S-DAT-00013-001 | MECHANICAL DATA SHEET BMP SECONDARY CALCITE BEDS PACKAGE 085U0010 | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-040053 | 019-P-STS-00001-001 | 019-P-STS-00001-001 | LOAD BALANCE N 2 HYDROCRAKING UNIT - 2HCU SUBSTATION SST019R01 | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 2
CON-BMP-TRA-040054 | 019-P-SLD-00001-001 | 019-P-SLD-00001-001 | KEY SINGLE LINE DIAGRAM N 2 HYDROCRAKING UNIT - 2HCU SUBSTATION SST019R01 | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-040055 | 010-A-MSD-00001-001 | 010-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-002 | 010-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-003 | 010-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-004 | 010-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - GAS COMPRESSION SECT DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-005 | 010-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - DEBUTANIZER/NAPHTA SPLITTER DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-006 | 010-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT EQUIPMENT MATERIAL TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-007 | 010-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT EQUIPMENT MATERIAL TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-008 | 010-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE DISTILLATION EQUIPMENT MATERIAL TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-009 | 010-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE DISTILLATION DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-010 | 010-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM SOUR WATER AND SLOPS CLOSED DRAINS | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-011 | 010-A-MSD-00001-011 | MATERIAL SELECTION DIAGRAM FLARE KO DRUM | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-012 | 010-A-MSD-00001-012 | MATERIAL SELECTION DIAGRAM FUEL GAS KO DRUM | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 011-A-MSD-00001-001 | 011-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM VACUUM DISTILLAION DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 011-A-MSD-00001-002 | 011-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM STEAM GENERATION AND PRODUCTS COOLING DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 011-A-MSD-00001-003 | 011-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM VACUUM DISTILLATION EQUIPMENT TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040055 | 011-A-MSD-00001-004 | 011-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM STEAM GENERATION AND PRODUCTS COOLING EQUIPMENT TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-25 | CLASS 2
CON-BMP-TRA-040056 | 019-C-DAT-10008-001 | 019-C-DAT-10008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HEAVY DIESEL STRIPPER 019C0008 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-24 | CLASS 2
CON-BMP-TRA-040056 | 019-C-DAT-10009-001 | 019-C-DAT-10009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER 019C0009 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-24 | CLASS 2
CON-BMP-TRA-040057 | 010-C-DAT-10001-001 | 010-C-DAT-10001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR ATMOSPHERIC COLUMN 010C0001 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-24 | CLASS 2
CON-BMP-TRA-040057 | 010-C-DAT-10002-001 | 010-C-DAT-10002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR KERO STRIPPER 010C0002 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-24 | CLASS 2
CON-BMP-TRA-040057 | 010-C-DAT-10003-001 | 010-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR DIESEL STRIPPER 010C0003 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 3 - REVIEWED WITH COMMENTS | 2018-05-24 | CLASS 2
CON-BMP-TRA-040058 | 010-E-DAT-00016-001 | 010-E-DAT-00016-001 | SHELL AND TUBE HEX DATA SHEET FOR COMPRESSOR INTERSTAGE COOLER 010E0018 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040058 | 010-E-DAT-00017-001 | 010-E-DAT-00017-001 | SHELL AND TUBE HEX DATA SHEET FOR STABILIZER FEED/NAPHTHA SPLITTER BOTTOM EXCHANGER 010E0024 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040058 | 010-E-DAT-00024-001 | 010-E-DAT-00024-001 | SHELL AND TUBE HEX DATA SHEET FOR STABILIZER CONDENSER 010E0027 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040058 | 010-E-GAD-00016-001 | 010-E-GAD-00016-001 | SETTING PLAN COMPRESSOR INTERSTAGE COOLER 010E0018 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040058 | 010-E-GAD-00017-001 | 010-E-GAD-00017-001 | SETTING PLAN FOR STABILIZER FEED/NAPHTHA SPLITTER BOTTOM EXCHANGER 010E0024 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040058 | 010-E-GAD-00024-001 | 010-E-GAD-00024-001 | SETTING PLAN FOR STABILIZER CONDENSER 010E0027 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040059 | 011-E-DAT-00002-001 | 011-E-DAT-00002-001 | SHELL AND TUBE HEX DATA SHEET FOR LEAN AMINE | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040059 | 011-E-GAD-00002-001 | 011-E-GAD-00002-001 | SETTING PLAN FOR LEAN AMINE COOLER 0110E0008 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040060 | 019-E-DAT-00025-001 | 019-E-DAT-00025-001 | SHELL AND TUBE HEX DATA SHEET FOR NAPHTHA STABILIZER FEED - BOTTOMS EXCHANGER 019E0035 | A | 2018-04-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040060 | 019-E-DAT-00026-001 | 019-E-DAT-00026-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0043 | A | 2018-04-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040060 | 019-E-DAT-00027-001 | 019-E-DAT-00027-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0046 | A | 2018-04-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040060 | 019-E-DAT-00028-001 | 019-E-DAT-00028-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0048 | A | 2018-04-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040060 | 019-E-GAD-00025-001 | 019-E-GAD-00025-001 | SETTING PLAN 019E0035 NAPHTHA STABILIZER FEED BOTTOMS EXCHANGER | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040060 | 019-E-GAD-00026-001 | 019-E-GAD-00026-001 | SETTING PLAN 019E0043 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040060 | 019-E-GAD-00027-001 | 019-E-GAD-00027-001 | SETTING PLAN 019E0046 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040060 | 019-E-GAD-00028-001 | 019-E-GAD-00028-001 | SETTING PLAN 019E0048 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040061 | 019-E-DAT-00032-001 | 019-E-DAT-00032-001 | SHELL AND TUBE HEX DATA SHEET FOR KEROSENE PRODUCT TRIM COOLER 019E0020 | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040061 | 019-E-DAT-00036-001 | 019-E-DAT-00036-001 | SHELL AND TUBE HEX DATA SHEET FOR DIESEL PRODUCT TRIM COOLER 019E0026 | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040062 | 019-C-DAT-00005-001 | 019-C-DAT-00005-001 | MECHANICAL DATA SHEET HIGH PRESSURE CENTRIFUGAL SEPARATOR 019V0005 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040063 | 019-E-GAD-00032-001 | 019-E-GAD-00032-001 | SETTING PLAN FOR KEROSENE PRODUCT TRIM COOLER 019E0020 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040063 | 019-E-GAD-00036-001 | 019-E-GAD-00036-001 | SETTING PLAN FOR KEROSENE PRODUCT TRIM COOLER 019E0026 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-29 | CLASS 2
CON-BMP-TRA-040064 | 010-E-GAD-00022-001 | 010-E-GAD-00022-001 | SETTING PLAN FOR DESALTED CRUDE/KERO EXCHANGER 010E0007 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040065 | 011-E-DAT-00006-001 | 011-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 011E0004 LVGO PA COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040065 | 011-E-DAT-00007-001 | 011-E-DAT-00007-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 011E0009 TEMPERED WATR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00038-001 | 019-E-DAT-00038-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0014 PRODUCT STRIPPER OVERHEAD AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00039-001 | 019-E-DAT-00039-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0017 FRACTIONATOR OVERHEAD AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00040-001 | 019-E-DAT-00040-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0019 KEROSENE PRODUCT AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00042-001 | 019-E-DAT-00042-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0034 FRACTIONATOR BOTTOMS STARTUP AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00043-001 | 019-E-DAT-00043-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0033 UCO PRODUCT BLEED COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00044-001 | 019-E-DAT-00044-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0036 NAPHTHA STABILIZER OVERHEAD AIR COOLER | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00048-001 | 019-E-DAT-00048-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0051 BACKWASH OIL AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00049-001 | 019-E-DAT-00049-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0045 MAKE-UP HYDROGEN SPILLBACK COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040067 | 019-C-DAT-00034-001 | 019-C-DAT-00034-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FLARE KO DRUM 019V0034 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00010-001 | 010-G-DAT-00010-001 | DATA SHEET FOR DESALTER WATER RECYCLE PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00011-001 | 010-G-DAT-00011-001 | MECHANICAL DATA SHEET ATMOSPHERIC COLUMN OVHD SOUR WATER PUMPS 010P0024 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00012-001 | 010-G-DAT-00012-001 | MECHANICAL DATA SHEET STABILIZER REFLUX PUMPS 010P0025 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00013-001 | 010-G-DAT-00013-001 | MECHANICAL DATA SHEET NAPHTHA SPLITTER REFLUX PUMPS 010P0027 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00014-001 | 010-G-DAT-00014-001 | MECHANICAL DATA SHEET SR HEAVY NAPHTHA PUMPS 010P0028 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00016-001 | 010-G-DAT-00016-001 | MECHANICAL DATA SHEET ATM COLUMN REFLUX PUMPS 010P0005 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00017-001 | 010-G-DAT-00017-001 | MECHANICAL DATA SHEET KEROSENE PUMPS 010P0008 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00101-001 | 010-G-DAT-00101-001 | DATA SHEET FOR STEAM TURBINE FOR ATM COLUMN REFLUX PUMP 010P0004B (EX 010-K-DAT-00002-001) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00003-001 | 011-G-DAT-00003-001 | MECHANICAL DATA SHEET BSGO PUMPS 011P0007 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00004-001 | 011-G-DAT-00004-001 | MECHANICAL DATA SHEET RICH AMINE PUMPS 011P0008 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00005-001 | 011-G-DAT-00005-001 | MECHANICAL DATA SHEET LVGO PUMPS 011P0001 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00006-001 | 011-G-DAT-00006-001 | MECHANICAL DATA SHEET MVGO PUMPS 011P0002 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00007-001 | 011-G-DAT-00007-001 | MECHANICAL DATA SHEET VACUUM COLUMN SOUR WATER PUMPS 011P0006 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00008-001 | 011-G-DAT-00008-001 | DATA SHEET FOR TEMPERED WATER PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00009-001 | 011-G-DAT-00009-001 | DATA SHEET FOR WGO PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00100-001 | 011-G-DAT-00100-001 | DATA SHEET FOR STEAM TURBINE FOR LVGO PUMPS 011P0002B (EX 011-K-DAT-00001-001) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00101-001 | 011-G-DAT-00101-001 | DATA SHEET FOR STEAM TURBINE TEMPERED WATER PUMPS 011P0008B (EX 011-K-DAT-00002-001) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00011-001 | 019-G-DAT-00011-001 | MECHANICAL DATA SHEET NAPHTHA SLITTER REFLUX PUMP 019P0009A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00012-001 | 019-G-DAT-00012-001 | MECHANICAL DATA SHEET FRACTIONATOR OVERHEAD WATER PUMP 019P0014A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00014-001 | 019-G-DAT-00014-001 | MECHANICAL DATA SHEET HEAVY DIESEL STRIPPER BOTTOMS PUMP 019P0024A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00015-001 | 019-G-DAT-00015-001 | MECHANICAL DATA SHEET BACKWASH OIL PUMP 019P0031A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00016-001 | 019-G-DAT-00016-001 | MECHANICAL DATA SHEET VACUUM DRYER SLOP OIL PUMP 019P0032A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00017-001 | 019-G-DAT-00017-001 | MECHANICAL DATA SHEET VACUUM DRYER OILY WATER PUMP 019P0033A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00018-001 | 019-G-DAT-00018-001 | MECHANICAL DATA SHEET KEROSENE EXTERNAL REFLUX PUMP 019P0035A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00020-001 | 019-G-DAT-00020-001 | DATA SHEET FOR BFW CIRCULATION PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00021-001 | 019-G-DAT-00021-001 | MECHANICAL DATA SHEET RAW FEED BOOSTER PUMP 019P0001A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00022-001 | 019-G-DAT-00022-001 | MECHANICAL DATA SHEET KEROSENE PRODUCT PUMP 019P0006A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00023-001 | 019-G-DAT-00023-001 | MECHANICAL DATA SHEET HEAVY DIESEL PRODUCT PUMP 019P0011A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00024-001 | 019-G-DAT-00024-001 | MECHANICAL DATA SHEET PRODUCT STRIPPER REFLUX PUMP 019P0012A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00100-001 | 019-G-DAT-00100-001 | DATA SHEET FOR STEAM TURBINE FOR PRODUCT STRIPPER PUMPS 019P0004B 019T0004B (EX 019-K-DAT-00004-001) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040071 | 050-G-DAT-55002-001 | 050-G-DAT-55002-001 | DATA SHEET FOR 3HDU DIESEL FEED PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 1
CON-BMP-TRA-040071 | 050-G-DAT-55003-001 | 050-G-DAT-55003-001 | DATA SHEET FOR 2HCU HVGOFEED PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 1
CON-BMP-TRA-040071 | 050-G-DAT-55005-001 | 050-G-DAT-55005-001 | DATA SHEET FOR STEAM TURBINE FOR 3HDU DIESEL FEED PUMPS 050P0035A/B (EX 050-K-DAT-55005-001) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 1
CON-BMP-TRA-040071 | 050-G-DAT-55006-001 | 050-G-DAT-55006-001 | DATA SHEET FOR STEAM TURBINE FOR 2HCU HVGO FEED PUMPS 050P0036A/B (EX 050-K-DAT-55006-001) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 1
CON-BMP-TRA-040072 | 372-G-DAT-57003-001 | 372-G-DAT-57003-001 | MECHANICAL DATA SHEET UTILITY WATER PUMPS 372P3732A/B | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040074 | 011-G-DAT-00002-001 | 011-G-DAT-00002-001 | MECHANICAL DATA SHEET VACUUM RESIDUE PUMPS 01P0006A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-31 | CLASS 2
CON-BMP-TRA-040075 | 085-S-DAT-00014-001 | 085-S-DAT-00014-001 | MECHANICAL DATA SHEET BMP MAIN CW SIDE STREAM FILTERS PACKAGE 085U0002 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-040075 | 085-S-DAT-00015-001 | 085-S-DAT-00015-001 | MECHANICAL DATA SHEET BMP SECONDARY CW SIDE STREAM FILTERS PACKAGE 085U0003 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-040076 | 012-S-DAT-00001-001 | 012-S-DAT-00001-001 | MECHANICAL DATA SHEET LPG MERCAPTANS REMOVAL AND OLEFIN SATURATION PACKAGE 012U0001 / 017U0001 | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-001 | 085-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM CALCITE BEDS PACKAGE | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-002 | 085-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM BMP MAIN COOLING WATER SYSTEM | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-003 | 085-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM BMP MAIN COOLING WATER SYSTEM | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-004 | 085-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM BMP SECONDARY COOLING WATER SYSTEM | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-005 | 085-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM SIDE STREAM FILTER PACKAGE | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-006 | 085-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM CW CHEMICAL TREATMENT | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-007 | 085-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM BMP MAIN COOLING WATER DISTRIBUTION | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-008 | 085-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM BMP SECONDARY COOLING WATER DISTRIBUTION | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00018-001 | 010-E-GAD-00018-001 | SETTING PLAN 010E0001 A/B CRUDE/KERO EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00019-001 | 010-E-GAD-00019-001 | SETTING PLAN 010E0003 A/B CRUDE/DIESEL EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00020-001 | 010-E-GAD-00020-001 | SETTING PLAN 010E0004 A/B/C/D CRUDE/KERO PA EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00021-001 | 010-E-GAD-00021-001 | SETTING PLAN 010E0006 A/B DESALTED CRUDE/DIESEL EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00023-001 | 010-E-GAD-00023-001 | SETTING PLAN 010E0008 A/B/C/D DESALTED CRUDE/KERO PA EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00026-001 | 010-E-GAD-00026-001 | SETTING PLAN 010E0020 KERO/DESALTER WATER FEED PREHEAT EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00027-001 | 010-E-GAD-00027-001 | SETTING PLAN 010E0022 KERO TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00028-001 | 010-E-GAD-00028-001 | SETTING PLAN 010E0032 SR HEAVY NAPHTHA TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00029-001 | 010-E-GAD-00029-001 | SETTING PLAN 010E0030 LIGHT NAPHTHA COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00018-001 | 010-E-DAT-00018-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0001 A/B CRUDE/KERO EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00019-001 | 010-E-DAT-00019-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0003 A/B CRUDE/DIESEL EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00020-001 | 010-E-DAT-00020-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0004 A/B/C/D CRUDE/KERO PA EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00021-001 | 010-E-DAT-00021-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0006 A/B DESALTED CRUDE/DIESEL EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00022-001 | 010-E-DAT-00022-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0007 A/B DESALTED CRUDE/KERO EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00023-001 | 010-E-DAT-00023-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0008 A/B/C/D DESALTED CRUDE/KERO PA EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00026-001 | 010-E-DAT-00026-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0020 KERO/DESALTER WATER FEED PREHEAT EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00027-001 | 010-E-DAT-00027-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0022 KERO TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00028-001 | 010-E-DAT-00028-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0032 SR HEAVY NAPHTHA TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00029-001 | 010-E-DAT-00029-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0030 LIGHT NAPHTHA COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040080 | 011-E-DAT-00003-001 | 011-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0005 A/B MVGO/HVGO COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040080 | 011-E-DAT-00004-001 | 011-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0007 A/B/C/D VACUUM RESIDUE COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040080 | 011-E-DAT-00005-001 | 011-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0010 STEAM BLOWDOWN COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040081 | 011-E-GAD-00003-001 | 011-E-GAD-00003-001 | SETTING PLAN 011E0005 A/B MVGO/HVGO COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040081 | 011-E-GAD-00004-001 | 011-E-GAD-00004-001 | SETTING PLAN 011E0007 A/B/C/D VACUUM RESIDUE COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040081 | 011-E-GAD-00005-001 | 011-E-GAD-00005-001 | SETTING PLAN 011E0010 STEAM BLOWDOWN COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00029-001 | 019-E-DAT-00029-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0001 KEROSENE PRODUCT/FRESH FEED EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00030-001 | 019-E-DAT-00030-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0018 KEROSENE STRIPPER REBOILER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00031-001 | 019-E-DAT-00031-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0052 STEAM BLOWDOWN COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00033-001 | 019-E-DAT-00033-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0040 NAPHTA SPLITTER REBOILER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00034-001 | 019-E-DAT-00034-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0042 HEAVY NAPHTA PRODUCT TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00035-001 | 019-E-DAT-00035-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0024 LIGHT DIESEL / BFW EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00037-001 | 019-E-DAT-00037-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0021 LIGHT DIESEL P/A MP STEAM GENERATOR | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040083 | 010-G-DAT-00018-001 | 010-G-DAT-00018-001 | MECHANICAL DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMP 010P0018 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040083 | 010-G-DAT-00019-001 | 010-G-DAT-00019-001 | MECHANICAL DATA SHEET SOUR WATER SUMP PUMP 010P0017 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040084 | 019-G-DAT-00013-001 | 019-G-DAT-00013-001 | MECHANICAL DATA SHEET FOR NAPHTA STABILIZER REFLUX PUMP 019P0018 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040084 | 019-G-DAT-00025-001 | 019-G-DAT-00025-001 | MECHANICAL DATA SHEET FOR RECOVERED PROCESS SLOP OIL SUMP PUMP 019P0026 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040084 | 019-G-DAT-00026-001 | 019-G-DAT-00026-001 | MECHANICAL DATA SHEET FOR AMINE SUMP PUMP 019P0027 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040084 | 019-G-DAT-00027-001 | 019-G-DAT-00027-001 | MECHANICAL DATA SHEET FOR SOUR WATER SUMP PUMP 019P0028 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040085 | 050-G-DAT-55004-001 | 050-G-DAT-55004-001 | MECHANICAL DATA SHEET FOR 7CDU FEED BOOSTER PUMPS 010P0031 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00029-001 | 019-E-GAD-00029-001 | SETTING PLAN 019E0001 KEROSENE PRODUCT / FRESH FEED EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00030-001 | 019-E-GAD-00030-001 | SETTING PLAN 019E0018 KEROSENE STRIPPER REBOILER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00031-001 | 019-E-GAD-00031-001 | SETTING PLAN 019E0052 STEAM BLOWDOWN COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00033-001 | 019-E-GAD-00033-001 | SETTING PLAN 019E0040 NAPHTA SPLITTER REBOILER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00034-001 | 019-E-GAD-00034-001 | SETTING PLAN 019E0042 HEAVY NAPHTA PRODUCT TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00035-001 | 019-E-GAD-00035-001 | SETTING PLAN 019E0024 LIGHT DIESEL / BFW EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00037-001 | 019-E-GAD-00037-001 | SETTING PLAN 019E0021 LIGHT DIESEL P/A MP STEAM GENERATOR | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-30 | CLASS 2
CON-BMP-TRA-040088 | 011-K-DAT-00004-001 | 011-K-DAT-00004-001 | DATA SHEET FOR STEAM TURBINE FOR VACUUM RESIDUE PUMPS 011P0006 B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040088 | 011-K-DAT-00004-001 | 011-K-DAT-00004-001 | DATA SHEET FOR STEAM TURBINE FOR VACUUM RESIDUE PUMPS 011P0006 B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040089 | 085-G-DAT-00003-001 | 085-G-DAT-00003-001 | MECHANICAL DATA SHEET BACKWASH WATER PUMPS 085P0003A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040089 | 085-G-DAT-00004-001 | 085-G-DAT-00004-001 | MECHANICAL DATA SHEET BACKWASH WATER PUMPS 085P0004A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040090 | 019-C-DAT-00025-001 | 019-C-DAT-00025-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STEAM DRUM 019V0025 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040090 | 019-C-DAT-00031-001 | 019-C-DAT-00031-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STEAM BLOWDOWN DRUM 019V0031 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040090 | 019-C-DAT-10011-001 | 019-C-DAT-10011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR VACUUM DRYER 019C0011 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00005-001 | 019-K-DAT-00005-001 | MECHANICAL DATA SHEET PRODUCT STRIPPER BOTTOM PUMPS 019P0005 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00006-001 | 019-K-DAT-00006-001 | MECHANICAL DATA SHEET FRACTIONATOR BOTTOM PUMPS 019P0017 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00007-001 | 019-K-DAT-00007-001 | MECHANICAL DATA SHEET LIGHT DIESEL PUMPAROUND PUMPS 019P0010 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00008-001 | 019-K-DAT-00008-001 | MECHANICAL DATA SHEET FRACTIONATOR NAPHTHA PUMPS 019P0006 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00009-001 | 019-K-DAT-00009-001 | MECHANICAL DATA SHEET STEAM TURBINE FOR HEAVY DIESEL PUMPAROUND PUMPS 019P0012B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040092 | 085-K-DAT-00001-001 | 085-K-DAT-00001-001 | MECHANICAL DATA SHEET STEAM TURBINE FOR MAIN COOLING WATER CIRCULATING PUMPS 085P0001 A/B/C | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040092 | 085-K-DAT-00001-001 | 085-K-DAT-00001-001 | MECHANICAL DATA SHEET STEAM TURBINE FOR MAIN COOLING WATER CIRCULATING PUMPS 085P0001 A/B/C | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040092 | 085-K-DAT-00002-001 | 085-K-DAT-00002-001 | MECHANICAL DATA SHEET STEAM TURBINE FOR SECONDARY COOLING WATER CIRCULATING PUMPS 085P0002 A | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040092 | 085-K-DAT-00002-001 | 085-K-DAT-00002-001 | MECHANICAL DATA SHEET STEAM TURBINE FOR SECONDARY COOLING WATER CIRCULATING PUMPS 085P0002 A | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040093 | 011-C-DAT-00006-001 | 011-C-DAT-00006-001 | MECHANICAL DATA SHEET LVGO COLD REFLUX FILTERS 011V0002 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040093 | 011-C-DAT-00007-001 | 011-C-DAT-00007-001 | MECHANICAL DATA SHEET LVGO HOT REFLUX FILTERS 011V0003 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040093 | 011-C-DAT-00008-001 | 011-C-DAT-00008-001 | MECHANICAL DATA SHEET HVGO HOT REFLUX FILTERS 011V0005 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040093 | 011-C-DAT-00009-001 | 011-C-DAT-00009-001 | MECHANICAL DATA SHEET LVGO HOT REFLUX FILTERS 011V0004 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040094 | 010-C-DAT-00012-001 | 010-C-DAT-00012-001 | MECHANICAL DATA SHEET CRUDE FEED FILTERS 010V0001 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040094 | 010-C-DAT-00016-001 | 010-C-DAT-00016-001 | MECHANICAL DATA SHEET DESALTED CRUDE FILTERS 010V0004 A/B | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00005-001 | 010-C-GAD-00005-001 | GENERAL ARRANGEMENT 010V0005 PRE FLASH DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00007-001 | 010-C-GAD-00007-001 | GENERAL ARRANGEMENT 010V0007 OVERHEAD PRODUCT ACCUMULATOR | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00008-001 | 010-C-GAD-00008-001 | MECHANICAL DRAWING FOR 010V0008 COMPRESSOR K.O. DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00009-001 | 010-C-GAD-00009-001 | MECHANICAL DRAWING FOR 010V0009 COMPRESSOR INTERSTAGE K.O. DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00010-001 | 010-C-GAD-00010-001 | GENERAL ARRANGEMENT 010V0010 STABILIZER REFLUX DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00011-001 | 010-C-GAD-00011-001 | MECHANICAL DRAWING FOR 010V0011 NAPHTHA SPLITTER REFLUX DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00012-001 | 010-C-GAD-00012-001 | MECHANICAL DRAWING FOR 010V0012 DESALTER WATER SURGE DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00013-001 | 010-C-GAD-00013-001 | MECHANICAL DRAWING FOR 010V0013 SOUR WATER SUMP | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00014-001 | 010-C-GAD-00014-001 | MECHANICAL DRAWING FOR 010V0014 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00016-001 | 010-C-GAD-00016-001 | MECHANICAL DRAWING FOR 010V0016 FUEL GAS KO DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00001-001 | 011-C-GAD-00001-001 | MECHANICAL DRAWING FOR VACUUM HOT WELL 011V0001 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00006-001 | 011-C-GAD-00006-001 | MECHANICAL DRAWING FOR HOTWELL VAPOR WATER SEAL DRUM 011V0006 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00007-001 | 011-C-GAD-00007-001 | MECHANICAL DRAWING FOR SWEET TAIL GAS KO DRUM 011V0007 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00008-001 | 011-C-GAD-00008-001 | MECHANICAL DRAWING FOR TEMPERED WATER DRUM 011V0008 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00009-001 | 011-C-GAD-00009-001 | MECHANICAL DRAWING FOR STEAM DRUM 011V0009 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00010-001 | 011-C-GAD-00010-001 | MECHANICAL DRAWING FOR BLOWDOWN FLUSH DRUM 011V0010 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00001-001 | 019-C-GAD-00001-001 | GENERAL ARRANGEMENT 019V0001 RAW FEED SURGE DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00002-001 | 019-C-GAD-00002-001 | MECHANICAL DRAWING FOR 1ST STAGE FEED SURGE DRUM 019V0002 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00007-001 | 019-C-GAD-00007-001 | GENERAL ARRANGEMENT 019V0007 2ND STAGE FEED SURGE DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00012-001 | 019-C-GAD-00012-001 | GENERAL ARRANGEMENT 019V0012 PRODUCT SPLITTER REFLUX DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00013-001 | 019-C-GAD-00013-001 | MECHANICAL DRAWING FOR FRACTIONATOR REFLUX DRUM 019V0013 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00015-001 | 019-C-GAD-00015-001 | MECHANICAL DRAWING FOR NAPHTA SPLITTER REFLUX DRUM 019V0015 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00016-001 | 019-C-GAD-00016-001 | MECHANICAL DRAWING FOR NAPHTA SPLITTER REBOILER CONDENSATE POT 019V0016 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00017-001 | 019-C-GAD-00017-001 | MECHANICAL DRAWING FOR VACUUM DRYER HOTWELL 019V0017 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00018-001 | 019-C-GAD-00018-001 | GENERAL ARRANGEMENT 019V0018 MAKE-UP HYDROGEN FIRST STAGE SUCTION DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00019-001 | 019-C-GAD-00019-001 | GENERAL ARRANGEMENT 019V0019 MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00020-001 | 019-C-GAD-00020-001 | GENERAL ARRANGEMENT 019V0020 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00021-001 | 019-C-GAD-00021-001 | GENERAL ARRANGEMENT 019V0021 MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00022-001 | 019-C-GAD-00022-001 | GENERAL ARRANGEMENT 019V0022 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00023-001 | 019-C-GAD-00023-001 | GENERAL ARRANGEMENT 019V0023 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00024-001 | 019-C-GAD-00024-001 | GENERAL ARRANGEMENT 019V0024 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00025-001 | 019-C-GAD-00025-001 | MECHANICAL DRAWING FOR STEAM DRUM 019V0025 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00026-001 | 019-C-GAD-00026-001 | MECHANICAL DRAWING FOR LEAN AMINE SURGE DRUM 019V0026 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00027-001 | 019-C-GAD-00027-001 | MECHANICAL DRAWING FOR INJECTION WATER DRUM 019V0027 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00030-001 | 019-C-GAD-00030-001 | MECHANICAL DRAWING FOR BACKWASH OIL SURGE DRUM 019V0030 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00031-001 | 019-C-GAD-00031-001 | MECHANICAL DRAWING FOR STEAM BLOWDOWN DRUM 019V0031 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00032-001 | 019-C-GAD-00032-001 | MECHANICAL DRAWING FOR FUEL GAS KO DRUM 019V0032 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00033-001 | 019-C-GAD-00033-001 | MECHANICAL DRAWING FOR PROCESS GAS KO DRUM 019V0033 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00036-001 | 019-C-GAD-00036-001 | MECHANICAL DRAWING FOR RECOVERED PROCESS SLOP OIL SUMP 019V0036 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00037-001 | 019-C-GAD-00037-001 | MECHANICAL DRAWING FOR AMINE SUMP 019V0037 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00038-001 | 019-C-GAD-00038-001 | MECHANICAL DRAWING FOR SOUR WATER SUMP 019V0038 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-10011-001 | 019-C-GAD-10011-001 | MECHANICAL DRAWING FOR VACUUM DRYER 019C0011 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040098 | 019-C-DAT-00011-001 | 019-C-DAT-00011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR COLD LOW PRESSURE SEPARATOR 019V0011 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040098 | 019-C-DAT-00014-001 | 019-C-DAT-00014-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER REFLUX DRUM 019V0014 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040098 | 019-C-DAT-00028-001 | 019-C-DAT-00028-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RICH AMINE FLASH DRUM 019V0028 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040098 | 019-C-DAT-00029-001 | 019-C-DAT-00029-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SOUR WATER FLASH DRUM 019V0029 | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040099 | 011-S-DAT-00001-001 | 011-S-DAT-00001-001 | MECHANICAL DATA SHEET PHOPSPHATE INJECTION PACKAGE 011U0002 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040100 | 010-S-DAT-00001-001 | 010-S-DAT-00001-001 | MECHANICAL DATA SHEET NEUTRALIZING AMINE INJECTION PACKAGE 010U0002 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040100 | 010-S-DAT-00002-001 | 010-S-DAT-00002-001 | MECHANICAL DATA SHEET FILMING AMINE INJECTION PACKAGE 010U0003 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040100 | 010-S-DAT-00003-001 | 010-S-DAT-00003-001 | MECHANICAL DATA SHEET ANTIFOAMING INJECTION PACKAGE 010U0005 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040100 | 010-S-DAT-00004-001 | 010-S-DAT-00004-001 | MECHANICAL DATA SHEET DEMULSIFIER INJECTION PACKAGE 010U0004 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040101 | 372-D-GAD-57079-001 | 372-D-GAD-57079-001 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040101 | 372-D-GAD-57079-002 | 372-D-GAD-57079-002 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040101 | 372-D-GAD-57079-003 | 372-D-GAD-57079-003 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040101 | 372-D-GAD-57079-004 | 372-D-GAD-57079-004 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55001-001 | 050-D-GAD-55001-001 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55001-002 | 050-D-GAD-55001-002 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55001-003 | 050-D-GAD-55001-003 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55001-004 | 050-D-GAD-55001-004 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55002-001 | 050-D-GAD-55002-001 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | A | 2018-04-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55002-002 | 050-D-GAD-55002-002 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55002-003 | 050-D-GAD-55002-003 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55002-004 | 050-D-GAD-55002-004 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55003-001 | 050-D-GAD-55003-001 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55003-002 | 050-D-GAD-55003-002 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55003-003 | 050-D-GAD-55003-003 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55003-004 | 050-D-GAD-55003-004 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55004-001 | 050-D-GAD-55004-001 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55004-002 | 050-D-GAD-55004-002 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55004-003 | 050-D-GAD-55004-003 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55004-004 | 050-D-GAD-55004-004 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00001-001 | 085-S-DAT-00001-001 | MECHANICAL DATA SHEET OXIDIZING BIOCIDE DOSING PACKAGE 085U0004 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00002-001 | 085-S-DAT-00002-001 | MECHANICAL DATA SHEET ANTICALE DISPERSANT DOSING PACKAGE 085U0005 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00003-001 | 085-S-DAT-00003-001 | MECHANICAL DATA SHEET BIODISPERSANT DOSING PACKAGE 085U0006 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00004-001 | 085-S-DAT-00004-001 | MECHANICAL DATA SHEET CORROSION INHIBITOR DOSING PACKAGE 085U0007 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00005-001 | 085-S-DAT-00005-001 | MECHANICAL DATA SHEET SULPHURIC ACID DOSING PACKAGE 085U0008 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00006-001 | 085-S-DAT-00006-001 | MECHANICAL DATA SHEET SODIUM HYDROXIDE DOSING PACKAGE 085U0009 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00011-001 | 085-S-DAT-00011-001 | MECHANICAL DATA SHEET MAIN NON OXIDIZING BIOCIDE DOSING PACKAGE 085U0011 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00016-001 | 085-S-DAT-00016-001 | MECHANICAL DATA SHEET SECONDARY NON OXIDIZING BIOCIDE DOSING PACKAGE 085U0012 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040104 | 010-G-DAT-00015-001 | 010-G-DAT-00015-001 | MECHANICAL DATA SHEET FLARE KO DRUM PUMPS 010P0019 A/B | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040105 | 019-S-DAT-00001-001 | 019-S-DAT-00001-001 | MECHANICAL DATA SHEET ANTIFOAM INJECTION PACKAGE 019U0003 | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040105 | 019-S-DAT-00002-001 | 019-S-DAT-00002-001 | MECHANICAL DATA SHEET ANTISTATIC ADDITIVE PACKAGE 019U0005 | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040105 | 019-S-DAT-00003-001 | 019-S-DAT-00003-001 | MECHANICAL DATA SHEET PHOSPHATE INJECTION PACKAGE 019U0006 | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040105 | 019-S-DAT-00004-001 | 019-S-DAT-00004-001 | MECHANICAL DATA SHEET ANTIOXIDANT ADDITIVE PACKAGE 019U0004 | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040106 | 085-C-DAT-00001-001 | 085-C-DAT-00001-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 085V0008 A/B | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040106 | 085-C-DAT-00002-001 | 085-C-DAT-00002-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 085V0009 A/B | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040107 | 010-P-STS-00001-001 | 010-P-STS-00001-001 | LOAD BALANCE N 7 CDU SUBSTATION SST010R01 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040108 | 019-A-PPN-00001-001 | 019-A-PPN-00001-001 | PLOT PLAN C019 - 2HCU HYDROCRACKING UNIT (EX 019-L-PPN-00001-001) | A | 2018-05-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040108 | 019-A-PPN-00001-002 | 019-A-PPN-00001-002 | PLOT PLAN C019 - 2HCU HYDROCRACKING UNIT (EX 019-L-PPN-00001-002) | A | 2018-05-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040109 | 076551C-000M-MR-1011-002 | 000-K-MRQ-70007-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSORS UNIT 012 AND 017 | AP | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-08 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040110 | 019-C-DAT-00050-001 | 019-C-DAT-00050-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 019V0035 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040111 | 010-C-DAT-00017-001 | 010-C-DAT-00017-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 010V0017 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040112 | 017-G-DAT-00017-001 | 017-G-DAT-00017-001 | MECHANICAL DATA SHEET AMINE SUMP PUMP 017P0017 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 3 - REVIEWED WITH COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-040112 | 017-G-DAT-00018-001 | 017-G-DAT-00018-001 | MECHANICAL DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMP 017P0016 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 3 - REVIEWED WITH COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-040113 | 050-K-DAT-55001-001 | 050-K-DAT-55001-001 | MECHANICAL DATA SHEET D1003 PROPELLER MIXER 050MX5011 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040113 | 050-K-DAT-55002-001 | 050-K-DAT-55002-001 | MECHANICAL DATA SHEET D1004 PROPELLER MIXER 050MX5012 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040113 | 050-K-DAT-55003-001 | 050-K-DAT-55003-001 | MECHANICAL DATA SHEET D1001 PROPELLER MIXER 050MX5013 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040113 | 050-K-DAT-55004-001 | 050-K-DAT-55004-001 | MECHANICAL DATA SHEET D1002 PROPELLER MIXER 050MX5014 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040114 | 012-G-DAT-00017-001 | 012-G-DAT-00017-001 | MECHANICAL DATA SHEET AMINE SUMP PUMP 012P0017 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040114 | 012-G-DAT-00018-001 | 012-G-DAT-00018-001 | MECHANICAL DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMPS 012P0016 A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040115 | 011-C-DAT-00005-001 | 011-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STEAM DRUM 011V0009 | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040116 | 010-E-DAT-00033-001 | 010-E-DAT-00033-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0031 SR HEAVY NAPHTA AIR COOLER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-06 | CLASS 2
CON-BMP-TRA-040117 | 085-A-PFD-00001-001 | 085-A-PFD-00001-001 | PROCESS FLOW DIAGRAM CALCITE BEDS PACKAGE | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-002 | 085-A-PFD-00001-002 | PROCESS FLOW DIAGRAM SECONDARY CALCITE BEDS PACKAGE | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-003 | 085-A-PFD-00001-003 | PROCESS FLOW DIAGRAM MAIN COOLING WATER SYSTEM | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-004 | 085-A-PFD-00001-004 | PROCESS FLOW DIAGRAM SECONDARY COOLING WATER SYSTEM | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-005 | 085-A-PFD-00001-005 | PROCESS FLOW DIAGRAM SIDE STREAM FILTER PACKAGES | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-006 | 085-A-PFD-00001-006 | PROCESS FLOW DIAGRAM CW CHEMICAL TREATMENT | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-007 | 085-A-PFD-00001-007 | PROCESS FLOW DIAGRAM MAIN COOLING WATER DISTRIBUTION | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-008 | 085-A-PFD-00001-008 | PROCESS FLOW DIAGRAM SECONDARY COOLING WATER DISTRIBUTION | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-009 | 085-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-010 | 085-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-011 | 085-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-012 | 085-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040117 | 085-A-PFD-00001-013 | 085-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040118 | 010-A-PFD-00001-001 | 010-A-PFD-00001-001 | PROCESS FLOW DIAGRAM CRUDE PREHEAT 1 | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040118 | 010-A-PFD-00001-002 | 010-A-PFD-00001-002 | PROCESS FLOW DIAGRAM CRUDE PREHEAT 2 | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040118 | 010-A-PFD-00001-003 | 010-A-PFD-00001-003 | PROCESS FLOW DIAGRAM CRUDE DISTILLATION | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040118 | 010-A-PFD-00001-004 | 010-A-PFD-00001-004 | PROCESS FLOW DIAGRAM GAS COMPRESSION SECTION | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040118 | 010-A-PFD-00001-005 | 010-A-PFD-00001-005 | PROCESS FLOW DIAGRAM NAPHTHA STABILIZER / SPLITTER | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040119 | 085-A-PPN-00001-001 | 085-A-PPN-00001-001 | PLOT PLAN 085-CW CLOSED COOLING WATER (EX 085-L-PPN-00001-001) | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040119 | 085-A-PPN-00001-002 | 085-A-PPN-00001-002 | PLOT PLAN 085-CW BUILDING (EX 085-L-PPN-00001-002) | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00001-001 | 085-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP MAIN COOLING TOWER | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00002-001 | 085-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP MAIN COOLING WATER CIRCULATING PUMPS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00003-001 | 085-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP MAIN COOLING WATER CIRCULATING PUMPS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00004-001 | 085-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP SECONDARY COOLING TOWER | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00005-001 | 085-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP SECONDARY COOLING WATER CIRCULATING PUMPS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00006-001 | 085-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW COOLING TOWER FANS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00007-001 | 085-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW P0001A STEAM TURBINE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00008-001 | 085-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW P0001B STEAM TURBINE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00009-001 | 085-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW P0001C STEAM TURBINE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00010-001 | 085-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW P0002A STEAM TURBINE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00011-001 | 085-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP MAIN CALCITE BEDS PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00011-002 | 085-A-PID-00011-002 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP MAIN CALCITE BEDS PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00012-001 | 085-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP SECONDARY CALCITE BEDS PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00013-001 | 085-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP MAIN SIDE STREAM FILTERS PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00013-002 | 085-A-PID-00013-002 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP MAIN SIDE STREAM FILTERS PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00013-003 | 085-A-PID-00013-003 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP MAIN SIDE STREAM FILTERS PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00014-001 | 085-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BMP SECONDARY SIDE STREAM FILTERS PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00015-001 | 085-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BACKWASH SYSTEM SECTION A | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00016-001 | 085-A-PID-00016-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BACKWASH SYSTEM SECTION B | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00017-001 | 085-A-PID-00017-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW STEAM DISTRIBUTION | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00018-001 | 085-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW STEAM CONDENSATE AND BFW DISTRIBUTION | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00019-001 | 085-A-PID-00019-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW WATER DISTRIBUTION | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00020-001 | 085-A-PID-00020-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW COOLING WATER DISTRIBUTION | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00021-001 | 085-A-PID-00021-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW UTILITY AND DRINKING WATER | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00022-001 | 085-A-PID-00022-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW INSTRUMENT AND YARD AIR | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00024-001 | 085-A-PID-00024-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BATTERY LIMIT PROCESS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00025-001 | 085-A-PID-00025-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BATTERY LIMIT PROCESS AUXILIARY | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00026-001 | 085-A-PID-00026-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BATTERY LIMIT UTILITIES | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00026-002 | 085-A-PID-00026-002 | PIPING AND INSTRUMENT DIAGRAM - CLCW BATTERY LIMIT UTILITIES | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00026-003 | 085-A-PID-00026-003 | PIPING AND INSTRUMENT DIAGRAM - CLCW BATTERY LIMIT UTILITIES | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00027-001 | 085-A-PID-00027-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW OXIDIZING BIOCIDE DOSING PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00028-001 | 085-A-PID-00028-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW ANTI SCALE / DISPERSANT DOSING PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00029-001 | 085-A-PID-00029-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW BIODISPERSANT DOSING PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00030-001 | 085-A-PID-00030-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW CORROSION INHIBITOR DOSING PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00031-001 | 085-A-PID-00031-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW SULPHURIC ACID DOSING PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00032-001 | 085-A-PID-00032-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW SODIUM HYDROXIDE DOSING PACKAGE | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040120 | 085-A-PID-00033-001 | 085-A-PID-00033-001 | PIPING AND INSTRUMENT DIAGRAM - CLCW NON OXYDANT BIOCIDE DOSING SYSTEM | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-04 | CLASS 1
CON-BMP-TRA-040121 | 010-A-BOD-00001-001 | 010-A-BOD-00001-001 | BASIS OF DESIGN 7 CDU/VDU (UNIT 010/011) | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040122 | 372-A-PID-57001-001 | 372-A-PID-57001-001 | PIPING AND INSTRUMENT DIAGRAM - BFWCD FLASH EVAPORATED DISTILLATE STORAGE 372D0279 | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040122 | 372-A-PID-57002-001 | 372-A-PID-57002-001 | PIPING AND INSTRUMENT DIAGRAM - BFWCD FED CW MAKE-UP PUMPS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040122 | 372-A-PID-57003-001 | 372-A-PID-57003-001 | PIPING AND INSTRUMENT DIAGRAM - BFWCD UTILITY WATER PUMPS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040122 | 372-A-PID-57004-001 | 372-A-PID-57004-001 | PIPING AND INSTRUMENT DIAGRAM - BFWCD FED UTILITY WATER AND CW MAKE UP BATTERY LIMIT | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040122 | 372-A-PID-57005-001 | 372-A-PID-57005-001 | PIPING AND INSTRUMENT DIAGRAM - BFWCD STEAM AND CONDENSATE SYSTEM | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040122 | 372-A-PID-57006-001 | 372-A-PID-57006-001 | PIPING AND INSTRUMENT DIAGRAM - BFWCD INSTRUMENT AIR, YARD AIR SYSTEM | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040123 | MOC-BMM-MOM-000001 | 000-A-MOM-70001-001 | NEW TAGGING EQUIPMENT LIST | 0 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040123 | MOC-BMM-MOM-000002 | 000-A-MOM-70002-001 | 019-2 HCU PRE-EPC P&IDS TECHNICAL REVIEW SESSION | 0 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040123 | MOC-BMM-MOM-000003 | 000-A-MOM-70003-001 | UNITS 010/011 7CDU/7VDU PRE-EPC P&IDS TECHNICAL REVIEWED SESSION | 0 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040123 | MOC-BMM-MOM-000004 | 000-A-MOM-70004-001 | P012/P017-1,2 SGP PRE-EPC P&IDS TECHNICAL REVIEW SESSIONS | 0 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040123 | MOC-BMM-MOM-000006 | 000-A-MOM-70005-001 | 2HCU RVS TAGGING MEETING | 0 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040124 | 050-A-PID-55001-001 | 050-A-PID-55001-001 | PIPING AND INSTRUMENT DIAGRAM - RTF CRUDE FEED RUNDOWN SYSTEM REFINERY TANKS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040124 | 050-A-PID-55002-001 | 050-A-PID-55002-001 | PIPING AND INSTRUMENT DIAGRAM - RTF CRUDE FEED RUNDOWN SYSTEM REFINERY TANKS | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040124 | 050-A-PID-55003-001 | 050-A-PID-55003-001 | PIPING AND INSTRUMENT DIAGRAM - RTF 1RHCU FEED TANK D0003 | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040124 | 050-A-PID-55004-001 | 050-A-PID-55004-001 | PIPING AND INSTRUMENT DIAGRAM - RTF 1RHCU FEED TANK D0004 | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040124 | 050-A-PID-55005-001 | 050-A-PID-55005-001 | PIPING AND INSTRUMENT DIAGRAM - RTF STEAM AND CONDENSATE SYSTEM | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040124 | 050-A-PID-55006-001 | 050-A-PID-55006-001 | PIPING AND INSTRUMENT DIAGRAM - RTF COOLING AND UTILITY WATER SYSTEM | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040124 | 050-A-PID-55007-001 | 050-A-PID-55007-001 | PIPING AND INSTRUMENT DIAGRAM - RTF INSTRUMENT AIR YARD AIR SYSTEM | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040125 | 010-A-PPN-00001-001 | 010-A-PPN-00001-001 | PLOT PLAN P010-7CDU/P011-7VDU CRUDE AND VACCUM DISTILLATION UNIT (EX 010-L-PPN-00001-001) | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040125 | 010-L-PPN-00001-002 | 010-L-PPN-00001-002 | PLOT PLAN P010-7CDU/P011-7VDU CRUDE AND VACCUM DISTILLATION UNIT | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040125 | 010-L-PPN-00001-003 | 010-L-PPN-00001-003 | PLOT PLAN P010-7CDU/P011-7VDU CRUDE AND VACCUM DISTILLATION UNIT | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040126 | 011-A-PFD-00001-001 | 011-A-PFD-00001-001 | PROCESS FLOW DIAGRAM VACUUM DISTILLATION | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040126 | 011-A-PFD-00001-002 | 011-A-PFD-00001-002 | PROCESS FLOW DIAGRAM STEAM GENERATION & PRODUCTS COOLING | B | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040126 | 011-A-PFD-00001-006 | 011-A-PFD-00001-006 | PROCESS FLOW DIAGRAM VACUUM AND AMINE SYSTEM | A | 2018-05-25 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040127 | 019-C-DAT-00022-001 | 019-C-DAT-00022-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM 019V0022 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-040127 | 019-C-DAT-00023-001 | 019-C-DAT-00023-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM 019V0023 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-040127 | 019-C-DAT-00024-001 | 019-C-DAT-00024-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM 019V0024 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-040128 | 050-A-PPN-55001-001 | 050-L-PPN-55001-001 | PLOT PLAN F050/U372 REFINERY TANK FARM | A | 2018-05-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040128 | 050-A-PPN-55001-002 | 050-L-PPN-55001-002 | PLOT PLAN F050/U372 REFINERY TANK FARM | A | 2018-05-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-11 | 3 - REVIEWED WITH COMMENTS | 2018-06-07 | CLASS 1
CON-BMP-TRA-040129 | 010-E-DAT-00002-001 | 010-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR DESALTED CRUDE/MVGO AND HVGO EXCHNAGER 010E0005 A/B/C/D | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00003-001 | 010-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR FLASHED CRUDE/DIESEL EXCHNAGER 010E0009 A/B | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00005-001 | 010-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR FLUSHED CRUDE/VACUUM RESIDUE EXCHNAGER - 1ST 010E0011 A/B | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00006-001 | 010-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR FLUSHED CRUDE/HVGO PA EXCHNAGER - 1ST 010E0012 A/B/C/D | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00007-001 | 010-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR FLASHED CRUDE/DIESEL PA EXCHNAGER - 2ND 010E0013 A/B | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00008-001 | 010-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR FLASHED CRUDE/HVGO PA EXCHNAGER - 2ND 010E0014 A/B/C/D | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00009-001 | 010-E-DAT-00009-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR FLUSHED CRUDE/VACUUM RESIDUE EXCHNAGER - 2ND 010E0015 A/B/C/D | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00010-001 | 010-E-DAT-00010-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR SPLITTER REBOILER 010E0028 A/B | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00011-001 | 010-E-DAT-00011-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR KERO STRIPPER REBOILER 010E0019 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00012-001 | 010-E-DAT-00012-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR BRINE TRIM COOLER 010E0035 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00014-001 | 010-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR STABILIZER REBOILER 010E0026 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040129 | 010-E-DAT-00015-001 | 010-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR BRINE/DESALTER WATER PREHEAT EXCHANGER 010E0033 A/B | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040130 | 011-E-DAT-00001-001 | 011-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR VACUUM RESIDUE STEAM GENERATOR 011E0006 A/B/C/D | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00016-001 | 019-E-DAT-00016-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR HEAVY DIESEL PRODUCT/FESH FEED EXCHANGER 019E0002 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00017-001 | 019-E-DAT-00017-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR HEAVY DIESEL P/A MP STEAM GENERATOR 019E0027 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00018-001 | 019-E-DAT-00018-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR NAPHTHA STABILIZER REBOILER 019E0037 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00019-001 | 019-E-DAT-00019-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR LIGHT DIESEL MP STEAM GENERATOR 019E0023 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00020-001 | 019-E-DAT-00020-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR HEAVY DIESEL/BFW EXCHANGER 019E0028 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00021-001 | 019-E-DAT-00021-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR FRACTIONATOR BOTTOMS MP STEAM GENERATOR 019E0037 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00022-001 | 019-E-DAT-00022-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR LIGHT DIESEL STRIPPER REBOILER 019E0022 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00023-001 | 019-E-DAT-00023-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR FRACTIONATOR BOTTOMS/FRESH FEED EXCHANGER 019E0003 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040131 | 019-E-DAT-00024-001 | 019-E-DAT-00024-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FORSOUR WATER COOLER 019E0050 | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040132 | 050-D-DAT-55001-001 | 050-D-DAT-55001-001 | TANK DESIGN SPECIFICATION FOR 050D1001/050D1002 A/B CRUDE OIL TANKS | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 3 - REVIEWED WITH COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040132 | 050-D-DAT-55003-001 | 050-D-DAT-55003-001 | TANK DESIGN SPECIFICATION FOR 050D1003/050D1004 1RHCU FEED TANK | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 3 - REVIEWED WITH COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040133 | 019-P-INX-00001-001 | 019-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST N 2 HYDROCRACKING UNIT - 2HCU | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 3 - REVIEWED WITH COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040134 | 010-E-DAT-00004-001 | 010-E-DAT-00004-001 | SHEEL AND TUBE HEAT EXCHANGER DATA SHEET FOR 010E0010 A/B FLASHED CRUDE/DIESEL PA EXCHANGER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 3 - REVIEWED WITH COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-040135 | 019-C-DAT-00001-001 | 019-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RAW FEED SURGE DRUM 019V0001 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040135 | 019-C-DAT-00007-001 | 019-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAGE FEED SURGE DRUM 019V0007 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040135 | 019-C-DAT-00012-001 | 019-C-DAT-00012-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT STRIPPER REFLUX DRUM 019V0012 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040135 | 019-C-DAT-00018-001 | 019-C-DAT-00018-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR MAKE-UP HYDROGEN FIRST STAGE SUCTION DRUM 019V0018 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040135 | 019-C-DAT-00019-001 | 019-C-DAT-00019-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM 019V0019 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040135 | 019-C-DAT-00020-001 | 019-C-DAT-00020-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM 019V0020 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040135 | 019-C-DAT-00021-001 | 019-C-DAT-00021-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM 019V0021 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040136 | 010-C-GAD-00006-001 | 010-C-GAD-00006-001 | GENERAL ARRANGEMENT 010V0008 ATMOSPHERIC COLUMN REFLUX DRUM | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040136 | 010-C-GAD-00006-002 | 010-C-GAD-00006-002 | GENERAL ARRANGEMENT 010V0008 ATMOSPHERIC COLUMN REFLUX DRUM | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040136 | 010-C-GAD-00006-003 | 010-C-GAD-00006-003 | GENERAL ARRANGEMENT 010V0008 ATMOSPHERIC COLUMN REFLUX DRUM | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040137 | 019-A-PFD-00001-001 | 019-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HIGH PRESSURE LOOP | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-040137 | 019-A-PFD-00001-002 | 019-A-PFD-00001-002 | PROCESS FLOW DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-040137 | 019-A-PFD-00001-003 | 019-A-PFD-00001-003 | PROCESS FLOW DIAGRAM FRACTIONATION | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-040137 | 019-A-PFD-00001-004 | 019-A-PFD-00001-004 | PROCESS FLOW DIAGRAM NAPHTA PRODUCT SECTION | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-040137 | 019-A-PFD-00001-005 | 019-A-PFD-00001-005 | PROCESS FLOW DIAGRAM FEED AND PRODUCT RUNDOWN | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-040137 | 019-A-PFD-00001-006 | 019-A-PFD-00001-006 | PROCESS FLOW DIAGRAM MAKE-UP HYDROGEN COMPRESSION SECTION | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-040137 | 019-A-PFD-00001-007 | 019-A-PFD-00001-007 | PROCESS FLOW DIAGRAM AMINE AND SOUR WATER SYSTEM | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-040138 | 010-A-PFD-00001-006 | 010-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-040138 | 010-A-PFD-00001-007 | 010-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-040138 | 010-A-PFD-00001-008 | 010-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-040138 | 010-A-PFD-00001-009 | 010-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-040138 | 010-A-PFD-00001-010 | 010-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-040138 | 010-A-PFD-00001-011 | 010-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-040138 | 010-A-PFD-00001-012 | 010-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE CRUDE BLEND CASE | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-040139 | 011-A-PFD-00001-003 | 011-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040139 | 011-A-PFD-00001-004 | 011-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040139 | 011-A-PFD-00001-005 | 011-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CRUDE BLEND CASE | B | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040140 | 010-C-DAT-00005-001 | 010-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PREFLASH DRUM 010V0007 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040140 | 010-C-DAT-00006-001 | 010-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR ATMOSPHERIC COLUMN REFLUX DRUM 010V0008 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040140 | 010-C-DAT-00010-001 | 010-C-DAT-00010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STABILIZER REFLUX DRUM 010V0012 | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040141 | 372-D-DAT-57079-001 | 372-D-DAT-57079-001 | TANK DESIGN SPECIFICATION FOR 372D0279 FED STORAGE TANK | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040142 | 012-G-DAT-00016-001 | 012-G-DAT-00016-001 | MECHANICAL DATA SHEET COLD CONDENSATE MAKE UP PUMPS 012P0015 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00004-001 | 017-G-DAT-00004-001 | MECHANICAL DATA SHEET ABSORBER FEED PUMPS 017P0001 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00005-001 | 017-G-DAT-00005-001 | MECHANICAL DATA SHEET ABSORBER BOTTOM PUMPS 017P0003 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00006-001 | 017-G-DAT-00006-001 | MECHANICAL DATA SHEET ABSORBER REFLUX PUMPS 017P0002 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00007-001 | 017-G-DAT-00007-001 | MECHANICAL DATA SHEET DEETHANIZER FEED PUMPS 017P0004 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00008-001 | 017-G-DAT-00008-001 | MECHANICAL DATA SHEET DEETHANIZER BOTTOM PUMPS 017P0005 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00009-001 | 017-G-DAT-00009-001 | MECHANICAL DATA SHEET NAPHTHA SPLITTER REFLUX PUMPS 017P0007 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00010-001 | 017-G-DAT-00010-001 | MECHANICAL DATA SHEET C3/C4 SPLITTER REFLUX PUMPS 017P0009 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00011-001 | 017-G-DAT-00011-001 | MECHANICAL DATA SHEET LPG WATER WASH CIRCULATION PUMPS 017P0013 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00012-001 | 017-G-DAT-00012-001 | MECHANICAL DATA SHEET LP LEAN AMINE PUMPS 017P0010 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00013-001 | 017-G-DAT-00013-001 | MECHANICAL DATA SHEET RICH AMINE PUMPS 017P0012 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00015-001 | 017-G-DAT-00015-001 | MECHANICAL DATA SHEET CAUSTIC CIRCULATION PUMPS 017P0019 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040143 | 017-G-DAT-00016-001 | 017-G-DAT-00016-001 | MECHANICAL DATA SHEET COLD CONDENSATE MAKE UP PUPS 017P0015 A/B | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040144 | 011-P-INX-00001-001 | 011-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST N 7 VACUUM DISTILLATION UNIT - 7VDU | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040145 | 010-P-INX-00001-001 | 010-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST N 7 CRUDE DISTILLATION UNIT - 7CDU | A | 2018-05-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-14 | 3 - REVIEWED WITH COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-040146 | 019-A-PFD-00001-008 | 019-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-009 | 019-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-010 | 019-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-011 | 019-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-012 | 019-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-013 | 019-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-014 | 019-A-PFD-00001-014 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-015 | 019-A-PFD-00001-015 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-016 | 019-A-PFD-00001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-017 | 019-A-PFD-00001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-018 | 019-A-PFD-00001-018 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-019 | 019-A-PFD-00001-019 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-020 | 019-A-PFD-00001-020 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-021 | 019-A-PFD-00001-021 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-022 | 019-A-PFD-00001-022 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-023 | 019-A-PFD-00001-023 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-024 | 019-A-PFD-00001-024 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-025 | 019-A-PFD-00001-025 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-026 | 019-A-PFD-00001-026 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040146 | 019-A-PFD-00001-027 | 019-A-PFD-00001-027 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-028 | 019-A-PFD-00001-028 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-029 | 019-A-PFD-00001-029 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-030 | 019-A-PFD-00001-030 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-031 | 019-A-PFD-00001-031 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-032 | 019-A-PFD-00001-032 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-033 | 019-A-PFD-00001-033 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-034 | 019-A-PFD-00001-034 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-035 | 019-A-PFD-00001-035 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-036 | 019-A-PFD-00001-036 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-037 | 019-A-PFD-00001-037 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-038 | 019-A-PFD-00001-038 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-039 | 019-A-PFD-00001-039 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-040 | 019-A-PFD-00001-040 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-041 | 019-A-PFD-00001-041 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-042 | 019-A-PFD-00001-042 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-043 | 019-A-PFD-00001-043 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-044 | 019-A-PFD-00001-044 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-045 | 019-A-PFD-00001-045 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-046 | 019-A-PFD-00001-046 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040147 | 019-A-PFD-00001-047 | 019-A-PFD-00001-047 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-048 | 019-A-PFD-00001-048 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-049 | 019-A-PFD-00001-049 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-050 | 019-A-PFD-00001-050 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-051 | 019-A-PFD-00001-051 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-052 | 019-A-PFD-00001-052 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-053 | 019-A-PFD-00001-053 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-054 | 019-A-PFD-00001-054 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-055 | 019-A-PFD-00001-055 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-056 | 019-A-PFD-00001-056 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-057 | 019-A-PFD-00001-057 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-058 | 019-A-PFD-00001-058 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040148 | 019-A-PFD-00001-059 | 019-A-PFD-00001-059 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | B | 2018-05-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-040149 | 012-G-DAT-00001-001 | 012-G-DAT-00001-001 | MECHANICAL DATA SHEET STABILIZER REFLUX PUMPS 012P0006 A/B | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-040149 | 012-G-DAT-00002-001 | 012-G-DAT-00002-001 | MECHANICAL DATA SHEET NAPHTHA SPLITTER BOTTOM PUMPS 012P0008 A/B | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-040149 | 012-G-DAT-00003-001 | 012-G-DAT-00003-001 | MECHANICAL DATA SHEET LEAN AMINE PUMPS 012P0011 A/B | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-040150 | 017-G-DAT-00001-001 | 017-G-DAT-00001-001 | MECHANICAL DATA SHEET STABILIZER REFLUX PUMPS 017P0006 A/B | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-040150 | 017-G-DAT-00002-001 | 017-G-DAT-00002-001 | MECHANICAL DATA SHEET NAPHTHA SPLITTER BOTTOM PUMPS 017P0008 A/B | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-040150 | 017-G-DAT-00003-001 | 017-G-DAT-00003-001 | MECHANICAL DATA SHEET LEAN AMINE PUMPS 017P0011 A/B | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-040151 | 012-A-RPT-00001-001 | 012-A-STS-00001-001 | SGP UNIT SIMULATION REPORT | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040152 | 019-A-PID-00001-001 | 019-A-PID-00001-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION FEED SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00002-001 | 019-A-PID-00002-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION RAW FEED SURGE DRUM & BOOSTER PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00003-001 | 019-A-PID-00003-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION FEED PREHEAT EXCHANGERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00004-001 | 019-A-PID-00004-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION FEED FILTERS 1 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00005-001 | 019-A-PID-00005-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION FEED FILTERS 2 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00006-001 | 019-A-PID-00006-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION 1ST STAGE FEED SURGE DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00007-001 | 019-A-PID-00007-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION 1ST STAGE REACTION FEED PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00008-001 | 019-A-PID-00008-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION 1ST STAGE REACTION EFFLUENT EXCHANGES 1 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00009-001 | 019-A-PID-00009-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION 1ST STAGE REACTION EFFLUENT EXCHANGES 2 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00010-001 | 019-A-PID-00010-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION 1ST STAGE REACTION FEED FURNACE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00011-001 | 019-A-PID-00011-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION 1ST STAGE REACTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00012-001 | 019-A-PID-00012-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION 1ST STAGE REACTION EFFLUENT / FRACTIONATOR FEED EXCHANG | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00013-001 | 019-A-PID-00013-001 | P&ID - 2HCU 1ST STAGE REACTION SECTION 1ST STAGE HHPS AND VAPOR / RECYCLE GAS EXCHANGER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00014-001 | 019-A-PID-00014-001 | P&ID - 2HCU RECYCLE GAS SECTION 1ST STAGE HHPS VAPOR AIR COOLERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00015-001 | 019-A-PID-00015-001 | P&ID - 2HCU RECYCLE GAS SECTION 1ST STAGE CHPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00016-001 | 019-A-PID-00016-001 | P&ID - 2HCU RECYCLE GAS SECTION HP H2S ABSORBER AND HIGH PRESSURE CENTRIFUGAL SEPARATOR | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00017-001 | 019-A-PID-00017-001 | P&ID - 2HCU 2ND STAGE REACTION SECTION 2ND STAGE FEED SURGE DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00018-001 | 019-A-PID-00018-001 | P&ID - 2HCU 2ND STAGE REACTION SECTION 2ND STAGE REACTOR FEED PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00019-001 | 019-A-PID-00019-001 | P&ID - 2HCU 2ND STAGE REACTION SECTION 2ND STAGE REACTOR FEED/EFFLUENT EXCHANGERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040152 | 019-A-PID-00020-001 | 019-A-PID-00020-001 | P&ID - 2HCU 2ND STAGE REACTION SECTION 2ND STAGE REACTOR FEED FURNACE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00021-001 | 019-A-PID-00021-001 | P&ID - 2HCU 2ND STAGE REACTION SECTION 2ND STAGE REACTOR | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-20 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00022-001 | 019-A-PID-00022-001 | P&ID - 2HCU 2ND STAGE REACTION SECTION 2ND STAGE HHPS & HHPS VAPOR/CLPS LIQUID EXCHANGER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00023-001 | 019-A-PID-00023-001 | P&ID - 2HCU 2ND STAGE REACTION SECTION 2ND STAGE HHPS VAPOR AIR COOLER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00024-001 | 019-A-PID-00024-001 | P&ID - 2HCU 2ND STAGE REACTION SECTION 2ND STAGE CHPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00025-001 | 019-A-PID-00025-001 | P&ID - 2HCU RECYCLE GAS SECTION RECYCLE GAS KNOCKOUT DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00026-001 | 019-A-PID-00026-001 | P&ID - 2HCU RECYCLE GAS SECTION RECYCLE GAS COMPRESSOR | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00027-001 | 019-A-PID-00027-001 | P&ID - 2HCU MAKE-UP HYDROGEN COMPRESSION SECTION MAKE-UP H2 COMPRESSOR SYSTEM & SPILLBACK | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00028-001 | 019-A-PID-00028-001 | P&ID - 2HCU MAKE-UP HYDROGEN COMPRESSION SECTION MAKE-UP H2 COMPRESSOR S019K0002 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00029-001 | 019-A-PID-00029-001 | P&ID - 2HCU MAKE-UP HYDROGEN COMPRESSION SECTION MAKE-UP H2 COMPRESSOR S019K0003 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00030-001 | 019-A-PID-00030-001 | P&ID - 2HCU MAKE-UP HYDROGEN COMPRESSION SECTION MAKE-UP H2 COMPRESSOR S019K0004 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00031-001 | 019-A-PID-00031-001 | P&ID - 2HCU LP SEPARATION SECTION HLPS AND HLPS VAPOR AIR COOLER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00032-001 | 019-A-PID-00032-001 | P&ID - 2HCU LP SEPARATION SECTION COLD LOW PRESSURE SEPARATOR | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00033-001 | 019-A-PID-00033-001 | P&ID - 2HCU PRODUCT STRIPPER SECTION PRODUCT STRIPPER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00034-001 | 019-A-PID-00034-001 | P&ID - 2HCU PRODUCT STRIPPER SECTION PRODUCT STRIPPER BOTTOMS PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00035-001 | 019-A-PID-00035-001 | P&ID - 2HCU PRODUCT STRIPPER SECTION PRODUCT STRIPPER OVERHEAD AIR COOLER AND DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00036-001 | 019-A-PID-00036-001 | P&ID - 2HCU PRODUCT STRIPPER SECTION PRODUCT STRIPPER REFLUX PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00037-001 | 019-A-PID-00037-001 | P&ID - 2HCU FRACTIONATION SECTION FRACTIONATOR FEED FURNACE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00038-001 | 019-A-PID-00038-001 | P&ID - 2HCU FRACTIONATION SECTION PRODUCT FRACTIONATOR TOP SECTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00039-001 | 019-A-PID-00039-001 | P&ID - 2HCU FRACTIONATION SECTION PRODUCT FRACTIONATOR BOTTOM SECTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040153 | 019-A-PID-00040-001 | 019-A-PID-00040-001 | P&ID - 2HCU FRACTIONATION SECTION FRACTIONATOR OVERHEAD SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040154 | 019-C-DAT-00002-001 | 019-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE FEED SURGE DRUM 019V0002 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00013-001 | 019-C-DAT-00013-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FRACTIONATOR REFLUX DRUM 019V0013 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00015-001 | 019-C-DAT-00015-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER REFLUX DRUM 019V0015 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00016-001 | 019-C-DAT-00016-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER REBOILER CONDENSATE POT 019V0016 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00017-001 | 019-C-DAT-00017-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR VACUUM DRYER HOTWELL 019V0017 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00026-001 | 019-C-DAT-00026-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LEAN AMINE SURGE DRUM 019V0026 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00030-001 | 019-C-DAT-00030-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR BACKWASH OIL SURGE DRUM 019V0030 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00032-001 | 019-C-DAT-00032-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FUEL GAS KO DRUM 019V0032 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00036-001 | 019-C-DAT-00036-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECOVERED PROCESS SLOP OIL SUMP 019V0036 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00037-001 | 019-C-DAT-00037-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR AMINE SUMP 019V0037 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040154 | 019-C-DAT-00038-001 | 019-C-DAT-00038-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SOUR WATER SUMP 019V0038 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040155 | 019-A-PID-00041-001 | 019-A-PID-00041-001 | P&ID - 2HCU FRACTIONATION SECTION FRACTIONATOR NAPHTHA PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00042-001 | 019-A-PID-00042-001 | P&ID - 2HCU FRACTIONATION SECTION FRACTIONATOR BOTTOMS PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00043-001 | 019-A-PID-00043-001 | P&ID - 2HCU FRACTIONATION SECTION KEROSENE STRIPPER REBOILER & PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00044-001 | 019-A-PID-00044-001 | P&ID - 2HCU FRACTIONATION SECTION KEROSENE PRODUCT COOLING SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00045-001 | 019-A-PID-00045-001 | P&ID - 2HCU FRACTIONATION SECTION KEROSENE EXTERNAL REFLUX PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00046-001 | 019-A-PID-00046-001 | P&ID - 2HCU LIGHT DIESEL SECTION LIGHT DIESEL STRIPPER REBOILER AND PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00047-001 | 019-A-PID-00047-001 | P&ID - 2HCU FRACTIONATION SECTION LIGHT DIESEL PRODUCT COOLING SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00048-001 | 019-A-PID-00048-001 | P&ID - 2HCU FRACTIONATION SECTION DIESEL PRODUCT COOLING SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00049-001 | 019-A-PID-00049-001 | P&ID - 2HCU FRACTIONATION SECTION HEAVY DIESEL STRIPPER AND STRIPPER BOTTOMS PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00050-001 | 019-A-PID-00050-001 | P&ID - 2HCU FRACTIONATION SECTION HEAVY DIESEL EXCHANGERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00051-001 | 019-A-PID-00051-001 | P&ID - 2HCU FRACTIONATION SECTION DIESEL VACUUM DRYER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00052-001 | 019-A-PID-00052-001 | P&ID - 2HCU FRACTIONATION SECTION VACUUM DRYER EJECTOR SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00053-001 | 019-A-PID-00053-001 | P&ID - 2HCU FRACTIONATION SECTION VACUUM DRYER HOTWELL | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00054-001 | 019-A-PID-00054-001 | P&ID - 2HCU FRACTIONATION SECTION FRACTIONATOR BOTTOMS STEAM GENERATOR | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00055-001 | 019-A-PID-00055-001 | P&ID - 2HCU FRACTIONATION SECTION FRACTIONATOR BOTTOMS COOLING SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040155 | 019-A-PID-00056-001 | 019-A-PID-00056-001 | P&ID - 2HCU FRACTIONATION SECTION LIGHT DIESEL P/A STEAM GENERATOR | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00057-001 | 019-A-PID-00057-001 | P&ID - 2HCU FRACTIONATION SECTION LIGHT DIESEL P/A PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00058-001 | 019-A-PID-00058-001 | P&ID - 2HCU FRACTIONATION SECTION HEAVY DIESEL P/A STEAM GENERATOR | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00059-001 | 019-A-PID-00059-001 | P&ID - 2HCU FRACTIONATION SECTION HEAVY DIESEL P/A PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00060-001 | 019-A-PID-00060-001 | P&ID - 2HCU NAPHTHA PRODUCT SECTION NAPHTHA STABILIZER REBOILER AND EXCHANGER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00061-001 | 019-A-PID-00061-001 | P&ID - 2HCU NAPHTHA PRODUCT SECTION NAPHTHA STABILIZER OVERHEAD SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00062-001 | 019-A-PID-00062-001 | P&ID - 2HCU NAPHTHA PRODUCT SECTION NAPHTHA STABILIZER REFLUX PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00063-001 | 019-A-PID-00063-001 | P&ID - 2HCU NAPHTHA PRODUCT SECTION NAPHTHA SPLITTER/REBOILER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00064-001 | 019-A-PID-00064-001 | P&ID - 2HCU NAPHTHA PRODUCT SECTION NAPHTHA SPLITTER OVERHEAD SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00065-001 | 019-A-PID-00065-001 | P&ID - 2HCU NAPHTHA PRODUCT SECTION NAPHTHA SPLITTER REFLUX PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00066-001 | 019-A-PID-00066-001 | P&ID - 2HCU NAPHTHA PRODUCT SECTION NAPHTHA SPLITTER BOTTOM PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00067-001 | 019-A-PID-00067-001 | P&ID - 2HCU NAPHTHA PRODUCT SECTION NAPHTHA PRODUCT COOLING SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00068-001 | 019-A-PID-00068-001 | P&ID - 2HCU REACTION SECTION REACTION FURNACES STEAM GENERATION SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00069-001 | 019-A-PID-00069-001 | P&ID - 2HCU FRACTIONATION SECTION FRACTIONATOR FEED FURNACE STEAM GENERATION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00070-001 | 019-A-PID-00070-001 | P&ID - 2HCU RECYCLE GAS SECTION LEAN AMINE SURGE DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00071-001 | 019-A-PID-00071-001 | P&ID - 2HCU RECYCLE GAS SECTION HIGH PRESSURE LEAN AMINE PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00072-001 | 019-A-PID-00072-001 | P&ID - 2HCU RECYCLE GAS SECTION INJECTION WATER DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00073-001 | 019-A-PID-00073-001 | P&ID - 2HCU RECYCLE GAS SECTION INJECTION WATER PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00074-001 | 019-A-PID-00074-001 | P&ID - 2HCU AMINE AND WATER SECTION RICH AMINE FLASH DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00075-001 | 019-A-PID-00075-001 | P&ID - 2HCU LP SEPARATION SECTION SOUR WATER FLASH DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040156 | 019-A-PID-00076-001 | 019-A-PID-00076-001 | P&ID - 2HCU LP SEPARATION SECTION FILTER BACKWASH SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00077-001 | 019-A-PID-00077-001 | P&ID - 2HCU FUEL GAS KO DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00078-001 | 019-A-PID-00078-001 | P&ID - 2HCU FUEL GAS SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00079-001 | 019-A-PID-00079-001 | P&ID - 2HCU REACTION SECTION 019F0001 FUEL GAS SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00080-001 | 019-A-PID-00080-001 | P&ID - 2HCU REACTION SECTION 019F0002 FUEL GAS SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00081-001 | 019-A-PID-00081-001 | P&ID - 2HCU FRACTIONATION SECTION 019F0003 FUEL GAS SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00082-001 | 019-A-PID-00082-001 | P&ID - 2HCU FRACTIONATION SECTION 019F0003 AIR PREHEATING | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00083-001 | 019-A-PID-00083-001 | P&ID - 2HCU RECOVERED PROCESS SLOP OIL DRAIN DRUM AND SLOP SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00083-002 | 019-A-PID-00083-002 | P&ID - 2HCU PROCESS SLOP OIL DRAIN DISTRIBUTION SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00083-003 | 019-A-PID-00083-003 | P&ID - 2HCU PROCESS SLOP OIL DRAIN DISTRIBUTION SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00083-004 | 019-A-PID-00083-004 | P&ID - 2HCU PROCESS SLOP OIL DRAIN DISTRIBUTION SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00084-001 | 019-A-PID-00084-001 | P&ID - 2HCU AMINE CLOSED DRAIN SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00084-002 | 019-A-PID-00084-002 | P&ID - 2HCU AMINE DRAIN DISTRIBUTION SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00085-001 | 019-A-PID-00085-001 | P&ID - 2HCU SOUR WATER DRAIN SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00085-002 | 019-A-PID-00085-002 | P&ID - SOUR WATER SUMP COLLECTION HEADER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00086-001 | 019-A-PID-00086-001 | P&ID - 2HCU FLARE KO DRUM AND DISTRIBUTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00086-002 | 019-A-PID-00086-002 | P&ID - 2HCU FLARE PURGE GAS DISTRIBUTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00086-003 | 019-A-PID-00086-003 | P&ID - 2HCU FLARE DISTRIBUTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00087-001 | 019-A-PID-00087-001 | P&ID - 2HCU 550 / 110 STEAM SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00088-001 | 019-A-PID-00088-001 | P&ID - 2HCU 60 STEAM SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040157 | 019-A-PID-00088-002 | 019-A-PID-00088-002 | P&ID - 2HCU 60 STEAM SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040158 | 012-A-BOD-00001-001 | 012-A-BOD-00001-001 | SPG UNIT BASIS OF DESIGN | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00001-001 | 011-A-PID-00001-001 | P&ID - 7VDU VACUUM HEATER SECTION VACUUM HEATER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00002-001 | 011-A-PID-00002-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION VACUUM COLUMN TOP SECTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00003-001 | 011-A-PID-00003-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION VACUUM COLUMN BOTTOM SECTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00004-001 | 011-A-PID-00004-001 | P&ID - 7VDU VACUUM SYSTEM SECTION FIRST STAGE EJECTORS / CONDENSERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00004-002 | 011-A-PID-00004-002 | P&ID - 7VDU VACUUM SYSTEM SECTION SECOND STAGE EJECTORS / CONDENSERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00004-003 | 011-A-PID-00004-003 | P&ID - 7VDU VACUUM SYSTEM SECTION THIRD STAGE EJECTORS / CONDENSERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00005-001 | 011-A-PID-00005-001 | P&ID - 7VDU VACUUM SYSTEM SECTION VACUUM HOT WELL | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00006-001 | 011-A-PID-00006-001 | P&ID - 7VDU VDU OFFGAS AND AMINE SECTION VDU OFFGAS AMINE ABSORBER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00007-001 | 011-A-PID-00007-001 | P&ID - 7VDU VDU OFFGAS AND AMINE SECTION LEAN AMINE COOLERS/RICH AMINE PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00008-001 | 011-A-PID-00008-001 | P&ID - 7VDU VDU OFFGAS AND AMINE SECTION SWEET TAIL GAS KO DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00009-001 | 011-A-PID-00009-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION LVGO PUMPAROUND PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00010-001 | 011-A-PID-00010-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION LVGO COOLER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040159 | 011-A-PID-00011-001 | 011-A-PID-00011-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION MVGO PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00012-001 | 011-A-PID-00012-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION MVGO AND BSGO PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00013-001 | 011-A-PID-00013-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION MVGO/HVGO COOLER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00014-001 | 011-A-PID-00014-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION VACUUM RESIDUE PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00015-001 | 011-A-PID-00015-001 | P&ID - 7VDU VACUUM DISTILLATION SECTION VACUUM RESIDUE COOLER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00016-001 | 011-A-PID-00016-001 | P&ID - 7VDU STEAM GENERATION SECTION STEAM GENERATION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00017-001 | 011-A-PID-00017-001 | P&ID - 7VDU STEAM GENERATION SECTION STEAM BLOWDOWN SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00018-001 | 011-A-PID-00018-001 | P&ID - 7VDU VACUUM HEATER SECTIN FUEL GAS SYSTEM FURNACE 011F0001 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00019-001 | 011-A-PID-00019-001 | P&ID - 7VDU TEMPERED WATER SECTION TEMPERED WATER SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00020-001 | 011-A-PID-00020-001 | P&ID - 7VDU VACUUM HEATER SECTION HEATER STACK AND DETAIL | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00021-001 | 011-A-PID-00021-001 | P&ID - 7VDU VACUUM HEATER SECTION PASSES INSTRUMENTATION TAGS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00022-001 | 011-A-PID-00022-001 | P&ID - 7VDU CHEMICAL INJECTION SECTION PHOSPHATE INJECTION PACKAGE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040160 | 011-A-PID-00023-001 | 011-A-PID-00023-001 | P&ID - 7VDU AIR FIN DETAILS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00001-001 | 010-A-PID-00001-001 | P&ID - 7CDU CRUDE FEED PREHEAT SECTION CRUDE CHARGE PUMPS AND CRUDE PREHEAT/KERO | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00002-001 | 010-A-PID-00002-001 | P&ID - 7CDU CRUDE FEED PREHEAT SECTION CRUDE PREHEAT/CDU OVH | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00003-001 | 010-A-PID-00003-001 | P&ID - 7CDU CRUDE FEED PREHEAT SECTION CRUDE PREHEAT/KERO PA AND DIESEL | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00004-001 | 010-A-PID-00004-001 | P&ID - 7CDU DESALTING SECTION FIRST STAGE DESALTER-TRAIN A | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00005-001 | 010-A-PID-00005-001 | P&ID - 7CDU DESALTING SECTION SECOND STAGE DESALTER-TRAIN A | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00006-001 | 010-A-PID-00006-001 | P&ID - 7CDU DESALTING SECTION FIRST STAGE DESALTER-TRAIN B | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00007-001 | 010-A-PID-00007-001 | P&ID - 7CDU DESALTING SECTION SECOND STAGE DESALTER-TRAIN B | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00008-001 | 010-A-PID-00008-001 | P&ID - 7CDU DESALTING CRUDE PREHEAT SECTION DESALTED CRUDE PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00009-001 | 010-A-PID-00009-001 | P&ID - 7CDU DESALTING CRUDE PREHEAT SECTION CRUDE PREHEAT/MVGO/HVGO AND DIESEL | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00010-001 | 010-A-PID-00010-001 | P&ID - 7CDU DESALTING CRUDE PREHEAT SECTION CRUDE PREHEAT/KERO AND KERO PA | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00011-001 | 010-A-PID-00011-001 | P&ID - 7CDU FLASHED CRUDE PREHEAT SECTION PREFLASH DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00012-001 | 010-A-PID-00012-001 | P&ID - 7CDU FLASHED CRUDE PREHEAT SECTION CRUDE PREHEAT / DIESEL PA DIESEL AND VACUUM RESI | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00013-001 | 010-A-PID-00013-001 | P&ID - 7CDU FLASHED CRUDE PREHEAT SECTION CRUDE PREHEAT / HVGO & DIESEL PA | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00014-001 | 010-A-PID-00014-001 | P&ID - 7CDU FLASHED CRUDE PREHEAT SECTION CRUDE PREHEAT / HVGO PA AND VACUUM RESIDUE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00015-001 | 010-A-PID-00015-001 | P&ID - 7CDU CRUDE HEATER SECTION CRUDE HEATER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00016-001 | 010-A-PID-00016-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION CRUDE DISTILLATION COLUMN TOP SECTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00017-001 | 010-A-PID-00017-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION CRUDE DISTILLATION COLUMN BOTTOM SECTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00018-001 | 010-A-PID-00018-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION ATM COLUMN REFLUX DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00019-001 | 010-A-PID-00019-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION ATM COLUMN OVERHEAD COLLERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040161 | 010-A-PID-00020-001 | 010-A-PID-00020-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION OVERHEAD PRODUCT ACCUMULATOR | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00089-001 | 019-A-PID-00089-001 | P&ID - 2HCU STEAM BLOWDOWN COLLECTION SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00090-001 | 019-A-PID-00090-001 | P&ID - 2HCU LP BOILER FEED WATER SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00091-001 | 019-A-PID-00091-001 | P&ID - 2HCU 550 / 110 / 60 STEAM CONDENSATE SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00092-001 | 019-A-PID-00092-001 | P&ID - 2HCU COOLING WATER SYSTEM (MAIN) | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00093-001 | 019-A-PID-00093-001 | P&ID - 2HCU DRINKING AND UTILITY WATER SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00093-002 | 019-A-PID-00093-002 | P&ID - 2HCU DRINKING UTILITY AND CHILLED WATER SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00094-001 | 019-A-PID-00094-001 | P&ID - 2HCU INSTRUMENT AND YARD AIR SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00094-002 | 019-A-PID-00094-002 | P&ID - 2HCU INSTRUMENT AND YARD AIR SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00095-001 | 019-A-PID-00095-001 | P&ID - 2HCU NITROGEN SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00096-001 | 019-A-PID-00096-001 | P&ID - 2HCU FLUSHING OIL SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00101-001 | 019-A-PID-00101-001 | P&ID - 2HCU RECYCLE GAS SECTION ANTIFOAM INJECTION PACKAGE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00102-001 | 019-A-PID-00102-001 | P&ID - 2HCU FRACTIONATION SECTION ANTIOXIDANT ADDITIVE SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00103-001 | 019-A-PID-00103-001 | P&ID - 2HCU FRACTIONATION SECTION ANTISTATIC ADDITIVE SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00104-001 | 019-A-PID-00104-001 | P&ID - 2HCU FRACTIONATION SECTION PHOSPHATE INJECTION PACKAGE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00105-001 | 019-A-PID-00105-001 | P&ID - 2HCU AIR FIN DETAILS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00106-001 | 019-A-PID-00106-001 | P&ID - 2HCU AIR FIN DETAILS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040162 | 019-A-PID-00107-001 | 019-A-PID-00107-001 | P&ID - 2HCU AIR FIN DETAILS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00021-001 | 010-A-PID-00021-001 | P&ID - 7CDU GAS COMPRESSION SECTION CRUDE OVHD FIRST STAGE COMPRESSION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00022-001 | 010-A-PID-00022-001 | P&ID - 7CDU GAS COMPRESSION SECTION CRUDE OVHD SECOND STAGE COMPRESSION A | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00023-001 | 010-A-PID-00023-001 | P&ID - 7CDU GAS COMPRESSION SECTION CRUDE OVHD SECOND STAGE COMPRESSION B | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00024-001 | 010-A-PID-00024-001 | P&ID - 7CDU NAPHTHA STABILIZER SECTION STABILIZER FEED/EFFLUENT EXCHANGERS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00025-001 | 010-A-PID-00025-001 | P&ID - 7CDU NAPHTHA STABILIZER SECTION STABILIZER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00026-001 | 010-A-PID-00026-001 | P&ID - 7CDU NAPHTHA STABILIZER SECTION STABILIZER OVERHEAD REFLUX DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00027-001 | 010-A-PID-00027-001 | P&ID - 7CDU NAPHTHA SPLITTER SECTION NAPHTA SPLITTER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00028-001 | 010-A-PID-00028-001 | P&ID - 7CDU NAPHTHA SPLITTER SECTION NAPHTA SPLITTER REFLUX DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00029-001 | 010-A-PID-00029-001 | P&ID - 7CDU NAPHTHA SPLITTER SECTION NAPHTHA SPLITTER REFLUX PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00030-001 | 010-A-PID-00030-001 | P&ID - 7CDU NAPHTHA SPLITTER SECTION NAPHTHA SPLITTER BOTTOM PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00031-001 | 010-A-PID-00031-001 | P&ID - 7CDU NAPHTHA SPLITTER SECTION NAPHTHA PRODUCT COOLING SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00032-001 | 010-A-PID-00032-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION KERO STRIPPER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00033-001 | 010-A-PID-00033-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION DIESEL STRIPPER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00034-001 | 010-A-PID-00034-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION KERO/DIESEL PRODUCT COOLER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00035-001 | 010-A-PID-00035-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION KERO PA AND DIESEL PA PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00036-001 | 010-A-PID-00036-001 | P&ID - 7CDU CRUDE DISTILLATION SECTION REDUCED CRUDE PUMPS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00037-001 | 010-A-PID-00037-001 | P&ID - 7CDU DESALTING SECTION DESALTING WATER SURGE DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00038-001 | 010-A-PID-00038-001 | P&ID - 7CDU DESALTING SECTION DESALTER BRINE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00039-001 | 010-A-PID-00039-001 | P&ID - 7CDU FUEL GAS SYSTEM PROCESS FUEL GAS KO DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040163 | 010-A-PID-00040-001 | 010-A-PID-00040-001 | P&ID - 7CDU CRUDE HEATER SECTION FUEL GAS SYSEM FURNACE 010F0001 | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00041-001 | 010-A-PID-00041-001 | P&ID - 7CDU RECOVERED SLOPS CLOSED DRAIN SYSTEM RECOVERED SLOPS CLOSED DRAIN | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00041-002 | 010-A-PID-00041-002 | P&ID - 7CDU RECOVERED SLOPS CLOSED DRAIN SYSTEM RECOVERED SLOPS CLOSED DRAIN | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00041-003 | 010-A-PID-00041-003 | P&ID - 7CDU RECOVERED SLOPS CLOSED DRAIN SYSTEM RECOVERED SLOPS CLOSED DRAIN | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00041-004 | 010-A-PID-00041-004 | P&ID - 7CDU RECOVERED SLOPS CLOSED DRAIN SYSTEM RECOVERED SLOPS CLOSED DRAIN | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00041-005 | 010-A-PID-00041-005 | P&ID - 7CDU/7VDU RECOVERED SLOPS CLOSED DRAIN SYSTEM RECOVERED SLOPS CLOSED DRAIN | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00042-001 | 010-A-PID-00042-001 | P&ID - 7CDU SOUR WATER CLOSED DRAIN SYSTEM SOUR WATER DRAIN DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00042-002 | 010-A-PID-00042-002 | P&ID - 7CDU SOUR WATER CLOSED DRAIN SYSTEM SOUR WATER DRAIN HEADER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00043-001 | 010-A-PID-00043-001 | P&ID - 7CDU FLARE SYSTEM FLARE KO DRUM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00043-002 | 010-A-PID-00043-002 | P&ID - 7CDU FLARE PURGE GAS DISTRIBUTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00043-003 | 010-A-PID-00043-003 | P&ID - 7CDU FLARE SYSTEM FLARE DISTRIBUTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00044-001 | 010-A-PID-00044-001 | P&ID - 7CDU 60 / 110 / 550 STEAM SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00045-001 | 010-A-PID-00045-001 | P&ID - 7CDU 60 STEAM SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00045-002 | 010-A-PID-00045-002 | P&ID - 7CDU 60 STEAM SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00045-003 | 010-A-PID-00045-003 | P&ID - 7CDU 60 STEAM SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00046-001 | 010-A-PID-00046-001 | P&ID - 7CDU BOILER FEED WATER SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00047-001 | 010-A-PID-00047-001 | P&ID - 7CDU 60 / 110 / 550 STEAM CONDENSATE SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00048-001 | 010-A-PID-00048-001 | P&ID - 7CDU COOLING WATER SYSTEM (MAIN) | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00049-001 | 010-A-PID-00049-001 | P&ID - 7CDU/7VDU UTILITY DRINKING AND CHILLED WATER SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00050-001 | 010-A-PID-00050-001 | P&ID - 7CDU INSTRUMENT AIR AND YARD AIR SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040164 | 010-A-PID-00051-001 | 010-A-PID-00051-001 | P&ID - 7CDU NITROGEN SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00052-001 | 010-A-PID-00052-001 | P&ID - 7CDU FLUSHING OIL SYSTEM | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00057-001 | 010-A-PID-00057-001 | P&ID - 7CDU CRUDE HEATER SECTION COMBUSTION AIR PREHEATING | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00058-001 | 010-A-PID-00058-001 | P&ID - 7CDU CRUDE HEATER SECTION HEATER STACK & DETAIL | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00059-001 | 010-A-PID-00059-001 | P&ID - 7CDU CRUDE HEATER SECTION PASSES INSTRUMENTATION TAGS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00060-001 | 010-A-PID-00060-001 | P&ID - 7CDU CHEMICAL INJECTION SECTION NEUTRALIZINAG AMINE INJECTION PACKAGE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00061-001 | 010-A-PID-00061-001 | P&ID - 7CDU CHEMICAL INJECTION SECTION FILMING AMINE INJECTIN PACKAGE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00062-001 | 010-A-PID-00062-001 | P&ID - 7CDU CHEMICAL INJECTION SECTION DE-EMULSIFIER INJECTION | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00063-001 | 010-A-PID-00063-001 | P&ID - 7CDU CHEMICAL INJECTION SECTION ANTI-FOAMING AGENT INJECTION PACKAGE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00064-001 | 010-A-PID-00064-001 | P&ID - 7CDU CHEMICAL INJECTION SECTION ANTI FOULING INJECTION PACKAGE | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040165 | 010-A-PID-00065-001 | 010-A-PID-00065-001 | P&ID - 7CDU AIR FIN DETAILS | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040166 | 019-C-DAT-00005-001 | 019-C-DAT-00005-001 | MECHANICAL DATA SHEET HIGH PRESSURE CENTRIFUGAL SEPARATOR 019V0005 | B | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-040167 | 011-C-DAT-00003-001 | 011-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SWEET TAIL GAS KO DRUM 011V0007 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-040167 | 011-C-DAT-00004-001 | 011-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR TEMPERED WATER DRUM 011V0008 | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-040168 | 010-P-INX-00004-001 | 010-P-INX-00004-001 | HAZARDOUS SOURCE OF RELEASE LIST P010-7CDU/P011-7VDU | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-040169 | 085-A-BOD-00001-001 | 085-A-BOD-00001-001 | 085 BASIS OF DESIGN CWT COOLING WATER TOWER | A | 2018-06-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-040170 | 085-P-STS-00001-001 | 085-P-STS-00001-001 | LOAD BALANCE COOLING WATER SUBSTATION SST085R01 | A | 2018-06-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 2
CON-BMP-TRA-040171 | 010-P-SLD-00001-001 | 010-P-SLD-00001-001 | KEY SINGLE LINE DIAGRAM - 7CDU SUBSTATION SST010R01 | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040171 | 010-P-SLD-00001-002 | 010-P-SLD-00001-002 | KEY SINGLE LINE DIAGRAM - 7CDU SUBSTATION SST010R01 | A | 2018-06-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 1
CON-BMP-TRA-040172 | 019-C-DAT-00027-001 | 019-C-DAT-00027-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR INJECTION WATER DRUM 019V0027 | A | 2018-06-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 2
CON-BMP-TRA-040172 | 019-C-DAT-00033-001 | 019-C-DAT-00033-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PROCESS GAS KO DRUM 019V0033 | A | 2018-06-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 3 - REVIEWED WITH COMMENTS | 2018-06-15 | CLASS 2
CON-BMP-TRA-040173 | 019-G-DAT-00009-001 | 019-G-DAT-00009-001 | MECHANICAL DATA SHEET HEAVY NAPHTHA PRODUCT PUMPS 019P0020A/B/C | A | 2018-06-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-040173 | 019-G-DAT-00010-001 | 019-G-DAT-00010-001 | MECHANICAL DATA SHEET HEAVY DIESEL PUMP AROUND PUMP 019P0012A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-040174 | 019-G-DAT-00005-001 | 019-G-DAT-00005-001 | MECHANICAL DATA SHEET PRODUCT STRIPPER BOTTOM PUMPS 019P0005A/B | A | 2018-06-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-040174 | 019-G-DAT-00006-001 | 019-G-DAT-00006-001 | MECHANICAL DATA SHEET FRACTIONATOR BOTTOM PUMPS 019P0017A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-040174 | 019-G-DAT-00007-001 | 019-G-DAT-00007-001 | MECHANICAL DATA SHEET LIGHT DIESEL P/A PUMO 019P0010 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-040174 | 019-G-DAT-00008-001 | 019-G-DAT-00008-001 | MECHANICAL DATA SHEET FRACTIONATOR NAPHTA PUMPS 019P0006 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-040175 | 019-G-DAT-00028-001 | 019-G-DAT-00028-001 | MECHANICAL DATA SHEET LIGHT DIESEL PRODUCT PUMP 019P0011A/B | A | 2018-06-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-15 | CLASS 2
CON-BMP-TRA-040176 | 010-G-DAT-00001-001 | 010-G-DAT-00001-001 | MECHANICAL DATA SHEET CRUDE FEED PUMPS 010-P0001A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040176 | 010-G-DAT-00002-001 | 010-G-DAT-00002-001 | MECHANICAL DATA SHEET DESALTED CRUDE PUMPS 010P0002 A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040176 | 010-G-DAT-00003-001 | 010-G-DAT-00003-001 | MECHANICAL DATA SHEET PREFLASHED DRUM BOTTOM PUMPS 010P0029A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040176 | 010-G-DAT-00004-001 | 010-G-DAT-00004-001 | MECHANICAL DATA SHEET KERO PA PUMPS 010P0007A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040176 | 010-G-DAT-00005-001 | 010-G-DAT-00005-001 | MECHANICAL DATA SHEET DIESEL PA PUMPS 010P0010A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040176 | 010-G-DAT-00006-001 | 010-G-DAT-00006-001 | MECHANICAL DATA SHEET UNSTABILIZED NAPHTA PUMPS 010P0019A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040176 | 010-G-DAT-00008-001 | 010-G-DAT-00008-001 | MECHANICAL DATA SHEET DIESEL PRODUCT PUMPS 010P0012A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040177 | 011-G-DAT-00001-001 | 011-G-DAT-00001-001 | MECHANICAL DATA SHEET - HVGO PUMPS 011P0004 A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-040178 | 019-C-GAD-00011-001 | 019-C-GAD-00011-001 | GENERAL ARRANGEMENT COLD LOW PRESSURE SEPARATOR DRUM 019V0011 | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-040178 | 019-C-GAD-00014-001 | 019-C-GAD-00014-001 | GENERAL ARRANGEMENT NAPHTHA STABILIZER REFLUX DRUM 019V0014 | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-040178 | 019-C-GAD-00028-001 | 019-C-GAD-00028-001 | GENERAL ARRANGEMENT RICH AMINE FLASH DRUM 019V0028 | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-040178 | 019-C-GAD-00029-001 | 019-C-GAD-00029-001 | GENERAL ARRANGEMENT SOUR WATER FLASH DRUM 019V0029 | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-040179 | 050-G-DAT-55001-001 | 050-G-DAT-55001-001 | MECHANICAL DATA SHEET 1RHCU BOOSTER FEED PUMPS 018P0038 A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-040180 | 085-G-DAT-00001-001 | 085-G-DAT-00001-001 | MECHANICAL DATA SHEET MAIN COOLING WATER CIRCULATING PUMPS 085P0001 A/B/C/D/E | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040180 | 085-G-DAT-00002-001 | 085-G-DAT-00002-001 | MECHANICAL DATA SHEET SECONDARY COOLING WATER CIRCULATING PUMPS 085P0002A/B | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040181 | 372-G-DAT-57001-001 | 372-G-DAT-57001-001 | MECHANICAL DATA SHEET FED WATER PUMPS 372P0030 A/B/C | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040181 | 372-G-DAT-57002-001 | 372-G-DAT-57002-001 | MECHANICAL DATA SHEET COOLING WATER MAKE-UP PUMPS 372P0031 A/B/C | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040182 | 010-E-DAT-00030-001 | 010-E-DAT-00030-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0021 KERO AIR COOLER | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-040182 | 010-E-DAT-00031-001 | 010-E-DAT-00031-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0023 DIESEL AIR COOLER | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-040182 | 010-E-DAT-00032-001 | 010-E-DAT-00032-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0029 NAPHTA SPLITTER OVERHEAD AIR COOLER | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-040183 | 019-E-DAT-00041-001 | 019-E-DAT-00041-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0029 HEAVY DIESEL ARI COOLER | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 2
CON-BMP-TRA-040183 | 019-E-DAT-00045-001 | 019-E-DAT-00045-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0038 NAPHTA SPLITTER OVERHEAD AIR COOLER | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 3 - REVIEWED WITH COMMENTS | 2018-06-19 | CLASS 2
CON-BMP-TRA-040183 | 019-E-DAT-00046-001 | 019-E-DAT-00046-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0041 HEAVY NAPHTA PRODUCT AIR COOLER | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 2
CON-BMP-TRA-040183 | 019-E-DAT-00047-001 | 019-E-DAT-00047-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0025 DIESEL PRODUCT AIR COOLER | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 2
CON-BMP-TRA-040184 | 019-A-PID-00098-001 | 019-A-PID-00098-001 | PID 2HCU - BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-20 | CLASS 1
CON-BMP-TRA-040184 | 019-A-PID-00098-002 | 019-A-PID-00098-002 | PID 2HCU - BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 1
CON-BMP-TRA-040184 | 019-A-PID-00099-001 | 019-A-PID-00099-001 | PID 2HCU - BATTERY LIMIT PROCESS AUXILIARY | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 1
CON-BMP-TRA-040184 | 019-A-PID-00100-001 | 019-A-PID-00100-001 | PID 2HCU - BATTERY LIMIT UTILITIES | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 1
CON-BMP-TRA-040184 | 019-A-PID-00100-002 | 019-A-PID-00100-002 | PID 2HCU - BATTERY LIMIT UTILITIES | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 1
CON-BMP-TRA-040184 | 019-A-PID-00100-003 | 019-A-PID-00100-003 | PID 2HCU - BATTERY LIMIT UTILITIES | A | 2018-06-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-20 | CLASS 1
CON-BMP-TRA-040186 | 012-G-DAT-00004-001 | 012-G-DAT-00004-001 | MECHANICAL DATA SHEET ABSORBER FEED PUMPS 012P0001 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00005-001 | 012-G-DAT-00005-001 | MECHANICAL DATA SHEET ABSORBER BOTTOM PUMPS 012P0003 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00006-001 | 012-G-DAT-00006-001 | MECHANICAL DATA SHEET ABSORBER REFLUX PUMPS 012P0002 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00007-001 | 012-G-DAT-00007-001 | MECHANICAL DATA SHEET DEETHANIZER FEED PUMPS 012P00004 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00008-001 | 012-G-DAT-00008-001 | MECHANICAL DATA SHEET DEETHANIZER BOTTOM PUMPS 012P00005 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00009-001 | 012-G-DAT-00009-001 | MECHANICAL DATA SHEET NAPHTHA SPLITTER REFLUX PUMPS 012P0007 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00010-001 | 012-G-DAT-00010-001 | MECHANICAL DATA SHEET C3/C4 SPLITTER REFLUX PUMPS 012P0009 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00011-001 | 012-G-DAT-00011-001 | MECHANICAL DATA SHEET LPG WATER WASH CIRCULATION PUMPS 01P0013 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00012-001 | 012-G-DAT-00012-001 | MECHANICAL DATA SHEET LP LEAN AMINE PUMPS 012P0010 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00013-001 | 012-G-DAT-00013-001 | MECHANICAL DATA SHEET RICH AMINE PUMPS 012P0012 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040186 | 012-G-DAT-00015-001 | 012-G-DAT-00015-001 | MECHANICAL DATA SHEET CAUSTIC CIRCULATION PUMPS 012P0019 A/B | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 3 - REVIEWED WITH COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040187 | 372-G-DAT-57003-001 | 372-G-DAT-57003-001 | MECHANICAL DATA SHEET UTILITY WATER PUMPS 372P3732 A/B | B | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040188 | 012-P-INX-00001-001 | 012-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST N 1 SATURATED GAS PLANT UNIT 1SGP | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040190 | 011-G-DAT-00002-001 | 011-G-DAT-00002-001 | MECHANICAL DATA SHEET VACUUM RESIDUE PUMPS 01P0006A/B | B | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-040191 | 019-C-DAT-00003-001 | 019-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE HOT HIGH PRESSURE SEPARATOR 019V0003 | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040191 | 019-C-DAT-00008-001 | 019-C-DAT-00008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAGE HOT HIGH PRESSURE SEPARATOR 019V0008 | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040191 | 019-C-DAT-00010-001 | 019-C-DAT-00010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HOT LOW PRESSURE SEPARATOR 019V0010 | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-040192 | 000-P-STS-70003-001 | 000-P-STS-70003-001 | SHORTCIRCUIT STUDY UNITS 7CDU-7VDU-1SGP-2SGP-2HCU-CWT | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 3 - REVIEWED WITH COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040193 | 017-P-INX-00001-001 | 017-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST N 2 SATURATED GAS PLANT UNIT 2SGP | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 3 - REVIEWED WITH COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040194 | 085-P-INX-00001-001 | 085-P-INX-00001-001 | ELECTRICAL CONSUMERS LIST COOLING WATER TOWER UNIT CWT | A | 2018-06-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040195 | 010-A-EQL-00001-001 | 010-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 7 CRUDE DISTILLATION UNIT (7CDU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-21 | 3 - REVIEWED WITH COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-040196 | 011-A-EQL-00001-001 | 011-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 7 VACUUM DISTILLATION UNIT (7 VDU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-21 | 3 - REVIEWED WITH COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-040197 | 085-A-EQL-00001-001 | 085-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - COOLING WATER TOWER - CWT | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-040198 | 012-A-EQL-00001-001 | 012-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 1 SATURATED GAS PLANT- 1SGP | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-040199 | 050-A-EQL-55001-001 | 050-A-EQL-55001-001 | ITEM INDEX (EQUIPMENT LIST) - REFINERY TANK FARM (PLANT N F050) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-040200 | 372-A-EQL-57001-001 | 372-A-EQL-57001-001 | ITEM INDEX (EQUIPMENT LIST) - BOILER FEED WATER AND CONDENSATE DISTRIBUTION (PLANT N U372) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-040201 | 010-C-DAT-00002-001 | 010-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FUEL GAS KO DRUM 010V0018 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040201 | 010-C-DAT-00004-001 | 010-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR DESLATER WATER SURGE DRUM 010V0014 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040201 | 010-C-DAT-00007-001 | 010-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR OVERHEAD PRODUCT ACCUMULATOR 010V0009 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040201 | 010-C-DAT-00008-001 | 010-C-DAT-00008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR COMPRESSOR KO DRUM 010V0010 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040201 | 010-C-DAT-00009-001 | 010-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR COMPRESSOR INTERSTAGE KO DRUM 010V0011 A/B | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040201 | 010-C-DAT-00011-001 | 010-C-DAT-00011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER REFLUX DRUM 010V0013 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040201 | 010-C-DAT-00013-001 | 010-C-DAT-00013-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SOUR WATER SUMP 010V0015 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040201 | 010-C-DAT-00014-001 | 010-C-DAT-00014-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECOVERED PROCESS SLOP OIL SUMP 010V0016 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-040202 | 017-A-EQL-00001-001 | 017-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 2 SATURATED GAS PLANT - 2SGP | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 3 - REVIEWED WITH COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-040203 | 011-C-DAT-00001-001 | 011-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR VACUUM HOT WELL 011V0001 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040203 | 011-C-DAT-00002-001 | 011-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HOTWELL VAPOR WATER SEAL DRUM 011V0006 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040203 | 011-C-DAT-00010-001 | 011-C-DAT-00010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR BLOWDOWN FLASH DRUM 011V0010 | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040204 | 085-C-DAT-00001-001 | 085-C-DAT-00001-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 085V0008 A/B | B | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040204 | 085-C-DAT-00002-001 | 085-C-DAT-00002-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 085V0009 A/B | B | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040205 | 085-S-DAT-00017-001 | 085-S-DAT-00017-001 | MECHANICAL DATA SHEET MAIN SULPHURIC ACID MIXER 085MX0001 | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040205 | 085-S-DAT-00018-001 | 085-S-DAT-00018-001 | MECHANICAL DATA SHEET SECONDARY SULPHURIC ACID MIXER 085MX0002 | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040206 | 012-S-DAT-00005-001 | 012-S-DAT-00005-001 | MECHANICAL DATA SHEET LPG AMINE MIXER 012MX0001 | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040207 | 017-S-DAT-00005-001 | 017-S-DAT-00005-001 | MECHANICAL DATA SHEET LPG/AMINE MIXER 017MX0001 | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040208 | 050-S-DAT-55004-001 | 050-S-DAT-55004-001 | MECHANICAL DATA SHEET CRUDE OIL STATIC MIXER 050MX0010 | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040209 | 012-A-PFD-00001-001 | 012-A-PFD-00001-001 | PROCESS FLOW DIAGRAM FEED GAS SECTION DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00001-002 | 012-A-PFD-00001-002 | PROCESS FLOW DIAGRAM ABSORBER DEETHANIZER DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00001-003 | 012-A-PFD-00001-003 | PROCESS FLOW DIAGRAM STABILIZER NAPHTHA SPLITTER DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00001-004 | 012-A-PFD-00001-004 | PROCESS FLOW DIAGRAM LPG AMINE ABSORBER DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00001-005 | 012-A-PFD-00001-005 | PROCESS FLOW DIAGRAM LPG MERCAPTAN REMOVAL OLEFIN SATURATION AND C3-C4 SPLITTER DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00001-006 | 012-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00001-007 | 012-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00001-008 | 012-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00001-009 | 012-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-001 | 012-A-PFD-00002-001 | PROCESS FLOW DIAGRAMFEED GAS SECTION ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-002 | 012-A-PFD-00002-002 | PROCESS FLOW DIAGRAM ABSORBER DEETHANIZER ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-003 | 012-A-PFD-00002-003 | PROCESS FLOW DIAGRAM STABILIXER NAPHTHA SPLITTER ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-004 | 012-A-PFD-00002-004 | PROCESS FLOW DIAGRAM LPG AMINE ABSORBER ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-005 | 012-A-PFD-00002-005 | PROCESS FLOW DIAGRAM LPG MERCAPTAN REMOVAL OLEFIN SATURATION AND C3-C4 SPLITTER ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-006 | 012-A-PFD-00002-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-007 | 012-A-PFD-00002-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-008 | 012-A-PFD-00002-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040209 | 012-A-PFD-00002-009 | 012-A-PFD-00002-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE ALTERNATIVE 5 CASE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040210 | 085-P-SLD-00001-001 | 085-P-SLD-00001-001 | KEY SINGLE LINE DIAGRAM COOLING WATER SUBSTATION SST085R01 | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00001-001 | 085-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - CWT MAIN COOLING TOWER | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00002-001 | 085-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - CWT MAIN COOLING WATER CIRCULATING PUMPS | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00003-001 | 085-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - CWT MAIN COOLING WATER CIRCULATING PUMPS | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00004-001 | 085-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - CWT SECONDARY COOLING TOWER | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00005-001 | 085-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - CWT SECONDARY COOLING WATER CIRCULATING PUMPS | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00006-001 | 085-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - CWT COOLING TOWER FANS | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00007-001 | 085-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - CWT 085P0001A STEAM TURBINE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00008-001 | 085-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - CWT 085P0001B STEAM TURBINE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00009-001 | 085-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - CWT 085P0001C STEAM TURBINE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00010-001 | 085-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - CWT 085P0002A STEAM TURBINE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00011-001 | 085-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - CWT MAIN CALCITE BEDS PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00011-002 | 085-A-PID-00011-002 | PIPING AND INSTRUMENT DIAGRAM - CWT MAIN CALCITE BEDS PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00012-001 | 085-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - CWT SECONDARY CALCITE BEDS PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00013-001 | 085-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - CWT MAIN SIDE STREAM FILTERS PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00013-002 | 085-A-PID-00013-002 | PIPING AND INSTRUMENT DIAGRAM - CWT MAIN SIDE STREAM FILTERS PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00013-003 | 085-A-PID-00013-003 | PIPING AND INSTRUMENT DIAGRAM - CWT MAIN SIDE STREAM FILTERS PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00014-001 | 085-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - CWT SECONDARY SIDE STREAM FILTERS PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040211 | 085-A-PID-00015-001 | 085-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - CWT BACKWASH SYSTEM SECTION A | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00016-001 | 085-A-PID-00016-001 | PIPING AND INSTRUMENT DIAGRAM - CWT BACKWASH SYSTEM SECTION B | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00017-001 | 085-A-PID-00017-001 | PIPING AND INSTRUMENT DIAGRAM - CWT STEAM DISTRIBUTION | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00018-001 | 085-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM - CWT STEAM CONDENSATE AND BFW DISTRIBUTION | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00019-001 | 085-A-PID-00019-001 | PIPING AND INSTRUMENT DIAGRAM - CWT WATER DISTRIBUTION | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00020-001 | 085-A-PID-00020-001 | PIPING AND INSTRUMENT DIAGRAM - CWT COOLING WATER DISTRIBUTION | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00021-001 | 085-A-PID-00021-001 | PIPING AND INSTRUMENT DIAGRAM - CWT UTILITY AND DRINKING WATER | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00022-001 | 085-A-PID-00022-001 | PIPING AND INSTRUMENT DIAGRAM - CWT INSTRUMENT AND YARD AIR | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00024-001 | 085-A-PID-00024-001 | PIPING AND INSTRUMENT DIAGRAM - CWT BATTERY LIMIT PROCESS | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00025-001 | 085-A-PID-00025-001 | PIPING AND INSTRUMENT DIAGRAM - CWT BATTERY LIMIT PROCESS AUXILIARY | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00026-001 | 085-A-PID-00026-001 | PIPING AND INSTRUMENT DIAGRAM - CCWT BATTERY LIMIT UTILITIES | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00026-002 | 085-A-PID-00026-002 | PIPING AND INSTRUMENT DIAGRAM - CWT BATTERY LIMIT UTILITIES | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00026-003 | 085-A-PID-00026-003 | PIPING AND INSTRUMENT DIAGRAM - CWT BATTERY LIMIT UTILITIES | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00027-001 | 085-A-PID-00027-001 | PIPING AND INSTRUMENT DIAGRAM - CWT OXIDIZING BIOCIDE DOSING PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00028-001 | 085-A-PID-00028-001 | PIPING AND INSTRUMENT DIAGRAM - CWT ANTI SCALE / DISPERSANT DOSING PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00029-001 | 085-A-PID-00029-001 | PIPING AND INSTRUMENT DIAGRAM - CWT BIODISPERSANT DOSING PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00030-001 | 085-A-PID-00030-001 | PIPING AND INSTRUMENT DIAGRAM - CWT CORROSION INHIBITOR DOSING PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00031-001 | 085-A-PID-00031-001 | PIPING AND INSTRUMENT DIAGRAM - CWT SULPHURIC ACID DOSING PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00032-001 | 085-A-PID-00032-001 | PIPING AND INSTRUMENT DIAGRAM - CWT SODIUM HYDROXIDE DOSING PACKAGE | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040212 | 085-A-PID-00033-001 | 085-A-PID-00033-001 | PIPING AND INSTRUMENT DIAGRAM - CWT NON OXYDANT BIOCIDE DOSING SYSTEM | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-040213 | 076551C-000M-MR-0841-003 | 000-S-MRQ-70002-001 | MATERIAL REQUISITION FOR HIGH PRESSURE CENTRIFUGAL SEPARATOR | A | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 1
CON-BMP-TRA-040214 | 010-E-GAD-00002-001 | 010-E-GAD-00002-001 | GENERAL ARRANGEMENT 010E0005 A/B/C/D DESALTED CRUDE/MVGO AND HVGO EXCHANGER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00003-001 | 010-E-GAD-00003-001 | GENERAL ARRANGEMENT 010E0009 A/B FLASHED CRUDE/DIESEL EXCHANGER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00004-001 | 010-E-GAD-00004-001 | GENERAL ARRANGEMENT 010E0010 A/B FLASHED CRUDE DIESEL PA EXCHANGER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00005-001 | 010-E-GAD-00005-001 | GENERAL ARRANGEMENT 010E0011 A/B FLUSHED CRUDE/VACUUM RESIDUE EXCHANGER - 1ST | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00006-001 | 010-E-GAD-00006-001 | GENERAL ARRANGEMENT 010E0012 A/B/C/D FLUSHED CRUDE/HVGO PA EXCHANGER - 1ST | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00007-001 | 010-E-GAD-00007-001 | GENERAL ARRANGEMENT 010E0013 A/B FLASHED CRUDE/DIESEL PA EXCHANGER - 2ND | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00008-001 | 010-E-GAD-00008-001 | GENERAL ARRANGEMENT 010E0014 A/B/C/D FLASHED CRUDE/HVGO PA EXCHANGER - 2ND | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00009-001 | 010-E-GAD-00009-001 | GENERAL ARRANGEMENT 010E0015 A/B/C/D 2ND - FLUSHED CRUDE/VACUUM RESIDUE EXCHNAGER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00010-001 | 010-E-GAD-00010-001 | GENERAL ARRANGEMENT 010E0028 A/B SPLITTER REBOILER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00011-001 | 010-E-GAD-00011-001 | GENERAL ARRANGEMENT 010E0019 KERO STRIPPER REBOILER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00012-001 | 010-E-GAD-00012-001 | GENERAL ARRANGEMENT 010E0035 BRINE TRIM COOLER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00014-001 | 010-E-GAD-00014-001 | GENERAL ARRANGEMENT 010E0035 BRINE TRIM COOLER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040214 | 010-E-GAD-00015-001 | 010-E-GAD-00015-001 | GENERAL ARRANGEMENT 010E0033 A/B BRINE/DESALTER WATER PREHEAT EXCHANGER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00016-001 | 019-E-GAD-00016-001 | GENERAL ARRANGEMENT 019E0002 HEAVY DIESEL PRODUCT/FESDH FEED EXCHANGER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00017-001 | 019-E-GAD-00017-001 | GENERAL ARRANGEMENT 019E0027 HEAVY DIESEL P/A MP STEAM GENERATOR | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00018-001 | 019-E-GAD-00018-001 | GENERAL ARRANGEMENT 019E0037 NAPHTHA STABILIZER REBOILER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00019-001 | 019-E-GAD-00019-001 | GENERAL ARRANGEMENT 019E0023 LIGHT DIESEL MP STEAM GENERATOR | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00020-001 | 019-E-GAD-00020-001 | GENERAL ARRANGEMENT 019E0028 HEAVY DIESEL/BFW EXCHANGER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00021-001 | 019-E-GAD-00021-001 | GENERAL ARRANGEMENT 019E0032 FRACTIONATOR BOTTOMS MP STEAM GENERATOR | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00022-001 | 019-E-GAD-00022-001 | GENERAL ARRANGEMENT 019E0022 LIGHT DIESEL STRIPPER REBOILER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00023-001 | 019-E-GAD-00023-001 | GENERAL ARRANGEMENT 019E0003 FRACTIONATOR BOTTOMS/FRESH FEED EXCHANGER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040215 | 019-E-GAD-00024-001 | 019-E-GAD-00024-001 | GENERAL ARRANGEMENT 019E0050 SOUR WATER COOLER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040216 | 011-E-GAD-00001-001 | 011-E-GAD-00001-001 | GENERAL ARRANGEMENT 011E0006 A/B/C/D VACCUM RESIDUE STEAM GENERATOR | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040217 | 010-C-DAT-00017-001 | 010-C-DAT-00017-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 010V0019 A/B | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-001 | 012-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - ABSORBER FEED GAS COMPRESSOR/PSA PURGE GAS COMPRESSOR/LIQUID FE | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-002 | 012-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - NORMAL CASE DEETHANIZER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-003 | 012-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - NORMAL CASE NAPHTHA SPLITTER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-004 | 012-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - LPG/AMINE ABSORBER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-005 | 012-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - C3/C4 SPLITTER | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-006 | 012-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - NORMAL CASE DEETHANIZER - EQUIPMENT TABLE | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-007 | 012-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - NORMAL CASE NAPHTHA SPLITTER - EQUIPMENT | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-008 | 012-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM BMP UNITS CONDENSATE FLASH DRUM | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040218 | 012-A-MSD-00001-009 | 012-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM GENERAL NOTES | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 3 - REVIEWED WITH COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040219 | 010-E-DAT-00016-001 | 010-E-DAT-00016-001 | SHELL AND TUBE HEX DATA SHEET FOR COMPRESSOR INTERSTAGE COOLER 010E0018 A/B | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040219 | 010-E-DAT-00017-001 | 010-E-DAT-00017-001 | SHELL AND TUBE HEX DATA SHEET FOR STABILIZER FEED/NAPHTHA SPLITTER BOTTOM EXCHANGER 010E0024 A/B | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040219 | 010-E-DAT-00024-001 | 010-E-DAT-00024-001 | SHELL AND TUBE HEX DATA SHEET FOR STABILIZER CONDENSER 010E0027 A/B | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-24 | CLASS 2
CON-BMP-TRA-040220 | 011-E-DAT-00002-001 | 011-E-DAT-00002-001 | SHELL AND TUBE HEX DATA SHEET FOR LEAN AMINE COOLER 011E0008 A/B | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040221 | 019-E-DAT-00025-001 | 019-E-DAT-00025-001 | SHELL AND TUBE HEX DATA SHEET FOR NAPHTHA STABILIZER FEED - BOTTOMS EXCHANGER 019E0035 | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040221 | 019-E-DAT-00026-001 | 019-E-DAT-00026-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0043 | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040221 | 019-E-DAT-00027-001 | 019-E-DAT-00027-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0046 | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040221 | 019-E-DAT-00028-001 | 019-E-DAT-00028-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0048 | B | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040222 | 019-P-INX-00004-001 | 019-P-INX-00004-001 | HAZARDOUS SOURCE OF RELEASE LIST N 2 HYDROCRACKING UNIT HCU | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 3 - REVIEWED WITH COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040223 | 010-G-DAT-00018-001 | 010-G-DAT-00018-001 | MECHANICAL DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMP 010P0018 A/B | B | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040223 | 010-G-DAT-00019-001 | 010-G-DAT-00019-001 | MECHANICAL DATA SHEET SOUR WATER SUMP PUMP 010P0017 A/B | B | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-040224 | 019-G-DAT-00025-001 | 019-G-DAT-00025-001 | MECHANICAL DATA SHEET FOR RECOVERED PROCESS SLOP OIL SUMP PUMP 019P0026 A/B | B | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040224 | 019-G-DAT-00026-001 | 019-G-DAT-00026-001 | MECHANICAL DATA SHEET FOR AMINE SUMP PUMP 019P0027 A/B | B | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040224 | 019-G-DAT-00027-001 | 019-G-DAT-00027-001 | MECHANICAL DATA SHEET FOR SOUR WATER SUMP PUMP 019P0028 A/B | B | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-040225 | 050-G-DAT-55004-001 | 050-G-DAT-55004-001 | MECHANICAL DATA SHEET FOR 7CDU FEED BOOSTER PUMPS 010P0031 A/B | B | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040226 | 019-A-EQL-00001-001 | 019-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - HYDROCRACKER UNIT (2 HCU) | B | 2018-06-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 1
CON-BMP-TRA-040227 | 019-G-DAT-00019-001 | 019-G-DAT-00019-001 | MECHANICAL DATA SHEET FLARE KO DRUM PUMP 019P0025A/B | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040228 | 017-G-DAT-00016-001 | 017-G-DAT-00016-001 | MECHANICAL DATA SHEET COLD CONDENSATE MAKE UP PUMPS 017P0015 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040229 | 012-G-DAT-00016-001 | 012-G-DAT-00016-001 | MECHANICAL DATA SHEET COLD CONDENSATE MAKE UP PUMPS 012P0015 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040230 | 019-E-GAD-00032-001 | 019-E-GAD-00032-001 | GENERAL ARRANGEMENT DRAWING 019E0020 KEROSENE PRODUCT TRIM COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040230 | 019-E-GAD-00036-001 | 019-E-GAD-00036-001 | GENERAL ARRANGEMENT 019E0026 DIESEL PRODUCT TRIM COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040231 | 011-E-GAD-00002-001 | 011-E-GAD-00002-001 | GENERAL ARRANGEMENT DRAWING 011E0008 A/B LEAN AMINE COOLER | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040232 | 019-P-HAC-00001-001 | 019-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION C019-2HCU HYDROCRACKING UNIT | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 3 - REVIEWED WITH COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-040232 | 019-P-HAC-00001-002 | 019-P-HAC-00001-002 | HAZARDOUS AREA CLASSIFICATION C019-2HCU HYDROCRACKING UNIT | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 1
CON-BMP-TRA-040233 | 085-P-INX-00004-001 | 085-P-INX-00004-001 | HAZARDOUS SOURCE OF RELEASE LIST U085-CW-CLOSED LOOPO CW SYSTEM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 3 - REVIEWED WITH COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040234 | 050-P-INX-55001-001 | 050-P-INX-55001-001 | ELECTRICAL CONSUMERS LIST TANK FARM F050 UNIT | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 3 - REVIEWED WITH COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-040234 | 050-P-INX-55004-001 | 050-P-INX-55004-001 | HAZARDOUS SOURCE OF RELEASE LIST F050/U372 TANK FARM UNIT | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 3 - REVIEWED WITH COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-040235 | 019-E-GAD-00025-001 | 019-E-GAD-00025-001 | GENERAL ARRANGEMENT DRAWING 019E0035 NAPHTHA STABILIZER FEED BOTTOMS EXCHANGER | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040235 | 019-E-GAD-00026-001 | 019-E-GAD-00026-001 | GENERAL ARRANGEMENT DRAWING 019E0043 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040235 | 019-E-GAD-00027-001 | 019-E-GAD-00027-001 | GENERAL ARRANGEMENT DRAWINGS 019E0046 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040235 | 019-E-GAD-00028-001 | 019-E-GAD-00028-001 | GENERAL ARRANGEMENT DRAWING 019E0048 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040236 | 010-E-GAD-00016-001 | 010-E-GAD-00016-001 | GENERAL ARRANGEMENT DRAWING 010E0018A/B COMPRESSOR INTERSTAGE COOLER | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040236 | 010-E-GAD-00017-001 | 010-E-GAD-00017-001 | GENERAL ARRANGEMENT DRAWING 010E0024A/B STABILIZER FEED/NAPHTHA SPLITTER BOTTOM EXCHANGER | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040236 | 010-E-GAD-00024-001 | 010-E-GAD-00024-001 | GENERAL ARRANGEMENT DRAWING 010E0027A/B STABILIZER CONDENSER | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040237 | 050-K-DAT-55001-001 | 050-K-DAT-55001-001 | MECHANICAL DATA SHEET D1003 PROPELLER MIXER 050MX5011 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040237 | 050-K-DAT-55002-001 | 050-K-DAT-55002-001 | MECHANICAL DATA SHEET D1004 PROPELLER MIXER 050MX5012 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040237 | 050-K-DAT-55003-001 | 050-K-DAT-55003-001 | MECHANICAL DATA SHEET D1001 PROPELLER MIXER 050MX5013 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040237 | 050-K-DAT-55004-001 | 050-K-DAT-55004-001 | MECHANICAL DATA SHEET D1002 PROPELLER MIXER 050MX5014 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040238 | 012-G-DAT-00001-001 | 012-G-DAT-00001-001 | MECHANICAL DATA SHEET STABILIZER REFLUX PUMPS 012P0006 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040238 | 012-G-DAT-00002-001 | 012-G-DAT-00002-001 | MECHANICAL DATA SHEET NAPHTHA SPLITTER BOTTOM PUMPS 012P0008 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040238 | 012-G-DAT-00003-001 | 012-G-DAT-00003-001 | MECHANICAL DATA SHEET LEAN AMINE PUMPS 012P0011 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-040239 | 017-A-PFD-00001-001 | 017-A-PFD-00001-001 | PROCESS FLOW DIAGRAM - FEED COMPRESSOR DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00001-002 | 017-A-PFD-00001-002 | PROCESS FLOW DIAGRAM - ABSORBER DEETHANIZER DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00001-003 | 017-A-PFD-00001-003 | PROCESS FLOW DIAGRAM - STABILIZER NAPHTHA SPLITTER DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00001-004 | 017-A-PFD-00001-004 | PROCESS FLOW DIAGRAM - LPG AMINE ABSORBER DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00001-005 | 017-A-PFD-00001-005 | PROCESS FLOW DIAGRAM - LPG MERCAPTAN REMOVAL OLEFIN SATURATION AND C3/C4 SPLITTER DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00001-006 | 017-A-PFD-00001-006 | PROCESS FLOW DIAGRAM - HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00001-007 | 017-A-PFD-00001-007 | PROCESS FLOW DIAGRAM - HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00001-008 | 017-A-PFD-00001-008 | PROCESS FLOW DIAGRAM - HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00001-009 | 017-A-PFD-00001-009 | PROCESS FLOW DIAGRAM - HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-001 | 017-A-PFD-00002-001 | PROCESS FLOW DIAGRAM - FEED GAS COMPRESSOR ALTERNATIVE 5 CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-002 | 017-A-PFD-00002-002 | PROCESS FLOW DIAGRAM - ABSORBER DEETHANIZER ALTERNATIVE 5 CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-003 | 017-A-PFD-00002-003 | PROCESS FLOW DIAGRAM - STABILIZER/NAPHTHA SPLITTER ALTERNATIVE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-004 | 017-A-PFD-00002-004 | PROCESS FLOW DIAGRAM - LPG/AMINE ABSORBER ALTERNATIVE 5 CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-005 | 017-A-PFD-00002-005 | PROCESS FLOW DIAGRAM - LPG MERCAPTAN REMOVAL OLEFIN SATURATION AND C3/C4 SPLITTER ALTERNATIVE 5 CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-006 | 017-A-PFD-00002-006 | PROCESS FLOW DIAGRAM - HEAT AND MATERIAL BALANCE ALTERNATIVE 5 CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-007 | 017-A-PFD-00002-007 | PROCESS FLOW DIAGRAM - HEAT AND MATERIAL BALANCE ALTERNATIVE 5 CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-008 | 017-A-PFD-00002-008 | PROCESS FLOW DIAGRAM - HEAT AND MATERIAL BALANCE ALTERNATIVE 5 CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040239 | 017-A-PFD-00002-009 | 017-A-PFD-00002-009 | PROCESS FLOW DIAGRAM - HEAT AND MATERIAL BALANCE ALTERNATIVE 5 CASE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040240 | 010-P-HAC-00001-001 | 010-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION P010 - 7CDU / P011 - 7VDU CRUDE VACCUM DISTILLATION UNIT | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040240 | 010-P-HAC-00001-002 | 010-P-HAC-00001-002 | HAZARDOUS AREA CLASSIFICATION P010 - 7CDU / P011 - 7VDU CRUDE VACCUM DISTILLATION UNIT | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040241 | 085-P-HAC-00001-001 | 085-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION U085 - CW CLOSED LOOP CW SYSTEM | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040242 | 010-E-GAD-00025-001 | 010-E-GAD-00025-001 | GENERAL ARRANGEMENT DRAWING 010E0025 FOR STABILIZER FEED/EFFLUENT EXCHANGER | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040243 | 010-E-DAT-00025-001 | 010-E-DAT-00025-001 | SHELL AND TUBE HEX DATA SHEET FOR STABILIZER FEED/EFFLUENT EXCHANGER 010E0025 | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040244 | 017-G-DAT-00001-001 | 017-G-DAT-00001-001 | CENTRIFUGAL PUMPS DATA SHEET STABILIZER REFLUX PUMPS 017P0006 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040244 | 017-G-DAT-00002-001 | 017-G-DAT-00002-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA SPLITTER BOTTOM PUMPS 017P0008 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040244 | 017-G-DAT-00003-001 | 017-G-DAT-00003-001 | CENTRIFUGAL PUMPS DATA SHEET LEAN AMINE PUMPS 017P0011 A/B | B | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040245 | 076551C-000M-MR-0610-003 | 000-E-MRQ-70003-001 | MATERIAL REQUISITION FOR WET H2S AND SPECIAL SERVICE CARBON STEEL SHELL AND TUBE HEAT EXCHANGER | A | 2018-05-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 1
CON-BMP-TRA-040246 | 076551C-000M-MR-0710-002 | 000-E-MRQ-70008-001 | MATERIAL REQUISITION FOR AIR COOLERS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00029-001 | 019-E-DAT-00029-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0001 KEROSENE PRODUCT/FRESH FEED EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00030-001 | 019-E-DAT-00030-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0018 KEROSENE STRIPPER REBOILER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00031-001 | 019-E-DAT-00031-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0052 STEAM BLOWDOWN COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00032-001 | 019-E-DAT-00032-001 | SHELL AND TUBE HEX DATA SHEET FOR KEROSENE PRODUCT TRIM COOLER 019E0020 | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00033-001 | 019-E-DAT-00033-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0040 NAPHTA SPLITTER REBOILER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00034-001 | 019-E-DAT-00034-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0042 HEAVY NAPHTA PRODUCT TRIM COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00035-001 | 019-E-DAT-00035-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0024 LIGHT DIESEL / BFW EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00036-001 | 019-E-DAT-00036-001 | SHELL AND TUBE HEX DATA SHEET FOR DIESEL PRODUCT TRIM COOLER 019E0026 | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040247 | 019-E-DAT-00037-001 | 019-E-DAT-00037-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0021 LIGHT DIESEL P/A MP STEAM GENERATOR | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00018-001 | 010-E-DAT-00018-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0001 A/B CRUDE/KERO EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00019-001 | 010-E-DAT-00019-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0003 A/B CRUDE/DIESEL EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00020-001 | 010-E-DAT-00020-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0004 A/B/C/D CRUDE/KERO PA EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00021-001 | 010-E-DAT-00021-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0006 A/B DESALTED CRUDE/DIESEL EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00022-001 | 010-E-DAT-00022-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0007 A/B DESALTED CRUDE/KERO EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00023-001 | 010-E-DAT-00023-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0008 A/B/C/D DESALTED CRUDE/KERO PA EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00026-001 | 010-E-DAT-00026-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0020 KERO/DESALTER WATER FEED PREHEAT EXCHANGER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00027-001 | 010-E-DAT-00027-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0022 KERO TRIM COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00028-001 | 010-E-DAT-00028-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0032 SR HEAVY NAPHTHA TRIM COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040248 | 010-E-DAT-00029-001 | 010-E-DAT-00029-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0030 LIGHT NAPHTHA COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040249 | 011-E-DAT-00003-001 | 011-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0005 A/B MVGO/HVGO COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-040249 | 011-E-DAT-00004-001 | 011-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0007 A/B/C/D VACUUM RESIDUE COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-040249 | 011-E-DAT-00005-001 | 011-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0010 STEAM BLOWDOWN COOLER | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-040250 | 012-G-DAT-00017-001 | 012-G-DAT-00017-001 | MECHANICAL DATA SHEET AMINE SUMP PUMP 012P0017 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040250 | 012-G-DAT-00018-001 | 012-G-DAT-00018-001 | MECHANICAL DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMPS 012P0016 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040251 | 017-G-DAT-00017-001 | 017-G-DAT-00017-001 | MECHANICAL DATA SHEET AMINE SUMP PUMP 017P0017 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040251 | 017-G-DAT-00018-001 | 017-G-DAT-00018-001 | MECHANICAL DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMP 017P0016 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040252 | 010-G-DAT-00010-001 | 010-G-DAT-00010-001 | CENTRIFUGAL PUMPS DATA SHEET FOR DESALTER WATER RECYCLE PUMPS 010P00014 A/B/C | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040252 | 010-G-DAT-00011-001 | 010-G-DAT-00011-001 | CENTRIFUGAL PUMPS DATA SHEET ATMOSPHERIC COLUMN OVHD SOUR WATER PUMPS 010P0016 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040252 | 010-G-DAT-00012-001 | 010-G-DAT-00012-001 | CENTRIFUGAL PUMPS DATA SHEET STABILIZER REFLUX PUMPS 010P0011 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040252 | 010-G-DAT-00013-001 | 010-G-DAT-00013-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA SPLITTER REFLUX PUMPS 010P0012 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040252 | 010-G-DAT-00014-001 | 010-G-DAT-00014-001 | CENTRIFUGAL PUMPS DATA SHEET SR HEAVY NAPHTHA PUMPS 010P0013 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040252 | 010-G-DAT-00017-001 | 010-G-DAT-00017-001 | CENTRIFUGAL PUMPS DATA SHEET KERO PRODUCT PUMPS 010P0006 A/B | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040253 | 010-C-DAT-00015-001 | 010-C-DAT-00015-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FLARE KO DRUM 010V0017 | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-040254 | 050-G-DAT-55002-001 | 050-G-DAT-55002-001 | CENTRIFUGAL PUMPS DATA SHEET FOR 3HDU DIESEL FEED PUMPS 021P0013 A/B/C | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-040254 | 050-G-DAT-55003-001 | 050-G-DAT-55003-001 | CENTRIFUGAL PUMPS DATA SHEET FOR 2HCU HVGOFEED PUMPS 019P0029 A/B/C | B | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-040255 | 076551C-000M-MR-0610-004 | 000-E-MRQ-70004-001 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGERS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-040256 | 010-G-DAT-00015-001 | 010-G-DAT-00015-001 | CENTRIFUGAL PUMPS DATA SHEET FLARE KO DRUM PUMPS 010P0019 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040256 | 010-G-DAT-00016-001 | 010-G-DAT-00016-001 | CENTRIFUGAL PUMPS DATA SHEET ATM COLUMN REFLUX PUMPS 010P0004 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00011-001 | 019-G-DAT-00011-001 | CENTRIFUGAL PUMPS DATA SHEET NAPHTHA SLITTER REFLUX PUMP 019P0009 A/B/C | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00012-001 | 019-G-DAT-00012-001 | CENTRIFUGAL PUMPS DATA SHEET FRACTIONATOR OVERHEAD WATER PUMP 019P0007 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00013-001 | 019-G-DAT-00013-001 | CENTRIFUGAL PUMPS DATA SHEET FOR NAPHTA STABILIZER REFLUX PUMP 019P0018 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00014-001 | 019-G-DAT-00014-001 | CENTRIFUGAL PUMPS DATA SHEET HEAVY DIESEL STRIPPER BOTTOMS PUMP 019P0013 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00015-001 | 019-G-DAT-00015-001 | CENTRIFUGAL PUMPS DATA SHEET BACKWASH OIL PUMP 019P0023 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00016-001 | 019-G-DAT-00016-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM DRYER SLOP OIL PUMP 019P0015 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00017-001 | 019-G-DAT-00017-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM DRYER OILY WATER PUMP 019P0016 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00018-001 | 019-G-DAT-00018-001 | CENTRIFUGAL PUMPS DATA SHEET KEROSENE EXTERNAL REFLUX PUMP 019P0008 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00020-001 | 019-G-DAT-00020-001 | CENTRIFUGAL PUMPS DATA SHEET BFW CIRCULATION PUMPS 019P0024 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00021-001 | 019-G-DAT-00021-001 | CENTRIFUGAL PUMPS DATA SHEET RAW FEED BOOSTER PUMP 019P0001 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00022-001 | 019-G-DAT-00022-001 | CENTRIFUGAL PUMPS DATA SHEET KEROSENE PRODUCT PUMP 019P0009 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00023-001 | 019-G-DAT-00023-001 | CENTRIFUGAL PUMPS DATA SHEET HEAVY DIESEL PRODUCT PUMP 019P0014 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040257 | 019-G-DAT-00024-001 | 019-G-DAT-00024-001 | CENTRIFUGAL PUMP DATA SHEET PRODUCT STRIPPER REFLUX PUMP 019P0004 A/B | B | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040258 | 011-G-DAT-00003-001 | 011-G-DAT-00003-001 | CENTRIFUGAL PUMPS DATA SHEET BSGO PUMPS 011P0005 A/B | B | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040258 | 011-G-DAT-00004-001 | 011-G-DAT-00004-001 | CENTRIFUGAL PUMPS DATA SHEET RICH AMINE PUMPS 011P0007 A/B | B | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040258 | 011-G-DAT-00005-001 | 011-G-DAT-00005-001 | CENTRIFUGAL PUMPS DATA SHEET LVGO PUMPS 011P0002 A/B | B | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040258 | 011-G-DAT-00006-001 | 011-G-DAT-00006-001 | CENTRIFUGAL PUMPS DATA SHEET MVGO PUMPS 011P0003 A/B | B | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040258 | 011-G-DAT-00007-001 | 011-G-DAT-00007-001 | CENTRIFUGAL PUMPS DATA SHEET VACUUM COLUMN SOUR WATER PUMPS 011P0009 A/B | B | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040258 | 011-G-DAT-00008-001 | 011-G-DAT-00008-001 | CENTRIFUGAL PUMPS DATA SHEET FOR TEMPERED WATER PUMPS 011P0008 A/B | B | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040258 | 011-G-DAT-00009-001 | 011-G-DAT-00009-001 | CENTRIFUGAL PUMPS DATA SHEET FOR WGO PUMPS 011P0001 A/B | B | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040259 | 019-C-DAT-30001-001 | 019-C-DAT-30001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE REACTOR 019C0001R | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040259 | 019-C-DAT-30002-001 | 019-C-DAT-30002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAGE REACTOR 019C0002R | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040260 | 010-G-DAT-00101-001 | 010-G-DAT-00101-001 | GEN PURP STEAM TURBINE API 611 5TH ED DATA SHEET FOR ATM COLUMN REFLUX PUMP 010P0004B/010T0004B (EX 010-K-DAT-00002-001) | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040261 | 050-G-DAT-55005-001 | 050-G-DAT-55005-001 | GEN PURP STEAM TURBINE API 611 5TH ED DATA SHEET FOR 3HDU DIESEL FEED PUMPS 021P0013/T0013 A/B (EX 050-K-DAT-55005-001) | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040261 | 050-G-DAT-55006-001 | 050-G-DAT-55006-001 | GEN PURP STEAM TURBINE API 611 5TH ED DATA SHEET FOR 2HCU HVGO FEED PUMPS 019P0029/019T0029 A/B (EX 050-K-DAT-55006-001) | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040262 | 011-G-DAT-00100-001 | 011-G-DAT-00100-001 | GEN PURP STEAM TURBINE API 611 5TH ED DATA SHEET FOR LVGO PUMPS 011P0002B 011T0002B (EX 011-K-DAT-00001-001) | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040262 | 011-G-DAT-00101-001 | 011-G-DAT-00101-001 | GEN PURP STEAM TURBINE API 611 5TH ED DATA SHEET FOR TEMPERED WATER PUMPS 011P0008B 011T0008B (EX 011-K-DAT-00002-001) | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040263 | 050-D-DAT-55001-001 | 050-D-DAT-55001-001 | TANK DESIGN SPECIFICATION FOR 050D1001/050D1002 A/B CRUDE OIL TANKS | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040263 | 050-D-DAT-55003-001 | 050-D-DAT-55003-001 | TANK DESIGN SPECIFICATION FOR 050D1003/050D1004 1RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040264 | 019-G-DAT-00100-001 | 019-G-DAT-00100-001 | GEN PURP STEAM TURBINE API 611 5TH ED DATA SHEET FOR PRODUCT STRIPPER PUMPS 019P0004B/019T0004B (EX 019-K-DAT-00004-001) | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040265 | 011-E-DAT-00006-001 | 011-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 011E0004 LVGO PA COOLER | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040265 | 011-E-DAT-00007-001 | 011-E-DAT-00007-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 011E0009 TEMPERED WATER COOLER | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040266 | 050-P-HAC-55001-001 | 050-P-HAC-55001-001 | HAZARDOUS AREA CLASSIFICATION F050/U372 REFINERY TANK FARM | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040266 | 050-P-HAC-55001-002 | 050-P-HAC-55001-002 | HAZARDOUS AREA CLASSIFICATION F050/U372 REFINERY TANK FARM | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040267 | 372-D-DAT-57079-001 | 372-D-DAT-57079-001 | TANK DESIGN SPECIFICATION FOR 372D0279 FED STORAGE TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55001-001 | 050-D-GAD-55001-001 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55001-002 | 050-D-GAD-55001-002 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55001-003 | 050-D-GAD-55001-003 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55001-004 | 050-D-GAD-55001-004 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55002-001 | 050-D-GAD-55002-001 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55002-002 | 050-D-GAD-55002-002 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55002-003 | 050-D-GAD-55002-003 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55002-004 | 050-D-GAD-55002-004 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55003-001 | 050-D-GAD-55003-001 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55003-002 | 050-D-GAD-55003-002 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55003-003 | 050-D-GAD-55003-003 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55003-004 | 050-D-GAD-55003-004 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55004-001 | 050-D-GAD-55004-001 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55004-002 | 050-D-GAD-55004-002 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55004-003 | 050-D-GAD-55004-003 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040268 | 050-D-GAD-55004-004 | 050-D-GAD-55004-004 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | B | 2018-06-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-040269 | 076551C-000M-DL-0910-006 | 000-G-IDL-70006-001 | DEVIATION LIST FOR VERTICAL PUMPS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040269 | 076551C-000M-ITP-0910-006 | 000-G-ITP-70006-001 | INSPECTION AND TEST PLAN FOR VERTICAL PUMPS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040269 | 076551C-000M-MR-0910-006 | 000-G-MRQ-70006-001 | MATERIAL REQUISITION FOR VERTICAL PUMPS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040269 | 076551C-000M-SP-0910-006 | 000-G-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR VERTICAL PUMPS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040269 | 076551C-000M-SR-0910-006 | 000-G-SOW-70006-001 | SCOPE OF SUPPLY FOR VERTICAL PUMPS | A | 2018-05-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-040270 | 076551C-000M-DL-0920-001 | 000-G-IDL-70007-001 | DEVIATION LIST FOR RECIPROCATING PUMPS | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040270 | 076551C-000M-ITP-0920-001 | 000-G-ITP-70007-001 | INSPECTION AND TEST PLAN FOR RECIPROCATING PUMPS | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040270 | 076551C-000M-MR-0920-001 | 000-G-MRQ-70007-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040270 | 076551C-000M-SP-0920-001 | 000-G-GRD-70007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING PUMPS | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040270 | 076551C-000M-SR-0920-001 | 000-G-SOW-70007-001 | SCOPE OF SUPPLY FOR RECIPROCATING PUMPS | A | 2018-06-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 1
CON-BMP-TRA-040271 | 372-D-GAD-57079-001 | 372-D-GAD-57079-001 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | B | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040271 | 372-D-GAD-57079-002 | 372-D-GAD-57079-002 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | B | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040271 | 372-D-GAD-57079-003 | 372-D-GAD-57079-003 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | B | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040271 | 372-D-GAD-57079-004 | 372-D-GAD-57079-004 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | B | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-040272 | 076551C-000M-DL-2520-001 | 000-D-IDL-70001-001 | DEVIATION LIST FOR STORAGE TANK | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040272 | 076551C-000M-ITP-2520-001 | 000-D-ITP-70001-001 | INSPECTION AND TEST PLAN FOR STORAGE TANK | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040272 | 076551C-000M-MR-2520-001 | 000-D-MRQ-70001-001 | MATERIAL REQUISITION FOR STORAGE TANK | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040272 | 076551C-000M-SP-2520-001 | 000-D-GRD-70001-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR STORAGE TANK | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040272 | 076551C-000M-SR-2520-001 | 000-D-SOW-70001-001 | SCOPE OF SUPPLY FOR STORAGE TANK | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040273 | 012-A-PPN-00001-001 | 012-A-PPN-00001-001 | PLOT PLAN 012/017 SATURATE GAS PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040273 | 012-A-PPN-00001-002 | 012-A-PPN-00001-002 | PLOT PLAN 012/017 SATURATE GAS PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040274 | 076551C-000M-DL-0910-002 | 000-G-IDL-70003-001 | DEVIATION LIST FOR ASME PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040274 | 076551C-000M-ITP-0910-002 | 000-G-ITP-70003-001 | INSPECTION AND TEST PLAN FOR ASME PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040274 | 076551C-000M-MR-0910-002 | 000-G-MRQ-70003-001 | MATERIAL REQUISITION FOR ASME PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040274 | 076551C-000M-SP-0910-002 | 000-G-GRD-70003-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR ASME PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040274 | 076551C-000M-SR-0910-002 | 000-G-SOW-70003-001 | SCOPE OF SUPPLY FOR ASME PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040275 | 076551C-000M-DL-4260-001 | 000-K-IDL-70004-001 | DEVIATION LIST FOR MIXER ROTATIVE | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040275 | 076551C-000M-ITP-4260-001 | 000-K-ITP-70004-001 | INSPECTION AND TEST PLAN FOR MIXER ROTATIVE | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040275 | 076551C-000M-MR-4260-001 | 000-K-MRQ-70004-001 | MATERIAL REQUISITION FOR MIXER ROTATIVE | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040275 | 076551C-000M-SP-4260-001 | 000-K-GRD-70004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR MIXER ROTATIVE | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040275 | 076551C-000M-SR-4260-001 | 000-K-SOW-70004-001 | SCOPE OF SUPPLY FOR MIXER ROTATIVE | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-040276 | 012-C-DAT-10001-001 | 012-C-DAT-10001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR ABSORBER 012C0001 | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-040276 | 012-C-DAT-10002-001 | 012-C-DAT-10002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR DEETHANIZER 012C0002 | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-040276 | 012-C-DAT-10003-001 | 012-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STABILIZER 12C0003 | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-040276 | 012-C-DAT-10007-001 | 012-C-DAT-10007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR C3/C4 12C0007 | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-040277 | 012-K-DAT-00001-001 | 012-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FEED GAS COMPRESSOR 012K0001A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-040278 | 017-K-DAT-00001-001 | 017-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FEED GAS COMPRESSOR 017K0001A/B | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-07 | CLASS 2
CON-BMP-TRA-040279 | 085-A-PPN-00001-001 | 085-A-PPN-00001-001 | PLOT PLAN 085-CW CLOSED COOLING WATER (EX 085-L-PPN-00001-001) | B | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-040279 | 085-A-PPN-00001-002 | 085-A-PPN-00001-002 | PLOT PLAN 085-CW BUILDING (EX 085-L-PPN-00001-002) | B | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-040280 | 012-C-DAT-00002-001 | 012-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET 012V0002 FEED GAS SEPARATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040280 | 012-C-DAT-00005-001 | 012-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET 012V0005 DEETHANIZER FEED SURGE DRUM | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040280 | 012-C-DAT-00010-001 | 012-C-DAT-00010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET 012V0010 C3 AND C4 SPLITTER OVERHEAD RECEIVER | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040280 | 012-C-DAT-00021-001 | 012-C-DAT-00021-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET 012V0021 COLD CONDENSATE SURGE DRUM | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040280 | 012-C-DAT-10004-001 | 012-C-DAT-10004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET 012C0004 NAPHTHA SPLITTER | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040281 | 019-C-GAD-00034-001 | 019-C-GAD-00034-001 | GENERAL ARRANGEMENT 019V0034 FLARE KO DRUM | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040281 | 019-C-GAD-00034-002 | 019-C-GAD-00034-002 | GENERAL ARRANGEMENT 019V0034 FLARE KO DRUM | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040281 | 019-C-GAD-00034-003 | 019-C-GAD-00034-003 | GENERAL ARRANGEMENT 019V0034 FLARE KO DRUM | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040281 | 019-C-GAD-00034-004 | 019-C-GAD-00034-004 | GENERAL ARRANGEMENT 019V0034 FLARE KO DRUM | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040282 | 012-P-INX-00004-001 | 012-P-INX-00004-001 | HAZARDOUS SOURCE OF RELEASE LIST P012/P017 - SGP SATURATE GAS PLAN | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-040283 | 019-E-GAD-00013-001 | 019-E-GAD-00013-001 | GENERAL ARRANGEMENT DRAWING 019E0044 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040283 | 019-E-GAD-00014-001 | 019-E-GAD-00014-001 | GENERAL ARRANGEMENT DRAWING 019E0047 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040283 | 019-E-GAD-00015-001 | 019-E-GAD-00015-001 | GENERAL ARRANGEMENT DRAWING 019E0049 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-06-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040284 | 076551C-000M-DL-0841-001 | 000-C-IDL-70011-001 | DEVIATION LIST FOR FILTERS | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040284 | 076551C-000M-ITP-0841-001 | 000-C-ITP-70011-001 | INSPECTION AND TEST PLAN FOR FILTERS | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040284 | 076551C-000M-MR-0841-001 | 000-C-MRQ-70011-001 | MATERIAL REQUISITION FOR FILTERS | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040284 | 076551C-000M-SP-0841-001 | 000-C-GRD-70011-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR FILTERS | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040284 | 076551C-000M-SR-0841-001 | 000-C-SOW-70011-001 | SCOPE OF SUPPLY FOR FILTERS | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040285 | 076551C-000M-DL-0811-004 | 000-C-IDL-70012-001 | DEVIATION LIST FOR CS VESSELS MORE THAN 19 MM | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040285 | 076551C-000M-ITP-0811-004 | 000-C-ITP-70012-001 | INSPECTION AND TEST PLAN FOR CS VESSELS MORE THAN 19 MM | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040285 | 076551C-000M-MR-0811-004 | 000-C-MRQ-70012-001 | MATERIAL REQUISITION FOR CS VESSELS MORE THAN 19 MM | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040285 | 076551C-000M-SP-0811-004 | 000-C-GRD-70012-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR CS VESSELS MORE THAN 19 MM | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040285 | 076551C-000M-SR-0811-004 | 000-C-SOW-70012-001 | SCOPE OF SUPPLY FOR CS VESSELS MORE THAN 19 MM | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-040286 | 019-G-DAT-00019-001 | 019-G-DAT-00019-001 | MECHANICAL DATA SHEET FLARE KO DRUM PUMP 019P0025A/B | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-040287 | 019-C-DAT-10003-001 | 019-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HP H2S ABSORBER 019C0003 | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-040288 | 019-P-SLD-00002-001 | 019-P-SLD-00002-001 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5000K AND BUS5001K | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00003-001 | 019-P-SLD-00003-001 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5002L AND BUS5003L | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00003-002 | 019-P-SLD-00003-002 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5002L AND BUS5003L | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00100-001 | 019-P-SLD-00100-001 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5004N AND BUS5005N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00100-002 | 019-P-SLD-00100-002 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5004N AND BUS5005N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00100-003 | 019-P-SLD-00100-003 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5004N AND BUS5005N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00100-004 | 019-P-SLD-00100-004 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5004N AND BUS5005N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00100-005 | 019-P-SLD-00100-005 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5004N AND BUS5005N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00101-001 | 019-P-SLD-00101-001 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5006N AND BUS5007N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00101-002 | 019-P-SLD-00101-002 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5006N AND BUS5007N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00101-003 | 019-P-SLD-00101-003 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5006N AND BUS5007N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00101-004 | 019-P-SLD-00101-004 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5006N AND BUS5007N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00101-005 | 019-P-SLD-00101-005 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5006N AND BUS5007N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00102-001 | 019-P-SLD-00102-001 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5008N AND BUS5009N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00102-002 | 019-P-SLD-00102-002 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5008N AND BUS5009N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00103-001 | 019-P-SLD-00103-001 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5010N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00103-002 | 019-P-SLD-00103-002 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5010N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00103-003 | 019-P-SLD-00103-003 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5010N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040288 | 019-P-SLD-00103-004 | 019-P-SLD-00103-004 | NO.2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM BUS5010N | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-040289 | 010-E-DAT-00001-001 | 010-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR DESALTED CRUDE/CDU OVERHEAD EXCHANGER 010E0002 A-H | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-040289 | 010-E-DAT-00013-001 | 010-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR ATMOSPHERIC COLUMN OVERHEAD TRIM COOLER 010E0017 A/B | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-040290 | 010-S-EQL-00001-001 | 010-S-EQL-00001-001 | FIRE AND GAS EQUIPMENT LIST CRUDE DISTILLATION UNIT (CDU) AND VACUUM UNIT (VDC) | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-040291 | 019-S-EQL-00001-001 | 019-S-EQL-00001-001 | FIRE AND GAS EQUIPMENT LIST HYDROCRACKER UNIT 2HCU | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040292 | 012-S-EQL-00001-001 | 012-S-EQL-00001-001 | FIRE AND GAS EQUIPMENT LIST SATURATED GAS PLANT UNIT | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040293 | 000-P-STS-70004-001 | 000-P-STS-70004-001 | LOAD FLOW STUDY UNITS 7CDU-7VDU-1SGP-2SGP-2HCU-CWT | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040294 | 010-E-DAT-00004-001 | 010-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 010E0010 A/B FLASHED CRUDE/DIESEL PA EXCHANGER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00002-001 | 010-E-GAD-00002-001 | GENERAL ARRANGEMENT 010E0005 A/B/C/D DESALTED CRUDE/MVGO AND HVGO EXCHANGER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00004-001 | 010-E-GAD-00004-001 | GENERAL ARRANGEMENT 010E0010 A/B FLASHED CRUDE DIESEL PA EXCHANGER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00005-001 | 010-E-GAD-00005-001 | GENERAL ARRANGEMENT 010E0011 A/B FLUSHED CRUDE/VACUUM RESIDUE EXCHANGER - 1ST | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00006-001 | 010-E-GAD-00006-001 | GENERAL ARRANGEMENT 010E0012 A/B/C/D FLUSHED CRUDE/HVGO PA EXCHANGER - 1ST | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00007-001 | 010-E-GAD-00007-001 | GENERAL ARRANGEMENT 010E0013 A/B FLASHED CRUDE/DIESEL PA EXCHANGER - 2ND | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00008-001 | 010-E-GAD-00008-001 | GENERAL ARRANGEMENT 010E0014 A/B/C/D FLASHED CRUDE/HVGO PA EXCHANGER - 2ND | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00009-001 | 010-E-GAD-00009-001 | GENERAL ARRANGEMENT 010E0015 A/B/C/D 2ND - FLUSHED CRUDE/VACUUM RESIDUE EXCHNAGER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00010-001 | 010-E-GAD-00010-001 | GENERAL ARRANGEMENT 010E0028 A/B SPLITTER REBOILER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00011-001 | 010-E-GAD-00011-001 | GENERAL ARRANGEMENT 010E0019 KERO STRIPPER REBOILER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040295 | 010-E-GAD-00014-001 | 010-E-GAD-00014-001 | GENERAL ARRANGEMENT 010E0035 BRINE TRIM COOLER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040296 | 019-E-GAD-00018-001 | 019-E-GAD-00018-001 | GENERAL ARRANGEMENT 019E0037 NAPHTHA STABILIZER REBOILER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040296 | 019-E-GAD-00022-001 | 019-E-GAD-00022-001 | GENERAL ARRANGEMENT 019E0022 LIGHT DIESEL STRIPPER REBOILER | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040297 | 011-E-GAD-00001-001 | 011-E-GAD-00001-001 | GENERAL ARRANGEMENT 011E0006 A/B/C/D VACCUM RESIDUE STEAM GENERATOR | B | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040298 | 050-S-PED-55812-001 | 050-S-PED-55812-001 | CONCRETE BOX SOUTH CULVERT SECTIONS AND DETAILS | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040298 | 050-S-PED-55812-002 | 050-S-PED-55812-002 | CONCRETE BOX SOUTH CULVERT SECTIONS AND DETAILS | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040298 | 050-S-PED-55812-003 | 050-S-PED-55812-003 | CONCRETE BOX SOUTH CULVERT SECTIONS AND DETAILS | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040298 | 050-S-PED-55812-004 | 050-S-PED-55812-004 | CONCRETE BOX SOUTH CULVERT SECTIONS AND DETAILS | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040298 | 050-S-PED-55813-001 | 050-S-PED-55813-001 | CONCRETE BOX SOUTH CULVERT SECTIONS AND DETAILS | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040298 | 050-S-PED-55813-002 | 050-S-PED-55813-002 | CONCRETE BOX SOUTH CULVERT SECTIONS AND DETAILS | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040298 | 050-S-PED-55813-003 | 050-S-PED-55813-003 | CONCRETE BOX SOUTH CULVERT SECTIONS AND DETAILS | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040298 | 050-S-PED-55813-004 | 050-S-PED-55813-004 | CONCRETE BOX SOUTH CULVERT SECTIONS AND DETAILS | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040299 | 012-P-HAC-00001-001 | 012-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION P012-P017 - SGP SATURATE GAS PLAN | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-040299 | 012-P-HAC-00001-002 | 012-P-HAC-00001-002 | HAZARDOUS AREA CLASSIFICATION P012-P017 - SGP SATURATE GAS PLAN | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-040300 | 050-S-EQL-55001-001 | 050-S-EQL-55001-001 | FIRE AND GAS EQUIPMENT LIST REFINERY TANK FARM PLANT N 050 | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-040301 | 012-C-DAT-00016-001 | 012-C-DAT-00016-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTA SPLITTER REBOILER POT 012/017V0016A/B | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040302 | 012-C-DAT-00013-001 | 012-C-DAT-00013-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 012V0013 DEETHANIZER REBOILER CONDENSATE POT | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040302 | 012-C-DAT-00018-001 | 012-C-DAT-00018-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 012V0018 C3/C4 SPLITTER REBOILER CONDENSATE POT | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040302 | 012-C-DAT-00024-001 | 012-C-DAT-00024-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR AMINE SUMP DRUM 012V0024 | A | 2018-07-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-040303 | 000-P-STS-70005-001 | 000-P-STS-70005-001 | MOTOR STARTING STUDY UNITS 7CDU-7VDU-1SGP-2SGP-2HCU-CWT | A | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040304 | 012-C-DAT-00004-001 | 012-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR ABSORBER OVERHEAD DRUM 012/017V0004 | A | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040304 | 012-C-DAT-00006-001 | 012-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STABILIZER OVERHEAD RECEIVER 012/017V0006 | A | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040304 | 012-C-DAT-00012-001 | 012-C-DAT-00012-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RICH AMINE ACCUMULATOR 012/017V0012 | A | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040304 | 012-C-DAT-00014-001 | 012-C-DAT-00014-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STABILIZER REBOILER CONDENSARE POT 012/017V0014 | A | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040304 | 012-C-DAT-00023-001 | 012-C-DAT-00023-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECOVERED PROCESS SLOP OIL SUMP 012/017V0023 | A | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040304 | 012-C-DAT-00025-001 | 012-C-DAT-00025-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FLARE KO DRUM 012/017V0025 | A | 2018-07-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-17 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040305 | 076551C-000M-DL-0910-001 | 000-G-IDL-70002-001 | DEVIATION LIST FOR OH2 API 610 PUMPS | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040305 | 076551C-000M-ITP-0910-001 | 000-G-ITP-70002-001 | INSPECTION AND TEST PLAN FOR OH2 API 610 PUMPS | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040305 | 076551C-000M-MR-0910-001 | 000-G-MRQ-70002-001 | MATERIAL REQUISITION FOR OH2 API 610 PUMPS | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040305 | 076551C-000M-SP-0910-001 | 000-G-GRD-70002-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR OH2 API 610 PUMPS | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040305 | 076551C-000M-SR-0910-001 | 000-G-SOW-70002-001 | SCOPE OF SUPPLY FOR OH2 API 610 PUMPS | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040306 | 076551C-000M-DL-4046-001 | 000-S-IDL-70007-001 | DEVIATION LIST FOR DOSING SYSTEM | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040306 | 076551C-000M-ITP-4046-001 | 000-S-ITP-70007-001 | INSPECTION AND TEST PLAN FOR DOSING SYSTEM | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040306 | 076551C-000M-MR-4046-001 | 000-S-MRQ-70007-001 | MATERIAL REQUISITION FOR DOSING SYSTEM | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040306 | 076551C-000M-SP-4046-001 | 000-S-GRD-70007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR DOSING SYSTEM | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040306 | 076551C-000M-SR-4046-001 | 000-S-SOW-70007-001 | SCOPE OF SUPPLY FOR DOSING SYSTEM | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-040307 | 076551C-000M-DL-0811-003 | 000-C-IDL-70002-001 | DEVIATION LIST FOR CS VESSEL UP TO 19 MM THICKNESS/20 TM | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040307 | 076551C-000M-ITP-0811-003 | 000-C-ITP-70002-001 | INSPECTION AND TEST PLAN FOR CS VESSEL UP TO 19 MM THICKNESS/20 TM | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040307 | 076551C-000M-MR-0811-003 | 000-C-MRQ-70002-001 | MATERIAL REQUISITION FOR CS VESSEL UP TO 19 MM THICKNESS/20 TM | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040307 | 076551C-000M-SP-0811-003 | 000-C-GRD-70002-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR CS VESSEL UP TO 19 MM THICKNESS/20 TM | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040307 | 076551C-000M-SR-0811-003 | 000-C-SOW-70002-001 | SCOPE OF SUPPLY FOR CS VESSEL UP TO 19 MM THICKNESS/20 TM | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040308 | 019-C-DAT-00033-001 | 019-C-DAT-00033-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PROCESS GAS KO DRUM 019V0033 | B | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-040309 | 000-P-DAT-70001-001 | 000-P-DAT-70001-001 | HV/HV POWER TRANSFORMERS 33/11-5 KV AND 33/6-9 KV DATA SHEET | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040309 | 000-P-DAT-70002-001 | 000-P-DAT-70002-001 | HV/LV DISTRIBUTION TRANSFORMER 6-6/0-42 KV DATA SHEET | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040309 | 000-P-DAT-70003-001 | 000-P-DAT-70003-001 | NEUTRAL EARTHING RESISTORS DATA SHEET | A | 2018-07-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040310 | 019-C-DAT-10006-001 | 019-C-DAT-10006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR KEROSENE STRIPPER 019C0006 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040310 | 019-C-DAT-10010-001 | 019-C-DAT-10010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER 019C0010 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040311 | 085-S-DAT-00017-001 | 085-S-DAT-00017-001 | MECHANICAL DATA SHEET MAIN SULPHURIC ACID MIXER 085MX0001 | B | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040311 | 085-S-DAT-00018-001 | 085-S-DAT-00018-001 | MECHANICAL DATA SHEET SECONDARY SULPHURIC ACID MIXER 085MX0002 | B | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 |  |  | CLASS 2
CON-BMP-TRA-040312 | 012-S-DAT-00005-001 | 012-S-DAT-00005-001 | MECHANICAL DATA SHEET LPG AMINE MIXER 012MX0001 | B | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040313 | 017-S-DAT-00005-001 | 017-S-DAT-00005-001 | MECHANICAL DATA SHEET LPG/AMINE MIXER 017MX0001 | B | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040314 | 050-S-DAT-55004-001 | 050-S-DAT-55004-001 | MECHANICAL DATA SHEET CRUDE OIL STATIC MIXER 050MX0010 | B | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10001-001 | 012-C-GAD-10001-001 | GENERAL ARRANGEMENT FOR ABSORBER 012C0001 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10001-002 | 012-C-GAD-10001-002 | GENERAL ARRANGEMENT FOR ABSORBER 012C0001 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10001-003 | 012-C-GAD-10001-003 | GENERAL ARRANGEMENT FOR ABSORBER 012C0001 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10002-001 | 012-C-GAD-10002-001 | GENERAL ARRANGEMENT FOR DEETHANIZER 012C0002 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10002-002 | 012-C-GAD-10002-002 | GENERAL ARRANGEMENT FOR DEETHANIZER 012C0002 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10002-003 | 012-C-GAD-10002-003 | GENERAL ARRANGEMENT FOR DEETHANIZER 012C0002 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10003-001 | 012-C-GAD-10003-001 | GENERAL ARRANGEMENT FOR STABILIZER 012C0003 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10003-002 | 012-C-GAD-10003-002 | GENERAL ARRANGEMENT FOR STABILIZER 012C0003 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10003-003 | 012-C-GAD-10003-003 | GENERAL ARRANGEMENT FOR STABILIZER 012C0003 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10004-001 | 012-C-GAD-10004-001 | GENERAL ARRANGEMENT FOR NAPHTHA SPLITTER 012C0004 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10004-002 | 012-C-GAD-10004-002 | GENERAL ARRANGEMENT FOR NAPHTHA SPLITTER 012C0004 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10004-003 | 012-C-GAD-10004-003 | GENERAL ARRANGEMENT FOR NAPHTHA SPLITTER 012C0004 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10007-001 | 012-C-GAD-10007-001 | GENERAL ARRANGEMENT FOR C3/C4 SPLITTER 012C0007 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10007-002 | 012-C-GAD-10007-002 | GENERAL ARRANGEMENT FOR C3/C4 SPLITTER 012C0007 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040315 | 012-C-GAD-10007-003 | 012-C-GAD-10007-003 | GENERAL ARRANGEMENT FOR C3/C4 SPLITTER 012C0007 | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-040316 | 019-A-STS-00001-001 | 019-A-STS-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET - HYDROCRACKER UNIT (2HCU) | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040317 | 011-A-CAL-00001-001 | 011-A-STS-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET - NO 7 VACUUM DISTILLATION UNIT (7VDU) | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040318 | 010-A-CAL-00001-001 | 010-A-STS-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET - NO 7 CRUDE DISTILLATION UNIT (7CDU) | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040319 | 085-A-CAL-00001-001 | 085-A-STS-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL COOLING WATER TOWER - CWT CALCULATION SHEET | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040320 | 017-A-CAL-00001-001 | 017-A-STS-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL COOLING WATER TOWER - CWT CALCULATION SHEET | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040321 | 372-A-CAL-57001-001 | 372-A-STS-57001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL BOILER FEED WATER AND CONDENSATE DISTRIBUTION CALCULATION SHEET | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040322 | 050-A-CAL-55001-001 | 050-A-STS-55001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL REFINERY TANK FARM (PLANT N 050) CALCULATION SHEET | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040323 | 012-A-CAL-00001-001 | 012-A-STS-00002-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL NO 1 SATURATED GAS PLANT 1SGP CALCULATION SHEET | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040324 | 019-C-DAT-00004-001 | 019-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE COLD HIGH PRESSURE SEPARATOR 019V0004 | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040324 | 019-C-DAT-00006-001 | 019-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECYCLE GAS KO DRUM 019V0006 | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040324 | 019-C-DAT-00009-001 | 019-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAEG COLD HIGH PRESSURE SEPARATOR 019V0009 | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040324 | 019-C-DAT-10004-001 | 019-C-DAT-10004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT STRIPPER 019C0004 | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040324 | 019-C-DAT-10005-001 | 019-C-DAT-10005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT FRACTIONATOR 019C0005 | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040324 | 019-C-DAT-10007-001 | 019-C-DAT-10007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LIGHT DIESEL STRIPPER 019C0007 | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040324 | 019-C-DAT-10008-001 | 019-C-DAT-10008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HEAVY DIESEL STRIPPER 019C0008 | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040324 | 019-C-DAT-10009-001 | 019-C-DAT-10009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER 019C0009 | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040325 | 019-E-DAT-00001-001 | 019-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0006 A/B 1ST STAGE REACTOR EFFLUENT / FRESH FEED EXCHANGER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040325 | 019-E-DAT-00002-001 | 019-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0004 A/B 1ST STAGE REACTOR EFFLUENT / EFFLUENT EXCHANGER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040325 | 019-E-DAT-00003-001 | 019-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0005 A/B 1ST STAGE REACTOR EFFLUENT / FRACTIONATOR FEED EXCHANGER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040325 | 019-E-DAT-00004-001 | 019-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0007 A/B 1ST STAGE HHPS VAPOR / RECYCLE GAS EXCHANGER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040325 | 019-E-DAT-00005-001 | 019-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0011 A/B 2ND STAGE HHPS VAPOR /CLPS LIQUID EXCHANGER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040325 | 019-E-DAT-00006-001 | 019-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0009 A/B 2ND STAGE REACTOR FEED /EFFLUENT EXCHANGER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040325 | 019-E-DAT-00007-001 | 019-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0010 2ND STAGE REACTOR EFFLUENT / RECYCLE GAS EXCHANGER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040325 | 019-E-DAT-00013-001 | 019-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0044 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040325 | 019-E-DAT-00014-001 | 019-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0047 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040326 | 085-S-EQL-00001-001 | 085-S-EQL-00001-001 | FIRE AND GAS RISK EQUIPMENT LIST COOLING WATER TOWER - CWT | A | 2018-07-05 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 1
CON-BMP-TRA-040327 | 010-Q-PED-00201-001 | 010-Q-PED-00201-001 | PIPE RACK D010PR100 AXIS 1P TO 5P PLAN AND SECTIONS | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040327 | 010-Q-PED-00201-002 | 010-Q-PED-00201-002 | PIPE RACK D010PR100 AXIS 1P TO 5P REINFORCEMENT | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040328 | 019-Q-PED-00201-001 | 019-Q-PED-00201-001 | FOUNDATION PIPE RACK E019PR100 AXIS 1P TO 5P | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040328 | 019-Q-PED-00201-002 | 019-Q-PED-00201-002 | FOUNDATION PIPE RACK E019PR100 AXIS 1P TO 5P | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040329 | 011-C-DAT-10001-001 | 011-C-DAT-10001-001 | UNFIRED PRESSURE VESSEL DEASIGN SPECIFICATION SHEET FOR VACUUM COLUMN 011C0001 | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040329 | 011-C-DAT-10002-001 | 011-C-DAT-10002-001 | UNFIRED PRESSURE VESSEL DEASIGN SPECIFICATION SHEET FOR TAIL GAS ABSORBER 011C0002 | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040330 | 010-E-DAT-00035-001 | 010-E-DAT-00035-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0016 ATMOSPHERIC COLUMN OVERHEAD COOLER | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00001-001 | 012-A-PID-00001-001 | PID 1SGP - FEED GAS COMPRESSOR KO DRUM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00002-001 | 012-A-PID-00002-001 | PID 1SGP - FEED GAS COMPRESSOR A | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00003-001 | 012-A-PID-00003-001 | PID 1SGP - FEED GAS COMPRESSOR B | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00004-001 | 012-A-PID-00004-001 | PID 1SGP - FEED GAS SEPARATOR | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00005-001 | 012-A-PID-00005-001 | PID 1SGP - LIQUID FEED SURGE DRUM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00006-001 | 012-A-PID-00006-001 | PID 1SGP - ABSORBER COLUMN | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00007-001 | 012-A-PID-00007-001 | PID 1SGP - ABSORBER OVHD PRODUCT SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00008-001 | 012-A-PID-00008-001 | PID 1SGP - ABSORBER BOTTOMS PUMPS | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00009-001 | 012-A-PID-00009-001 | PID 1SGP - DEETHANIZER FEED SURGE DRUM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00010-001 | 012-A-PID-00010-001 | PID 1SGP - DEETHANIZER COLUMN | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00011-001 | 012-A-PID-00011-001 | PID 1SGP - STABILIZER COLUMN | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00012-001 | 012-A-PID-00012-001 | PID 1SGP - STABILIZER OVHD PRODUCT SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00013-001 | 012-A-PID-00013-001 | PID 1SGP - NAPHTHA SPLITTER | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00014-001 | 012-A-PID-00014-001 | PID 1SGP - NAPHTHA SPLITTER OVHD PRODUCT SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00015-001 | 012-A-PID-00015-001 | PID 1SGP - LIGHT NAPHTHA PRODUCT COOLING SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00016-001 | 012-A-PID-00016-001 | PID 1SGP - LIGHT NAPHTHA CAUSTIC SETTLER | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00017-001 | 012-A-PID-00017-001 | PID 1SGP - NAPHTHA SPLITTER BOTTOMS PUMPS | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00018-001 | 012-A-PID-00018-001 | PID 1SGP - HEAVY NAPHTHA PRODUCT COOLING SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00019-001 | 012-A-PID-00019-001 | PID 1SGP - OFF GAS AMINE ABSORBER | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040331 | 012-A-PID-00020-001 | 012-A-PID-00020-001 | PID 1SGP - LPG AMINE ABSORBER | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00021-001 | 012-A-PID-00021-001 | PID 1SGP - LPG AMINE SETTLER COOLER AND PUMPS | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00022-001 | 012-A-PID-00022-001 | PID 1SGP - LPG MERCAPTANS REMOVAL AND OLEFIN SATURATION PACKAGE | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00023-001 | 012-A-PID-00023-001 | PID 1SGP - C3/C4 SPLITTER | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00024-001 | 012-A-PID-00024-001 | PID 1SGP - C3/C4 SPLITTER OVHD PRODUCT SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00025-001 | 012-A-PID-00025-001 | PID 1SGP - PROPANE PRODUCT COOLING SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00026-001 | 012-A-PID-00026-001 | PID 1SGP - BUTANE PRODUCT COOLING SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00027-001 | 012-A-PID-00027-001 | PID 1SGP - LEAN AMINE SURGE DRUM AND LP AMINE PUMPS | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00028-001 | 012-A-PID-00028-001 | PID 1SGP - HIGH PRESSURE LEAN AMINE PUMPS | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00029-001 | 012-A-PID-00029-001 | PID 1SGP - COLD CONDENSATE INJECTION SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00030-001 | 012-A-PID-00030-001 | PID 1SGP - RICH AMINE ACCUMULATOR | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00031-001 | 012-A-PID-00031-001 | PID 1SGP - RECOVERED SLOP CLOSED DRAIN | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00031-002 | 012-A-PID-00031-002 | PID 1SGP - PROCESS SLOP OIL DRAIN DISTRIBUTION | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00031-003 | 012-A-PID-00031-003 | PID 1SGP - PROCESS SLOP OIL DRAIN DISTRIBUTION | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00032-001 | 012-A-PID-00032-001 | PID 1SGP - AMINE CLOSED DRAIN SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00032-002 | 012-A-PID-00032-002 | PID 1SGP - AMINE DRAIN DISTRIBUTION SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00033-001 | 012-A-PID-00033-001 | PID 1SGP - FLARE KO DRUM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00033-002 | 012-A-PID-00033-002 | PID 1SGP - FLARE SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00034-001 | 012-A-PID-00034-001 | PID 1SGP - 60/110/550 STEAM SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00034-002 | 012-A-PID-00034-002 | PID 1SGP - 60 STEAM SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040332 | 012-A-PID-00034-003 | 012-A-PID-00034-003 | PID 1SGP - 60 STEAM SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00035-001 | 012-A-PID-00035-001 | PID 1SGP - 60/110/550 STEAM CONDENSATE SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00036-001 | 012-A-PID-00036-001 | PID 1SGP - HP CONDENSATE FLASH DRUM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00037-001 | 012-A-PID-00037-001 | PID 1SGP - LP CONDENSATE FLASH DRUM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00038-001 | 012-A-PID-00038-001 | PID 1SGP - CONDENSATE RECOVERY SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00039-001 | 012-A-PID-00039-001 | PID 1SGP - COOLING WATER SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00040-001 | 012-A-PID-00040-001 | PID 1SGP - UTILITY AND DRINKING WATER SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00041-001 | 012-A-PID-00041-001 | PID 1SGP - INSTRUMENT AIR AND YARD AIR SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00042-001 | 012-A-PID-00042-001 | PID 1SGP - NITROGEN SYSTEM | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00044-001 | 012-A-PID-00044-001 | PID 1SGP - BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00044-002 | 012-A-PID-00044-002 | PID 1SGP - BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00044-003 | 012-A-PID-00044-003 | PID 1SGP - BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00045-001 | 012-A-PID-00045-001 | PID 1SGP - BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00046-001 | 012-A-PID-00046-001 | PID 1SGP - BATTERY LIMIT UTILITIES | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00046-002 | 012-A-PID-00046-002 | PID 1SGP - BATTERY LIMIT UTILITIES | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00046-003 | 012-A-PID-00046-003 | PID 1SGP - BATTERY LIMIT UTILITIES | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00047-001 | 012-A-PID-00047-001 | PID 1SGP - AIR FIN DETAILS | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040333 | 012-A-PID-00048-001 | 012-A-PID-00048-001 | PID 1SGP - AIR FIN DETAILS | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040334 | 050-Q-PED-55690-001 | 050-Q-PED-55690-001 | SLEEPERWAY AREA TANKS 050D1001/050D1002 PLAN SECTIONS AND DETAILS | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040334 | 050-Q-PED-55690-002 | 050-Q-PED-55690-002 | SLEEPERWAY AREA TANKS 050D1001/050D1002 PLAN SECTIONS AND DETAILS | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040334 | 050-Q-PED-55690-003 | 050-Q-PED-55690-003 | SLEEPERWAY AREA TANKS 050D1001/050D1002 PLAN SECTIONS AND DETAILS | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040334 | 050-Q-PED-55690-004 | 050-Q-PED-55690-004 | SLEEPERWAY AREA TANKS 050D1001/050D1002 PLAN SECTIONS AND DETAILS | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040335 | 019-C-DAT-00027-001 | 019-C-DAT-00027-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR INJECTION WATER DRUM 019V0027 | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-040336 | 010-C-GAD-10004-001 | 010-C-GAD-10004-001 | GENERAL ARRANGEMENT 010C0004 STABILIZER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040336 | 010-C-GAD-10004-002 | 010-C-GAD-10004-002 | GENERAL ARRANGEMENT 010C0004 STABILIZER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040336 | 010-C-GAD-10004-003 | 010-C-GAD-10004-003 | GENERAL ARRANGEMENT 010C0004 STABILIZER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040336 | 010-C-GAD-10005-001 | 010-C-GAD-10005-001 | GENERAL ARRANGEMENT 010C0005 NAPHTHA SPLITTER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040336 | 010-C-GAD-10005-002 | 010-C-GAD-10005-002 | GENERAL ARRANGEMENT 010C0005 NAPHTHA SPLITTER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040336 | 010-C-GAD-10005-003 | 010-C-GAD-10005-003 | GENERAL ARRANGEMENT 010C0005 NAPHTHA SPLITTER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-10006-001 | 019-C-GAD-10006-001 | GENERAL ARRANGEMENT 019C0006 KEROSENE STRIPPER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-10006-002 | 019-C-GAD-10006-002 | GENERAL ARRANGEMENT 019C0006 KEROSENE STRIPPER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-10006-003 | 019-C-GAD-10006-003 | GENERAL ARRANGEMENT 019C0006 KEROSENE STRIPPER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-10010-001 | 019-C-GAD-10010-001 | GENERAL ARRANGEMENT 019C0010 NAPHTHA SPLITTER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-10010-002 | 019-C-GAD-10010-002 | GENERAL ARRANGEMENT 019C0010 NAPHTHA SPLITTER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-10010-003 | 019-C-GAD-10010-003 | GENERAL ARRANGEMENT 019C0010 NAPHTHA SPLITTER | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-30001-001 | 019-C-GAD-30001-001 | GENERAL ARRANGEMENT 019C0001R 1ST STAGE REACTOR | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-30001-002 | 019-C-GAD-30001-002 | GENERAL ARRANGEMENT 019C0001R 1ST STAGE REACTOR | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-30001-003 | 019-C-GAD-30001-003 | GENERAL ARRANGEMENT 019C0001R 1ST STAGE REACTOR | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-30002-001 | 019-C-GAD-30002-001 | GENERAL ARRANGEMENT 019C0002R 2ND STAGE REACTOR | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-30002-002 | 019-C-GAD-30002-002 | GENERAL ARRANGEMENT 019C0002R 2ND STAGE REACTOR | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040337 | 019-C-GAD-30002-003 | 019-C-GAD-30002-003 | GENERAL ARRANGEMENT 019C0002R 2ND STAGE REACTOR | 0 | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040338 | 011-H-DAT-00001-001 | 011-H-DAT-00001-001 | MECHANICAL DATA SHEET FOR VACUUM PACKAGE 011U0001 | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040339 | 010-C-GAD-10001-001 | 010-C-GAD-10001-001 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040339 | 010-C-GAD-10002-001 | 010-C-GAD-10002-001 | GENERAL ARRANGEMENT 010C0002 KERO STRIPPER | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040339 | 010-C-GAD-10003-001 | 010-C-GAD-10003-001 | GENERAL ARRANGEMENT 010C0003 DIESEL STRIPPER | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040340 | 010-E-DAT-00034-001 | 010-E-DAT-00034-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0034 BRINE AIR COOLER | A | 2018-05-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 1
CON-BMP-TRA-040341 | 010-K-DAT-00001-001 | 010-K-DAT-00001-001 | MECHANICAL DATA SHEET CDU OVERHEAD VAPOR COMPRESSOR 010K0001 A/B | A | 2018-05-09 | FOR OCS REVIEW | BMP Project Director | 2018-07-23 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040342 | 011-C-GAD-10001-001 | 011-C-GAD-10001-001 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040342 | 011-C-GAD-10002-001 | 011-C-GAD-10002-001 | GENERAL ARRANGEMENT 011C0002 TAL GAS ABSORBER | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-040343 | 076551C-000M-DL-0610-002 | 000-E-IDL-70002-001 | DEVIATION LIST FOR CLAD AND ALLOY SHELL AND TUBE HEAT EXCHANGERS | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040343 | 076551C-000M-ITP-0610-002 | 000-E-ITP-70002-001 | INSPECTION AND TEST PLAN FOR CLAD AND ALLOY SHELL AND TUBE HEAT EXCHANGERS | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040343 | 076551C-000M-MR-0610-002 | 000-E-MRQ-70002-001 | MATERIAL REQUISITION FOR CLAD AND ALLOY SHELL AND TUBE HEAT EXCHANGERS | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040343 | 076551C-000M-SP-0610-002 | 000-E-GRD-70002-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR CLAD AND ALLOY SHELL AND TUBE HEAT EXCHANGERS | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040343 | 076551C-000M-SR-0610-002 | 000-E-SOW-70002-001 | SCOPE OF SUPPLY FOR CLAD AND ALLOY SHELL AND TUBE HEAT EXCHANGERS | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-040344 | 019-Q-PED-00209-001 | 019-Q-PED-00209-001 | FOUNDATION PIPE RACK E019PR300 AXIS AP TO EP | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040344 | 019-Q-PED-00209-002 | 019-Q-PED-00209-002 | FOUNDATION PIPE RACK E019PR300 AXIS AP TO EP | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040344 | 019-Q-PED-00210-001 | 019-Q-PED-00210-001 | FOUNDATION PIPE RACK E019PR300 AXIS FP TO JP | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040344 | 019-Q-PED-00210-002 | 019-Q-PED-00210-002 | FOUNDATION PIPE RACK E019PR300 AXIS FP TO JP | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040345 | 019-C-DAT-00001-001 | 019-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RAW FEED SURGE DRUM 019V0001 | 0 | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040345 | 019-C-DAT-00007-001 | 019-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAGE FEED SURGE DRUM 019V0007 | 0 | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040345 | 019-C-DAT-00012-001 | 019-C-DAT-00012-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT STRIPPER REFLUX DRUM 019V0012 | 0 | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040346 | 934-A-CAL-00001-001 | 934-A-STS-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL TANK FARM BOOSTER PUMPS/REFINERY TANK FARM (PLANT N 934) CALCULATION SHEET | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040347 | 012-C-DAT-00001-001 | 012-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FEED GAS COMPRESSOR KO DRUM 012/017V0001 | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040347 | 012-C-DAT-00007-001 | 012-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER OVERHEAD RECEIVER 012/017V0001 | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040347 | 012-C-DAT-00019-001 | 012-C-DAT-00019-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HP CONDENSATE FLASH DRUM 012/017V0019 | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040347 | 012-C-DAT-00020-001 | 012-C-DAT-00020-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LP CONDENSARE FLASH DRUM 012/017V0020 | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040347 | 012-C-DAT-00022-001 | 012-C-DAT-00022-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LIGHT NAPHTHA CAUSTIC SETTLER 012/017V0022 | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 3 - REVIEWED WITH COMMENTS | 2018-07-20 | CLASS 2
CON-BMP-TRA-040348 | 934-A-EQL-00001-001 | 934-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - TANK FARM BOOSTER PUMPS/REFINERY TANK FARM (PLANT N 934) | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-040349 | 019-C-DAT-30001-001 | 019-C-DAT-30001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE REACTOR 019C0001R | 0 | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-040349 | 019-C-DAT-30002-001 | 019-C-DAT-30002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAGE REACTOR 019C0002R | 0 | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-040350 | 011-L-INX-00001-001 | 011-L-INX-00001-001 | CONSTRUCTION LINE LIST NO 7 VACUUM DISTILLATION UNIT - 7VDU | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-040351 | 010-L-INX-00001-001 | 010-L-INX-00001-001 | CONSTRUCTION LINE LIST NO 7 CRUDE DISTILLATION UNIT - 7CDU | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-040352 | 085-L-INX-00001-001 | 085-L-INX-00001-001 | CONSTRUCTION LINE LIST COOLING WATER TOWER - CWT | A | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-040353 | 050-A-EQL-55001-001 | 050-A-EQL-55001-001 | ITEM INDEX (EQUIPMENT LIST) - REFINERY TANK FARM (PLANT N F050) | 0 | 2018-07-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-040354 | 372-A-EQL-57001-001 | 372-A-EQL-57001-001 | ITEM INDEX (EQUIPMENT LIST) - BOILER FEED WATER AND CONDENSATE DISTRIBUTION | 0 | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-040355 | 019-L-INX-00001-001 | 019-L-INX-00001-001 | CONSTRUCTION LINE LIST NO 2 HYDROCRACKING UNIT - 2HCU | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-25 | 3 - REVIEWED WITH COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-040356 | 050-Q-PED-55691-001 | 050-Q-PED-55691-001 | SLEEPERWAY AREA TANKS 050D1003/050D1004 PLAN SECTIONS AND DETAILS | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-040356 | 050-Q-PED-55691-002 | 050-Q-PED-55691-002 | SLEEPERWAY AREA TANKS 050D1003/050D1004 PLAN SECTIONS AND DETAILS | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-040356 | 050-Q-PED-55691-003 | 050-Q-PED-55691-003 | SLEEPERWAY AREA TANKS 050D1003/050D1004 SCHEDULE | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-040356 | 050-Q-PED-55691-004 | 050-Q-PED-55691-004 | SLEEPERWAY AREA TANKS 050D1003/050D1004 SCHEDULE | A | 2018-07-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-26 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-040357 | 019-J-INX-00002-001 | 019-J-INX-00002-001 | I/O LIST 019 NO 2 HYDROCRACKING UNIT (2HCU) | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040358 | 010-E-GAD-00001-001 | 010-E-GAD-00001-001 | GENERAL ARRANGEMENT DRAWING 010E0002 A-H CRUDE/CDU HEAD EXCHANGER | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-040358 | 010-E-GAD-00013-001 | 010-E-GAD-00013-001 | GENERAL ARRANGEMENT DRAWING 010E0017 A/B ATMOSPHERIC COLUMN OVERHEAD TRIM COOLER | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-040359 | 017-A-PID-00001-001 | 017-A-PID-00001-001 | PID - 2SGP FEED GAS COMPRESSORS KO DRUM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00002-001 | 017-A-PID-00002-001 | PID - 2SGP FEED GAS COMPRESSOR A | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00003-001 | 017-A-PID-00003-001 | PID - 2SGP FEED GAS COMPRESSOR B | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00004-001 | 017-A-PID-00004-001 | PID - 2SGP FEED GAS SEPARATOR | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00005-001 | 017-A-PID-00005-001 | PID - 2SGP LIQUID FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00006-001 | 017-A-PID-00006-001 | PID - 2SGP ABSORBER COLUMN | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00007-001 | 017-A-PID-00007-001 | PID - 2SGP ABSORBER OVHD PRODUCT SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00008-001 | 017-A-PID-00008-001 | PID - 2SGP ABSORBER BOTTOMS PUMPS | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00009-001 | 017-A-PID-00009-001 | PID - 2SGP DEETHANIZER FEED SURGE DRUM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00010-001 | 017-A-PID-00010-001 | PID - 2SGP DEETHANIZER COLUMN | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00011-001 | 017-A-PID-00011-001 | PID - 2SGP STABILIZER COLUMN | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00012-001 | 017-A-PID-00012-001 | PID - 2SGP STABILIZER OVHD PRODUCTPRODUCT SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00013-001 | 017-A-PID-00013-001 | PID - 2SGP NAPHTHA SPLITTER | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00014-001 | 017-A-PID-00014-001 | PID - 2SGP NAPHTHA SPLITTER OVHD PRODUCT SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00015-001 | 017-A-PID-00015-001 | PID - 2SGP LIGHT NAPHTHA PRODUCT COOLING SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00016-001 | 017-A-PID-00016-001 | PID - 2SGP LIGHT NAPHTHA CAUSTIC SETTLER | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00017-001 | 017-A-PID-00017-001 | PID - 2SGP NAPHTHA SPLITTER BOTTOMS PUMPS | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00018-001 | 017-A-PID-00018-001 | PID - 2SGP HEAVY NAPHTHA PRODUCT COOLING SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00019-001 | 017-A-PID-00019-001 | PID - 2SGP OFF GAS AMINE ABSORBER | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040359 | 017-A-PID-00020-001 | 017-A-PID-00020-001 | PID - 2SGP LPG AMINE ABSORBER | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00021-001 | 017-A-PID-00021-001 | PID - 2SGP LPG AMINE SETTLER COOLER AND PUMPS | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00022-001 | 017-A-PID-00022-001 | PID - 2SGP LPG MERCAPTANS REMOVAL AND OLEFIN SATURATION PACKAGE | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00023-001 | 017-A-PID-00023-001 | PID - 2SGP C3/C4 SPLITTER | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00024-001 | 017-A-PID-00024-001 | PID - 2SGP C3/C4 SPLITTER OVHD PRODUCT SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00025-001 | 017-A-PID-00025-001 | PID - 2SGP PROPANE PRODUCT COOLING SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00026-001 | 017-A-PID-00026-001 | PID - 2SGP BUTANE PRODUCT COOLING SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00027-001 | 017-A-PID-00027-001 | PID - 2SGP LEAN AMINE SURGE DRUM AND LP AMINE PUMPS | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00028-001 | 017-A-PID-00028-001 | PID - 2SGP HIGH PRESSURE LEAN AMINE PUMPS | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00029-001 | 017-A-PID-00029-001 | PID - 2SGP COLD CONDENSATE INJECTION SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00030-001 | 017-A-PID-00030-001 | PID - 2SGP RICH AMINE ACCUMULATOR | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00031-001 | 017-A-PID-00031-001 | PID - 2SGP RECOVERED SLOPS CLOSED DRAIN | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00031-002 | 017-A-PID-00031-002 | PID - 2SGP PROCESS SLOP OIL DRAIN DISTRIBUTION SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00031-003 | 017-A-PID-00031-003 | PID - 2SGP PROCESS SLOP OIL DRAIN DISTRIBUTION SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00032-001 | 017-A-PID-00032-001 | PID - 2SGP AMINE CLOSED DRAIN SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00032-002 | 017-A-PID-00032-002 | PID - 2SGP AMINE DRAIN DISTRIBUTION SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00033-001 | 017-A-PID-00033-001 | PID - 2SGP FLARE KO DRUM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00033-002 | 017-A-PID-00033-002 | PID - 2SGP FLARE SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00034-001 | 017-A-PID-00034-001 | PID - 2SGP 60/110/550 STEAM SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00034-002 | 017-A-PID-00034-002 | PID - 2SGP 60 STEAM SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040360 | 017-A-PID-00034-003 | 017-A-PID-00034-003 | PID - 2SGP 60 STEAM SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00035-001 | 017-A-PID-00035-001 | PID - 2SGP 60/110/550 STEAM CONDENSATE SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00036-001 | 017-A-PID-00036-001 | PID - 2SGP HP CONDENSATE FLASH DRUM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00037-001 | 017-A-PID-00037-001 | PID - 2SGP LP CONDENSATE FLASH DRUM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00038-001 | 017-A-PID-00038-001 | PID - 2SGP LP CONDENSATE RECOVERY SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00039-001 | 017-A-PID-00039-001 | PID - 2SGP COOLING WATER SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00040-001 | 017-A-PID-00040-001 | PID - 2SGP UTILITY AND DRINKING WATER SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00041-001 | 017-A-PID-00041-001 | PID - 2SGP INSTRUMENT AIR AND YARD AIR SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00042-001 | 017-A-PID-00042-001 | PID - 2SGP NITROGEN SYSTEM | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00044-001 | 017-A-PID-00044-001 | PID - 2SGP BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00044-002 | 017-A-PID-00044-002 | PID - 2SGP BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00044-003 | 017-A-PID-00044-003 | PID - 2SGP BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00045-001 | 017-A-PID-00045-001 | PID - 2SGP BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00046-001 | 017-A-PID-00046-001 | PID - 2SGP BATTERY LIMIT UTILITIES | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00046-002 | 017-A-PID-00046-002 | PID - 2SGP BATTERY LIMIT UTILITIES | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00046-003 | 017-A-PID-00046-003 | PID - 2SGP BATTERY LIMIT UTILITIES | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00047-001 | 017-A-PID-00047-001 | PID - 2SGP AIR FIN DETAILS | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040361 | 017-A-PID-00048-001 | 017-A-PID-00048-001 | PID - 2SGP AIR FIN DETAILS | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040362 | 010-J-INX-00002-001 | 010-J-INX-00002-001 | I/O LIST 010 NO 7 CRUDE DISTILLATION UNIT (7CDU) | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040363 | 011-J-INX-00002-001 | 011-J-INX-00002-001 | I/O LIST 011 NO 7 VACUUM DISTILLATION UNIT (7VDU) | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040364 | 019-P-SLD-00202-001 | 019-P-SLD-00202-001 | NO 2 HYDROCRACKING UNIT - 2HCU SINGLE LINE DIAGRAM DCS SYSTEM 110 VDC C019 | A | 2018-07-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-040365 | 050-S-PED-55810-001 | 050-S-PED-55810-001 | RETAINING DIKE TANKS 050D1001/050D1002 PLAN SECTION AND DETAILS | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040365 | 050-S-PED-55811-001 | 050-S-PED-55811-001 | RETAINING DIKE TANKS 050D1003/050D1004 PLAN SECTION AND DETAILS | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040366 | 012-J-INX-00002-001 | 012-J-INX-00002-001 | I/O LIST 012 NO 1 SATURED GAS PLANT (1SGP) | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040367 | 017-J-INX-00002-001 | 017-J-INX-00002-001 | I/O LIST 017 NO 2 SATURED GAS PLANT (2SGP) | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040368 | 085-J-INX-00002-001 | 085-J-INX-00002-001 | I/O LIST 085 COOLING WATER TOWER (CWT) | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040369 | 934-J-INX-00002-001 | 934-J-INX-00002-001 | I/O LIST 934 TANK FARM BOOSTER PUMPS / REFINERY TANK FARM | A | 2018-07-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-27 | 3 - REVIEWED WITH COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-040370 | 050-J-INX-55002-001 | 050-J-INX-55002-001 | I/O LIST 050 REFINERY TANK FARM | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040371 | 372-J-INX-57002-001 | 372-J-INX-57002-001 | I/O LIST 372 BOILED FEED WATER AND CONDENSATE DISTRIBUTION UNIT (BFW) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040372 | 019-M-GAD-00601-001 | 019-M-GAD-00601-001 | STEEL STRUCTURE PIPE RACK E019PR100 AXIS 1P TO 5P | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040372 | 019-M-GAD-00601-002 | 019-M-GAD-00601-002 | STEEL STRUCTURE PIPE RACK E019PR100 AXIS 1P TO 5P | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040372 | 019-M-GAD-00601-003 | 019-M-GAD-00601-003 | STEEL STRUCTURE PIPE RACK E019PR100 AXIS 1P TO 5P | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040372 | 019-M-GAD-00601-004 | 019-M-GAD-00601-004 | STEEL STRUCTURE PIPE RACK E019PR100 AXIS 1P TO 5P | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00601-001 | 085-M-GAD-00601-001 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 1P TO 3P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00601-002 | 085-M-GAD-00601-002 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 1P TO 3P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00601-003 | 085-M-GAD-00601-003 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 1P TO 3P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00601-004 | 085-M-GAD-00601-004 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 1P TO 3P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00602-001 | 085-M-GAD-00602-001 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 4P TO 11P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00602-002 | 085-M-GAD-00602-002 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 4P TO 11P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00602-003 | 085-M-GAD-00602-003 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 4P TO 11P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00602-004 | 085-M-GAD-00602-004 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 4P TO 11P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00603-001 | 085-M-GAD-00603-001 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 12P TO 18P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00603-002 | 085-M-GAD-00603-002 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 12P TO 18P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00603-003 | 085-M-GAD-00603-003 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 12P TO 18P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00603-004 | 085-M-GAD-00603-004 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 12P TO 18P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00604-001 | 085-M-GAD-00604-001 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 19P TO 24P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00604-002 | 085-M-GAD-00604-002 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 19P TO 24P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00604-003 | 085-M-GAD-00604-003 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 19P TO 24P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00604-004 | 085-M-GAD-00604-004 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 19P TO 24P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00605-001 | 085-M-GAD-00605-001 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 25P TO 31P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00605-002 | 085-M-GAD-00605-002 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 25P TO 31P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00605-003 | 085-M-GAD-00605-003 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 25P TO 31P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040373 | 085-M-GAD-00605-004 | 085-M-GAD-00605-004 | STEEL STRUCTURE PIPE RACK K085PR100 AXIS 25P TO 31P PLANS AND ELEVATIONS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040374 | 010-P-SLD-00002-001 | 010-P-SLD-00002-001 | UNIT 7CDU-7VDU-1SGP-2SGP SINGLE LINE DIAGRAM BUS5300L AND BUS5301L | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00002-002 | 010-P-SLD-00002-002 | UNIT 7CDU-7VDU-1SGP-2SGP SINGLE LINE DIAGRAM BUS5300L AND BUS5301L | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00002-003 | 010-P-SLD-00002-003 | UNIT 7CDU-7VDU-1SGP-2SGP SINGLE LINE DIAGRAM BUS5300L AND BUS5301L | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00002-004 | 010-P-SLD-00002-004 | UNIT 7CDU-7VDU-1SGP-2SGP SINGLE LINE DIAGRAM BUS5300L AND BUS5301L | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00002-005 | 010-P-SLD-00002-005 | UNIT 7CDU-7VDU-1SGP-2SGP SINGLE LINE DIAGRAM BUS5300L AND BUS5301L | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00100-001 | 010-P-SLD-00100-001 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5302N AND BUS5303N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00100-002 | 010-P-SLD-00100-002 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5302N AND BUS5303N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00100-003 | 010-P-SLD-00100-003 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5302N AND BUS5303N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00100-004 | 010-P-SLD-00100-004 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5302N AND BUS5303N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00100-005 | 010-P-SLD-00100-005 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5302N AND BUS5303N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00101-001 | 010-P-SLD-00101-001 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5304N AND BUS5305N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00101-002 | 010-P-SLD-00101-002 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5304N AND BUS5305N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00101-003 | 010-P-SLD-00101-003 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5304N AND BUS5305N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00101-004 | 010-P-SLD-00101-004 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5304N AND BUS5305N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040374 | 010-P-SLD-00101-005 | 010-P-SLD-00101-005 | NO 7 CRUDE DISTILLATION UNIT - 7CDU SINGLE LINE DIAGRAM BUS5304N AND BUS5305N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00102-001 | 010-P-SLD-00102-001 | NO. 7 VACUUM DISTILLATION UNIT - 7VDU SINGLE LINE DIAGRAM BUS5307N AND BUS5308N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00102-002 | 010-P-SLD-00102-002 | NO. 7 VACUUM DISTILLATION UNIT - 7VDU SINGLE LINE DIAGRAM BUS5307N AND BUS5308N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00102-003 | 010-P-SLD-00102-003 | NO. 7 VACUUM DISTILLATION UNIT - 7VDU SINGLE LINE DIAGRAM BUS5307N AND BUS5308N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00102-004 | 010-P-SLD-00102-004 | NO. 7 VACUUM DISTILLATION UNIT - 7VDU SINGLE LINE DIAGRAM BUS5307N AND BUS5308N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00103-001 | 010-P-SLD-00103-001 | NO. 1 SATURED GAS PLANT - 1SGP SINGLE LINE DIAGRAM BUS5309N AND BUS5310N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00103-002 | 010-P-SLD-00103-002 | NO. 1 SATURED GAS PLANT - 1SGP SINGLE LINE DIAGRAM BUS5309N AND BUS5310N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00103-003 | 010-P-SLD-00103-003 | NO. 1 SATURED GAS PLANT - 1SGP SINGLE LINE DIAGRAM BUS5309N AND BUS5310N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00103-004 | 010-P-SLD-00103-004 | NO. 1 SATURED GAS PLANT - 1SGP SINGLE LINE DIAGRAM BUS5309N AND BUS5310N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00104-001 | 010-P-SLD-00104-001 | NO. 1 SATURED GAS PLANT - 1SGP SINGLE LINE DIAGRAM BUS5311N AND BUS5312N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00104-002 | 010-P-SLD-00104-002 | NO. 1 SATURED GAS PLANT - 1SGP SINGLE LINE DIAGRAM BUS5311N AND BUS5312N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040375 | 010-P-SLD-00104-003 | 010-P-SLD-00104-003 | NO. 1 SATURED GAS PLANT - 1SGP SINGLE LINE DIAGRAM BUS5311N AND BUS5312N | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040376 | 085-A-EQL-00001-001 | 085-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - COOLING WATER TOWER - CWT | 0 | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-29 | CLASS 1
CON-BMP-TRA-040377 | 019-P-SLD-00200-001 | 019-P-SLD-00200-001 | NO. 2 HYDROCRAKING UNIT - 2HCU SINGLE LINE DIAGRAM AC UPS FOR DCS SYSTEM 115V CO19-2HCU | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 1
CON-BMP-TRA-040378 | 012-A-EQL-00001-001 | 012-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 1 SATURATED GAS PLANT- 1SGP | 0 | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-29 | CLASS 1
CON-BMP-TRA-040379 | 085-J-INX-00001-001 | 085-J-INX-00001-001 | INSTRUMENT LIST - 085 COOLING WATER TOWER (CWT) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-040380 | 017-A-EQL-00001-001 | 017-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 2 SATURATED GAS PLANT - 2SGP | C | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-29 | CLASS 1
CON-BMP-TRA-040381 | 010-M-GAD-00601-001 | 010-M-GAD-00601-001 | STEEL STRUCTURE PIPE RACK D010PR100 AXIS 1P TO 5P | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040381 | 010-M-GAD-00601-002 | 010-M-GAD-00601-002 | STEEL STRUCTURE PIPE RACK D010PR100 AXIS 1P TO 5P | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-040382 | 010-S-GAD-00003-001 | 010-S-GAD-00003-001 | FIRE EXPOSED ENVELOPE AND FIRE PROOFING LIMITS D010-7CDU/D011-7VDU CRUDE AND VACUUM DISTILLATION UNIT | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-040383 | 019-A-BOD-00001-001 | 019-A-BOD-00001-001 | PROCESS BASIS OF DESIGN 2HCU (UNIT C019) HYDROCRACKER UNIT | B | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-040384 | 019-J-DAT-00001-001 | 019-J-DAT-00001-001 | INSTRUMENT DATA SHEET FOR ULTRASONIC FLOWMETER NO 2 HYDROCRACKING UNIT (2HCU) | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-040384 | 019-J-DAT-00002-001 | 019-J-DAT-00002-001 | INSTRUMENT DATA SHEET FOR ON/OFF SPECIAL VALVES NO 2 HYDROCRACKING UNIT (2HCU) | A | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-040385 | 011-A-EQL-00001-001 | 011-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 7 VACUUM DISTILLATION UNIT (7 VDU) | C | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-29 | CLASS 2
CON-BMP-TRA-040386 | 010-A-EQL-00001-001 | 010-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 7 CRUDE DISTILLATION UNIT (7CDU) | C | 2018-07-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-01 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-29 | CLASS 2
CON-BMP-TRA-040387 | 019-J-BLD-00001-001 | 019-J-BLD-00001-001 | CONTROL SYSTEM BLOCK DIAGRAM SATELLITE RACK ROOM - 154RR01 HYDROCRACKING UNIT | A | 2018-07-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040388 | 085-J-BLD-00001-001 | 085-J-BLD-00001-001 | CONTROL SYSTEM BLOCK DIAGRAM SATELLITE RACK ROOM - 160RR01 COOLING TOWER | A | 2018-07-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-040389 | 000-J-BLD-70001-001 | 000-J-BLD-70001-001 | CONTROL SYSTEM BLOCK DIAGRAM SATELLITE RACK ROOM - 156RR01 CDU/VDU/SGP | A | 2018-07-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-040389 | 000-J-BLD-70002-001 | 000-J-BLD-70002-001 | CONTROL SYSTEM BLOCK DIAGRAM SATELLITE RACK ROOM - 163RR01 TANKS AND BOOSTER PUMPS | A | 2018-07-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-040390 | 010-P-SLD-00105-001 | 010-P-SLD-00105-001 | NO. 2 SATURED GAS PLANT - 2SGP SINGLE LINE DIAGRAM BUS5313N AND BUS5314N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00105-002 | 010-P-SLD-00105-002 | NO. 2 SATURED GAS PLANT - 2SGP SINGLE LINE DIAGRAM BUS5313N AND BUS5314N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00105-003 | 010-P-SLD-00105-003 | NO. 2 SATURED GAS PLANT - 2SGP SINGLE LINE DIAGRAM BUS5313N AND BUS5314N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00105-004 | 010-P-SLD-00105-004 | NO. 2 SATURED GAS PLANT - 2SGP SINGLE LINE DIAGRAM BUS5313N AND BUS5314N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00106-001 | 010-P-SLD-00106-001 | NO. 2 SATURED GAS PLANT - 2SGP SINGLE LINE DIAGRAM BUS5315N AND BUS5316N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00106-002 | 010-P-SLD-00106-002 | NO. 2 SATURED GAS PLANT - 2SGP SINGLE LINE DIAGRAM BUS5315N AND BUS5316N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00106-003 | 010-P-SLD-00106-003 | NO. 2 SATURED GAS PLANT - 2SGP SINGLE LINE DIAGRAM BUS5315N AND BUS5316N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00107-001 | 010-P-SLD-00107-001 | UNITS 7CDU-7VDU-1SGP-2SGP SINGLE LINE DIAGRAM BUS5306N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00107-002 | 010-P-SLD-00107-002 | UNITS 7CDU-7VDU-1SGP-2SGP SINGLE LINE DIAGRAM BUS5306N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040390 | 010-P-SLD-00107-003 | 010-P-SLD-00107-003 | UNITS 7CDU-7VDU-1SGP-2SGP SINGLE LINE DIAGRAM BUS5306N | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040391 | 019-S-GAD-00003-001 | 019-S-GAD-00003-001 | FIRE EXPOSED ENVELOPE AND FIRE PROOFING LIMITS 019 HCU HYDROCRACKER | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040391 | 019-S-GAD-00003-002 | 019-S-GAD-00003-002 | FIRE EXPOSED ENVELOPE AND FIRE PROOFING LIMITS 019 HCU HYDROCRACKER | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040392 | 019-R-PED-00900-001 | 019-R-PED-00900-001 | SUBSTATION 2HCU 019SSTR01 ARCHITECTURE PLANS | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040392 | 019-R-PED-00905-001 | 019-R-PED-00905-001 | SUBSTATION 2HCU 019SSTR01 ARCHITECTURE ELEVATIONS AND SECTIONS | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-040393 | 012-S-GAD-00003-001 | 012-S-GAD-00003-001 | FIRE EXPOSED ENVELOPE AND FIRE PROOFING LIMITS 012 - 1SGP / 017 - 2SGP NO 1 / NO 2 SATURATED GAS PLANT | A | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-040393 | 012-S-GAD-00003-002 | 012-S-GAD-00003-002 | FIRE EXPOSED ENVELOPE AND FIRE PROOFING LIMITS 012 - 1SGP / 017 - 2SGP NO 1 / NO 2 SATURATED GAS PLANT | A | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-02 | CLASS 2
CON-BMP-TRA-040394 | 011-J-INX-00001-001 | 011-J-INX-00001-001 | INSTRUMENT LIST 011 - NO 7 VACUUM DISTILLATION UNIT | A | 2018-07-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040395 | 019-M-GAD-00609-001 | 019-M-GAD-00609-001 | STEEL STRUCTURE PIPE RACK E019PR300 AXIS AP TO EP | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040395 | 019-M-GAD-00609-002 | 019-M-GAD-00609-002 | STEEL STRUCTURE PIPE RACK E019PR300 AXIS AP TO EP | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040395 | 019-M-GAD-00609-003 | 019-M-GAD-00609-003 | STEEL STRUCTURE PIPE RACK E019PR300 AXIS AP TO EP | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040395 | 019-M-GAD-00609-004 | 019-M-GAD-00609-004 | STEEL STRUCTURE PIPE RACK E019PR300 AXIS AP TO EP | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040395 | 019-M-GAD-00610-001 | 019-M-GAD-00610-001 | STEEL STRUCTURE PIPE RACK E019PR300 AXIS FP TO JP | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040395 | 019-M-GAD-00610-002 | 019-M-GAD-00610-002 | STEEL STRUCTURE PIPE RACK E019PR300 AXIS FP TO JP | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040395 | 019-M-GAD-00610-003 | 019-M-GAD-00610-003 | STEEL STRUCTURE PIPE RACK E019PR300 AXIS FP TO JP | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040396 | 085-A-BOD-00001-001 | 085-A-BOD-00001-001 | BASIS OF DESIGN FOR 085 COOLING WATER TOWER | B | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040397 | 934-A-PID-00001-001 | 934-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - RTF 7CDU BOOSTER PUMPS | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040397 | 934-A-PID-00002-001 | 934-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - RTF HVGO FEED SYSTEM 2HCU HVGO FEED PUMPS | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040397 | 934-A-PID-00003-001 | 934-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - RTF DIESEL FEED SYSTEM 3HDU DIESEL FEED PUMPS | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040397 | 934-A-PID-00004-001 | 934-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - RTF 1RHCU FEED PUMPS | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040397 | 934-A-PID-00005-001 | 934-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - RTF P1900A STEAM TURBINE | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040397 | 934-A-PID-00006-001 | 934-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - RTF P1900B STEAM TURBINE | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040397 | 934-A-PID-00007-001 | 934-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - RTF P2100A STEAM TURBINE | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040397 | 934-A-PID-00008-001 | 934-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - RTF P2100B STEAM TURBINE | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55001-001 | 050-A-PID-55001-001 | PIPING AND INSTRUMENT DIAGRAM - RTF CRUDE FEED RUNDOWN SYSTEM REFINERY TANKS | B | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55002-001 | 050-A-PID-55002-001 | PIPING AND INSTRUMENT DIAGRAM - RTF CRUDE FEED RUNDOWN SYSTEM REFINERY TANKS | B | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55003-001 | 050-A-PID-55003-001 | PIPING AND INSTRUMENT DIAGRAM - RTF 1RHCU FEED TANK D1003 | B | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55004-001 | 050-A-PID-55004-001 | PIPING AND INSTRUMENT DIAGRAM - RTF 1RHCU FEED TANK D1004 | B | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55005-001 | 050-A-PID-55005-001 | PIPING AND INSTRUMENT DIAGRAM - RTF 60 STEAM AND CONDENSATE SYSTEM | B | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55005-002 | 050-A-PID-55005-002 | PIPING AND INSTRUMENT DIAGRAM - RTF 110 STEAM AND CONDENSATE SYSTEM | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55005-003 | 050-A-PID-55005-003 | PIPING AND INSTRUMENT DIAGRAM - RTF 550 STEAM AND CONDENSATE SYSTEM | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55006-001 | 050-A-PID-55006-001 | PIPING AND INSTRUMENT DIAGRAM - RTF COOLING WATER SYSTEM | B | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55006-002 | 050-A-PID-55006-002 | PIPING AND INSTRUMENT DIAGRAM - RTF UTILITY WATER SYSTEM | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55006-003 | 050-A-PID-55006-003 | PIPING AND INSTRUMENT DIAGRAM - RTF BOILER FEED WATER SYSTEM | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55007-001 | 050-A-PID-55007-001 | PIPING AND INSTRUMENT DIAGRAM - RTF INSTRUMENT AIR YARD AIR SYSTEM | B | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55008-001 | 050-A-PID-55008-001 | PIPING AND INSTRUMENT DIAGRAM - RTF NITROGEN SYSTEM | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040398 | 050-A-PID-55009-001 | 050-A-PID-55009-001 | PIPING AND INSTRUMENT DIAGRAM - RTF FLUSHING OIL SYSTEM | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55010-001 | 050-A-PID-55010-001 | PIPING AND INSTRUMENT DIAGRAM - RTF CRUDE OIL BLENDING SYSTEM | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55011-001 | 050-A-PID-55011-001 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55011-002 | 050-A-PID-55011-002 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55011-003 | 050-A-PID-55011-003 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55011-004 | 050-A-PID-55011-004 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55011-005 | 050-A-PID-55011-005 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55011-006 | 050-A-PID-55011-006 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55012-001 | 050-A-PID-55012-001 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT UTILITIES | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55012-002 | 050-A-PID-55012-002 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT UTILITIES | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55012-003 | 050-A-PID-55012-003 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT UTILITIES | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040399 | 050-A-PID-55012-004 | 050-A-PID-55012-004 | PIPING AND INSTRUMENT DIAGRAM - RTF BATTERY LIMIT UTILITIES | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040400 | 085-S-GAD-00003-001 | 085-S-GAD-00003-001 | FIRE EXPOSED ENVELOPE AND FIRE PROOFING LIMITS 085-CWT COOLING WATER TOWER | A | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040401 | 012-J-INX-00001-001 | 012-J-INX-00001-001 | INSTRUMENT LIST 012 - NO 1 SATURATED GAS PLANT - 1SGP | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 1
CON-BMP-TRA-040402 | 017-J-INX-00001-001 | 017-J-INX-00001-001 | INSTRUMENT LIST 017 - NO 2 SATURED GAS PLANT - 2SGP | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 1
CON-BMP-TRA-040403 | 934-J-INX-00001-001 | 934-J-INX-00001-001 | INSTRUMENT LIST 934 - REFINERY TANK FARM BOOSTER PUMPS | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-040404 | 372-J-INX-57001-001 | 372-J-INX-57001-001 | INSTRUMENT LIST 372 - BFW AND CONDEN DISTR DEAREATOR | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-02 | CLASS 1
CON-BMP-TRA-040405 | 012-E-DAT-00020-001 | 012-E-DAT-00020-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 012E0001 FEED GAS COMPRESSOR AIR COOLER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040405 | 012-E-DAT-00023-001 | 012-E-DAT-00023-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 012E0021 FBUTENE AIR COOLER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040405 | 012-E-DAT-00024-001 | 012-E-DAT-00024-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 012E0015 HEAVY NAPHTA AIR COOLER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040405 | 012-E-DAT-00025-001 | 012-E-DAT-00025-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 012E0025 STEAM CONDENSER AIR COOLER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040405 | 012-E-DAT-00026-001 | 012-E-DAT-00026-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 012E0026 CONDENSATE AIR COOLER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040406 | 012-E-DAT-00010-001 | 012-E-DAT-00010-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 012E0017 LPG PRODUCT COOOLER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040406 | 012-E-DAT-00012-001 | 012-E-DAT-00012-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 012E0024 A/B HP LEAN AMINE COOLER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00201-001 | 085-Q-PED-00201-001 | FOUNDATION PIPE RACK K085PR100 AXIS 1P TO 3P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00201-002 | 085-Q-PED-00201-002 | FOUNDATION PIPE RACK K085PR100 AXIS 1P TO 3P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00201-003 | 085-Q-PED-00201-003 | FOUNDATION PIPE RACK K085PR100 AXIS 1P TO 3P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00202-001 | 085-Q-PED-00202-001 | FOUNDATION PIPE RACK K085PR100 AXIS 4P TO 11P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00202-002 | 085-Q-PED-00202-002 | FOUNDATION PIPE RACK K085PR100 AXIS 4P TO 11P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00202-003 | 085-Q-PED-00202-003 | FOUNDATION PIPE RACK K085PR100 AXIS 4P TO 11P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00203-001 | 085-Q-PED-00203-001 | FOUNDATION PIPE RACK K085PR100 AXIS 12P TO 18P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00203-002 | 085-Q-PED-00203-002 | FOUNDATION PIPE RACK K085PR100 AXIS 12P TO 18P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00203-003 | 085-Q-PED-00203-003 | FOUNDATION PIPE RACK K085PR100 AXIS 12P TO 18P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00204-001 | 085-Q-PED-00204-001 | FOUNDATION PIPE RACK K085PR100 AXIS 19P TO 24P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00204-002 | 085-Q-PED-00204-002 | FOUNDATION PIPE RACK K085PR100 AXIS 19P TO 24P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00204-003 | 085-Q-PED-00204-003 | FOUNDATION PIPE RACK K085PR100 AXIS 19P TO 24P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00205-001 | 085-Q-PED-00205-001 | FOUNDATION PIPE RACK K085PR100 AXIS 25P TO 31P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00205-002 | 085-Q-PED-00205-002 | FOUNDATION PIPE RACK K085PR100 AXIS 25P TO 31P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040407 | 085-Q-PED-00205-003 | 085-Q-PED-00205-003 | FOUNDATION PIPE RACK K085PR100 AXIS 25P TO 31P | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040408 | 019-C-DAT-10006-001 | 019-C-DAT-10006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR KEROSENE STRIPPER 019C0006 | 0 | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040408 | 019-C-DAT-10010-001 | 019-C-DAT-10010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER 019C0010 | 0 | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040409 | 050-Q-PED-55255-001 | 050-Q-PED-55255-001 | FOUNDATION FOR TANK 50D1001 PLAN SECTIONS AND DETAILS | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040409 | 050-Q-PED-55256-001 | 050-Q-PED-55256-001 | FOUNDATION FOR TANK 50D1002 PLAN SECTIONS AND DETAILS | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040409 | 050-Q-PED-55257-001 | 050-Q-PED-55257-001 | FOUNDATION FOR TANK 50D1003 PLAN SECTIONS AND DETAILS | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040409 | 050-Q-PED-55258-001 | 050-Q-PED-55258-001 | FOUNDATION FOR TANK 50D1004 PLAN SECTIONS AND DETAILS | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040410 | 085-M-CAL-00602-001 | 085-M-CAL-00602-001 | STEEL STRUCTURE PIPE RACK K085PR100 CALCULATION REPORT | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040411 | 019-Q-PED-00020-001 | 019-Q-PED-00020-001 | FOUNDATIONS FOR EXCHANGERS | A | 2018-07-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-07 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00001-001 | 012-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E0002 FEED GAS COMPRESSOR TRIM COOLER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00002-001 | 012-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E0006 A/B ABSORBER BOTTOM WATER COOLER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00003-001 | 012-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E00008 BOTTOM/STABILIZER FEED EXCHANGER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00004-001 | 012-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E00003 ABSORBER OVHD CONDENSER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00005-001 | 012-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E0007 DEETHANIZER REBOILER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00006-001 | 012-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E00011 A/B STABILIZER REBOILER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00007-001 | 012-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E00004 ABSORBER UPPER INTERCOOLER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00008-001 | 012-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E0005 ABSORBER LOWER INTERCOOLER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00009-001 | 012-E-DAT-00009-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E00010 LPG COOLER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00011-001 | 012-E-DAT-00011-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E00023 LP LEAN AMINE COOLER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00014-001 | 012-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E00020 C3/C4 SPLITTER REBOILER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040412 | 012-E-DAT-00018-001 | 012-E-DAT-00018-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 012E00014 A/B NAPHTHA SPLITTER REBOILER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040413 | 012-E-DAT-00021-001 | 012-E-DAT-00021-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 012E0009 STABILIZER OVHD AIR CONDENSER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040413 | 012-E-DAT-00022-001 | 012-E-DAT-00022-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 012E0012 NAPHTHA SPLITTER OVHD CONDENSER | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00002-001 | 085-P-SLD-00002-001 | SINGLE LINE DIAGRAN BUS5600L AND BUS5601L | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00002-002 | 085-P-SLD-00002-002 | SINGLE LINE DIAGRAN BUS5600L AND BUS5601L | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00003-001 | 085-P-SLD-00003-001 | SINGLE LINE DIAGRAN BUS5603L | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00100-001 | 085-P-SLD-00100-001 | SINGLE LINE DIAGRAN BUS5604N AND BUS5605N | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00100-002 | 085-P-SLD-00100-002 | SINGLE LINE DIAGRAN BUS5604N AND BUS5605N | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00100-003 | 085-P-SLD-00100-003 | SINGLE LINE DIAGRAN BUS5604N AND BUS5605N | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00100-004 | 085-P-SLD-00100-004 | SINGLE LINE DIAGRAN BUS5604N AND BUS5605N | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00100-005 | 085-P-SLD-00100-005 | SINGLE LINE DIAGRAN BUS5604N AND BUS5605N | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040414 | 085-P-SLD-00101-001 | 085-P-SLD-00101-001 | SINGLE LINE DIAGRAN BUS5606N | A | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-03 | CLASS 2
CON-BMP-TRA-040415 | 010-C-DAT-10004-001 | 010-C-DAT-10004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STABILIZER 010C0004 | 0 | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040415 | 010-C-DAT-10005-001 | 010-C-DAT-10005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER 010C0005 | 0 | 2018-07-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-040416 | 050-S-GAD-55003-001 | 050-S-GAD-55003-001 | GENERAL ARRANGEMENT FIRE EXPOSED ENVELOPE AND FIRE PROOFING LIMITS | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040416 | 050-S-GAD-55003-002 | 050-S-GAD-55003-002 | GENERAL ARRANGEMENT FIRE EXPOSED ENVELOPE AND FIRE PROOFING LIMITS | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-05 | CLASS 2
CON-BMP-TRA-040417 | 019-R-PED-00901-001 | 019-R-PED-00901-001 | SATELLITE RACK ROOM 019SRR01 ARCHITECTURE PLANS | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-040417 | 019-R-PED-00906-001 | 019-R-PED-00906-001 | SATELLITE RACK ROOM 019SRR01 ARCHITECTURE PLANS | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-08 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-040418 | 012-C-DAT-00003-001 | 012-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LIQUID FEED SURGE DRUM 012V0003 | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 3 - REVIEWED WITH COMMENTS | 2018-08-06 | CLASS 2
CON-BMP-TRA-040418 | 012-C-DAT-00008-001 | 012-C-DAT-00008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR AMINE SETTLER 012V0008 | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 3 - REVIEWED WITH COMMENTS | 2018-08-06 | CLASS 2
CON-BMP-TRA-040418 | 012-C-DAT-00011-001 | 012-C-DAT-00011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LEAN AMINE SURGE DRUM 012V0011 | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 3 - REVIEWED WITH COMMENTS | 2018-08-06 | CLASS 2
CON-BMP-TRA-040418 | 012-C-DAT-10005-001 | 012-C-DAT-10005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR OFF GAS AMINE ABDORBER 012C0005 | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 3 - REVIEWED WITH COMMENTS | 2018-08-06 | CLASS 2
CON-BMP-TRA-040419 | 019-Q-CAL-00201-001 | 019-Q-CAL-00201-001 | FOUNDATION PIPE RACK E019PR100 AXIS 1P TO 5P CALCULATION REPORT | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 3 - REVIEWED WITH COMMENTS | 2018-08-06 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00001-001 | 012-C-GAD-00001-001 | GENERAL ARRANGEMENT 012V0001 FEED GAS KO DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00001-002 | 012-C-GAD-00001-002 | GENERAL ARRANGEMENT 012V0001 FEED GAS KO DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00001-003 | 012-C-GAD-00001-003 | GENERAL ARRANGEMENT 012V0001 FEED GAS KO DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00002-001 | 012-C-GAD-00002-001 | GENERAL ARRANGEMENT 012V0002 FEED GAS SEPARATOR | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00002-002 | 012-C-GAD-00002-002 | GENERAL ARRANGEMENT 012V0002 FEED GAS SEPARATOR | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00002-003 | 012-C-GAD-00002-003 | GENERAL ARRANGEMENT 012V0002 FEED GAS SEPARATOR | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00003-001 | 012-C-GAD-00003-001 | GENERAL ARRANGEMENT 012V0003 LIQUID FEED SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00003-002 | 012-C-GAD-00003-002 | GENERAL ARRANGEMENT 012V0003 LIQUID FEED SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00003-003 | 012-C-GAD-00003-003 | GENERAL ARRANGEMENT 012V0003 LIQUID FEED SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00004-001 | 012-C-GAD-00004-001 | GENERAL ARRANGEMENT 012V0004 ABSORBER OVERHEAD DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00004-002 | 012-C-GAD-00004-002 | GENERAL ARRANGEMENT 012V0004 ABSORBER OVERHEAD DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00004-003 | 012-C-GAD-00004-003 | GENERAL ARRANGEMENT 012V0004 ABSORBER OVERHEAD DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00004-004 | 012-C-GAD-00004-004 | GENERAL ARRANGEMENT 012V0004 ABSORBER OVERHEAD DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00005-001 | 012-C-GAD-00005-001 | GENERAL ARRANGEMENT 012V0005 DEETHANIZER FEED SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00005-002 | 012-C-GAD-00005-002 | GENERAL ARRANGEMENT 012V0005 DEETHANIZER FEED SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00005-003 | 012-C-GAD-00005-003 | GENERAL ARRANGEMENT 012V0005 DEETHANIZER FEED SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00006-001 | 012-C-GAD-00006-001 | GENERAL ARRANGEMENT 012V0006 STABILIZER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00006-002 | 012-C-GAD-00006-002 | GENERAL ARRANGEMENT 012V0006 STABILIZER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00006-003 | 012-C-GAD-00006-003 | GENERAL ARRANGEMENT 012V0006 STABILIZER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040420 | 012-C-GAD-00006-004 | 012-C-GAD-00006-004 | GENERAL ARRANGEMENT 012V0006 STABILIZER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00007-001 | 012-C-GAD-00007-001 | GENERAL ARRANGEMENT 012V0007 NAPHTHA SPLITTER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00007-002 | 012-C-GAD-00007-002 | GENERAL ARRANGEMENT 012V0007 NAPHTHA SPLITTER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00007-003 | 012-C-GAD-00007-003 | GENERAL ARRANGEMENT 012V0007 NAPHTHA SPLITTER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00008-001 | 012-C-GAD-00008-001 | GENERAL ARRANGEMENT 012V0008 AMINE SETTLER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00008-002 | 012-C-GAD-00008-002 | GENERAL ARRANGEMENT 012V0008 AMINE SETTLER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00008-003 | 012-C-GAD-00008-003 | GENERAL ARRANGEMENT 012V0008 AMINE SETTLER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00008-004 | 012-C-GAD-00008-004 | GENERAL ARRANGEMENT 012V0008 AMINE SETTLER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00010-001 | 012-C-GAD-00010-001 | GENERAL ARRANGEMENT 012V0010 C3/C4 SPLITTER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00010-002 | 012-C-GAD-00010-002 | GENERAL ARRANGEMENT 012V0010 C3/C4 SPLITTER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00010-003 | 012-C-GAD-00010-003 | GENERAL ARRANGEMENT 012V0010 C3/C4 SPLITTER OVERHEAD RECEIVER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00011-001 | 012-C-GAD-00011-001 | GENERAL ARRANGEMENT 012V0011 LEAN AMINE SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00011-002 | 012-C-GAD-00011-002 | GENERAL ARRANGEMENT 012V0011 LEAN AMINE SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00011-003 | 012-C-GAD-00011-003 | GENERAL ARRANGEMENT 012V0011 LEAN AMINE SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00013-001 | 012-C-GAD-00013-001 | GENERAL ARRANGEMENT 012V0013 DEETHANIZER REBOILER CONDENSARE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00013-002 | 012-C-GAD-00013-002 | GENERAL ARRANGEMENT 012V0013 DEETHANIZER REBOILER CONDENSARE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00013-003 | 012-C-GAD-00013-003 | GENERAL ARRANGEMENT 012V0013 DEETHANIZER REBOILER CONDENSARE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00014-001 | 012-C-GAD-00014-001 | GENERAL ARRANGEMENT 012V0014 A/B STABILIZER REBOILER CONDENSATE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00014-002 | 012-C-GAD-00014-002 | GENERAL ARRANGEMENT 012V0014 A/B STABILIZER REBOILER CONDENSATE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040421 | 012-C-GAD-00014-003 | 012-C-GAD-00014-003 | GENERAL ARRANGEMENT 012V0014 A/B STABILIZER REBOILER CONDENSATE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00016-001 | 012-C-GAD-00016-001 | GENERAL ARRANGEMENT 012V0016 NAPHTHA SPLITTER REBOILER POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00016-002 | 012-C-GAD-00016-002 | GENERAL ARRANGEMENT 012V0016 NAPHTHA SPLITTER REBOILER POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00016-003 | 012-C-GAD-00016-003 | GENERAL ARRANGEMENT 012V0016 NAPHTHA SPLITTER REBOILER POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00018-001 | 012-C-GAD-00018-001 | GENERAL ARRANGEMENT 012V0018 C3/C4 SPLITTER REBOILER CONDENSATE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00018-002 | 012-C-GAD-00018-002 | GENERAL ARRANGEMENT 012V0018 C3/C4 SPLITTER REBOILER CONDENSATE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00018-003 | 012-C-GAD-00018-003 | GENERAL ARRANGEMENT 012V0018 C3/C4 SPLITTER REBOILER CONDENSATE POT | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00019-001 | 012-C-GAD-00019-001 | GENERAL ARRANGEMENT 012V0019 HP CONDENSATE FLASH DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00019-002 | 012-C-GAD-00019-002 | GENERAL ARRANGEMENT 012V0019 HP CONDENSATE FLASH DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00019-003 | 012-C-GAD-00019-003 | GENERAL ARRANGEMENT 012V0019 HP CONDENSATE FLASH DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00020-001 | 012-C-GAD-00020-001 | GENERAL ARRANGEMENT 012V0020 LP CONDENSATE FLASH DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00020-002 | 012-C-GAD-00020-002 | GENERAL ARRANGEMENT 012V0020 LP CONDENSATE FLASH DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00020-003 | 012-C-GAD-00020-003 | GENERAL ARRANGEMENT 012V0020 LP CONDENSATE FLASH DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00021-001 | 012-C-GAD-00021-001 | GENERAL ARRANGEMENT 012V0021 COLD CONDENSATE SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00021-002 | 012-C-GAD-00021-002 | GENERAL ARRANGEMENT 012V0021 COLD CONDENSATE SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00021-003 | 012-C-GAD-00021-003 | GENERAL ARRANGEMENT 012V0021 COLD CONDENSATE SURGE DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00022-001 | 012-C-GAD-00022-001 | GENERAL ARRANGEMENT 012V0022 LIGHT NAPHTHA CAUSTIC SETTLER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00022-002 | 012-C-GAD-00022-002 | GENERAL ARRANGEMENT 012V0022 LIGHT NAPHTHA CAUSTIC SETTLER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040422 | 012-C-GAD-00022-003 | 012-C-GAD-00022-003 | GENERAL ARRANGEMENT 012V0022 LIGHT NAPHTHA CAUSTIC SETTLER | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00023-001 | 012-C-GAD-00023-001 | GENERAL ARRANGEMENT 012V0023 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00023-002 | 012-C-GAD-00023-002 | GENERAL ARRANGEMENT 012V0023 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00023-003 | 012-C-GAD-00023-003 | GENERAL ARRANGEMENT 012V0023 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00024-001 | 012-C-GAD-00024-001 | GENERAL ARRANGEMENT 012V0024 AMINE SUMP DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00024-002 | 012-C-GAD-00024-002 | GENERAL ARRANGEMENT 012V0024 AMINE SUMP DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00024-003 | 012-C-GAD-00024-003 | GENERAL ARRANGEMENT 012V0024 AMINE SUMP DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00025-001 | 012-C-GAD-00025-001 | GENERAL ARRANGEMENT 012V0025 FLARE KO DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00025-002 | 012-C-GAD-00025-002 | GENERAL ARRANGEMENT 012V0025 FLARE KO DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040423 | 012-C-GAD-00025-003 | 012-C-GAD-00025-003 | GENERAL ARRANGEMENT 012V0025 FLARE KO DRUM | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040424 | 019-C-DAT-00013-001 | 019-C-DAT-00013-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FRACTIONATOR REFLUX DRUM 019V0013 | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040424 | 019-C-DAT-00014-001 | 019-C-DAT-00014-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER REFLUX DRUM 019V0014 | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040424 | 019-C-DAT-00015-001 | 019-C-DAT-00015-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER REFLUX DRUM 019V0015 | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040424 | 019-C-DAT-00026-001 | 019-C-DAT-00026-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LEAN AMINE SURGE DRUM 019V0026 | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040424 | 019-C-DAT-00028-001 | 019-C-DAT-00028-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RICH AMINE FLASH DRUM 019V0028 | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040424 | 019-C-DAT-00029-001 | 019-C-DAT-00029-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SOUR WATER FLASH DRUM 019V0029 | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040424 | 019-C-DAT-00030-001 | 019-C-DAT-00030-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR BACKWASH OIL SURGE DRUM 019V0030 | 0 | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040425 | 050-M-GAD-55441-001 | 050-M-GAD-55441-001 | STEEL STRUCTURES SLEEPERWAY TANKS AREA 050D1003/1004 | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040426 | 012-E-DAT-00013-001 | 012-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR C3/C4 SPLITTER OVHD CONDENSER 012E018 A/B | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040426 | 012-E-DAT-00015-001 | 012-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR BUTANE TRIM COOLER 012E0022 | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-040427 | 076551C-000M-TBT-0110-001 | 000-F-TBE-70001-001 | TECHNICAL BID EVALUATIONS FOR 2HCU FIRED HEATERS | A | 2018-07-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-040427 | 076551C-000M-TBT-0110-002 | 000-F-TBE-70002-001 | TECHNICAL BID EVALUATIONS FOR 7CDU/7VDU HEATERS | A | 2018-07-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-040428 | 076551C-000M-ITP-0411-001 | 000-C-ITP-70006-001 | INSPECTION AND TEST PLAN FOR HCU REACTORS | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-040428 | 076551C-000M-MR-0411-001 | 000-C-MRQ-70006-001 | MATERIAL REQUISITION FOR HCU REACTORS | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-040428 | 076551C-000M-SP-0411-001 | 000-C-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR HCU REACTORS | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-040428 | 076551C-000M-SR-0411-001 | 000-C-SOW-70006-001 | SCOPE OF SUPPLY FOR HCU REACTORS | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-040428 | 076551C-O6873 | 000-C-MPO-50002-001 | PURCHASE ORDER RELEVANT TO 000M-MR-0411-001 FOR REACTORS HCU | 0 | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-10 | 1 - APPROVED | 2018-08-13 | CLASS 2
CON-BMP-TRA-040429 | 076551C-000M-ITP-0470-001 | 000-C-ITP-70007-001 | INSPECTION AND TEST PLAN FOR 2HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040429 | 076551C-000M-MR-0470-001 | 000-C-MRQ-70007-001 | MATERIAL REQUISITION FOR 2HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040429 | 076551C-000M-SP-0470-001 | 000-C-GRD-70007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040429 | 076551C-000M-SR-0470-001 | 000-C-SOW-70007-001 | SCOPE OF SUPPLY FOR 2HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040429 | 076551C-O6917 | 000-C-MPO-50005-001 | PURCHASE ORDER RELEVANT TO 000M-MR-00470-001 FOR HCU REACTOR INTERNALS | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 5 - RETAINED FOR INFORMATION | 2018-08-12 | CLASS 2
CON-BMP-TRA-040430 | 010-S-BLD-00001-001 | 010-S-BLD-00001-001 | BLOCK DIAGRAM FIRE AND GAS SYSTEM SATELLITE RACK ROOM 156RR01 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040431 | 019-S-BLD-00001-001 | 019-S-BLD-00001-001 | BLOCK DIAGRAM FIRE AND GAS SYSTEM SATELLITE RACK ROOM 154RR01 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040432 | 085-S-BLD-00001-001 | 085-S-BLD-00001-001 | BLOCK DIAGRAM FIRE AND GAS SYSTEM SATELLITE RACK ROOM 160RR01 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040433 | 012-S-BLD-00001-001 | 012-S-BLD-00001-001 | BLOCK DIAGRAM FIRE AND GAS SYSTEM SATELLITE RACK ROOM 156RR01 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040434 | 050-S-BLD-55001-001 | 050-S-BLD-55001-001 | BLOCK DIAGRAM FIRE AND GAS SYSTEM SATELLITE RACK ROOM 163RR01 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040435 | 019-P-SLD-00201-001 | 019-P-SLD-00201-001 | SINGLE LINE DIAGRAM AC UPS FOR ESD SYSTEM 115 V | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040436 | 010-P-SLD-00200-001 | 010-P-SLD-00200-001 | SINGLE LINE DIAGRAM AC UPS FOR DCS SYSTEM 115 V | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040437 | 010-P-SLD-00201-001 | 010-P-SLD-00201-001 | SINGLE LINE DIAGRAM AC UPS FOR EDS SYSTEM 115 V | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040438 | 010-P-SLD-00202-001 | 010-P-SLD-00202-001 | SINGLE LINE DIAGRAM DC SYSTEM 110 VDC | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040439 | 085-P-SLD-00200-001 | 085-P-SLD-00200-001 | SINGLE LINE DIAGRAM AC UPS FOR DCS SYSTEM 115 V | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040440 | 085-P-SLD-00201-001 | 085-P-SLD-00201-001 | SINGLE LINE DIAGRAM AC UPS FOR EDS SYSTEM 115 V | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040441 | 085-P-SLD-00202-001 | 085-P-SLD-00202-001 | SINGLE LINE DIAGRAM DC SYSTEM 110 VDC | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040442 | 019-M-GAD-00602-001 | 019-M-GAD-00602-001 | STEEL STRUCTURE PIPE RACK E019PR100 AXIS 6P TO 8P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040442 | 019-M-GAD-00602-002 | 019-M-GAD-00602-002 | STEEL STRUCTURE PIPE RACK E019PR100 AXIS 6P TO 8P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040443 | 012-M-GAD-00604-001 | 012-M-GAD-00604-001 | STEEL STRUCTURE PIPE RACK F012PR100 AXIS 16P TO 19P PLANS AND ELEVATIONS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040443 | 012-M-GAD-00604-002 | 012-M-GAD-00604-002 | STEEL STRUCTURE PIPE RACK F012PR100 AXIS 16P TO 19P PLANS AND ELEVATIONS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040443 | 012-M-GAD-00604-003 | 012-M-GAD-00604-003 | STEEL STRUCTURE PIPE RACK F012PR100 AXIS 16P TO 19P PLANS AND ELEVATIONS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040443 | 012-M-GAD-00604-004 | 012-M-GAD-00604-004 | STEEL STRUCTURE PIPE RACK F012PR100 AXIS 16P TO 19P PLANS AND ELEVATIONS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040443 | 012-M-GAD-00604-005 | 012-M-GAD-00604-005 | STEEL STRUCTURE PIPE RACK F012PR100 AXIS 16P TO 19P PLANS AND ELEVATIONS | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040444 | 012-E-GAD-00001-001 | 012-E-GAD-00001-001 | GENERAL ARRANGEMENT FEED GAS COMPRESSORS TRIM COOLER 012E002 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040444 | 012-E-GAD-00002-001 | 012-E-GAD-00002-001 | GENERAL ARRANGEMENT ABSORBER BOTTOM WATER COOLER 012E0006A/B | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040444 | 012-E-GAD-00003-001 | 012-E-GAD-00003-001 | GENERAL ARRANGEMENT BOTTOM/STABILIZER FEED EXCHANGER 012E0008 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040444 | 012-E-GAD-00004-001 | 012-E-GAD-00004-001 | GENERAL ARRANGEMENT ABSORBER OVHD CONDENSER 012E0003 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040444 | 012-E-GAD-00007-001 | 012-E-GAD-00007-001 | GENERAL ARRANGEMENT ABSORBER UPPER INTERCOOLER 012E0004 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040444 | 012-E-GAD-00008-001 | 012-E-GAD-00008-001 | GENERAL ARRANGEMENT ABSORBER LOWER INTERCOOLER 012E0005 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040444 | 012-E-GAD-00009-001 | 012-E-GAD-00009-001 | GENERAL ARRANGEMENT LPG COOLER 012E0010 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040444 | 012-E-GAD-00010-001 | 012-E-GAD-00010-001 | GENERAL ARRANGEMENT LPG PRODUCT COOLER 012E0017 | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040445 | 019-C-DAT-00011-001 | 019-C-DAT-00011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR COLD LOW PRESSURE SEPARATOR 019V0011 | 0 | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-040446 | 012-Q-PED-00204-001 | 012-Q-PED-00204-001 | FOUNDATION PIPE RACK F012PR100 AXIS 16P TO 19P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040446 | 012-Q-PED-00204-002 | 012-Q-PED-00204-002 | FOUNDATION PIPE RACK F012PR100 AXIS 16P TO 19P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040447 | 010-J-CRD-00100-001 | 010-J-CRD-00100-001 | TELECOM EQUIPMENT LAYOUT AND CABLE ROUTING 010-7CDU/011-7VDU | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040448 | 012-J-CRD-00100-001 | 012-J-CRD-00100-001 | TELECOM EQUIPMENT LAYOUT AND CABLE ROUTING 012-1SGP/017-2SGP | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040449 | 085-J-CRD-00100-001 | 085-J-CRD-00100-001 | TELECOM EQUIPMENT LAYOUT AND CABLE ROUTING 085 - COOLING WATER TOWER | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040450 | 019-C-DAT-00010-001 | 019-C-DAT-00010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HOT LOW PRESSURE SEPARATOR 019V0010 | 0 | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040451 | 019-J-CRD-00100-001 | 019-J-CRD-00100-001 | TELECOM EQUIPMENT LAYOUT AND CABLE ROUTING 019 HYDROCRACKING UNIT 2HCU | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040452 | 012-E-DAT-00016-001 | 012-E-DAT-00016-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR LIGHT NAPHTHA TRIM COOLER 012E0013 | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040452 | 012-E-DAT-00017-001 | 012-E-DAT-00017-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR HEAVY NAPHTHA TRIM COOLER 012E0016 | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040452 | 012-E-DAT-00019-001 | 012-E-DAT-00019-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR PROPANE TRIM COOLER 012E0019 | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040453 | 019-R-PFD-00940-001 | 019-R-PFD-00940-001 | SUBSTATION 2HCU 019SSTR01 HVAC PROCESS FLOW DIAGRAM BUILDING | A | 2018-07-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-21 | 3 - REVIEWED WITH COMMENTS | 2018-08-10 | CLASS 1
CON-BMP-TRA-040454 | 076551C-000M-TBT-0811-002 | 000-C-TBE-70001-001 | TECHNICAL BID EVALUATIONS FOR H.P. VESSELS | A | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-040455 | 012-E-GAD-00012-001 | 012-E-GAD-00012-001 | GENERAL ARRANGEMENT DRAWING 012E0024 HP LEAN AMINE COOLER | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-21 | 3 - REVIEWED WITH COMMENTS | 2018-08-12 | CLASS 2
CON-BMP-TRA-040456 | 050-A-PPN-55001-001 | 050-A-PPN-55001-001 | GENERAL PLOT PLAN NORTH AREA (EX 050-L-PPN-55001-001) | B | 2018-07-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 1
CON-BMP-TRA-040456 | 050-A-PPN-55001-002 | 050-A-PPN-55001-002 | GENERAL PLOT PLAN SOUTH AREA (EX 050-L-PPN-55001-002) | B | 2018-07-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-21 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 1
CON-BMP-TRA-040457 | 019-J-GAD-00001-001 | 019-J-GAD-00001-001 | EQUIPMENT LAYOUT SATELLITE RACK ROOM 154SRR01 019- NO 2 HYDROCRACKING UNIT - 2HCU | A | 2018-07-31 | FOR BAPCO INFORMATION | BMP Project Director |  | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 3
CON-BMP-TRA-040458 | 076551C-000M-TBT-0610-001 | 000-E-TBE-70001-001 | TECHNICAL BID EVALUATION FOR HP SHELL & TUBE HEAT EXCHANGERS | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-040459 | 076551C-000M-TBT-0846-001 | 000-S-TBE-70003-001 | TECHNICAL BID EVALUATION FOR FEED FILTER | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040460 | 010-K-DAT-00004-001 | 010-K-DAT-00004-001 | BRIDGE CRANE DATA SHEET FOR 010C0001 BRIDGE CRANE FOR 010K0001A/B | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040461 | 372-A-PPN-57001-001 | 372-A-PPN-57001-001 | GENERAL PLOT PLAN | A | 2018-08-01 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-22 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 1
CON-BMP-TRA-040462 | 019-K-DAT-00010-001 | 019-K-DAT-00010-001 | BRIDGE CRANE DATA SHEET 019OC0002 BRIDGE CRANE FOR 019K0001 | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040462 | 019-K-DAT-00011-001 | 019-K-DAT-00011-001 | BRIDGE CRANE DATA SHEET 019OC0001 BRIDGE CRANE FOR 019K0002/03/04 | A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040463 | 019-C-GAD-10006-001 | 019-C-GAD-10006-001 | GENERAL ARRANGEMENT 019C0006 KEROSENE STRIPPER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040463 | 019-C-GAD-10006-002 | 019-C-GAD-10006-002 | GENERAL ARRANGEMENT 019C0006 KEROSENE STRIPPER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040463 | 019-C-GAD-10006-003 | 019-C-GAD-10006-003 | GENERAL ARRANGEMENT 019C0006 KEROSENE STRIPPER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040463 | 019-C-GAD-10010-001 | 019-C-GAD-10010-001 | GENERAL ARRANGEMENT 019C0010 NAPHTHA SPLITTER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040463 | 019-C-GAD-10010-002 | 019-C-GAD-10010-002 | GENERAL ARRANGEMENT 019C0010 NAPHTHA SPLITTER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040463 | 019-C-GAD-10010-003 | 019-C-GAD-10010-003 | GENERAL ARRANGEMENT 019C0010 NAPHTHA SPLITTER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040464 | 010-C-GAD-10004-001 | 010-C-GAD-10004-001 | GENERAL ARRANGEMENT 010C0004 STABILIZER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040464 | 010-C-GAD-10004-002 | 010-C-GAD-10004-002 | GENERAL ARRANGEMENT 010C0004 STABILIZER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040464 | 010-C-GAD-10004-003 | 010-C-GAD-10004-003 | GENERAL ARRANGEMENT 010C0004 STABILIZER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040464 | 010-C-GAD-10005-001 | 010-C-GAD-10005-001 | GENERAL ARRANGEMENT 010C0005 NAPHTHA SPLITTER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040464 | 010-C-GAD-10005-002 | 010-C-GAD-10005-002 | GENERAL ARRANGEMENT 010C0005 NAPHTHA SPLITTER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040464 | 010-C-GAD-10005-003 | 010-C-GAD-10005-003 | GENERAL ARRANGEMENT 010C0005 NAPHTHA SPLITTER | 0A | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040465 | 076551C-000M-DL-0511-001 | 000-C-IDL-70008-001 | DEVIATION LIST FOR CS COLUMNS | 0 | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040465 | 076551C-000M-ITP-0511-001 | 000-C-ITP-70008-001 | INSPECTION AND TEST PLAN FOR CS COLUMNS | 0 | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040465 | 076551C-000M-MR-0511-001 | 000-C-MRQ-70008-001 | MATERIAL REQUISITION FOR CS COLUMNS | 0 | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040465 | 076551C-000M-SP-0511-001 | 000-C-GRD-70008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS COLUMNS | 0 | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040465 | 076551C-000M-SR-0511-001 | 000-C-SOW-70008-001 | SCOPE OF SUPPLY FOR CS COLUMNS | 0 | 2018-08-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040465 | 076551C-O6908 | 000-C-MPO-50004-001 | PURCHASE ORDER RELEVANT TO 000M-MR-0511-001 FOR CS COLUMNS | 0 | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 5 - RETAINED FOR INFORMATION | 2018-08-14 | CLASS 2
CON-BMP-TRA-040466 | 010-A-CAL-00001-001 | 010-A-CAL-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET - NO 7 CRUDE DISTILLATION UNIT (7CDU) (EX 010-A-STS-00001-001) | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040467 | 011-A-CAL-00001-001 | 011-A-CAL-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET - NO 7 VACUUM DISTILLATION UNIT (7VDU) (EX 011-A-STS-00001-001) | B | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040468 | 019-C-DAT-00016-001 | 019-C-DAT-00016-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA SPLITTER REBOILER CONDENSATE POT 019V0016 | 0 | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040468 | 019-C-DAT-00025-001 | 019-C-DAT-00025-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STEAM DRUM 019V0025 | 0 | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040468 | 019-C-DAT-00032-001 | 019-C-DAT-00032-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FUEL GAS KO DRUM 019V0032 | 0 | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040468 | 019-C-DAT-00036-001 | 019-C-DAT-00036-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECOVERED PROCESS SLOP OIL SUMP 019V0036 | 0 | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040468 | 019-C-DAT-00037-001 | 019-C-DAT-00037-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR AMINE SUMP 019V0037 | 0 | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040468 | 019-C-DAT-00038-001 | 019-C-DAT-00038-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SOUR WATER SUMP 019V0038 | 0 | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040468 | 019-C-DAT-10011-001 | 019-C-DAT-10011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR VACUUM DRYER 019C0011 | 0 | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-040469 | 019-Q-PED-00110-001 | 019-Q-PED-00110-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR E019STR300 | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-040471 | 050-D-DAT-55001-001 | 050-D-DAT-55001-001 | TANK DATA SHEET FOR 050D1001/050D1002 A/B CRUDE OIL TANKS | 0 | 2018-08-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040471 | 050-D-DAT-55003-001 | 050-D-DAT-55003-001 | TANK DATA SHEET FOR 050D1003/050D1004 1RHCU FEED TANKS | 0 | 2018-08-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040472 | 019-R-PFD-00941-001 | 019-R-PFD-00941-001 | SATELLITE RACK ROOM 019SRR01 HVAC PROCESS FLOW DIAGRAMS BUILDING | A | 2018-08-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 1
CON-BMP-TRA-040473 | 076551C-000M-TBT-0840-002 | 000-S-TBE-70001-001 | TECHNICAL BID EVALUATION FOR SIDE STREAM FILTERS PACKAGE | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040473 | 076551C-000M-TBT-0848-002 | 000-S-TBE-70004-001 | TECHNICAL BID EVALUATION FOR CALCITE BED PACKAGE | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 2
CON-BMP-TRA-040474 | 010-E-GAD-00001-001 | 010-E-GAD-00001-001 | GENERAL ARRANGEMENT DRAWING 010E0002 A-H CRUDE/CDU HEAD EXCHANGER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040474 | 010-E-GAD-00013-001 | 010-E-GAD-00013-001 | GENERAL ARRANGEMENT DRAWING 010E0017 A/B ATMOSPHERIC COLUMN OVERHEAD TRIM COOLER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040475 | 019-A-INX-00001-001 | 019-A-INX-00001-001 | EFFLUENT LIST UNIT 019 NO 2 HYDROCRACKING UNIT 2HCU | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040476 | 010-A-INX-00001-001 | 010-A-INX-00001-001 | EFFLUENT LIST UNIT 010 NO 7 CRUDE DISTILLATION UNIT | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040477 | 011-A-INX-00001-001 | 011-A-INX-00001-001 | EFFLUENT LIST UNIT 011 NO 7 VACUUM DISTILLATION UNIT | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040478 | 012-A-INX-00001-001 | 012-A-INX-00001-001 | EFFLUENT LIST UNIT 012 NO 1 SATURATED GAS PLANT 1SGP | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040479 | 085-A-INX-00001-001 | 085-A-INX-00001-001 | EFFLUENT LIST UNIT 085 COOLING WATER TOWER | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00001-001 | 019-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0006 A/B 1ST STAGE REACTOR EFFLUENT / FRESH FEED EXCHANGER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00002-001 | 019-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0004 A/B 1ST STAGE REACTOR EFFLUENT / EFFLUENT EXCHANGER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00003-001 | 019-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0005 A/B 1ST STAGE REACTOR EFFLUENT / FRACTIONATOR FEED EXCHANGER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00004-001 | 019-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0007 A/B 1ST STAGE HHPS VAPOR / RECYCLE GAS EXCHANGER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00005-001 | 019-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0011 A/B 2ND STAGE HHPS VAPOR /CLPS LIQUID EXCHANGER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00006-001 | 019-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0009 A/B 2ND STAGE REACTOR FEED /EFFLUENT EXCHANGER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00007-001 | 019-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0010 2ND STAGE REACTOR EFFLUENT / RECYCLE GAS EXCHANGER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00013-001 | 019-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0044 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00014-001 | 019-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0047 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040480 | 019-E-DAT-00015-001 | 019-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0049 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | B | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040481 | 011-A-MSD-00001-001 | 011-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM VACUUM DISTILLAION DESIGN CASE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040481 | 011-A-MSD-00001-002 | 011-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM STEAM GENERATION AND PRODUCTS COOLING DESIGN CASE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040481 | 011-A-MSD-00001-003 | 011-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM VACUUM DISTILLATION EQUIPMENT TABLE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040481 | 011-A-MSD-00001-004 | 011-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM STEAM GENERATION AND PRODUCTS COOLING EQUIPMENT TABLE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-001 | 010-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - CRUDE PREHEAT DESIGN CASE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-002 | 010-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - CRUDE PREHEAT DESIGN CASE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-003 | 010-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - CRUDE PREHEAT DESIGN CASE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-004 | 010-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - GAS COMPRESSION SECT DESIGN CASE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-005 | 010-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - DEBUTANIZER/NAPHTA SPLITTER DESIGN CASE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-006 | 010-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - CRUDE PREHEAT EQUIPMENT MATERIAL TABLE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 1 - APPROVED | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-007 | 010-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - CRUDE PREHEAT EQUIPMENT MATERIAL TABLE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 1 - APPROVED | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-008 | 010-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - CRUDE DISTILLATION EQUIPMENT MATERIAL TABLE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 1 - APPROVED | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-009 | 010-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM 7CDU/VDU - CRUDE DISTILLATION DESIGN CASE | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-010 | 010-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM SOUR WATER AND SLOPS CLOSED DRAINS | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-011 | 010-A-MSD-00001-011 | MATERIAL SELECTION DIAGRAM FLARE KO DRUM | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 1 - APPROVED | 2018-08-15 | CLASS 1
CON-BMP-TRA-040482 | 010-A-MSD-00001-012 | 010-A-MSD-00001-012 | MATERIAL SELECTION DIAGRAM FUEL GAS KO DRUM | 0 | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-27 | 1 - APPROVED | 2018-08-15 | CLASS 1
CON-BMP-TRA-040483 | 076551C-000M-TBT-0851-001 | 000-H-TBE-70001-001 | TECHNICAL BID EVALUATION FOR VACUUM UNIT PACKAGE | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-040484 | 019-M-GAD-00603-001 | 019-M-GAD-00603-001 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK E019PR100 AXIS 9P TO 14P | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040484 | 019-M-GAD-00603-002 | 019-M-GAD-00603-002 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK E019PR100 AXIS 9P TO 14P | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040484 | 019-M-GAD-00603-003 | 019-M-GAD-00603-003 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK E019PR100 AXIS 9P TO 14P | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040484 | 019-M-GAD-00603-004 | 019-M-GAD-00603-004 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK E019PR100 AXIS 9P TO 14P | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040485 | 019-Q-PED-00152-001 | 019-Q-PED-00152-001 | PLAN SECTIONS AND DETAILS FOUNDATION FOR VERTICAL VESSELS 019C0005 | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040485 | 019-Q-PED-00154-001 | 019-Q-PED-00154-001 | PLAN SECTIONS AND DETAILS FOUNDATION FOR VERTICAL VESSELS 019C0009 | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040485 | 019-Q-PED-00202-001 | 019-Q-PED-00202-001 | PLAN ELEVATIONS AND DETAILS PIPE RACK E019PR100 AXIS 6P TO 8P | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040485 | 019-Q-PED-00202-002 | 019-Q-PED-00202-002 | PLAN ELEVATIONS AND DETAILS PIPE RACK E019PR100 AXIS 6P TO 8P | A | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040486 | 012-Q-PED-00201-001 | 012-Q-PED-00201-001 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040486 | 012-Q-PED-00201-002 | 012-Q-PED-00201-002 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040486 | 012-Q-PED-00202-001 | 012-Q-PED-00202-001 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK 012PR100 AXIS 6P TO 10P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040486 | 012-Q-PED-00202-002 | 012-Q-PED-00202-002 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK 012PR100 AXIS 6P TO 10P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040486 | 012-Q-PED-00203-001 | 012-Q-PED-00203-001 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK 012PR100 AXIS 11P TO 15P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040486 | 012-Q-PED-00203-002 | 012-Q-PED-00203-002 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK 012PR100 AXIS 11P TO 15P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040486 | 012-Q-PED-00205-001 | 012-Q-PED-00205-001 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK 012PR100 AXIS 20P TO 22P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040486 | 012-Q-PED-00205-002 | 012-Q-PED-00205-002 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK 012PR100 AXIS 20P TO 22P | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 3 - REVIEWED WITH COMMENTS | 2018-08-14 | CLASS 2
CON-BMP-TRA-040487 | 019-C-DAT-10004-001 | 019-C-DAT-10004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT STRIPPER 019C0004 | 0 | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040487 | 019-C-DAT-10007-001 | 019-C-DAT-10007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LIGHT DIESEL STRIPPER 019C0007 | 0 | 2018-08-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-15 | CLASS 2
CON-BMP-TRA-040488 | 012-M-GAD-00603-001 | 012-M-GAD-00603-001 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 11P TO 15P | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040488 | 012-M-GAD-00603-002 | 012-M-GAD-00603-002 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 11P TO 15P | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040488 | 012-M-GAD-00603-003 | 012-M-GAD-00603-003 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 11P TO 15P | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040488 | 012-M-GAD-00603-004 | 012-M-GAD-00603-004 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 11P TO 15P | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040488 | 012-M-GAD-00603-005 | 012-M-GAD-00603-005 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 11P TO 15P | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040488 | 012-M-GAD-00603-006 | 012-M-GAD-00603-006 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 11P TO 15P | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 3 - REVIEWED WITH COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-040489 | MOC-BMM-MOM-000032 | 000-A-MOM-70006-001 | UNIT 012/017 - SGP SIMULATION REPORT REVIEW | 0 | 2018-08-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040490 | 012-C-DAT-00001-001 | 012-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 012V0001 FEED GAS COMPRESSOR KO DRUM | 0 | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040490 | 012-C-DAT-00002-001 | 012-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 012V0002 FEED GAS SEPARATOR | 0 | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040490 | 012-C-DAT-00005-001 | 012-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 012V0005 DEETHANIZER FEED SURGE DRUM | 0 | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040490 | 012-C-DAT-00007-001 | 012-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 012V0007 NAPHTHA SPLITTER OVERHEAD RECEIVER | 0 | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040491 | 019-R-PED-00940-001 | 019-R-PED-00940-001 | SUBSTATION 2HCU 019SSTR01 HVAC LAYOUT GROUNG FLOOR BUILDING | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-040491 | 019-R-PED-00941-001 | 019-R-PED-00941-001 | SUBSTATION 2HCU 019SSTR01 HVAC LAYOUT ROOF FLOOR BUILDING | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-040491 | 019-R-PED-00943-001 | 019-R-PED-00943-001 | SATELLITE RACK ROOM 019SRR01 HVAC LAYOUT GROUNG FLOOR BUILDING | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-040491 | 019-R-PED-00944-001 | 019-R-PED-00944-001 | SATELLITE RACK ROOM 019SRR01 HVAC LAYOUT ROOF FLOOR BUILDING | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-040492 | 010-P-DAT-00001-001 | 010-P-DAT-00001-001 | HV/HV 33/6-9 KV DATA SHEET FOR TR4001J5/TR4002J5 POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-040493 | 085-P-DAT-00001-001 | 085-P-DAT-00001-001 | HV/HV 33/6-9 KV DATA SHEET FOR TR4003J2/TR4004J2 POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 3 - REVIEWED WITH COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-040494 | 076551C-000M-TBT-0710-002 | 000-E-TBE-70008-001 | TECHNICAL BID EVALUATION FOR AIR COOLERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040495 | MOC-BMM-MOM-000034 | 000-A-MOM-70007-001 | AIR COOLERS TUBE THICKNESS AND FANS MATERIAL | 0 | 2018-08-08 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040496 | 019-P-DAT-00000-001 | 019-P-DAT-00000-001 | HV/HV 33/11.5 KV DATA SHEET FOR TR4003J3/TR4004J3 POWER TRANSFORMERS | A | 2018-08-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-040496 | 019-P-DAT-00001-001 | 019-P-DAT-00001-001 | HV/HV 33/6.9 KV DATA SHEET FOR TR4003J4/TR4004J4 POWER TRANSFORMERS | A | 2018-08-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-040497 | 019-E-DAT-00039-001 | 019-E-DAT-00039-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0017 FRACTIONATOR OVERHEAD AIR COOLER | B | 2018-08-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040498 | 012-P-DAT-00100-001 | 012-P-DAT-00100-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5300L4/TR5301L4 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040498 | 012-P-DAT-00101-001 | 012-P-DAT-00101-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5300L5/TR5301L5 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040499 | 017-P-DAT-00100-001 | 017-P-DAT-00100-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5300L6/TR5301L6 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040499 | 017-P-DAT-00101-001 | 017-P-DAT-00101-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5300L7/TR5301L7 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040500 | 011-P-DAT-00100-001 | 011-P-DAT-00100-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5300L3/TR5301L3 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040501 | 019-P-DAT-00100-001 | 019-P-DAT-00100-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5002L3/TR5003L3 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040501 | 019-P-DAT-00101-001 | 019-P-DAT-00101-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5002L2/TR5003L2 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040501 | 019-P-DAT-00102-001 | 019-P-DAT-00102-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5002L1/TR5003L1 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040502 | 010-P-DAT-00100-001 | 010-P-DAT-00100-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5300L1/TR5301L1 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040502 | 010-P-DAT-00101-001 | 010-P-DAT-00101-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5300L2/TR5301L2 POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040503 | 085-P-DAT-00100-001 | 085-P-DAT-00100-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5600L/TR5601L POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040503 | 085-P-DAT-00101-001 | 085-P-DAT-00101-001 | HV/LV 6.6/0.42 KV DATA SHEET FOR TR5603L POWER TRANSFORMERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 3 - REVIEWED WITH COMMENTS | 2018-08-20 | CLASS 2
CON-BMP-TRA-040504 | 019-C-DAT-00017-001 | 019-C-DAT-00017-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 019V0017 VACUUM DRYER HOTWELL | 0 | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00005-001 | 012-E-GAD-00005-001 | GENERAL ARRANGEMENT DRAWING 012E0007 DEETHANIZER REBOILER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00006-001 | 012-E-GAD-00006-001 | GENERAL ARRANGEMENT DRAWING 012E0011A/B STABILIZER REBOILER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00011-001 | 012-E-GAD-00011-001 | GENERAL ARRANGEMENT DRAWING 012E0023 LP LEAN AMINE COOLER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00013-001 | 012-E-GAD-00013-001 | GENERAL ARRANGEMENT DRAWING 012E018A/B C3/C4 SPLITTER OVHD CONDENSER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00014-001 | 012-E-GAD-00014-001 | GENERAL ARRANGEMENT DRAWING 012E020 C3/C4 SPLITTER REBOILER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00015-001 | 012-E-GAD-00015-001 | GENERAL ARRANGEMENT DRAWING 012E022 BUTANE TRIM COOLER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00016-001 | 012-E-GAD-00016-001 | GENERAL ARRANGEMENT DRAWING 012E013 LIGHT NAPHTHA TRIM COOLER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00017-001 | 012-E-GAD-00017-001 | GENERAL ARRANGEMENT DRAWING 012E016 HEAVY NAPHTHA TRIM COOLER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00018-001 | 012-E-GAD-00018-001 | GENERAL ARRANGEMENT DRAWING 012E014A/B NAPHTHA SPLITTER REBOILER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040505 | 012-E-GAD-00019-001 | 012-E-GAD-00019-001 | GENERAL ARRANGEMENT DRAWING 012E019 PROPANE TRIM COOLER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-040506 | 076551C-000M-TBT-0511-002 | 000-C-TBE-70009-001 | TECHNICAL BIDS EVALUATION FOR CLADDED COLUMNS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040507 | 076551C-000M-TBT-0710-001 | 000-E-TBE-70007-001 | TECHNICAL BIDS EVALUATION FOR HP & SPECIAL MATERIALS AIR COOLERS | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040508 | 050-A-CAL-55001-001 | 050-A-CAL-55001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCILATION SHEET REFINERY TANK FARM (PLANT N 050) (EX 050-A-STS-55001-001) | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040509 | 012-A-CAL-00001-001 | 012-A-CAL-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET NO 1 SATURATED GAS PLANT 1SGP (EX 012-A-STS-00002-001) | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040510 | 085-A-CAL-00001-001 | 085-A-CAL-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET COOLING WATER TOWER - CWT (EX 085-A-STS-00001-001) | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040511 | 017-A-CAL-00001-001 | 017-A-CAL-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET NO 2 SATURATED GAS PLANT 2SGP (EX 017-A-STS-00001-001) | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040512 | 010-P-DAT-00200-001 | 010-P-DAT-00200-001 | DATA SHEET FOR NER4001V5/NER4002V5 NEUTRAL EARTHING RESISTORS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040513 | 019-P-DAT-00200-001 | 019-P-DAT-00200-001 | DATA SHEET FOR NER4003V4/NER4004V4 NEUTRAL EARTHING RESISTORS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040513 | 019-P-DAT-00201-001 | 019-P-DAT-00201-001 | DATA SHEET FOR NER4003V3/NER4004V3 NEUTRAL EARTHING RESISTORS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040514 | 085-P-DAT-00200-001 | 085-P-DAT-00200-001 | DATA SHEET FOR NER4003V2/NER4004V2 NEUTRAL EARTHING RESISTORS | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-040515 | 934-A-CAL-00001-001 | 934-A-CAL-00001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET FEED BOOSTER PUMP HOUSE PLANT N 934 (EX 934-A-STS-00001-001) | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040516 | 372-A-CAL-57001-001 | 372-A-CAL-57001-001 | EQUIPMENT/MATERIAL CRITICALITY LEVEL CALCULATION SHEET BOILER FEED WATER AND CONDENSATE DISTRIBUTION (EX 372-A-STS-57001 | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040517 | 010-Q-PED-00151-001 | 010-Q-PED-00151-001 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSELS 010C0002 AND 010C0003 | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040517 | 010-Q-PED-00152-001 | 010-Q-PED-00152-001 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSELS 010C0004 AND 010C0005 | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040517 | 010-Q-PED-00152-003 | 010-Q-PED-00152-003 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSELS 010C0004 AND 010C0005 | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040517 | 010-Q-PED-00153-001 | 010-Q-PED-00153-001 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSELS 010C0007 | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040518 | 012-M-GAD-00602-001 | 012-M-GAD-00602-001 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 6P TO 10P | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040518 | 012-M-GAD-00602-002 | 012-M-GAD-00602-002 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 6P TO 10P | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040518 | 012-M-GAD-00602-003 | 012-M-GAD-00602-003 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 6P TO 10P | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040518 | 012-M-GAD-00602-004 | 012-M-GAD-00602-004 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 6P TO 10P | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040519 | 012-Q-PED-00115-001 | 012-Q-PED-00115-001 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSEL 012STR400 | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040519 | 012-Q-PED-00115-002 | 012-Q-PED-00115-002 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSEL 012STR400 | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040519 | 012-Q-PED-00120-001 | 012-Q-PED-00120-001 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSEL 012STR500 | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040519 | 012-Q-PED-00150-001 | 012-Q-PED-00150-001 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSEL 012C0007 | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040520 | 019-A-MSD-00001-001 | 019-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-002 | 019-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-003 | 019-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM FRACTIONATION | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-004 | 019-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM NAPHTHA PRODUCT SECTION | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-005 | 019-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM FEED AND RUNDOWN | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-006 | 019-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM HYDROGEN COMPRESSION SECTION | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-007 | 019-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM AMINE AND SOUR WATER SYSTEM | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-008 | 019-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-009 | 019-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM FRACTIONATION | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-010 | 019-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM NAPHTHA PRODUCT SECTION | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-011 | 019-A-MSD-00001-011 | MATERIAL SELECTION DIAGRAM FEED AND RUNDOWN | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-012 | 019-A-MSD-00001-012 | MATERIAL SELECTION DIAGRAM CLG NOTES FOR MATERIAL SELECTION DRAWINGS | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-013 | 019-A-MSD-00001-013 | MATERIAL SELECTION DIAGRAM FEED FILTER SECTION | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-014 | 019-A-MSD-00001-014 | MATERIAL SELECTION DIAGRAM LP STEAM GENERATION SYSTEM | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-015 | 019-A-MSD-00001-015 | MATERIAL SELECTION DIAGRAM PHOSPHATE INJECTION PACKAGE | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-016 | 019-A-MSD-00001-016 | MATERIAL SELECTION DIAGRAM STEAM BLOWDOWN COLLECTION SYSTEM | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-017 | 019-A-MSD-00001-017 | MATERIAL SELECTION DIAGRAM FUEL GAS KO DRUM | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-018 | 019-A-MSD-00001-018 | MATERIAL SELECTION DIAGRAM FLARE KO DRUM | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040520 | 019-A-MSD-00001-019 | 019-A-MSD-00001-019 | MATERIAL SELECTION DIAGRAM SOUR WATER SLOPS AND AMINE | 0 | 2018-08-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-03 |  |  | CLASS 1
CON-BMP-TRA-040521 | 019-E-GAD-00050-001 | 019-E-GAD-00050-001 | GENERAL ARRANGEMENT DRAWING 019E0039 LIGHT NAPHTHA PRODUCT TRIM COOLER | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040522 | 019-E-DAT-00050-001 | 019-E-DAT-00050-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0039 LIGHT NAPHTHA PRODUCT TRIM COOLER | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040523 | 019-C-DAT-00018-001 | 019-C-DAT-00018-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 019V0018 MAKE-UP HYDROGEN FIRST STAGE SUCTION DRUM | 0 | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040523 | 019-C-DAT-00019-001 | 019-C-DAT-00019-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 019V0019 MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM | 0 | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040523 | 019-C-DAT-00020-001 | 019-C-DAT-00020-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 019V0020 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | 0 | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040523 | 019-C-DAT-00021-001 | 019-C-DAT-00021-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 019V0021 MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM | 0 | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040523 | 019-C-DAT-00022-001 | 019-C-DAT-00022-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 019V0022 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | 0 | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040523 | 019-C-DAT-00023-001 | 019-C-DAT-00023-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 019V0023 MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM | 0 | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040523 | 019-C-DAT-00024-001 | 019-C-DAT-00024-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 019V0024 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | 0 | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040524 | 019-S-PED-00820-001 | 019-S-PED-00820-001 | PLAN ELEVATION AND DETAILS UNDERGROUND OWS SYSTEM MANHOLE SCHEDULE | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040524 | 019-S-PED-00825-001 | 019-S-PED-00825-001 | PLAN ELEVATION AND DETAILS UNDERGROUND CSS SYSTEM MANHOLE SCHEDULE | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-040525 | 000-P-STS-70007-001 | 000-P-STS-70007-001 | HARMONICS STUDY UNITS 7CDU-7VDU-1SGP-2SGP-2HCU-CWT | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-27 | CLASS 2
CON-BMP-TRA-040526 | 076551C-000M-TBT-0570-001 | 000-C-TBE-70010-001 | TECHNICAL BIDS EVALUATION FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-01 |  |  | CLASS 2
CON-BMP-TRA-040527 | 019-M-GAD-00604-001 | 019-M-GAD-00604-001 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 019PR100 AXIS 14P TO 18P | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040527 | 019-M-GAD-00604-002 | 019-M-GAD-00604-002 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 019PR100 AXIS 14P TO 18P | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040527 | 019-M-GAD-00604-003 | 019-M-GAD-00604-003 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 019PR100 AXIS 14P TO 18P | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040527 | 019-M-GAD-00604-004 | 019-M-GAD-00604-004 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 019PR100 AXIS 14P TO 18P | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040528 | 012-C-DAT-10006-001 | 012-C-DAT-10006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LPG AMINE ABSORBER 012C0006 | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040529 | 010-Q-PED-00150-001 | 010-Q-PED-00150-001 | PLAN ELEVATION AND DETAILS FOUNDATIONS FOR VERTICAL VESSELS 010C0001 AND 011C0002 | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040530 | 019-Q-PED-00203-001 | 019-Q-PED-00203-001 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK E019PR100 AXIS 9P TO 14P | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040530 | 019-Q-PED-00203-002 | 019-Q-PED-00203-002 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK E019PR100 AXIS 9P TO 14P | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040530 | 019-Q-PED-00204-001 | 019-Q-PED-00204-001 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK E019PR100 AXIS 14P TO 18P | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040530 | 019-Q-PED-00204-002 | 019-Q-PED-00204-002 | PLAN ELEVATIONS AND DETAILS FOUNDATION PIPE RACK E019PR100 AXIS 14P TO 18P | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10004-001 | 019-C-GAD-10004-001 | GENERAL ARRANGEMENT 019C0004 PRODUCT STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10004-002 | 019-C-GAD-10004-002 | GENERAL ARRANGEMENT 019C0004 PRODUCT STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10004-003 | 019-C-GAD-10004-003 | GENERAL ARRANGEMENT 019C0004 PRODUCT STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10004-004 | 019-C-GAD-10004-004 | GENERAL ARRANGEMENT 019C0004 PRODUCT STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10005-001 | 019-C-GAD-10005-001 | GENERAL ARRANGEMENT 019C0005 PRODUCT FRACTIONATOR | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10005-002 | 019-C-GAD-10005-002 | GENERAL ARRANGEMENT 019C0005 PRODUCT FRACTIONATOR | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10005-003 | 019-C-GAD-10005-003 | GENERAL ARRANGEMENT 019C0005 PRODUCT FRACTIONATOR | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10007-001 | 019-C-GAD-10007-001 | GENERAL ARRANGEMENT 019C0007 LIGHT DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10007-002 | 019-C-GAD-10007-002 | GENERAL ARRANGEMENT 019C0007 LIGHT DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10007-003 | 019-C-GAD-10007-003 | GENERAL ARRANGEMENT 019C0007 LIGHT DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10008-001 | 019-C-GAD-10008-001 | GENERAL ARRANGEMENT 019C0008 HEAVY DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10008-002 | 019-C-GAD-10008-002 | GENERAL ARRANGEMENT 019C0008 HEAVY DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10008-003 | 019-C-GAD-10008-003 | GENERAL ARRANGEMENT 019C0008 HEAVY DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10009-001 | 019-C-GAD-10009-001 | GENERAL ARRANGEMENT 019C0009 NAPHTHA STABILIZER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10009-002 | 019-C-GAD-10009-002 | GENERAL ARRANGEMENT 019C0009 NAPHTHA STABILIZER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040531 | 019-C-GAD-10009-003 | 019-C-GAD-10009-003 | GENERAL ARRANGEMENT 019C0009 NAPHTHA STABILIZER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040532 | 011-C-GAD-10001-001 | 011-C-GAD-10001-001 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040532 | 011-C-GAD-10001-002 | 011-C-GAD-10001-002 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040532 | 011-C-GAD-10001-003 | 011-C-GAD-10001-003 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040532 | 011-C-GAD-10001-004 | 011-C-GAD-10001-004 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040532 | 011-C-GAD-10002-001 | 011-C-GAD-10002-001 | GENERAL ARRANGEMENT 011C0002 TAIL GAS ABSORBER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040532 | 011-C-GAD-10002-002 | 011-C-GAD-10002-002 | GENERAL ARRANGEMENT 011C0002 TAIL GAS ABSORBER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040532 | 011-C-GAD-10002-003 | 011-C-GAD-10002-003 | GENERAL ARRANGEMENT 011C0002 TAIL GAS ABSORBER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00004-001 | 019-C-GAD-00004-001 | GENERAL ARRANGEMENT 019V0004 1ST STAGE COLD HIGH PRESSURE SEPARATOR | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00004-002 | 019-C-GAD-00004-002 | GENERAL ARRANGEMENT 019V0004 1ST STAGE COLD HIGH PRESSURE SEPARATOR | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00004-003 | 019-C-GAD-00004-003 | GENERAL ARRANGEMENT 019V0004 1ST STAGE COLD HIGH PRESSURE SEPARATOR | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00006-001 | 019-C-GAD-00006-001 | GENERAL ARRANGEMENT 019V0006 RECYCLE GAS K.O. DRUM | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00006-002 | 019-C-GAD-00006-002 | GENERAL ARRANGEMENT 019V0006 RECYCLE GAS K.O. DRUM | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00006-003 | 019-C-GAD-00006-003 | GENERAL ARRANGEMENT 019V0006 RECYCLE GAS K.O. DRUM | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00009-001 | 019-C-GAD-00009-001 | GENERAL ARRANGEMENT 019V0009 2ND STAGE COLD HIGH PRESSURE SEPARATOR DRUM | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00009-002 | 019-C-GAD-00009-002 | GENERAL ARRANGEMENT 019V0009 2ND STAGE COLD HIGH PRESSURE SEPARATOR DRUM | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-00009-003 | 019-C-GAD-00009-003 | GENERAL ARRANGEMENT 019V0009 2ND STAGE COLD HIGH PRESSURE SEPARATOR DRUM | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-10003-001 | 019-C-GAD-10003-001 | GENERAL ARRANGEMENT 019C0003 HP H2S ABSORBER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-10003-002 | 019-C-GAD-10003-002 | GENERAL ARRANGEMENT 019C0003 HP H2S ABSORBER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-10003-003 | 019-C-GAD-10003-003 | GENERAL ARRANGEMENT 019C0003 HP H2S ABSORBER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040533 | 019-C-GAD-10003-004 | 019-C-GAD-10003-004 | GENERAL ARRANGEMENT 019C0003 HP H2S ABSORBER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10001-001 | 010-C-GAD-10001-001 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10001-002 | 010-C-GAD-10001-002 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10001-003 | 010-C-GAD-10001-003 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10001-004 | 010-C-GAD-10001-004 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10002-001 | 010-C-GAD-10002-001 | GENERAL ARRANGEMENT 010C0002 KERO STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10002-002 | 010-C-GAD-10002-002 | GENERAL ARRANGEMENT 010C0002 KERO STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10002-003 | 010-C-GAD-10002-003 | GENERAL ARRANGEMENT 010C0002 KERO STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10003-001 | 010-C-GAD-10003-001 | GENERAL ARRANGEMENT 010C0003 DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10003-002 | 010-C-GAD-10003-002 | GENERAL ARRANGEMENT 010C0003 DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040534 | 010-C-GAD-10003-003 | 010-C-GAD-10003-003 | GENERAL ARRANGEMENT 010C0003 DIESEL STRIPPER | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040535 | 010-S-PED-00820-001 | 010-S-PED-00820-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND OWS SYSTEM MANHOLE SCHEDULE | A | 2018-08-21 | FOR OCS REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040535 | 010-S-PED-00825-001 | 010-S-PED-00825-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND SYSTEM CSS MANHOLE SCHEDULE | A | 2018-08-21 | FOR OCS REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040536 | 085-S-DAT-00014-001 | 085-S-DAT-00014-001 | DUTY SPECIFICATION FOR MAIN COOLING WATER SIDE STREAM FILTERS PACKAGE 085U0002 | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040536 | 085-S-DAT-00015-001 | 085-S-DAT-00015-001 | DUTY SPECIFICATION FOR SECONDARY COOLING WATER SIDE STREAM FILTERS PACKAGE 085U0003 | 0 | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-040537 | 019-C-GAD-00034-001 | 019-C-GAD-00034-001 | GENERAL ARRANGEMENT 019V0034 FLARE KO DRUM | B | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040537 | 019-C-GAD-00034-002 | 019-C-GAD-00034-002 | GENERAL ARRANGEMENT 019V0034 FLARE KO DRUM | B | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040537 | 019-C-GAD-00034-003 | 019-C-GAD-00034-003 | GENERAL ARRANGEMENT 019V0034 FLARE KO DRUM | B | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040537 | 019-C-GAD-00034-004 | 019-C-GAD-00034-004 | GENERAL ARRANGEMENT 019V0034 FLARE KO DRUM | B | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040538 | 010-C-GAD-00008-001 | 010-C-GAD-00008-001 | GENERAL ARRANGEMENT 010V0010 COMPRESSOR KO DRUM | B | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040538 | 010-C-GAD-00008-002 | 010-C-GAD-00008-002 | GENERAL ARRANGEMENT 010V0010 COMPRESSOR KO DRUM | B | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040538 | 010-C-GAD-00008-003 | 010-C-GAD-00008-003 | GENERAL ARRANGEMENT 010V0010 COMPRESSOR KO DRUM | B | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040538 | 010-C-GAD-00015-001 | 010-C-GAD-00015-001 | GENERAL ARRANGEMENT 010V0017 FLARE KO DRUM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040538 | 010-C-GAD-00015-002 | 010-C-GAD-00015-002 | GENERAL ARRANGEMENT 010V0017 FLARE KO DRUM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040538 | 010-C-GAD-00015-003 | 010-C-GAD-00015-003 | GENERAL ARRANGEMENT 010V0017 FLARE KO DRUM | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040539 | 012-M-GAD-00420-001 | 012-M-GAD-00420-001 | GENERAL ARRANGEMENT STEEL STRUCTURE 012STR500 | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040539 | 012-M-GAD-00601-001 | 012-M-GAD-00601-001 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040539 | 012-M-GAD-00601-002 | 012-M-GAD-00601-002 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040539 | 012-M-GAD-00601-003 | 012-M-GAD-00601-003 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040539 | 012-M-GAD-00601-004 | 012-M-GAD-00601-004 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040539 | 012-M-GAD-00601-005 | 012-M-GAD-00601-005 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040539 | 012-M-GAD-00601-006 | 012-M-GAD-00601-006 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040539 | 012-M-GAD-00601-007 | 012-M-GAD-00601-007 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK 012PR100 AXIS 1P TO 5P | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040540 | 017-S-PED-00820-001 | 017-S-PED-00820-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND OWS SYSTEM MANHOLE SCHEDULE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040540 | 017-S-PED-00825-001 | 017-S-PED-00825-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND SYSTEM CSS MANHOLE SCHEDULE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040541 | 019-A-HZR-00001-001 | 019-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE OUT REPORT (DURING EPC) | 0 | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040542 | 050-S-PED-55820-001 | 050-S-PED-55820-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND OWS SYSTEM MANHOLE SCHEDULE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040542 | 050-S-PED-55825-001 | 050-S-PED-55825-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND SYSTEM CSS MANHOLE SCHEDULE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040543 | 085-S-PED-00820-001 | 085-S-PED-00820-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND OWS SYSTEM MANHOLE SCHEDULE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040543 | 085-S-PED-00825-001 | 085-S-PED-00825-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND SYSTEM CSS MANHOLE SCHEDULE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040544 | 012-S-PED-00820-001 | 012-S-PED-00820-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND OWS SYSTEM MANHOLE SCHEDULE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040544 | 012-S-PED-00825-001 | 012-S-PED-00825-001 | PLAN ELEVATIONS AND DETAILS UNDERGROUND SYSTEM CSS MANHOLE SCHEDULE | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040545 | 019-Q-PED-00155-001 | 019-Q-PED-00155-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR VERTICAL VESSEL 019C0010 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040545 | 019-Q-PED-00158-001 | 019-Q-PED-00158-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR VERTICAL VESSEL 019V0008 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040546 | 011-C-DAT-00001-001 | 011-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR VACUUM HOT WELL 011V0001 | 0 | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10001-001 | 012-C-GAD-10001-001 | GENERAL ARRANGEMENT 012C0001 ABSORBER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10001-002 | 012-C-GAD-10001-002 | GENERAL ARRANGEMENT 012C0001 ABSORBER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10001-003 | 012-C-GAD-10001-003 | GENERAL ARRANGEMENT 012C0001 ABSORBER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10002-001 | 012-C-GAD-10002-001 | GENERAL ARRANGEMENT 012C0002 DEETHANIZER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10002-002 | 012-C-GAD-10002-002 | GENERAL ARRANGEMENT 012C0002 DEETHANIZER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10002-003 | 012-C-GAD-10002-003 | GENERAL ARRANGEMENT 012C0002 DEETHANIZER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10003-001 | 012-C-GAD-10003-001 | GENERAL ARRANGEMENT 012C0003 STABILIZER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10003-002 | 012-C-GAD-10003-002 | GENERAL ARRANGEMENT 012C0003 STABILIZER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10003-003 | 012-C-GAD-10003-003 | GENERAL ARRANGEMENT 012C0003 STABILIZER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10004-001 | 012-C-GAD-10004-001 | GENERAL ARRANGEMENT 012C0004 NAPHTHA SPLITTER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10004-002 | 012-C-GAD-10004-002 | GENERAL ARRANGEMENT 012C0004 NAPHTHA SPLITTER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10004-003 | 012-C-GAD-10004-003 | GENERAL ARRANGEMENT 012C0004 NAPHTHA SPLITTER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10007-001 | 012-C-GAD-10007-001 | GENERAL ARRANGEMENT 012C0007 C3/C4 SPLITTER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10007-002 | 012-C-GAD-10007-002 | GENERAL ARRANGEMENT 012C0007 C3/C4 SPLITTER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040547 | 012-C-GAD-10007-003 | 012-C-GAD-10007-003 | GENERAL ARRANGEMENT 012C0007 C3/C4 SPLITTER | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040548 | 019-K-DAT-00010-001 | 019-K-DAT-00010-001 | BRIDGE CRANE DATA SHEET 019OC0002 COMPRESSOR SHELTER BRIDGE CRANE 019K0001 | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040548 | 019-K-DAT-00011-001 | 019-K-DAT-00011-001 | BRIDGE CRANE DATA SHEET 019OC0001 COMPRESSOR SHELTER BRIDGE CRANE 019K0002/0003/0004 | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040549 | 010-K-DAT-00004-001 | 010-K-DAT-00004-001 | BRIDGE CRANE DATA SHEET FOR 010C0001 COMPRESSOR SHELTER BRIDGE CRANE FOR 010K0001A/B | B | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040550 | 085-P-CRD-00001-001 | 085-P-CRD-00001-001 | CABLE TRENCH LAYOUT COOLING WATER TOWER | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040551 | 050-P-CRD-55001-001 | 050-P-CRD-55001-001 | CABLE TRENCH LAYOUT REFINERY TANK FARM | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040551 | 050-P-CRD-55001-002 | 050-P-CRD-55001-002 | CABLE TRENCH LAYOUT REFINERY TANK FARM | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040552 | 019-Q-PED-00157-001 | 019-Q-PED-00157-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR VERTICAL VESSEL 019V0003 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040553 | 019-E-DAT-00001-001 | 019-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0006 A/B 1ST STAGE REACTOR EFFLUENT / FRESH FEED EXCHANGER | C | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040553 | 019-E-DAT-00002-001 | 019-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0004 A/B 1ST STAGE REACTOR EFFLUENT / EFFLUENT EXCHANGER | C | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040553 | 019-E-DAT-00003-001 | 019-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0005 A/B 1ST STAGE REACTOR EFFLUENT / FRACTIONATOR FEED EXCHANGER | C | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040553 | 019-E-DAT-00004-001 | 019-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0007 A/B 1ST STAGE HHPS VAPOR / RECYCLE GAS EXCHANGER | C | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040553 | 019-E-DAT-00005-001 | 019-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0011 A/B 2ND STAGE HHPS VAPOR /CLPS LIQUID EXCHANGER | C | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040553 | 019-E-DAT-00006-001 | 019-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0009 A/B 2ND STAGE REACTOR FEED /EFFLUENT EXCHANGER | C | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040553 | 019-E-DAT-00007-001 | 019-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0010 2ND STAGE REACTOR EFFLUENT / RECYCLE GAS EXCHANGER | C | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040554 | 019-J-INX-00001-001 | 019-J-INX-00001-001 | INSTRUMENT INDEX REPORT 019 N 2 HYDROCRACKING UNIT 2HCU | A | 2018-08-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-07 |  |  | CLASS 1
CON-BMP-TRA-040555 | 011-E-GAD-00001-001 | 011-E-GAD-00001-001 | GENERAL ARRANGEMENT 011E0006 A/B/C/D VACCUM RESIDUE STEAM GENERATOR | C | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-040556 | 085-A-PFD-00001-001 | 085-A-PFD-00001-001 | PROCESS FLOW DIAGRAM MAIN CALCITE BEDS PACKAGE | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-002 | 085-A-PFD-00001-002 | PROCESS FLOW DIAGRAM SECONDARY CALCITE BEDS PACKAGE | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-003 | 085-A-PFD-00001-003 | PROCESS FLOW DIAGRAM MAIN COOLING WATER SYSTEM | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-004 | 085-A-PFD-00001-004 | PROCESS FLOW DIAGRAM SECONDARY COOLING WATER SYSTEM | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-005 | 085-A-PFD-00001-005 | PROCESS FLOW DIAGRAM SECONDARY COOLING WATER SYSTEM | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-006 | 085-A-PFD-00001-006 | PROCESS FLOW DIAGRAM CW CHEMICAL TREATMENT | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-007 | 085-A-PFD-00001-007 | PROCESS FLOW DIAGRAM MAIN COOLING WATER DISTRIBUTION | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-008 | 085-A-PFD-00001-008 | PROCESS FLOW DIAGRAM SECONDARY COOLING WATER DISTRIBUTION | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-009 | 085-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-010 | 085-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-011 | 085-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-012 | 085-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040556 | 085-A-PFD-00001-013 | 085-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | 0 | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040557 | 372-P-CRD-57001-001 | 372-P-CRD-57001-001 | CABLE TRENCH LAYOUT BOILED FEED WATER AND CONDEN DISTR | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040558 | 934-P-CRD-00001-001 | 934-P-CRD-00001-001 | CABLE TRENCH LAYOUT FEED BOOSTER PUMP HOUSE | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040559 | 010-J-INX-00001-001 | 010-J-INX-00001-001 | INSTRUMENT INDEX REPORT 010 - NO 7 CRUDE DISTILLATION UNIT 7CDU | A | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-040560 | 011-E-DAT-00001-001 | 011-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 011E0006 A/B/C/D VACUUM RESIDUE STEAM GENERATOR | B | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040561 | 085-S-DAT-00012-001 | 085-S-DAT-00012-001 | DUTY SPECIFICATION FOR 085U0001 MAIN CALCITE BEDS PACKAGE | B | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040561 | 085-S-DAT-00013-001 | 085-S-DAT-00013-001 | DUTY SPECIFICATION FOR 085U0010 SECONDARY CALCITE BEDS PACKAGE | B | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040562 | 012-C-GAD-10005-001 | 012-C-GAD-10005-001 | GENERAL ARRANGEMENT 012C0005 OFFGAS AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040562 | 012-C-GAD-10005-002 | 012-C-GAD-10005-002 | GENERAL ARRANGEMENT 012C0005 OFFGAS AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040562 | 012-C-GAD-10005-003 | 012-C-GAD-10005-003 | GENERAL ARRANGEMENT 012C0005 OFFGAS AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040562 | 012-C-GAD-10006-001 | 012-C-GAD-10006-001 | GENERAL ARRANGEMENT 012C0006 LPG AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040562 | 012-C-GAD-10006-002 | 012-C-GAD-10006-002 | GENERAL ARRANGEMENT 012C0006 LPG AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040562 | 012-C-GAD-10006-003 | 012-C-GAD-10006-003 | GENERAL ARRANGEMENT 012C0006 LPG AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10001-001 | 017-C-GAD-10001-001 | GENERAL ARRANGEMENT 017C0001 ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10001-002 | 017-C-GAD-10001-002 | GENERAL ARRANGEMENT 017C0001 ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10001-003 | 017-C-GAD-10001-003 | GENERAL ARRANGEMENT 017C0001 ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10002-001 | 017-C-GAD-10002-001 | GENERAL ARRANGEMENT 017C0002 DEETHANIZER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10002-002 | 017-C-GAD-10002-002 | GENERAL ARRANGEMENT 017C0002 DEETHANIZER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10002-003 | 017-C-GAD-10002-003 | GENERAL ARRANGEMENT 017C0002 DEETHANIZER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10003-001 | 017-C-GAD-10003-001 | GENERAL ARRANGEMENT 017C0003 STABILIZER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10003-002 | 017-C-GAD-10003-002 | GENERAL ARRANGEMENT 017C0003 STABILIZER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10003-003 | 017-C-GAD-10003-003 | GENERAL ARRANGEMENT 017C0003 STABILIZER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10004-001 | 017-C-GAD-10004-001 | GENERAL ARRANGEMENT 017C0004 NAPHTA SPLITTER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10004-002 | 017-C-GAD-10004-002 | GENERAL ARRANGEMENT 017C0004 NAPHTA SPLITTER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10004-003 | 017-C-GAD-10004-003 | GENERAL ARRANGEMENT 017C0004 NAPHTA SPLITTER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10005-001 | 017-C-GAD-10005-001 | GENERAL ARRANGEMENT 017C0005 OFFGAS AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10005-002 | 017-C-GAD-10005-002 | GENERAL ARRANGEMENT 017C0005 OFFGAS AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040563 | 017-C-GAD-10005-003 | 017-C-GAD-10005-003 | GENERAL ARRANGEMENT 017C0005 OFFGAS AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040564 | 017-C-GAD-10006-001 | 017-C-GAD-10006-001 | GENERAL ARRANGEMENT 017C0006 LPG AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040564 | 017-C-GAD-10006-002 | 017-C-GAD-10006-002 | GENERAL ARRANGEMENT 017C0006 LPG AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040564 | 017-C-GAD-10006-003 | 017-C-GAD-10006-003 | GENERAL ARRANGEMENT 017C0006 LPG AMINE ABSORBER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040564 | 017-C-GAD-10007-001 | 017-C-GAD-10007-001 | GENERAL ARRANGEMENT 017C0007 C3/C4 SPLITTER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040564 | 017-C-GAD-10007-002 | 017-C-GAD-10007-002 | GENERAL ARRANGEMENT 017C0007 C3/C4 SPLITTER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040564 | 017-C-GAD-10007-003 | 017-C-GAD-10007-003 | GENERAL ARRANGEMENT 017C0007 C3/C4 SPLITTER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040565 | 011-J-PRD-00001-001 | 011-J-PRD-00001-001 | PROCESS CONTROL NARRATIVES - 011 - NO 7 VACUUM DISTILLATION UNIT 7VDU | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040566 | MOC-BMM-MOM-000018 | 000-A-MOM-70011-001 | 010/011¿7CDU-7VDU IBD P&IDS JOINT REVIEW | 0 | 2018-08-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040566 | MOC-BMM-MOM-000031 | 000-A-MOM-70010-001 | 010/011-7CDU-7VDU IBD P&IDS JOINT REVIEW FINAL CONSOLIDATION MEETING | 1 | 2018-08-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040566 | MOC-BMM-MOM-000033 | 000-A-MOM-70009-001 | 012/017-SGP UNIT IBD P&IDS JOINT REVIEW | 0 | 2018-08-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040566 | MOC-BMM-MOM-000037 | 000-A-MOM-70008-001 | 012/017-SGPIBD P&IDS JOINT REVIEW FINAL CONSOLIDATION MEETING | 0 | 2018-08-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040567 | 019-J-MTX-00001-001 | 019-J-MTX-00001-001 | CAUSE AND EFFECT MATRIX 019 NO 2 HYDROCRACKING UNIT 2HCU | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040568 | 019-J-PRD-00002-001 | 019-J-PRD-00002-001 | INTERLOCK PROCESS DESCRIPTION 019 NO 2 HYDROCRACKING UNIT 2HCU | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040569 | 010-J-MTX-00001-001 | 010-J-MTX-00001-001 | CAUSE AND EFFECT MATRIX 010 NO 7 CRUDE DISTILLATION UNIT 7CDU | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040570 | 010-J-PRD-00002-001 | 010-J-PRD-00002-001 | INTERLOCK PROCESS DESCRIPTION 010 NO 7 CRUDE DISTILLATION UNIT 7CDU | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040571 | 011-J-MTX-00001-001 | 011-J-MTX-00001-001 | CAUSE AND EFFECT MATRIX 011 NO 7 VACUUM DISTILLATION UNIT 7VDU | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040572 | 011-J-PRD-00002-001 | 011-J-PRD-00002-001 | INTERLOCK PROCESS DESCRIPTION 011 NO 7 VACUUM DISTILLATION UNIT 7VDU | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040573 | MOC-BMM-MOM-000022 | 000-A-MOM-70013-001 | P&IDS JOINT REVIEW UNIT 085 ¿ COOLING WATER TOWER - CWT | 1 | 2018-08-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040573 | MOC-BMM-MOM-000036 | 000-A-MOM-70012-001 | REVISION INDEX FOR NEW PIDS | 1 | 2018-08-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040573 | MOC-BMM-MOM-000039 | 000-A-MOM-70014-001 | REVISION OF REQUIREMENTS TO CENTRIFUGAL PUMPS ACCORDING FEED & PROJECT SPECIFICATION | 0 | 2018-08-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040574 | 019-Q-PED-00153-001 | 019-Q-PED-00153-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR VERTICAL VESSEL 019C0006 AND 019C0007 | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040575 | 019-M-GAD-00611-001 | 019-M-GAD-00611-001 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK E019PR400 AXIS AP TO DP | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040575 | 019-M-GAD-00611-002 | 019-M-GAD-00611-002 | GENERAL ARRANGEMENT STEEL STRUCTURE PIPE RACK E019PR400 AXIS AP TO DP | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-040576 | 019-C-DAT-00004-001 | 019-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE COLD HIGH PRESSURE SEPARATOR 019V0004 | 0 | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040576 | 019-C-DAT-00006-001 | 019-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECYCLE GAS KO DRUM 019V0006 | 0 | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040576 | 019-C-DAT-00009-001 | 019-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAEG COLD HIGH PRESSURE SEPARATOR 019V0009 | 0 | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040576 | 019-C-DAT-10003-001 | 019-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HP H2S ABSORBER 019C0003 | 0 | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040576 | 019-C-DAT-10005-001 | 019-C-DAT-10005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT FRACTIONATOR 019C0005 | 0 | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040576 | 019-C-DAT-10008-001 | 019-C-DAT-10008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HEAVY DIESEL STRIPPER 019C0008 | 0 | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040576 | 019-C-DAT-10009-001 | 019-C-DAT-10009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER 019C0009 | 0 | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00022-001 | 012-C-GAD-00022-001 | GENERAL ARRANGEMENT 012V0022 LIGHT NAPHTHA CAUSTIC SETTLER | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00022-002 | 012-C-GAD-00022-002 | GENERAL ARRANGEMENT 012V0022 LIGHT NAPHTHA CAUSTIC SETTLER | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00022-003 | 012-C-GAD-00022-003 | GENERAL ARRANGEMENT 012V0022 LIGHT NAPHTHA CAUSTIC SETTLER | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00023-001 | 012-C-GAD-00023-001 | GENERAL ARRANGEMENT 012V0023 RECOVERED PROCESS SLOP OIL SUMP | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00023-002 | 012-C-GAD-00023-002 | GENERAL ARRANGEMENT 012V0023 RECOVERED PROCESS SLOP OIL SUMP | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00023-003 | 012-C-GAD-00023-003 | GENERAL ARRANGEMENT 012V0023 RECOVERED PROCESS SLOP OIL SUMP | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00025-001 | 012-C-GAD-00025-001 | GENERAL ARRANGEMENT 012V0025 FLARE KO DRUM | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00025-002 | 012-C-GAD-00025-002 | GENERAL ARRANGEMENT 012V0025 FLARE KO DRUM | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040577 | 012-C-GAD-00025-003 | 012-C-GAD-00025-003 | GENERAL ARRANGEMENT 012V0025 FLARE KO DRUM | B | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-040578 | 010-J-PRD-00001-001 | 010-J-PRD-00001-001 | PROCESS CONTROL NARRATIVES - 010 - NO 7 CRUDE DISTILLATION UNIT 7CDU | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040579 | 076551C-000M-TBT-0411-002 | 000-C-TBE-70004-001 | TECHNICAL BID EVALUATIONS FOR SEPARATORS CR-MO | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-040580 | 076551C-000M-TBT-4141-001 | 000-S-TBE-70009-001 | TECHNICAL BID EVALUATION FOR DESALTER PACKAGE | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-040581 | 012-C-DAT-00022-001 | 012-C-DAT-00022-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 012V0022 LIGHT NAPHTHA CAUSTIC SETTLER | B | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-040582 | 085-J-DAT-00002-001 | 085-J-DAT-00002-001 | INSTRUMENT DATA SHEET FOR ULTRASONIC FLOWMETER COOLING WATER TOWER CWT | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040583 | 019-Q-PED-00211-001 | 019-Q-PED-00211-001 | PLAN ELEVATION AND DETAILS FOUNDATION PIPERACK 019PR400 AXIS AP TO DP | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040583 | 019-Q-PED-00211-002 | 019-Q-PED-00211-002 | PLAN ELEVATION AND DETAILS FOUNDATION PIPERACK 019PR400 AXIS AP TO DP | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040584 | 012-Q-PED-00161-001 | 012-Q-PED-00161-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR HORIZONTAL VESSEL 012V0022 | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040584 | 012-Q-PED-00162-001 | 012-Q-PED-00162-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR HORIZONTAL VESSEL 012V0025 | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040585 | 076551C-000M-IDL-4065-001 | 000-K-IDL-70008-001 | DEVIATION LIST FOR BRIDGE CRANE | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040585 | 076551C-000M-ITP-4065-001 | 000-K-ITP-70008-001 | INSPECTION AND TEST PLAN FOR BRIDGE CRANE | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040585 | 076551C-000M-MR-4065-001 | 000-K-MRQ-70008-001 | MATERIAL REQUISITION FOR BRIDGE CRANE | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040585 | 076551C-000M-SP-4065-001 | 000-K-GRD-70008-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR BRIDGE CRANE | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040585 | 076551C-000M-SR-4065-001 | 000-K-SOW-70008-001 | SCOPE OF SUPPLY FOR BRIDGE CRANE | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-040586 | 012-A-MSD-00001-001 | 012-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - ABSORBER FEED GAS COMPRESSOR/PSA PURGE GAS COMPRESSOR/LIQUID FE | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-002 | 012-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - NORMAL CASE DEETHANIZER | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-003 | 012-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - NORMAL CASE NAPHTHA SPLITTER | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-004 | 012-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - LPG/AMINE ABSORBER | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-005 | 012-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - C3/C4 SPLITTER | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-006 | 012-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - NORMAL CASE DEETHANIZER - EQUIPMENT TABLE | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-007 | 012-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A - NORMAL CASE NAPHTHA SPLITTER - EQUIPMENT | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-008 | 012-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM BMP UNITS CONDENSATE FLASH DRUM | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-009 | 012-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM SATURATED GAS PLANT TRAIN A LPG/AMINE ABSORBER-EQUIPMENT TABLE | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040586 | 012-A-MSD-00001-010 | 012-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM GENERAL NOTES | A | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040587 | 019-M-GAD-00606-001 | 019-M-GAD-00606-001 | GENERAL ARRANGEMENT DRAWING STEEL STRUCTURE PIPE RACK 019PR200 AXIS AP TO EP | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040587 | 019-M-GAD-00606-002 | 019-M-GAD-00606-002 | GENERAL ARRANGEMENT DRAWING STEEL STRUCTURE PIPE RACK 019PR200 AXIS AP TO EP | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040587 | 019-M-GAD-00606-003 | 019-M-GAD-00606-003 | GENERAL ARRANGEMENT DRAWING STEEL STRUCTURE PIPE RACK 019PR200 AXIS AP TO EP | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040587 | 019-M-GAD-00606-004 | 019-M-GAD-00606-004 | GENERAL ARRANGEMENT DRAWING STEEL STRUCTURE PIPE RACK 019PR200 AXIS AP TO EP | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040588 | 012-Q-PED-00154-001 | 012-Q-PED-00154-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR VERTICAL VESSEL 012C0004 | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040588 | 012-Q-PED-00156-001 | 012-Q-PED-00156-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR VERTICAL VESSEL 012C0006 | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040589 | 012-A-BOD-00001-001 | 012-A-BOD-00001-001 | UNIT BASIS OF DESIGN FOR 012 - NO 1 SATURATED GAS PLANT | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 1
CON-BMP-TRA-040590 | 012-A-RPT-00001-001 | 012-A-RPT-00001-001 | 012 - NO 1 SATURATED GAS PLANT 1SGP UNIT SIMULATION REPORT (EX 012-A-STS-00001-001) | B | 2018-08-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040591 | 019-Q-PED-00156-001 | 019-Q-PED-00156-001 | PLAN ELEVATION AND DETAILS FOUNDATION FOR VERTICAL VESSELS 019V0002 AND 019V0007 | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-040591 | 019-Q-PED-00156-003 | 019-Q-PED-00156-003 | PLAN ELEVATION AND DETAILS FOUNDATION FOR VERTICAL VESSELS 019V0002 AND 019V0007 | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-17 |  |  | CLASS 2
CON-BMP-TRA-070001 | 076551C-000S-DL-0113-001 | 000-F-IDL-80001-001 | DEVIATION LIST FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | 076551C-000S-ITP-0113-001 | 000-F-ITP-80001-001 | INSPECTION AND TEST PLAN FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | 076551C-000S-MR-0113-001 | 000-F-MRQ-80001-001 | MATERIAL REQUISITION FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | 076551C-000S-SP-0113-001 | 000-F-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | 076551C-000S-SR-0113-001 | 000-F-SOW-80001-001 | SCOPE OF SUPPLY FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09800007-001 | 098-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 098F9800 REFORMING FURNACE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09800008-001 | 098-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 098F9804 STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09800009-001 | 098-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 098E9801 PROCESS GAS BOILER | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09800010-001 | 098-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 098F9801 REFORMING FURNACE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09900007-001 | 099-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 099F9900 REFORMING FURNACE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09900008-001 | 099-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 099F9904 STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09900009-001 | 099-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 099E9901 PROCESS GAS BOILER | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09900010-001 | 099-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 099F9901 REFORMING FURNACE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-DL-0119-004 | 000-F-IDL-80002-001 | DEVIATION LIST FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-ITP-0119-004 | 000-F-ITP-80002-001 | INSPECTION AND TEST PLAN FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-MR-0119-004 | 000-F-MRQ-80002-001 | MATERIAL REQUISITION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-SP-0119-004 | 000-F-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-SR-0119-004 | 000-F-SOW-80002-001 | SCOPE OF SUPPLY FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04100007-001 | 041-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 041F4101 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04100008-001 | 041-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 041V4103 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04100009-001 | 041-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 041E4101 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04100010-001 | 041-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 041X4101 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04200007-001 | 042-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 041F4201 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04200008-001 | 042-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 042V4203 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04200009-001 | 042-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 042E4201 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04200010-001 | 042-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 042X4201 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04300007-001 | 043-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 043F4301 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04300008-001 | 043-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 043V4303 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04300009-001 | 043-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 043E4301 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04300010-001 | 043-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 043X4301 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-09 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-DL-0140-001 | 000-F-IDL-80003-001 | DEVIATION LIST FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-ITP-0140-001 | 000-F-ITP-80003-001 | INSPECTION AND TEST PLAN FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-MR-0140-001 | 000-F-MRQ-80003-001 | MATERIAL REQUISITION FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-SP-0140-001 | 000-F-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-SR-0140-001 | 000-F-SOW-80003-001 | SCOPE OF SUPPLY FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | SO6001-EJ1E-TDS-04400007-001 | 044-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 044U4401 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | SO6001-EJ1E-TDS-04500007-001 | 045-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 045U4501 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-DL-0150-001 | 000-F-IDL-80004-001 | DEVIATION LIST FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-ITP-0150-001 | 000-F-ITP-80004-001 | INSPECTION AND TEST PLAN FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-MR-0150-001 | 000-F-MRQ-80004-001 | MATERIAL REQUISITION FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-SP-0150-001 | 000-F-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-SR-0150-001 | 000-F-SOW-80004-001 | SCOPE OF SUPPLY FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | SO6001-EJ1E-TDS-31000001-001 | 310-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 310F0001 AUXILIARY STEAM BOILER | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | SO6001-EJ1E-TDS-31100001-001 | 311-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 311F0001 AUXILIARY STEAM BOILER | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-DL-0215-001 | 000-S-IDL-80002-001 | INSPECTION AND TEST PLAN FOR DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-ITP-0215-001 | 000-S-ITP-80002-001 | INSPECTION AND TEST PLAN FOR DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-MR-0215-001 | 000-S-MRQ-80002-001 | MATERIAL REQUISITION FOR MULTI EFFECT DESALINATION PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-SP-0215-001 | 000-S-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR MULTI EFFECT DESALINATION PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-SR-0215-001 | 000-S-SOW-80002-001 | SCOPE OF SUPPLY FOR MULTI EFFECT DESALINATION PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | SO6001-EJ2E-TDS-35600001-001 | 356-S-DAT-80002-001 | DUTY SPECIFICATION FOR 356U0001 NO6 DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | SO6001-EJ2E-TDS-35700001-001 | 357-S-DAT-80002-001 | DUTY SPECIFICATION FOR 356U0001 NO7 DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | SO6001-EJ2E-TDS-35800001-001 | 358-S-DAT-80002-001 | DUTY SPECIFICATION FOR 356U0001 NO8 DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3 - REVIEWED WITH COMMENTS | 2018-04-10 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-DL-4352-001 | 000-S-IDL-80010-001 | LIST OF DEVIATION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-ITP-4352-001 | 000-S-ITP-80010-001 | INSPECTION AND TEST PLAN FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-MR-4352-001 | 000-S-MRQ-80010-001 | MATERIAL REQUISITION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-SP-4352-001 | 000-S-GRD-80010-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-SR-4352-001 | 000-S-SOW-80010-001 | SCOPE OF SUPPLY FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | SO6001-EJ2E-TDS-09400001-001 | 094-S-DAT-00001-001 | DUTY SPECIFICATION FOR SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-DL-4010-001 | 000-S-IDL-80003-001 | DEVIATION LIST FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-ITP-4010-001 | 000-S-ITP-80003-001 | INSPECTION AND TEST PLAN FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-MR-4010-001 | 000-S-MRQ-80003-001 | MATERIAL REQUISITION FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-SP-4010-001 | 000-S-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-SR-4010-001 | 000-S-SOW-80003-001 | SCOPE OF SUPPLY FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | SO6001-EJ2E-TDS-09400002-001 | 094-S-DAT-00002-001 | DUTY SPECIFICATION FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3 - REVIEWED WITH COMMENTS | 2018-04-17 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-DL-0710-002 | 000-E-IDL-80007-001 | DEVIATION LIST FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-ITP-0710-002 | 000-E-ITP-80007-001 | INSPECTION AND TEST PLAN FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-MR-0710-002 | 000-E-MRQ-80007-001 | MATERIAL REQUISITION FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-SP-0710-002 | 000-E-GRD-80007-001 | PARTICULAR TECHNICAL SPEIFICATION FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-SR-0710-002 | 000-E-SOW-80007-001 | SCOPE OF SUPPLY FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-03600001-001 | 036-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 036E3611 REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-03600002-001 | 036-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 036E3612 AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-03700001-001 | 037-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 037E3711 REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-03700002-001 | 037-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 037E3712 AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04100001-001 | 041-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 041E4111 STEAM CONDENSER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04200001-001 | 042-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 042E4211 STEAM CONDENSER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04300001-001 | 043-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 043E4311 STEAM CONDENSER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400001-001 | 044-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4410 CONDENSATE AIR COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400002-001 | 044-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4411 QUENCH WATER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400003-001 | 044-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET 044E4412 AMINE REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400004-001 | 044-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4413 LEAN AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400005-001 | 044-E-DAT-00005-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4414 60# STEAM BLOWDOWN DRUM CONDENSER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400006-001 | 044-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4415 STEAM CONDENSER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04500001-001 | 045-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4511 QUENCH WATER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04500002-001 | 045-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4512 AMINE REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04500003-001 | 045-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4513 LEAN AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04600001-001 | 046-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 046E4611 STRIPPER PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04600002-001 | 046-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 046E4612 STRIPPED WATER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04700001-001 | 047-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 047E4711 STRIPPER PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04700002-001 | 047-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 047E4712 STRIPPED WATER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04800001-001 | 048-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4811 AMINE REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04800002-001 | 048-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4812 LEAN AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04800003-001 | 048-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4813 ARU STEAM CONDENSER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04800004-001 | 048-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4814 ARU CONDENSATE AIR COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04900001-001 | 049-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 049E4911 AMINE REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04900002-001 | 049-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 049E4912 LEAN AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-08800001-001 | 088-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 088E1931 KERO PRODUCT AIR COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-09800001-001 | 098-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 098E9805 PROCESS GAS COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-09900001-001 | 099-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 099E9905 PROCESS GAS COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-37155001-001 | 371-E-DAT-55001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 371E0002 60 PSIG EXCESS STEAM CONDENSATE AIR COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-24 | CLASS 1
CON-BMP-TRA-070009 | SO6001-ES0B-PHL-35600001-001 | 356-A-BOD-00001-001 | BASIS OF DESIGN 6,7,8 DESAL (UNIT 356/357/358) N¿ 6,7,8 DESALINATION PLANTS | A | 2018-04-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-070010 | SO6001-ES0B-PHL-09400001-001 | 094-A-BOD-00001-001 | BASIS OF DESIGN 2SHF (UNIT 094) SULPHUR HANDLING FACILITY | A | 2018-04-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3 - REVIEWED WITH COMMENTS | 2018-04-23 | CLASS 1
CON-BMP-TRA-070011 | 076551C-000S-DL-0411-001 | 000-C-IDL-80004-001 | DEVIATION LIST FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | 076551C-000S-ITP-0411-001 | 000-C-ITP-80004-001 | INSPECTION AND TEST PLAN FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | 076551C-000S-MR-0411-001 | 000-C-MRQ-80004-001 | MATERIAL REQUISITION FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | 076551C-000S-SP-0411-001 | 000-C-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | 076551C-000S-SR-0411-001 | 000-C-SOW-80004-001 | SCOPE OF SUPPLY FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-01600001-001-001 | 016-C-GAD-00001-001 | 016C1640 MEROX REACTOR TRAIN C MISC-P1052-B2-LH | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04100002-001-001 | 041-C-GAD-00001-001 | 041C4101 NO.1 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04100003-001-001 | 041-C-GAD-00002-001 | 041C4102 NO.2 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04200002-001-001 | 042-C-GAD-00001-001 | 042C4201 NO.1 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04200003-001-001 | 042-C-GAD-00002-001 | 042C4202 NO.2 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04300002-001-001 | 043-C-GAD-00001-001 | 043C4301 NO.1 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04300003-001-001 | 043-C-GAD-00002-001 | 043C4302 NO.2 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04400008-001-001 | 044-C-GAD-00001-001 | 044C4401 TAIL GAS REACTOR | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04500008-001-001 | 045-C-GAD-00001-001 | 045C4501 TAIL GAS REACTOR | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09800002-001-001 | 098-C-GAD-00001-001 | 098C9801 ZINC OXIDE DRUM | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09800003-001-001 | 098-C-GAD-00002-001 | 098C9802 ZINC OXIDE DRUM | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09800004-001-001 | 098-C-GAD-00003-001 | 098C9803 HIGH TEMPERATURE SHIFT REACTOR | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09900002-001-001 | 099-C-GAD-00001-001 | 099C9901 ZINC OXIDE DRUM | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09900003-001-001 | 099-C-GAD-00002-001 | 099C9902 ZINC OXIDE DRUM | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09900004-001-001 | 099-C-GAD-00003-001 | 099C9903 HIGH TEMPERATURE SHIFT REACTOR | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4 - NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-070012 | 076551C-000S-DL-4112-001 | 000-S-IDL-80008-001 | DEVIATION LIST FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | 076551C-000S-ITP-4112-001 | 000-S-ITP-80008-001 | INSPECTION AND TEST PLAN FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | 076551C-000S-MR-4112-001 | 000-S-MRQ-80008-001 | MATERIAL REQUISITION FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | 076551C-000S-SP-4112-001 | 000-S-GRD-80008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | 076551C-000S-SR-4112-001 | 000-S-SOW-80008-001 | SCOPE OF SUPPLY FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | SO6001-EJ2E-TDS-08300001-001 | 083-S-DAT-00001-001 | DUTY SPECIFICATION FOR 083U0001 NITROGEN PLANT | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3 - REVIEWED WITH COMMENTS | 2018-04-25 | CLASS 1
CON-BMP-TRA-070013 | SO6001-ES0B-PHL-00500001-001 | 005-A-BOD-00001-001 | BASIS OF DESIGN RLPG (UNIT 005) LPG C3-C4 STORAGE FACILITY AT REFINERY | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 1
CON-BMP-TRA-070014 | SO6001-ES0B-PHL-09800001-001 | 098-A-BOD-00001-001 | BASIS OF DESIGN 3H2,4H2 PLANT (UNIT 098,099) NO.3 NO.4 HYDROGEN PLANT | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-04-26 | CLASS 1
CON-BMP-TRA-070015 | SO6001-ES0B-PHL-34100001-001 | 341-A-BOD-00001-001 | BASIS OF DESIGN 2IAS (UNIT 341) AIR VOMPRESSOR AND DRYERS | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3 - REVIEWED WITH COMMENTS | 2018-04-27 | CLASS 1
CON-BMP-TRA-070016 | SO6001-ES0B-PHL-37155001-001 | 371-A-BOD-55001-001 | BASIS OF DESIGN STM G AND D (UNIT 371) STEAM GENERATION AND DISTRIBUTION | A | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 1
CON-BMP-TRA-070017 | SO6001-ES0B-PHL-37254001-001 | 372-A-BOD-54001-001 | BASIS OF DESIGN 2 BFW AND COND(UNIT 372) BOILER FEED WATER ANDCONDENSATE DISTRIBUTION | A | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3 - REVIEWED WITH COMMENTS | 2018-04-30 | CLASS 1
CON-BMP-TRA-070018 | SO6001-ES0D-PFD-01600001-001 | 016-A-PFD-00001-001 | PROCESS FLOW DIAGRAM TRAIN A AND B - (KERO MEROX OFFPLOT FACILITIES) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070018 | SO6001-ES0D-PFD-01600001-002 | 016-A-PFD-00001-002 | PROCESS FLOW DIAGRAM TRAIN C (KERO MEROX OFFPLOT FACILITIES) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070019 | SO6001-ES0D-MSD-00500001-001 | 005-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM C3 STORAGE BULLETS AND PUMPS | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070019 | SO6001-ES0D-MSD-00500001-002 | 005-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM C4 STORAGE BULLETS AND PUMPS | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070019 | SO6001-ES0D-MSD-00500001-003 | 005-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM OFF SPEC AND SPARE LPG BULLETS AND OFF SPEC LPG PUMPS | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070020 | SO6001-ES0D-MSD-01600001-001 | 016-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM MEROX PROCESS UNIT - TRAIN A AND B (KERO MEROX OFFPLOT FACILITIES) | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 2
CON-BMP-TRA-070020 | SO6001-ES0D-MSD-01600001-002 | 016-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM MEROX PROCESS UNIT TRAIN C | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 2
CON-BMP-TRA-070020 | SO6001-ES0D-MSD-01600001-003 | 016-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM MEROX PROCESS UNIT | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 2
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-001 | 041-A-PFD-00001-001 | PROCESS FLOW DIAGRAM ACID/ SWS OFF GAS KO DRUM & PUMP SECTION (#5SRU, #6SRU, #7SU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-002 | 041-A-PFD-00001-002 | PROCESS FLOW DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#5SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-003 | 041-A-PFD-00001-003 | PROCESS FLOW DIAGRAM SULPHUR DEGASSING AND STORAGE (#5SRU, #6SRU, #7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-004 | 041-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#5SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-005 | 041-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#5SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-006 | 041-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#5SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070022 | SO6001-ES0D-PFD-04200001-001 | 042-A-PFD-00001-001 | PROCESS FLOW DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#6SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070022 | SO6001-ES0D-PFD-04200001-002 | 042-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#6SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070022 | SO6001-ES0D-PFD-04200001-003 | 042-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#6SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070022 | SO6001-ES0D-PFD-04200001-004 | 042-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#6SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070023 | SO6001-ES0D-PFD-04300001-001 | 043-A-PFD-00001-001 | PROCESS FLOW DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070023 | SO6001-ES0D-PFD-04300001-002 | 043-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070023 | SO6001-ES0D-PFD-04300001-003 | 043-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070023 | SO6001-ES0D-PFD-04300001-004 | 043-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070024 | SO6001-ES0D-MSD-31000001-001 | 310-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HP STEAM BOILER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070024 | SO6001-ES0D-MSD-31000001-002 | 310-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM BLOWDOWN | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070024 | SO6001-ES0D-MSD-31000001-003 | 310-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM PHOSPHATE INJECTION PACKAGE | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070025 | SO6001-ES0D-MSD-31100001-001 | 311-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HP STEAM BOILER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070025 | SO6001-ES0D-MSD-31100001-002 | 311-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM BLOWDOWN | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070026 | SO6001-ES0D-PFD-04600001-001 | 046-A-PFD-00001-001 | PROCESS FLOW DIAGRAM NON PHENOLIC SOUR WATER UNIT (#5SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-070026 | SO6001-ES0D-PFD-04600001-002 | 046-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE WATER UNIT (#5SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-070026 | SO6001-ES0D-PFD-04600001-003 | 046-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE WATER UNIT (#5SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 1
CON-BMP-TRA-070027 | SO6001-ES0D-PFD-04700001-001 | 047-A-PFD-00001-001 | PROCESS FLOW DIAGRAM PHENOLIC SOUR STRIPPER UNIT (#6SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070027 | SO6001-ES0D-PFD-04700001-002 | 047-A-PFD-00001-002 | PROCESS FLOW DIAGRAM PHENOLIC SOUR STRIPPER UNIT (#6SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070027 | SO6001-ES0D-PFD-04700001-003 | 047-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT(#6SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070028 | SO6001-ES0D-MSD-38200001-001 | 382-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM OILY WATER BASIN, CONTAMINED STORM WATER SURGE BASIN AND CLEAN SEWER BASIN | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070028 | SO6001-ES0D-MSD-38200001-002 | 382-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM SANITARY BASINS | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-10 | CLASS 2
CON-BMP-TRA-070029 | SO6001-EJ1E-TDS-04100004-001 | 041-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E4102 NO.1 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070029 | SO6001-EJ1E-TDS-04100005-001 | 041-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E4103 NO.2 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070029 | SO6001-EJ1E-TDS-04100006-001 | 041-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E4104 NO.3 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070030 | SO6001-ES0D-PFD-08300001-001 | 083-A-PFD-00001-001 | PROCESS FLOW DIAGRAM NITROGEN SYSTEM BLOCK FLOW DIAGRAM | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070031 | SO6001-ES0D-PFD-08700001-001 | 087-A-PFD-00001-001 | PROCESS FLOW DIAGRAM LSFO COOLING TOWER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070031 | SO6001-ES0D-PFD-08700001-002 | 087-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070031 | SO6001-ES0D-PFD-08700001-003 | 087-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070032 | SO6001-ES0D-PFD-08800001-001 | 088-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KERO RERUN UNIT (EX BRB-229600 SH 01) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070032 | SO6001-ES0D-PFD-08800001-002 | 088-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3 - REVIEWED WITH COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070033 | SO6001-EJ1E-TDS-04200004-001 | 042-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 042E4202 NO.1 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070033 | SO6001-EJ1E-TDS-04200005-001 | 042-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 042E4203NO.2 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070033 | SO6001-EJ1E-TDS-04200006-001 | 042-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 042E4204 NO.3 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070034 | SO6001-EJ1E-TDS-04300004-001 | 043-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E4302 NO.1 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070034 | SO6001-EJ1E-TDS-04300005-001 | 043-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E4303 NO.2 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070034 | SO6001-EJ1E-TDS-04300006-001 | 043-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E4304 NO.3 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070035 | SO6001-EJ2E-TDS-34100001-001 | 341-S-DAT-00001-001 | DATASHHET FOR AIR DRYERS PACKAGE 341U0140A/B PLANT NO.: 341 MATERIAL CLASSIFICATION LETTER:S | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-001 | 094-A-PFD-00001-001 | PROCESS FLOW DIAGRAM 2SHF SULPHUR HANDLING FACILITIES STORAGE TANK/ PRECONDITIONER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-002 | 094-A-PFD-00001-002 | PROCESS FLOW DIAGRAM 2SHF SULPHUR HANDLING FACILITIES PELLETIZER/ COOLING/ LOADING | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-003 | 094-A-PFD-00001-003 | PROCESS FLOW DIAGRAM EXISTING SULPHUR HANDLING FACILITIES STORAGE TANK/ PRECONDITIONER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-004 | 094-A-PFD-00001-004 | PROCESS FLOW DIAGRAM PROPOSAL FOR SULPHUR STORAGE TANK OPTION WHEN SHF TANK D9600 IS OUT OF SERVICE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-005 | 094-A-PFD-00001-005 | PROCESS FLOW DIAGRAM EXISTING SULPHUR HANDLING FACILITIES PELLETIZER/ COOLING/ LOADING | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-006 | 094-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-007 | 094-A-PFD-00001-007 | PROCESS FLOW DIAGRAM 2SHF NEUTRALIZATION FACILITY | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-001 | 098-A-PFD-00001-001 | PROCESS FLOW DIAGRAM FEED DESULPHURISATION AND REFORMING | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-002 | 098-A-PFD-00001-002 | PROCESS FLOW DIAGRAM PROCESS GAS BOILER AND HTS REACTOR | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-003 | 098-A-PFD-00001-003 | PROCESS FLOW DIAGRAM PROCESS GAS BOILER AND HTS REACTOR | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-004 | 098-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-005 | 098-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-006 | 098-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-007 | 098-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE TURNDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-008 | 098-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE TURNDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-009 | 098-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE TURNDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-010 | 098-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE MIXED FUEL | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-011 | 098-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE MIXED FUEL | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1 - APPROVED | 2018-05-04 | CLASS 1
CON-BMP-TRA-070038 | SO6001-ES0B-PHL-03600001-001 | 036-A-BOD-00001-001 | BASIS OF DESIGN (UNIT 036,037,041,042,043,044,045,046,047,048,049) NO.3 SULPHUR PLANT | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-070039 | SO6001-EJ2E-TDS-34120001-001 | 341-K-DAT-00001-001 | DATASHEET FOR INTEGRALLY GEARED CENTRIFUGAL COMPRESSORS FOR 341K 3415 A-B-C-D AIR COMPRESSORS | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 4 - NOT APPROVED | 2018-05-09 | CLASS 2
CON-BMP-TRA-070040 | SO6001-ES0D-PFD-38200001-001 | 382-A-PFD-00001-001 | PROCESS FLOW DIAGRAM OILY WATER BASIN, CONTAMINED STORM WATER SURGE BASIN AND CLEAN WATER BASIN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070040 | SO6001-ES0D-PFD-38200001-002 | 382-A-PFD-00001-002 | PROCESS FLOW DIAGRAM SANITARY BASINS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070040 | SO6001-ES0D-PFD-38200001-003 | 382-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070041 | SO6001-ES0D-PFD-00500001-001 | 005-A-PFD-00001-001 | PROCESS FLOW DIAGRAM C3 STORAGE BULLETS AND PUMPS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070041 | SO6001-ES0D-PFD-00500001-002 | 005-A-PFD-00001-002 | PROCESS FLOW DIAGRAM C4 STORAGE BULLETS AND PUMPS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070041 | SO6001-ES0D-PFD-00500001-003 | 005-A-PFD-00001-003 | PROCESS FLOW DIAGRAM OFF SPEC AND SPARE LPG BULLETS AND OFF SPEC LPG PUMPS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070041 | SO6001-ES0D-PFD-00500001-004 | 005-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070042 | SO6001-ES0D-PFD-31000001-001 | 310-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HP STEAM BOILER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070042 | SO6001-ES0D-PFD-31000001-002 | 310-A-PFD-00001-002 | PROCESS FLOW DIAGRAM BLOWDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070042 | SO6001-ES0D-PFD-31000001-003 | 310-A-PFD-00001-003 | PROCESS FLOW DIAGRAM PHOSPHATE INJECTION PACKAGE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070042 | SO6001-ES0D-PFD-31000001-004 | 310-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070043 | SO6001-ES0D-PFD-31100001-001 | 311-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HP STEAM BOILER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070043 | SO6001-ES0D-PFD-31100001-002 | 311-A-PFD-00001-002 | PROCESS FLOW DIAGRAM BLOWDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070043 | SO6001-ES0D-PFD-31100001-003 | 311-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-08 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-001 | 341-A-PFD-00001-001 | PROCESS FLOW DIAGRAM AIR COMPRESSORS DRYERS & DISTRIBUTION | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-002 | 341-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AIR COMPRESSORS DRYERS & DISTRIBUTION | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-003 | 341-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-004 | 341-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-005 | 341-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 1
CON-BMP-TRA-070045 | SO6001-ES0D-PFD-37800001-001 | 378-A-PFD-00001-001 | PROCESS FLOW DIAGRAM SALT WATER SYSTEM | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 1
CON-BMP-TRA-070045 | SO6001-ES0D-PFD-37800001-002 | 378-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 1
CON-BMP-TRA-070046 | SO6001-ES0B-PHL-08300001-001 | 083-A-BOD-00001-001 | BASIS OF DESIGN FOR NITROGEN PLANT (UNIT 083) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-06 | CLASS 1
CON-BMP-TRA-070047 | SO6001-ES0B-PHL-38200001-001 | 382-A-BOD-00001-001 | BASIS OF DESIGN FOR SEWER SYSTEMS (UNIT 382) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-09 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-DL-1020-001 | 000-K-IDL-80001-001 | LIST OF DEVIATION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-ITP-1020-001 | 000-K-ITP-80001-001 | INSPECTION AND TESTS PLAN FOR RECIPROCATING COMPRESSORS | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-MR-1020-001 | 000-K-MRQ-80001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSORS | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-SP-1020-001 | 000-K-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-SR-1020-001 | 000-K-SOW-80001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSORS | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | SO6001-EJ2E-TDS-09820001-001 | 098-K-DAT-00001-001 | DATASHEET FOR RECIPROCATING COMPRESSOR FOR 098K9810 CIRCULATION NITROGEN COMPRESSOR | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | SO6001-EJ2E-TDS-09920001-001 | 099-K-DAT-00001-001 | DATASHEET FOR RECIPROCATING COMPRESSOR FOR 099K9910 CIRCULATION NITROGEN COMPRESSOR | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3 - REVIEWED WITH COMMENTS | 2018-05-10 | CLASS 1
CON-BMP-TRA-070049 | SO6001-ES0B-PHL-09800001-001 | 098-A-BOD-00001-001 | PROCESS DESIGN BASIS NO.3 NO.4 HYDROGEN PLANT (UNIT 098-099) | B | 2018-05-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-11 | CLASS 1
CON-BMP-TRA-070050 | SO6001-ES0D-MSD-04100001-001 | 041-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT SECTION (#5SRU, #6SRU, #7SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070050 | SO6001-ES0D-MSD-04100001-002 | 041-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#5SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070050 | SO6001-ES0D-MSD-04100001-003 | 041-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM SULPHUR DEGASSING AND STORAGE (#5SRU,#6SRU,#7SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070050 | SO6001-ES0D-MSD-04100001-004 | 041-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#5SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070051 | SO6001-ES0D-MSD-04200001-001 | 042-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#6SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070051 | SO6001-ES0D-MSD-04200001-002 | 042-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#6SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070052 | SO6001-ES0D-MSD-04300001-001 | 043-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#7SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070052 | SO6001-ES0D-MSD-04300001-002 | 043-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#7SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070053 | SO6001-ES0D-MSD-04500001-001 | 045-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM TAIL GAS REACTOR AND DCC (#4TGTU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070053 | SO6001-ES0D-MSD-04500001-002 | 045-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE ABSORBER REGENERATOR AND STORAGE (#4TGTU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070053 | SO6001-ES0D-MSD-04500001-003 | 045-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM INCINERATOR (#4TGTU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070053 | SO6001-ES0D-MSD-04500001-004 | 045-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM UNIT (#4TGTU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070054 | SO6001-ES0D-MSD-04600001-001 | 046-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM NON PHENOLIC SOUR WATER UNIT (#5SWS) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070054 | SO6001-ES0D-MSD-04600001-002 | 046-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM NON PHENOLIC SOUR WATER UNIT (#5SWS) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070055 | SO6001-ES0D-MSD-04700001-001 | 047-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM PHENOLIC SOUR WATER UNIT (#6SWS) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070055 | SO6001-ES0D-MSD-04700001-002 | 047-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM NON PHENOLIC SOUR WATER UNIT (#6SWS) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070056 | SO6001-ES0D-MSD-08800001-001 | 088-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KERO RETURN UNIT (EX BRB-229600 SH 01) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-001 | 094-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM BMP SULPHUR HANDLING FACILITIES STORAGE TANK / PRECONDITIONER | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-002 | 094-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM BMP SULPHUR HANDLING FACILITIES PELLETIZER / COOLING / LOADING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-003 | 094-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM EXISTING SULPHUR HANDLING FACILITIES STORAGE TANK / PRECONDITIONER | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-004 | 094-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM EXISTING SULPHUR HANDLING FACILITIES STORAGE TANK | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-005 | 094-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM EXISTING SULPHUR HANDLING FACILITIES PELLETIZER / COOLING / LOADING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-006 | 094-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM 2SHF NEUTRALIZATION FACILITY | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-001 | 098-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM FEED DESULPHURISATION AND REFORMING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-002 | 098-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM PROCESS GAS BOILER AND HTS REACTOR | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-003 | 098-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM PROCESS GAS COOLING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-004 | 098-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM DESULPHURISATION AND REFORMING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-005 | 098-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM PROCESS GAS COOLING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-16 | CLASS 2
CON-BMP-TRA-070059 | SO6001-ES0D-MSD-34100001-001 | 341-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM AIR COMPRESSORS DRYERS & DISTRIBUTION | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-18 | CLASS 2
CON-BMP-TRA-070059 | SO6001-ES0D-MSD-34100001-002 | 341-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AIR COMPRESSORS DRYERS & DISTRIBUTION | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-18 | CLASS 2
CON-BMP-TRA-070060 | SO6001-ES0D-MSD-37800001-001 | 378-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM SALT WATER SYSTEM | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-18 | CLASS 2
CON-BMP-TRA-070061 | SO6001-ES0D-PFD-35600001-001 | 356-A-PFD-00001-001 | PROCESS FLOW DIAGRAM MED DESALINATION | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 1
CON-BMP-TRA-070061 | SO6001-ES0D-PFD-35600001-002 | 356-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 1
CON-BMP-TRA-070062 | SO6001-ES0D-PFD-35700001-001 | 357-A-PFD-00001-001 | PROCESS FLOW DIAGRAM MED DESALINATION | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-070063 | SO6001-ES0D-PFD-35800001-001 | 358-A-PFD-00001-001 | PROCESS FLOW DIAGRAM MED DESALINATION | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-20 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-001 | 372-A-PFD-54001-001 | PROCESS FLOW DIAGRAM FED STORAGE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-002 | 372-A-PFD-54001-002 | PROCESS FLOW DIAGRAM FED TREATMENT MIXED BED | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-003 | 372-A-PFD-54001-003 | PROCESS FLOW DIAGRAM OIL SEPARATOR TANKS | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-004 | 372-A-PFD-54001-004 | PROCESS FLOW DIAGRAM HOTWELLS | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-005 | 372-A-PFD-54001-005 | PROCESS FLOW DIAGRAM CONDENSATE RECOVERY VESSEL | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-006 | 372-A-PFD-54001-006 | PROCESS FLOW DIAGRAM RECOVERED CONDENSATE STORAGE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-007 | 372-A-PFD-54001-007 | PROCESS FLOW DIAGRAM CONDENSATE TRETMENT ACTIVATED CARBON FILTERS | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-008 | 372-A-PFD-54001-008 | PROCESS FLOW DIAGRAM TREATED CONDENSATE STORAGE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-009 | 372-A-PFD-54001-009 | PROCESS FLOW DIAGRAM CONDENSATE TREATMENT MIXED BED | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-010 | 372-A-PFD-54001-010 | PROCESS FLOW DIAGRAM DEMINERALIZED WATER STORAGE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-011 | 372-A-PFD-54001-011 | PROCESS FLOW DIAGRAM DEAREATION AND BFW DISTRIBUTION | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-012 | 372-A-PFD-54001-012 | PROCESS FLOW DIAGRAM BFW CHEMICALS DOSING | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-013 | 372-A-PFD-54001-013 | PROCESS FLOW DIAGRAM NETURALIZATION FACILITIES | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-014 | 372-A-PFD-54001-014 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-015 | 372-A-PFD-54001-015 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-016 | 372-A-PFD-54001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-017 | 372-A-PFD-54001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254002-001 | 372-A-PFD-54002-001 | PROCESS FLOW DIAGRAM UTILITY WATER HEADER | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254002-002 | 372-A-PFD-54002-002 | PROCESS FLOW DIAGRAM DEMIN WATER HEADER | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254002-003 | 372-A-PFD-54002-003 | PROCESS FLOW DIAGRAM BFW HEADER | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3 - REVIEWED WITH COMMENTS | 2018-05-23 | CLASS 1
CON-BMP-TRA-070065 | SO6001-ES0D-MSD-35600001-001 | 356-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM MED DESALINATION | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-18 | CLASS 2
CON-BMP-TRA-070066 | SO6001-ES0D-MSD-35700001-001 | 357-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM MED DESALINATION | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-18 | CLASS 2
CON-BMP-TRA-070067 | SO6001-ES0D-MSD-35800001-001 | 358-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM MED DESALINATION | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-18 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-001 | 372-A-MSD-54001-001 | MATERIAL SELECTION DIAGRAM FED STORAGE | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-002 | 372-A-MSD-54001-002 | MATERIAL SELECTION DIAGRAM FED TREATMENT MIXED BED | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-003 | 372-A-MSD-54001-003 | MATERIAL SELECTION DIAGRAM OIL SEPARATOR TANKS | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-004 | 372-A-MSD-54001-004 | MATERIAL SELECTION DIAGRAM HOTWELLS | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-005 | 372-A-MSD-54001-005 | MATERIAL SELECTION DIAGRAM CONDENSATE RECOVERY VESSEL | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-006 | 372-A-MSD-54001-006 | MATERIAL SELECTION DIAGRAM RECOVERED CONDENSATE STORAGE | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-007 | 372-A-MSD-54001-007 | MATERIAL SELECTION DIAGRAM CONDENSATE TREATMENT ACTIVATED CARBON FILTERS | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-008 | 372-A-MSD-54001-008 | MATERIAL SELECTION DIAGRAM TREATED CONDENSATE STORAGE | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-009 | 372-A-MSD-54001-009 | MATERIAL SELECTION DIAGRAM CONDENSATE TREATMENT MIX BED | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-010 | 372-A-MSD-54001-010 | MATERIAL SELECTION DIAGRAM DEMI WATER STORAGE | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-011 | 372-A-MSD-54001-011 | MATERIAL SELECTION DIAGRAM DEAERATION & BFW DISTRIBUTION | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-012 | 372-A-MSD-54001-012 | MATERIAL SELECTION DIAGRAM BFW CHEMICALS DOSING | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-013 | 372-A-MSD-54001-013 | MATERIAL SELECTION DIAGRAM NEUTRALIZATION FACILITIES | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254002-001 | 372-A-MSD-54002-001 | MATERIAL SELECTION DIAGRAM UTILITY WATER HEADER | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254002-002 | 372-A-MSD-54002-002 | MATERIAL SELECTION DIAGRAM DEMIN WATER HEADER | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254002-003 | 372-A-MSD-54002-003 | MATERIAL SELECTION DIAGRAM BFW HEADER | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070069 | SO6001-ES0D-PFD-03600001-001 | 036-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KHUFF GAS TREATMENT UNIT (#2BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070069 | SO6001-ES0D-PFD-03600001-002 | 036-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (#2BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070069 | SO6001-ES0D-PFD-03600001-003 | 036-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (#2BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070070 | SO6001-ES0D-PFD-03700001-001 | 037-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KHUFF GAS TREATMENT UNIT (#3BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070070 | SO6001-ES0D-PFD-03700001-002 | 037-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (#3BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070070 | SO6001-ES0D-PFD-03700001-003 | 037-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (#3BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-001 | 044-A-PFD-00001-001 | PROCESS FLOW DIAGRAM TAIL GAS REACTOR QUENCH COLUMN (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-002 | 044-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE ABSORBER REGENERATOR AND STORAGE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-003 | 044-A-PFD-00001-003 | PROCESS FLOW DIAGRAM INCINERATOR (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-004 | 044-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HP STEAM AND CONDENSATE SECTION (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-005 | 044-A-PFD-00001-005 | PROCESS FLOW DIAGRAM LP STEAM AND BLOWDOWN SECTION (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-006 | 044-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-007 | 044-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-008 | 044-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-009 | 044-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-010 | 044-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-001 | 045-A-PFD-00001-001 | PROCESS FLOW DIAGRAM TAIL GAS REACTOR AND QUENCH COLUMN (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-002 | 045-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE ABSORBER, REGENERATOR AND STORAGE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-003 | 045-A-PFD-00001-003 | PROCESS FLOW DIAGRAM INCINERATOR (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-004 | 045-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-005 | 045-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-006 | 045-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-007 | 045-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070073 | SO6001-ES0D-PFD-04800001-001 | 048-A-PFD-00001-001 | PROCESS FLOW DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070073 | SO6001-ES0D-PFD-04800001-002 | 048-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070073 | SO6001-ES0D-PFD-04800001-003 | 048-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#2ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070073 | SO6001-ES0D-PFD-04800001-004 | 048-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#2ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070074 | SO6001-ES0D-PFD-04900001-001 | 049-A-PFD-00001-001 | PROCESS FLOW DIAGRAM AMINE REGENERATION (#3ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070074 | SO6001-ES0D-PFD-04900001-002 | 049-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070074 | SO6001-ES0D-PFD-04900001-003 | 049-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3 - REVIEWED WITH COMMENTS | 2018-05-17 | CLASS 1
CON-BMP-TRA-070075 | SO6001-EJ2E-TDS-09800004-001 | 098-S-DAT-00004-001 | DATASHEET FOR HYDROGEN PSA UNIT (098U0001) | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 2
CON-BMP-TRA-070076 | SO6001-EJ2E-TDS-09900004-001 | 099-S-DAT-00004-001 | DATASHEET FOR HYDROGEN PSA UNIT (099U0001) | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-23 | CLASS 2
CON-BMP-TRA-070077 | SO6001-ES0D-MSD-03600001-001 | 036-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (#2BAGRU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 2
CON-BMP-TRA-070077 | SO6001-ES0D-MSD-03600001-002 | 036-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (#2BAGRU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 2
CON-BMP-TRA-070078 | SO6001-ES0D-MSD-03700001-001 | 037-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (#3BAGRU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 2
CON-BMP-TRA-070078 | SO6001-ES0D-MSD-03700001-002 | 037-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (#3BAGRU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-001 | 044-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM TAIL GAS REACTOR AND DCC (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-002 | 044-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE ABSORBER REGENERATOR AND STORAGE (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-003 | 044-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM INCINERATOR (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-004 | 044-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM STEAM CONDENSATE AND BLOWDOWN SECTION (#3TGTU & #4TGTU ) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-005 | 044-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM UNIT (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-006 | 044-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM UNIT (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-007 | 044-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM UNIT (#3TGTU & #4TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070080 | SO6001-ES0D-MSD-04800001-001 | 048-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 2
CON-BMP-TRA-070080 | SO6001-ES0D-MSD-04800001-002 | 048-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 3 - REVIEWED WITH COMMENTS | 2018-05-20 | CLASS 2
CON-BMP-TRA-070081 | SO6001-ES0D-MSD-04900001-001 | 049-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#3ARU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070081 | SO6001-ES0D-MSD-04900001-002 | 049-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#3ARU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3 - REVIEWED WITH COMMENTS | 2018-05-21 | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-DL-0511-002 | 000-C-IDL-80007-001 | LIST OF DEVIATION FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-ITP-0511-002 | 000-C-ITP-80007-001 | INSPECTION AND TEST PLAN FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-MR-0511-002 | 000-C-MRQ-80007-001 | MATERIAL REQUISITION FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-SP-0511-002 | 000-C-GRD-80007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-SR-0511-002 | 000-C-SOW-80007-001 | SCOPE OF SUPPLY FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03600004-001 | 036-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03600004-002-001 | 036-C-GAD-00002-001 | 036C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03600004-003-002 | 036-C-GAD-00002-002 | 036C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03600004-004-003 | 036-C-GAD-00002-003 | 036C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03700004-001 | 037-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03700004-002-001 | 037-C-GAD-00002-001 | 037C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03700004-003-002 | 037-C-GAD-00002-002 | 037C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03700004-004-003 | 037-C-GAD-00002-003 | 037C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04400011-001 | 044-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04400011-002-001 | 044-C-GAD-00004-001 | 044C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04400011-003-002 | 044-C-GAD-00004-002 | 044C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04400011-004-003 | 044-C-GAD-00004-003 | 044C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04500006-001 | 045-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04500006-002-001 | 045-C-GAD-00004-001 | 045C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04500006-003-002 | 045-C-GAD-00004-002 | 045C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04500006-004-003 | 045-C-GAD-00004-003 | 045C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04600003-001 | 046-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046C0001 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04600003-002-001 | 046-C-GAD-00001-001 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04600003-003-002 | 046-C-GAD-00001-002 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04600003-004-003 | 046-C-GAD-00001-003 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04700003-001 | 047-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 047C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04700003-002-001 | 047-C-GAD-00001-001 | 047C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04700003-003-002 | 047-C-GAD-00001-002 | 047C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04700003-004-003 | 047-C-GAD-00001-003 | 047C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04800005-001 | 048-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04800005-002-001 | 048-C-GAD-00001-001 | 048C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04800005-003-002 | 048-C-GAD-00001-002 | 048C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04800005-004-003 | 048-C-GAD-00001-003 | 048C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04900003-001 | 049-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 049C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04900003-002-001 | 049-C-GAD-00001-001 | 049C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04900003-003-002 | 049-C-GAD-00001-002 | 049C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04900003-004-003 | 049-C-GAD-00001-003 | 049C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09800005-001 | 098-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09800005-002-001 | 098-C-GAD-00004-001 | 098C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09800005-003-002 | 098-C-GAD-00004-002 | 098C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09800005-004-003 | 098-C-GAD-00004-003 | 098C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09900005-001 | 099-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09900005-002-001 | 099-C-GAD-00004-001 | 099C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09900005-003-002 | 099-C-GAD-00004-002 | 099C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09900005-004-003 | 099-C-GAD-00004-003 | 099C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070083 | SO6001-ES0B-PHL-09400001-001 | 094-A-BOD-00001-001 | BASIS OF DESIGN 2SHF (UNIT 094) SULPHUR HANDLING FACILITY | B | 2018-05-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-05-28 | CLASS 1
CON-BMP-TRA-070084 | SO6001-EJ2E-TDS-01610003-001 | 016-G-DAT-00003-001 | DATA SHEET FOR CAUSTIC INJECTION PUMP TRAIN C | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 | 3 - REVIEWED WITH COMMENTS | 2018-05-28 | CLASS 2
CON-BMP-TRA-070085 | SO6001-EJ1E-TDS-04100004-001 | 041-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 041E0002 NO.1 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070085 | SO6001-EJ1E-TDS-04100005-001 | 041-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 041E0003 NO.2 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070085 | SO6001-EJ1E-TDS-04100006-001 | 041-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 041E0004 NO.3 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070086 | SO6001-EJ1E-TDS-04200004-001 | 042-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 042E0002 NO.1 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070086 | SO6001-EJ1E-TDS-04200005-001 | 042-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 042E0003 NO.2 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070086 | SO6001-EJ1E-TDS-04200006-001 | 042-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 042E0004 NO.3 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070087 | SO6001-EJ1E-TDS-04300004-001 | 043-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 043E0002 NO.1 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070087 | SO6001-EJ1E-TDS-04300005-001 | 043-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 043E0003 NO.2 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070087 | SO6001-EJ1E-TDS-04300006-001 | 043-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 043E0004 NO.3 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070088 | SO6001-EJ1E-TDS-04400012-001 | 044-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0002 WASTE HEAT BOILER | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070089 | SO6001-EJ1E-TDS-04500009-001 | 045-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 045E0002 WASTE HEAT BOILER | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-01 | CLASS 2
CON-BMP-TRA-070090 | SO6001-ES0D-MSD-04800001-003 | 048-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-07 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070091 | SO6001-EJ2E-TDS-04110001-001 | 041-G-DAT-00001-001 | DATA SHEET FOR 041P0001A/B SULPHUR TRANSFER PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070092 | SO6001-EJ2E-TDS-04210001-001 | 042-G-DAT-00001-001 | DATA SHEET FOR 042P0001A/B SULPHUR TRANSFER PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070093 | SO6001-EJ2E-TDS-04310001-001 | 043-G-DAT-00001-001 | DATA SHEET FOR 043P0001A/B SULPHUR TRANSFER PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070094 | SO6001-EJ2E-TDS-38210005-001 | 382-G-DAT-00005-001 | DATA SHEET FOR 382P3881A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070094 | SO6001-EJ2E-TDS-38210006-001 | 382-G-DAT-00006-001 | DATA SHEET FOR 382P3882A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070094 | SO6001-EJ2E-TDS-38210007-001 | 382-G-DAT-00007-001 | DATA SHEET FOR 382P3884A/B | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070095 | SO6001-EJ1E-TDS-04100002-002 | 041-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 041C0001R NO.1 CONVERTER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070095 | SO6001-EJ1E-TDS-04100003-002 | 041-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 041C0002R NO.2 CONVERTER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070096 | SO6001-EJ1E-TDS-04200002-002 | 042-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 042C0001R NO.1 CONVERTER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070096 | SO6001-EJ1E-TDS-04200003-002 | 042-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 042C0002R NO.2 CONVERTER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070097 | SO6001-EJ1E-TDS-04300002-002 | 043-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 043C0001R NO.1 CONVERTER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070097 | SO6001-EJ1E-TDS-04300003-002 | 043-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 043C0002R NO.2 CONVERTER | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070098 | SO6001-EJ1E-TDS-04400008-002 | 044-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0001R TAIL GAS REACTOR | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070099 | SO6001-SZ0P-EXE-000001 | 000-A-PRO-80002-001 | SOC ENGINEERING MANAGEMENT PLAN | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 |  |  | CLASS 2
CON-BMP-TRA-070100 | SO6001-EJ1E-TDS-04500008-002 | 045-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0001R TAIL GAS REACTOR | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070101 | SO6001-EJ1E-TDS-09800002-002 | 098-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098C0001R ZINC OXIDE DRUM | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070101 | SO6001-EJ1E-TDS-09800003-002 | 098-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098C0002R ZINC OXIDE DRUM | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070101 | SO6001-EJ1E-TDS-09800004-002 | 098-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098C0003R HIGH TEMPERATURE SHIFT REACTOR | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-04 | CLASS 2
CON-BMP-TRA-070102 | SO6001-EJ1E-TDS-09900002-002 | 099-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099C0001R ZINC OXIDE DRUM | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070102 | SO6001-EJ1E-TDS-09900003-002 | 099-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099C0002R ZINC OXIDE DRUM | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070102 | SO6001-EJ1E-TDS-09900004-002 | 099-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099C0003R HIGH TEMERATURE SHIFT REACTOR | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-05 | CLASS 2
CON-BMP-TRA-070103 | SO6001-EH0K-MMC-93200001-001 | 932-L-MOM-00001-001 | SOC-BASIS OF CHANGE ON PLOT PLAN FOR SULFUR BLOCKS | 0 | 2018-05-25 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-070104 | SO6001-EJ1E-TDS-01600001-002 | 016-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 016C1640 MEROX REACTOR | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070105 | SO6001-EJ2E-TDS-03610005-001 | 036-G-DAT-00005-001 | DATA SHEET FOR 036P0005A/B HP LEAN AMINE PUMPS | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070106 | SO6001-EJ2E-TDS-03710005-001 | 037-G-DAT-00005-001 | DATA SHEET FOR 037P0005A/B HP LEAN AMINE PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070107 | SO6001-EJ2E-TDS-04810004-001 | 048-G-DAT-00004-001 | DATASHEET FOR 048P0004A/B LEAN AMINE PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070108 | SO6001-EJ2E-TDS-04910004-001 | 049-G-DAT-00004-001 | DATASHEET FOR 049P0004A/B LEAN AMINE PUMPS | A | 2018-05-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070109 | SO6001-EJ2E-TDS-09810001-001 | 098-G-DAT-00001-001 | DATASHEET FOR 098P0001A/B HP BFW PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070110 | SO6001-EJ2E-TDS-09910001-001 | 099-G-DAT-00001-001 | DATASHEET FOR 099P0001A/B HP BFW PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070111 | SO6001-EJ2E-TDS-37210001-001 | 372-G-DAT-54001-001 | DATASHEET FOR 372P3734A/B/C RECOVERED CONDENSATE PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070111 | SO6001-EJ2E-TDS-37210002-001 | 372-G-DAT-54002-001 | DATASHEET FOR 372P3735A/B/C A.C. FILTER FEED PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070111 | SO6001-EJ2E-TDS-37210003-001 | 372-G-DAT-54003-001 | DATASHEET FOR 372P3737A/B/C CONDENSATE POLISHING FEED PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070111 | SO6001-EJ2E-TDS-37210004-001 | 372-G-DAT-54004-001 | DATASHEET FOR 372P3739A/B/C DEAERATOR FEED WATER PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070111 | SO6001-EJ2E-TDS-37210005-001 | 372-G-DAT-54005-001 | DATASHEET FOR HP BFW PUMPS (372P3741A/B/C) | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070111 | SO6001-EJ2E-TDS-37210006-001 | 372-G-DAT-54006-001 | DATASHEET FOR 372P3746A/B/C HP BOILER FEED WATER PUMPS | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070112 | SO6001-EJ2E-TDS-37220001-001 | 372-K-DAT-54001-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 372T3759A/B DEAERATOR FEED WATER PUMPS TURBINES | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070112 | SO6001-EJ2E-TDS-37220002-001 | 372-K-DAT-54002-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 372T3761A/B HP BFW PUMPS TURBINES | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070112 | SO6001-EJ2E-TDS-37220003-001 | 372-K-DAT-54003-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 372T3766A/B HP BOILER FEED WATER PUMPS TURBINES | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070113 | SO6001-EJ2E-TDS-37810001-001 | 378-G-DAT-00001-001 | DATASHEET FOR 378P1229 N.9 HIGH LIFT UNIT PUMP | A | 2018-05-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070114 | SO6001-EJ2E-TDS-01610001-001 | 016-G-DAT-00001-001 | DATA SHEET FOR 016P9600D KEROSENE FEED PUMP TRAIN C | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070115 | SO6001-EJ2E-TDS-03610001-001 | 036-G-DAT-00001-001 | DATA SHEET FOR 036P0001A/B RICH AMINE FLASH DRUM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070115 | SO6001-EJ2E-TDS-03610002-001 | 036-G-DAT-00002-001 | DATA SHEET FOR 036P0002A/B REGENERATOR BOTTOM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070115 | SO6001-EJ2E-TDS-03610003-001 | 036-G-DAT-00003-001 | DATA SHEET FOR 036P0003A/B REGENERATOR PUMP AROUND PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070115 | SO6001-EJ2E-TDS-03610004-001 | 036-G-DAT-00004-001 | DATA SHEET FOR 036P0004A/B LP LEAN AMINE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070116 | SO6001-EJ2E-TDS-03710001-001 | 037-G-DAT-00001-001 | DATA SHEET FOR 037P0001A/B RICH AMINE FLASH DRUM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070116 | SO6001-EJ2E-TDS-03710002-001 | 037-G-DAT-00002-001 | DATA SHEET FOR 037P0002A/B REGENERATOR BOTTOM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070116 | SO6001-EJ2E-TDS-03710003-001 | 037-G-DAT-00003-001 | DATA SHEET FOR 037P0003A/B REGENERATOR PUMP AROUND PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070116 | SO6001-EJ2E-TDS-03710004-001 | 037-G-DAT-00004-001 | DATA SHEET FOR 037P0004A/B LP LEAN AMINE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070117 | SO6001-EJ2E-TDS-04410001-001 | 044-G-DAT-00001-001 | DATA SHEET FOR 044P0001A/B QUENCH WATER CIRCULATION PUMP/COMMON PUMP (1, 10) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070117 | SO6001-EJ2E-TDS-04410002-001 | 044-G-DAT-00002-001 | DATA SHEET FOR 044P0002 QUENCH WATER CIRCULATION PUMP (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070117 | SO6001-EJ2E-TDS-04410003-001 | 044-G-DAT-00003-001 | DATA SHEET FOR 044P0003 A/B RICH AMINE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070117 | SO6001-EJ2E-TDS-04410004-001 | 044-G-DAT-00004-001 | DATA SHEET FOR 044P0004 A/B REGENERATOR BOTTOM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070117 | SO6001-EJ2E-TDS-04410005-001 | 044-G-DAT-00005-001 | DATA SHEET FOR 044P0005 A/B AMINE REGENERATOR PUMP AROUND PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070117 | SO6001-EJ2E-TDS-04410006-001 | 044-G-DAT-00006-001 | DATA SHEET FOR 044P0006 A/B LEAN AMINE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070117 | SO6001-EJ2E-TDS-04410008-001 | 044-G-DAT-00008-001 | DATA SHEET FOR 044P0008 A/B N.3 SULPHUR PLANT FLARE KO DRUM PUMPS (14) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070117 | SO6001-EJ2E-TDS-04410009-001 | 044-G-DAT-00009-001 | DATA SHEET FOR 044P0009 A/B CONDENSATE TRANSFER PUMPS | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070118 | SO6001-EJ2E-TDS-04510001-001 | 045-G-DAT-00001-001 | DATA SHEET FOR 045P0001A/B QUENCH WATER CIRCULATION PUMP | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070118 | SO6001-EJ2E-TDS-04510002-001 | 045-G-DAT-00002-001 | DATA SHEET FOR 045P0002 QUENCH WATER PUMP (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070118 | SO6001-EJ2E-TDS-04510003-001 | 045-G-DAT-00003-001 | DATA SHEET FOR 045P0003 A/B RICH AMINE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070118 | SO6001-EJ2E-TDS-04510004-001 | 045-G-DAT-00004-001 | DATA SHEET FOR 045P0004 A/B REGENERATOR BOTTOM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070118 | SO6001-EJ2E-TDS-04510005-001 | 045-G-DAT-00005-001 | DATA SHEET FOR 045P0005 A/B AMINE REGENERATOR PUMP AROUND PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070118 | SO6001-EJ2E-TDS-04510006-001 | 045-G-DAT-00006-001 | DATA SHEET FOR 045P0006 A/B LEAN AMINE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070119 | SO6001-EJ2E-TDS-04610001-001 | 046-G-DAT-00001-001 | DATA SHEET FOR 046P0001A/B SOUR WATER TRANSFER PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070119 | SO6001-EJ2E-TDS-04610002-001 | 046-G-DAT-00002-001 | DATA SHEET FOR 046P0002A/B SOUR WATER STRIPPER FEED PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070119 | SO6001-EJ2E-TDS-04610003-001 | 046-G-DAT-00003-001 | DATA SHEET FOR 046P0003A/B STRIPPED WATER PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070119 | SO6001-EJ2E-TDS-04610004-001 | 046-G-DAT-00004-001 | DATA SHEET FOR 046P0004A/B STRIPPER PUMP AROUND PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070119 | SO6001-EJ2E-TDS-04610007-001 | 046-G-DAT-00007-001 | DATA SHEET FOR 046P0007 OIL SKIMMING PUMP | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070120 | SO6001-EJ2E-TDS-04710001-001 | 047-G-DAT-00001-001 | DATA SHEET FOR 047P0001A/B SOUR WATER TRANSFER PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070120 | SO6001-EJ2E-TDS-04710002-001 | 047-G-DAT-00002-001 | DATA SHEET FOR 047P0002A/B SOUR WATER STRIPPER FEED PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070120 | SO6001-EJ2E-TDS-04710003-001 | 047-G-DAT-00003-001 | DATA SHEET FOR 047P0003A/B STRIPPED WATER PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070120 | SO6001-EJ2E-TDS-04710004-001 | 047-G-DAT-00004-001 | DATA SHEET FOR 047P0004A/B STRIPPER PUMPAROUND PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070121 | SO6001-EJ2E-TDS-04810001-001 | 048-G-DAT-00001-001 | DATA SHEET FOR 048P0001A/B RICH AMINE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070121 | SO6001-EJ2E-TDS-04810002-001 | 048-G-DAT-00002-001 | DATA SHEET FOR 048P0002A/B REGENERATOR BOTTOM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070121 | SO6001-EJ2E-TDS-04810003-001 | 048-G-DAT-00003-001 | DATA SHEET FOR 048P0003A/B REGENERATOR PUMP AROUND PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070121 | SO6001-EJ2E-TDS-04810006-001 | 048-G-DAT-00006-001 | DATA SHEET FOR 048P0006 FRESH AMINE MAKE UP PUMP (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070121 | SO6001-EJ2E-TDS-04810007-001 | 048-G-DAT-00007-001 | DATA SHEET FOR 048P0007 A/B ARU CONDENSATE TRANSFER PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070121 | SO6001-EJ2E-TDS-04810009-001 | 048-G-DAT-00009-001 | DATA SHEET FOR 048P0009 A/B ARU FLARE KO DRUM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070122 | SO6001-EJ2E-TDS-04910001-001 | 049-G-DAT-00001-001 | DATA SHEET FOR 049P0001A/B RICH AMINE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070122 | SO6001-EJ2E-TDS-04910002-001 | 049-G-DAT-00002-001 | DATA SHEET FOR 049P0002A/B REGENERATOR BOTTOM PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070122 | SO6001-EJ2E-TDS-04910003-001 | 049-G-DAT-00003-001 | DATA SHEET FOR 049P0003A/B REGENERATOR PUMP AROUND PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070123 | SO6001-EJ2E-TDS-09810008-001 | 098-G-DAT-00008-001 | DATA SHEET FOR 098P0008A/B PROCESS CONDENSATE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070124 | SO6001-EJ2E-TDS-09910008-001 | 099-G-DAT-00008-001 | DATA SHEET FOR 099P0008A/B PROCESS CONDENSATE PUMPS (1) | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070125 | SO6001-EJ2E-TDS-37210007-001 | 372-G-DAT-54007-001 | DATA SHEET FOR 372P3738 A/*B/C DEMINERALIZED WATER PUMPS | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070125 | SO6001-EJ2E-TDS-37210008-001 | 372-G-DAT-54008-001 | DATA SHEET FOR 372P3740 A/B/C HOTWELL FEED WATER PUMPS | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070125 | SO6001-EJ2E-TDS-37210009-001 | 372-G-DAT-54009-001 | DATA SHEET FOR 372P3742 A/B/C LP BFW PUMPS | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070126 | SO6001-EJ2E-TDS-37220004-001 | 372-K-DAT-54004-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 372T3760 A/B HOTWELL FEED WATER PUMPS TURBINES | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070126 | SO6001-EJ2E-TDS-37220005-001 | 372-K-DAT-54005-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 372T3762 A/B LP BFW PUMPS TURBINES | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070127 | SO6001-EJ1E-TDS-03600003-001 | 036-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036C0001 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-070128 | SO6001-EJ1E-TDS-03700003-001 | 037-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037C0001 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-070129 | SO6001-EJ1E-TDS-04400009-001 | 044-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0002 QUENCH COLUMN | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070129 | SO6001-EJ1E-TDS-04400010-001 | 044-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0003 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070130 | SO6001-EJ1E-TDS-04500004-001 | 045-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0002 QUENCH COLUMN | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070130 | SO6001-EJ1E-TDS-04500005-001 | 045-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0003 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070131 | SO6001-EJ1E-TDS-03600003-002-001 | 036-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 036C0001 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-070131 | SO6001-EJ1E-TDS-03600003-003-002 | 036-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 036C0001 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-070131 | SO6001-EJ1E-TDS-03600003-004-003 | 036-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 036C0001 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-070132 | SO6001-EJ1E-TDS-03700003-002-001 | 037-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 037C0001 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-070132 | SO6001-EJ1E-TDS-03700003-003-002 | 037-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 037C0001 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-070132 | SO6001-EJ1E-TDS-03700003-004-003 | 037-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 037C0001 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-07 | CLASS 2
CON-BMP-TRA-070133 | SO6001-EJ1E-TDS-04400009-002-001 | 044-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 044C0001 QUENCH COLUMN | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070133 | SO6001-EJ1E-TDS-04400009-003-002 | 044-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 044C0001 QUENCH COLUMN | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070133 | SO6001-EJ1E-TDS-04400009-004-003 | 044-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 044C0001 QUENCH COLUMN | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070133 | SO6001-EJ1E-TDS-04400010-002-001 | 044-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 044C0003 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070133 | SO6001-EJ1E-TDS-04400010-002-002 | 044-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 044C0003 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070133 | SO6001-EJ1E-TDS-04400010-002-003 | 044-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 044C0003 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070134 | SO6001-EJ1E-TDS-04500004-002-001 | 045-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 045C0002 QUENCH COLUMN | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070134 | SO6001-EJ1E-TDS-04500004-002-002 | 045-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 045C0002 QUENCH COLUMN | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070134 | SO6001-EJ1E-TDS-04500004-002-003 | 045-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 045C0002 QUENCH COLUMN | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070134 | SO6001-EJ1E-TDS-04500005-002-001 | 045-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 045C0003 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070134 | SO6001-EJ1E-TDS-04500005-003-002 | 045-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 045C0003 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070134 | SO6001-EJ1E-TDS-04500005-0040-003 | 045-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 045C0003 ABSORBER | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-08 | CLASS 2
CON-BMP-TRA-070135 | SO6001-EJ1E-TDS-01600001-001-001 | 016-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 016C1640 MEROX REACTOR TRAIN C MISC-P1052-B2-LH | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070135 | SO6001-EJ1E-TDS-01600001-001-002 | 016-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 016C1640 MEROX REACTOR TRAIN C MISC-P1052-B2-LH | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070135 | SO6001-EJ1E-TDS-01600001-001-003 | 016-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 016C1640 MEROX REACTOR TRAIN C MISC-P1052-B2-LH | A | 2018-05-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070136 | SO6001-EJ1E-TDS-04100002-001-001 | 041-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 041C001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070136 | SO6001-EJ1E-TDS-04100002-001-002 | 041-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 041C001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070136 | SO6001-EJ1E-TDS-04100002-001-003 | 041-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 041C001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070136 | SO6001-EJ1E-TDS-04100003-001-001 | 041-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 041C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070136 | SO6001-EJ1E-TDS-04100003-001-002 | 041-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 041C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070136 | SO6001-EJ1E-TDS-04100003-001-003 | 041-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 041C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070137 | SO6001-EJ1E-TDS-04200002-001-001 | 042-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 042C0001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070137 | SO6001-EJ1E-TDS-04200002-001-002 | 042-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 042C0001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070137 | SO6001-EJ1E-TDS-04200002-001-003 | 042-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 042C0001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070137 | SO6001-EJ1E-TDS-04200003-001-001 | 042-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 042C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070137 | SO6001-EJ1E-TDS-04200003-001-002 | 042-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 042C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070137 | SO6001-EJ1E-TDS-04200003-001-003 | 042-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 042C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070138 | SO6001-EJ1E-TDS-04300002-001-001 | 043-C-GAD-00001-001 | MECHANICAL DATA SHEET 043C0001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070138 | SO6001-EJ1E-TDS-04300002-001-002 | 043-C-GAD-00001-002 | MECHANICAL DATA SHEET 043C0001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070138 | SO6001-EJ1E-TDS-04300002-001-003 | 043-C-GAD-00001-003 | MECHANICAL DATA SHEET 043C0001R NO.1 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070138 | SO6001-EJ1E-TDS-04300003-001-001 | 043-C-GAD-00002-001 | MECHANICAL DATA SHEET 043C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070138 | SO6001-EJ1E-TDS-04300003-001-002 | 043-C-GAD-00002-002 | MECHANICAL DATA SHEET 043C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070138 | SO6001-EJ1E-TDS-04300003-001-003 | 043-C-GAD-00002-003 | MECHANICAL DATA SHEET 043C0002R NO.2 CONVERTER | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070139 | SO6001-EJ1E-TDS-04400008-001-001 | 044-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 044C0001R TAIL GAS REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070139 | SO6001-EJ1E-TDS-04400008-001-002 | 044-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 044C0001RTAIL GAS REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070139 | SO6001-EJ1E-TDS-04400008-001-003 | 044-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 044C0001R TAIL GAS REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070140 | SO6001-EJ1E-TDS-04500008-001-001 | 045-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 045C0001R TAIL GAS REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070140 | SO6001-EJ1E-TDS-04500008-001-002 | 045-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 045C0001R TAIL GAS REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070140 | SO6001-EJ1E-TDS-04500008-001-003 | 045-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 045C0001R TAIL GAS REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800002-001-001 | 098-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 098C0001R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800002-001-002 | 098-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 098C0001R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800002-001-003 | 098-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 098C0001R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800003-001-001 | 098-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 098C0002R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800003-001-002 | 098-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 098C0002R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800003-001-003 | 098-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 098C0002R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800004-001-001 | 098-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 098C0003R HIGH TEMPERATURE SHIFT REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800004-001-002 | 098-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 098C0003R HIGH TEMPERATURE SHIFT REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070141 | SO6001-EJ1E-TDS-09800004-001-003 | 098-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 098C0003R HIGH TEMPERATURE SHIFT REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900002-001-001 | 099-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 099C0001R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900002-001-002 | 099-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 099C0001R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900002-001-003 | 099-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 099C0001R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900003-001-001 | 099-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 099C0002R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900003-001-002 | 099-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 099C0002R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900003-001-003 | 099-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 099C0002R ZINC OXIDE DRUM | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900004-001-001 | 099-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 099C0003R HIGH TEMPERATURE SHIFT REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900004-001-002 | 099-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 099C0003R HIGH TEMPERATURE SHIFT REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070142 | SO6001-EJ1E-TDS-09900004-001-003 | 099-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 099C0003R HIGH TEMPERATURE SHIFT REACTOR | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070143 | SO6001-EJ2E-TDS-34120001-001 | 341-K-DAT-00001-001 | DATASHEET FOR INTEGRALLY GEARED CENTRIFUGAL COMPRESSORS 341K 3415 A-B-C-D AIR COMPRESSORS | B | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070143 | SO6001-EJ2E-TDS-34120002-001 | 341-K-DAT-00002-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES 341T3410 A-B AIR COMPRESSOR STEAM TURBINES | A | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070144 | SO6001-EJ2E-TDS-34100001-001 | 341-S-DAT-00001-001 | DATASHEET FOR AIR DRYERS PACKAGE | B | 2018-05-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-10 | CLASS 2
CON-BMP-TRA-070145 | SO6001-ES0B-PHL-01600001-001 | 016-A-BOD-00001-001 | PROCESS DESIGN BASIS KEROSENE MEROX UNIT (UNIT 016) | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 |  |  | CLASS 1
CON-BMP-TRA-070146 | 076551C-000S-MR-4111-001 | 000-S-MRQ-80007-001 | MATERIAL REQUISITION FOR HYDROGEN PSA UNIT | A | 2018-05-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-14 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 1
CON-BMP-TRA-070147 | SO6001-EJ1E-TDS-04100011-001 | 041-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070147 | SO6001-EJ1E-TDS-04100012-001 | 041-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070147 | SO6001-EJ1E-TDS-04100013-001 | 041-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070148 | SO6001-EJ1E-TDS-04200011-001 | 042-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 042E0005 N. 1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070148 | SO6001-EJ1E-TDS-04200012-001 | 042-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 042E0006 N. 2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070148 | SO6001-EJ1E-TDS-04200013-001 | 042-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 042E0007 COMBUSTION PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070149 | SO6001-EJ1E-TDS-04300011-001 | 043-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070149 | SO6001-EJ1E-TDS-04300012-001 | 043-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E0006 NO. 2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070149 | SO6001-EJ1E-TDS-04300013-001 | 043-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E0006 NO. 2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070150 | SO6001-EJ1E-TDS-04400013-001 | 044-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070151 | SO6001-EJ1E-TDS-04500010-001 | 045-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 045E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070152 | SO6001-EJ1E-TDS-04600004-001 | 046-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 046E0003 STRIPPED WATER TRIM COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070153 | SO6001-EJ1E-TDS-04700004-001 | 047-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 047E0003 STRIPPED WATER TRIM COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070154 | SO6001-EJ1E-TDS-08800002-001 | 088-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 088E3601A FEED/BOTTOMS EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070155 | SO6001-EJ1E-TDS-09800011-001 | 098-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 098E0007 A/B BLOWDOWN COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070156 | SO6001-EJ1E-TDS-09900011-001 | 099-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 099E007A/B BLOWDOWN COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070157 | SO6001-EJ1E-TDS-31000002-001 | 310-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 310E0001 BLOWDOWN COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070158 | SO6001-EJ1E-TDS-31100002-001 | 311-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 311E0001 BLOWDOWN COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100011-002-001 | 041-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 041E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100011-002-002 | 041-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 041E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100011-002-003 | 041-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 041E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100011-002-004 | 041-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 041E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100011-002-005 | 041-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 041E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100012-002-001 | 041-E-GAD-00002-001 | MECHANICAL DATA SHEET FOR 041E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100012-002-002 | 041-E-GAD-00002-002 | MECHANICAL DATA SHEET FOR 041E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100012-002-003 | 041-E-GAD-00002-003 | MECHANICAL DATA SHEET FOR 041E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100012-002-004 | 041-E-GAD-00002-004 | MECHANICAL DATA SHEET FOR 041E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100012-002-005 | 041-E-GAD-00002-005 | MECHANICAL DATA SHEET FOR 041E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100013-002-001 | 041-E-GAD-00003-001 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100013-002-002 | 041-E-GAD-00003-002 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100013-002-003 | 041-E-GAD-00003-003 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100013-002-004 | 041-E-GAD-00003-004 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070159 | SO6001-EJ1E-TDS-04100013-002-005 | 041-E-GAD-00003-005 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200011-002-001 | 042-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 042E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200011-002-002 | 042-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 042E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200011-002-003 | 042-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 042E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200011-002-004 | 042-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 042E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200011-002-005 | 042-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 042E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200012-002-001 | 042-E-GAD-00002-001 | MECHANICAL DATA SHEET FOR 042E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200012-002-002 | 042-E-GAD-00002-002 | MECHANICAL DATA SHEET FOR 042E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200012-002-003 | 042-E-GAD-00002-003 | MECHANICAL DATA SHEET FOR 042E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200012-002-004 | 042-E-GAD-00002-004 | MECHANICAL DATA SHEET FOR 042E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200012-002-005 | 042-E-GAD-00002-005 | MECHANICAL DATA SHEET FOR 042E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200013-002-001 | 042-E-GAD-00003-001 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200013-002-002 | 042-E-GAD-00003-002 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200013-002-003 | 042-E-GAD-00003-003 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200013-002-004 | 042-E-GAD-00003-004 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070160 | SO6001-EJ1E-TDS-04200013-002-005 | 042-E-GAD-00003-005 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300011-002-001 | 043-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 043E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300011-002-002 | 043-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 043E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300011-002-003 | 043-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 043E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300011-002-004 | 043-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 043E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300011-002-005 | 043-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 043E0005 NO.1 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300012-002-001 | 043-E-GAD-00002-001 | MECHANICAL DATA SHEET FOR 043E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300012-002-002 | 043-E-GAD-00002-002 | MECHANICAL DATA SHEET FOR 043E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300012-002-003 | 043-E-GAD-00002-003 | MECHANICAL DATA SHEET FOR 043E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300012-002-004 | 043-E-GAD-00002-004 | MECHANICAL DATA SHEET FOR 043E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300012-002-005 | 043-E-GAD-00002-005 | MECHANICAL DATA SHEET FOR 043E0006 NO.2 REHEAT EXCHANGER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300013-002-001 | 043-E-GAD-00003-001 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300013-002-002 | 043-E-GAD-00003-002 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300013-002-003 | 043-E-GAD-00003-003 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300013-002-004 | 043-E-GAD-00003-004 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070161 | SO6001-EJ1E-TDS-04300013-002-005 | 043-E-GAD-00003-005 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070162 | SO6001-EJ1E-TDS-04400013-002-001 | 044-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070162 | SO6001-EJ1E-TDS-04400013-002-002 | 044-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070162 | SO6001-EJ1E-TDS-04400013-002-003 | 044-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070162 | SO6001-EJ1E-TDS-04400013-002-004 | 044-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070162 | SO6001-EJ1E-TDS-04400013-002-005 | 044-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070163 | SO6001-EJ1E-TDS-04500010-001-001 | 045-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070163 | SO6001-EJ1E-TDS-04500010-001-002 | 045-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070163 | SO6001-EJ1E-TDS-04500010-001-003 | 045-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070163 | SO6001-EJ1E-TDS-04500010-001-004 | 045-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070163 | SO6001-EJ1E-TDS-04500010-001-005 | 045-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070164 | SO6001-EJ1E-TDS-04600004-002-001 | 046-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 046E0003 STRIPPED WATER TRIM COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070164 | SO6001-EJ1E-TDS-04600004-002-002 | 046-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 046E0003 STRIPPED WATER TRIM COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070164 | SO6001-EJ1E-TDS-04600004-002-003 | 046-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 046E0003 STRIPPED WATER TRIM COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070164 | SO6001-EJ1E-TDS-04600004-002-004 | 046-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 046E0003 STRIPPED WATER TRIM COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070164 | SO6001-EJ1E-TDS-04600004-002-005 | 046-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 046E0003 STRIPPED WATER TRIM COOLER | A | 2018-05-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070165 | SO6001-EJ1E-TDS-04700004-002-001 | 047-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 047E0003 STRIPPED WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070165 | SO6001-EJ1E-TDS-04700004-002-002 | 047-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 047E0003 STRIPPED WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070165 | SO6001-EJ1E-TDS-04700004-002-003 | 047-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 047E0003 STRIPPED WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070165 | SO6001-EJ1E-TDS-04700004-002-004 | 047-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 047E0003 STRIPPED WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070165 | SO6001-EJ1E-TDS-04700004-002-005 | 047-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 047E0003 STRIPPED WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070166 | SO6001-EJ1E-TDS-08800002-002-001 | 088-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 088E3601A FEED/BOTTOMS EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070166 | SO6001-EJ1E-TDS-08800002-002-002 | 088-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 088E3601A FEED/BOTTOMS EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070166 | SO6001-EJ1E-TDS-08800002-002-003 | 088-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 088E3601A FEED/BOTTOMS EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070166 | SO6001-EJ1E-TDS-08800002-002-004 | 088-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 088E3601A FEED/BOTTOMS EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070166 | SO6001-EJ1E-TDS-08800002-002-005 | 088-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 088E3601A FEED/BOTTOMS EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070167 | SO6001-EJ1E-TDS-09800011-002-001 | 098-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 098E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070167 | SO6001-EJ1E-TDS-09800011-002-002 | 098-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 098E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070167 | SO6001-EJ1E-TDS-09800011-002-003 | 098-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 098E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070167 | SO6001-EJ1E-TDS-09800011-002-004 | 098-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 098E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070167 | SO6001-EJ1E-TDS-09800011-002-005 | 098-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 098E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070168 | SO6001-EJ1E-TDS-09900011-002-001 | 099-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 099E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070168 | SO6001-EJ1E-TDS-09900011-002-002 | 099-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 099E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070168 | SO6001-EJ1E-TDS-09900011-002-003 | 099-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 099E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070168 | SO6001-EJ1E-TDS-09900011-002-004 | 099-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 099E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070168 | SO6001-EJ1E-TDS-09900011-002-005 | 099-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 099E0007 A/B BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070169 | SO6001-EJ1E-TDS-31000002-002-001 | 310-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 310E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070169 | SO6001-EJ1E-TDS-31000002-002-002 | 310-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 310E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070169 | SO6001-EJ1E-TDS-31000002-002-003 | 310-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 310E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070169 | SO6001-EJ1E-TDS-31000002-002-004 | 310-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 310E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070169 | SO6001-EJ1E-TDS-31000002-002-005 | 310-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 310E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-11 | CLASS 2
CON-BMP-TRA-070170 | SO6001-EJ1E-TDS-31100002-002-001 | 311-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 311E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070170 | SO6001-EJ1E-TDS-31100002-002-002 | 311-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 311E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070170 | SO6001-EJ1E-TDS-31100002-002-003 | 311-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 311E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070170 | SO6001-EJ1E-TDS-31100002-002-004 | 311-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 311E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070170 | SO6001-EJ1E-TDS-31100002-002-005 | 311-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 311E001 BLOWDOWN COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-15 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070171 | SO6001-EJ1E-TDS-04100014-001 | 041-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 041E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070172 | SO6001-EJ1E-TDS-04200014-001 | 042-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 042E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070173 | SO6001-EJ1E-TDS-04300014-001 | 043-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 043E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070174 | SO6001-EJ1E-TDS-04400014-001 | 044-E-DAT-00009-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070175 | SO6001-EJ1E-TDS-04500011-001 | 045-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 045E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070176 | SO6001-EJ1E-TDS-04800006-001 | 048-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070177 | SO6001-EJ1E-TDS-04900004-001 | 049-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070178 | SO6001-EJ1E-TDS-04100014-002-001 | 041-E-GAD-00004-001 | MECHANICAL DATA SHEET FOR 041E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070178 | SO6001-EJ1E-TDS-04100014-002-002 | 041-E-GAD-00004-002 | MECHANICAL DATA SHEET FOR 041E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070178 | SO6001-EJ1E-TDS-04100014-002-003 | 041-E-GAD-00004-003 | MECHANICAL DATA SHEET FOR 041E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070178 | SO6001-EJ1E-TDS-04100014-002-004 | 041-E-GAD-00004-004 | MECHANICAL DATA SHEET FOR 041E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070178 | SO6001-EJ1E-TDS-04100014-002-005 | 041-E-GAD-00004-005 | MECHANICAL DATA SHEET FOR 041E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070179 | SO6001-EJ1E-TDS-04200014-002-001 | 042-E-GAD-00004-001 | MECHANICAL DATA SHEET FOR 042E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070179 | SO6001-EJ1E-TDS-04200014-002-002 | 042-E-GAD-00004-002 | MECHANICAL DATA SHEET FOR 042E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070179 | SO6001-EJ1E-TDS-04200014-002-003 | 042-E-GAD-00004-003 | MECHANICAL DATA SHEET FOR 042E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070179 | SO6001-EJ1E-TDS-04200014-002-004 | 042-E-GAD-00004-004 | MECHANICAL DATA SHEET FOR 042E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070179 | SO6001-EJ1E-TDS-04200014-002-005 | 042-E-GAD-00004-005 | MECHANICAL DATA SHEET FOR 042E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070180 | SO6001-EJ1E-TDS-04300014-002-001 | 043-E-GAD-00004-001 | MECHANICAL DATA SHEET FOR 043E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070180 | SO6001-EJ1E-TDS-04300014-002-002 | 043-E-GAD-00004-002 | MECHANICAL DATA SHEET FOR 043E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070180 | SO6001-EJ1E-TDS-04300014-002-003 | 043-E-GAD-00004-003 | MECHANICAL DATA SHEET FOR 043E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070180 | SO6001-EJ1E-TDS-04300014-002-004 | 043-E-GAD-00004-004 | MECHANICAL DATA SHEET FOR 043E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070180 | SO6001-EJ1E-TDS-04300014-002-005 | 043-E-GAD-00004-005 | MECHANICAL DATA SHEET FOR 043E0008 ACID GAS PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070181 | SO6001-EJ1E-TDS-04400014-002-001 | 044-E-GAD-00002-001 | MECHANICAL DATA SHEET FOR 044E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070181 | SO6001-EJ1E-TDS-04400014-002-002 | 044-E-GAD-00002-002 | MECHANICAL DATA SHEET FOR 044E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070181 | SO6001-EJ1E-TDS-04400014-002-003 | 044-E-GAD-00002-003 | MECHANICAL DATA SHEET FOR 044E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070181 | SO6001-EJ1E-TDS-04400014-002-004 | 044-E-GAD-00002-004 | MECHANICAL DATA SHEET FOR 044E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070181 | SO6001-EJ1E-TDS-04400014-002-005 | 044-E-GAD-00002-005 | MECHANICAL DATA SHEET FOR 044E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070182 | SO6001-EJ1E-TDS-04500011-002-001 | 045-E-GAD-00002-001 | MECHANICAL DATA SHEET FOR 045E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070182 | SO6001-EJ1E-TDS-04500011-002-002 | 045-E-GAD-00002-002 | MECHANICAL DATA SHEET FOR 045E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070182 | SO6001-EJ1E-TDS-04500011-002-003 | 045-E-GAD-00002-003 | MECHANICAL DATA SHEET FOR 045E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070182 | SO6001-EJ1E-TDS-04500011-002-004 | 045-E-GAD-00002-004 | MECHANICAL DATA SHEET FOR 045E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070182 | SO6001-EJ1E-TDS-04500011-002-005 | 045-E-GAD-00002-005 | MECHANICAL DATA SHEET FOR 045E0009 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070183 | SO6001-EJ1E-TDS-04800006-002-001 | 048-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070183 | SO6001-EJ1E-TDS-04800006-002-002 | 048-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070183 | SO6001-EJ1E-TDS-04800006-002-003 | 048-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070183 | SO6001-EJ1E-TDS-04800006-002-004 | 048-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070183 | SO6001-EJ1E-TDS-04800006-002-005 | 048-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-13 | CLASS 2
CON-BMP-TRA-070184 | SO6001-EJ1E-TDS-04900004-002-001 | 049-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070184 | SO6001-EJ1E-TDS-04900004-002-002 | 049-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070184 | SO6001-EJ1E-TDS-04900004-002-003 | 049-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070184 | SO6001-EJ1E-TDS-04900004-002-004 | 049-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070184 | SO6001-EJ1E-TDS-04900004-002-005 | 049-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 3 - REVIEWED WITH COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070185 | SO6001-EJ1E-TDS-03600005-001 | 036-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 036E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070185 | SO6001-EJ1E-TDS-03600006-001 | 036-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 036E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070186 | SO6001-EJ1E-TDS-03700005-001 | 037-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 037E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070186 | SO6001-EJ1E-TDS-03700006-001 | 037-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 037E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070187 | SO6001-EJ1E-TDS-04400015-001 | 044-E-DAT-00010-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070187 | SO6001-EJ1E-TDS-04400016-001 | 044-E-DAT-00011-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0006A/B REGENERATOR REBOILERS | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070187 | SO6001-EJ1E-TDS-04400017-001 | 044-E-DAT-00012-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0004A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070188 | SO6001-EJ1E-TDS-04500012-001 | 045-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 045E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070188 | SO6001-EJ1E-TDS-04500013-001 | 045-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 045E0006A/B REGENERATOR REBOILERS | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070188 | SO6001-EJ1E-TDS-04500014-001 | 045-E-DAT-00009-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 045E0004A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-12 | CLASS 2
CON-BMP-TRA-070189 | SO6001-EJ1E-TDS-04600005-001 | 046-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 046E0001A/B FEED/BOTTOM EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070189 | SO6001-EJ1E-TDS-04600006-001 | 046-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 046E0002A/B STRIPPER REBOILERS | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070190 | SO6001-EJ1E-TDS-04700005-001 | 047-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 047E0001A/B FEED/BOTTOM EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070190 | SO6001-EJ1E-TDS-04700006-001 | 047-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 047E0002A/B STRIPPER REBOILERS | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070191 | SO6001-EJ1E-TDS-04800007-001 | 048-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 048E0001A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070191 | SO6001-EJ1E-TDS-04800008-001 | 048-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 048E0002A/B AMINE REGENERATOR REBOILERS | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070192 | SO6001-EJ1E-TDS-04900005-001 | 049-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 049E0001A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070192 | SO6001-EJ1E-TDS-04900006-001 | 049-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 049E0002A/B AMINE REGENERATOR REBOILERS | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070193 | SO6001-EJ1E-TDS-09800012-001 | 098-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 098E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070193 | SO6001-EJ1E-TDS-09800013-001 | 098-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 098E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070193 | SO6001-EJ1E-TDS-09800014-001 | 098-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 098E0004 DEAERATOR WATER PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070193 | SO6001-EJ1E-TDS-09800015-001 | 098-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 098E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070194 | SO6001-EJ1E-TDS-09900012-001 | 099-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 099E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070194 | SO6001-EJ1E-TDS-09900013-001 | 099-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 099E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070194 | SO6001-EJ1E-TDS-09900014-001 | 099-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 099E0004 DEAERATOR WATER PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070194 | SO6001-EJ1E-TDS-09900015-001 | 099-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 099E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-26 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600005-002-001 | 036-E-GAD-00001-001 | 036E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600005-002-002 | 036-E-GAD-00001-002 | 036E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600005-002-003 | 036-E-GAD-00001-003 | 036E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600005-002-004 | 036-E-GAD-00001-004 | 036E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600005-002-005 | 036-E-GAD-00001-005 | 036E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600006-002-001 | 036-E-GAD-00002-001 | 036E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600006-002-002 | 036-E-GAD-00002-002 | 036E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600006-002-003 | 036-E-GAD-00002-003 | 036E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600006-002-004 | 036-E-GAD-00002-004 | 036E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070195 | SO6001-EJ1E-TDS-03600006-002-005 | 036-E-GAD-00002-005 | 036E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700005-002-001 | 037-E-GAD-00001-001 | 037E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700005-002-002 | 037-E-GAD-00001-002 | 037E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700005-002-003 | 037-E-GAD-00001-003 | 037E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700005-002-004 | 037-E-GAD-00001-004 | 037E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700005-002-005 | 037-E-GAD-00001-005 | 037E0001 LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700006-002-001 | 037-E-GAD-00002-001 | 037E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700006-002-002 | 037-E-GAD-00002-002 | 037E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700006-002-003 | 037-E-GAD-00002-003 | 037E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700006-002-004 | 037-E-GAD-00002-004 | 037E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070196 | SO6001-EJ1E-TDS-03700006-002-005 | 037-E-GAD-00002-005 | 037E0002 REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400015-002-001 | 044-E-GAD-00003-001 | 044E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400015-002-002 | 044-E-GAD-00003-002 | 044E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400015-002-003 | 044-E-GAD-00003-003 | 044E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400015-002-004 | 044-E-GAD-00003-004 | 044E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400015-002-005 | 044-E-GAD-00003-005 | 044E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400015-002-006 | 044-E-GAD-00003-006 | 044E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400016-002-001 | 044-E-GAD-00004-001 | 044E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400016-002-002 | 044-E-GAD-00004-002 | 044E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400016-002-003 | 044-E-GAD-00004-003 | 044E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400016-002-004 | 044-E-GAD-00004-004 | 044E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400016-002-005 | 044-E-GAD-00004-005 | 044E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400017-002-001 | 044-E-GAD-00005-001 | 044E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400017-002-002 | 044-E-GAD-00005-002 | 044E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400017-002-003 | 044-E-GAD-00005-003 | 044E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400017-002-004 | 044-E-GAD-00005-004 | 044E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070197 | SO6001-EJ1E-TDS-04400017-002-005 | 044-E-GAD-00005-005 | 044E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500012-002-001 | 045-E-GAD-00003-001 | 045E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500012-002-002 | 045-E-GAD-00003-002 | 045E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500012-002-003 | 045-E-GAD-00003-003 | 045E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500012-002-004 | 045-E-GAD-00003-004 | 045E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500012-002-005 | 045-E-GAD-00003-005 | 045E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500012-002-006 | 045-E-GAD-00003-006 | 045E0005A/B/C LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500013-002-001 | 045-E-GAD-00004-001 | 045E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500013-002-002 | 045-E-GAD-00004-002 | 045E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500013-002-003 | 045-E-GAD-00004-003 | 045E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500013-002-004 | 045-E-GAD-00004-004 | 045E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500013-002-005 | 045-E-GAD-00004-005 | 045E0006 A/B REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500014-002-001 | 045-E-GAD-00005-001 | 045E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500014-002-002 | 045-E-GAD-00005-002 | 045E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500014-002-003 | 045-E-GAD-00005-003 | 045E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500014-002-004 | 045-E-GAD-00005-004 | 045E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070198 | SO6001-EJ1E-TDS-04500014-002-005 | 045-E-GAD-00005-005 | 045E0004 A/B QUENCH WATER TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600005-002-001 | 046-E-GAD-00002-001 | 046E0001 A/B FEED / BOTTOM EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600005-002-002 | 046-E-GAD-00002-002 | 046E0001 A/B FEED / BOTTOM EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600005-002-003 | 046-E-GAD-00002-003 | 046E0001 A/B FEED / BOTTOM EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600005-002-004 | 046-E-GAD-00002-004 | 046E0001 A/B FEED / BOTTOM EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600005-002-005 | 046-E-GAD-00002-005 | 046E0001 A/B FEED / BOTTOM EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600006-002-001 | 046-E-GAD-00003-001 | 046E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600006-002-002 | 046-E-GAD-00003-002 | 046E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600006-002-003 | 046-E-GAD-00003-003 | 046E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600006-002-004 | 046-E-GAD-00003-004 | 046E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070199 | SO6001-EJ1E-TDS-04600006-002-005 | 046-E-GAD-00003-005 | 046E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070200 | SO6001-EJ1E-TDS-04700006-002-001 | 047-E-GAD-00003-001 | 047E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070200 | SO6001-EJ1E-TDS-04700006-002-002 | 047-E-GAD-00003-002 | 047E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070200 | SO6001-EJ1E-TDS-04700006-002-003 | 047-E-GAD-00003-003 | 047E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070200 | SO6001-EJ1E-TDS-04700006-002-004 | 047-E-GAD-00003-004 | 047E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070200 | SO6001-EJ1E-TDS-04700006-002-005 | 047-E-GAD-00003-005 | 047E0002 A/B STRIPPER REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800007-002-001 | 048-E-GAD-00002-001 | 048E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800007-002-002 | 048-E-GAD-00002-002 | 048E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800007-002-003 | 048-E-GAD-00002-003 | 048E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800007-002-004 | 048-E-GAD-00002-004 | 048E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800007-002-005 | 048-E-GAD-00002-005 | 048E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800008-002-001 | 048-E-GAD-00003-001 | 048E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800008-002-002 | 048-E-GAD-00003-002 | 048E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800008-002-003 | 048-E-GAD-00003-003 | 048E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800008-002-004 | 048-E-GAD-00003-004 | 048E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070201 | SO6001-EJ1E-TDS-04800008-002-005 | 048-E-GAD-00003-005 | 048E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-20 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900005-002-001 | 049-E-GAD-00002-001 | 049E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900005-002-002 | 049-E-GAD-00002-002 | 049E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900005-002-003 | 049-E-GAD-00002-003 | 049E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900005-002-004 | 049-E-GAD-00002-004 | 049E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900005-002-005 | 049-E-GAD-00002-005 | 049E0001 A/B LEAN/RICH AMINE EXCHANGER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900006-002-001 | 049-E-GAD-00003-001 | 049E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900006-002-002 | 049-E-GAD-00003-002 | 049E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900006-002-003 | 049-E-GAD-00003-003 | 049E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900006-002-004 | 049-E-GAD-00003-004 | 049E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070202 | SO6001-EJ1E-TDS-04900006-002-005 | 049-E-GAD-00003-005 | 049E0002 A/B AMINE REGENERATOR REBOILER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800012-002-001 | 098-E-GAD-00002-001 | 098E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800012-002-002 | 098-E-GAD-00002-002 | 098E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800012-002-003 | 098-E-GAD-00002-003 | 098E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800012-002-004 | 098-E-GAD-00002-004 | 098E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800012-002-005 | 098-E-GAD-00002-005 | 098E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800013-002-001 | 098-E-GAD-00003-001 | 098E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800013-002-002 | 098-E-GAD-00003-002 | 098E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800013-002-003 | 098-E-GAD-00003-003 | 098E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800013-002-004 | 098-E-GAD-00003-004 | 098E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800013-002-005 | 098-E-GAD-00003-005 | 098E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800014-002-001 | 098-E-GAD-00004-001 | 098E0004 DEAERATOR WATER PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800014-002-002 | 098-E-GAD-00004-002 | 098E0004 DEAERATOR WATER PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800014-002-003 | 098-E-GAD-00004-003 | 098E0004 DEAERATOR WATER PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800014-002-004 | 098-E-GAD-00004-004 | 098E0004 DEAERATOR WATER PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800014-002-005 | 098-E-GAD-00004-005 | 098E0004 DEAERATOR WATER PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800015-002-001 | 098-E-GAD-00005-001 | 098E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800015-002-002 | 098-E-GAD-00005-002 | 098E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800015-002-003 | 098-E-GAD-00005-003 | 098E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800015-002-004 | 098-E-GAD-00005-004 | 098E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070203 | SO6001-EJ1E-TDS-09800015-002-005 | 098-E-GAD-00005-005 | 098E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900012-002-001 | 099-E-GAD-00002-001 | 099E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900012-002-002 | 099-E-GAD-00002-002 | 099E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900012-002-003 | 099-E-GAD-00002-003 | 099E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900012-002-004 | 099-E-GAD-00002-004 | 099E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900012-002-005 | 099-E-GAD-00002-005 | 099E0002 FEED PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900013-002-001 | 099-E-GAD-00003-001 | 099E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900013-002-002 | 099-E-GAD-00003-002 | 099E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900013-002-003 | 099-E-GAD-00003-003 | 099E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900013-002-004 | 099-E-GAD-00003-004 | 099E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900013-002-005 | 099-E-GAD-00003-005 | 099E0003 BFW PREHEATER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900015-002-001 | 099-E-GAD-00005-001 | 099E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900015-002-002 | 099-E-GAD-00005-002 | 099E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900015-002-003 | 099-E-GAD-00005-003 | 099E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900015-002-004 | 099-E-GAD-00005-004 | 099E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070204 | SO6001-EJ1E-TDS-09900015-002-005 | 099-E-GAD-00005-005 | 099E0006 PROCESS GAS TRIM COOLER | A | 2018-06-01 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070205 | SO6001-EJ2E-TDS-37254002-001 | 372-S-DAT-54002-001 | SUPERS. BY 370-S-DAT-00002-001 - DUTY SPECIFICATION FOR CONDENSATE POLISHING MIXED BED PACKAGE (372U0022) | A | 2018-06-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070205 | SO6001-EJ2E-TDS-37254003-001 | 372-S-DAT-54003-001 | SUPERS. BY 370-S-DAT-00003-001 - DUTY SPECIFICATION FOR FED POLISHING MIXED BED PACKAGE (372U0020) | A | 2018-06-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070206 | SO6001-EJ2E-TDS-01610002-001 | 016-G-DAT-00002-001 | DATA SHEET FOR 016P9604D CAUSTIC CIRCULATION PUMP | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070207 | SO6001-EJ2E-TDS-09410001-001 | 094-G-DAT-00001-001 | DATA SHEET FOR 094P0008A/B 2SHF FOUL WATER PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070207 | SO6001-EJ2E-TDS-09410002-001 | 094-G-DAT-00002-001 | DATA SHEET FOR 094P0009A/B 2SHF NEUTRALIZATION PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070208 | SO6001-EJ2E-TDS-31010001-001 | 310-G-DAT-00001-001 | DATA SHEET FOR 310P0001A/B BLOWDOWN PUMP | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070209 | SO6001-EJ2E-TDS-38210001-001 | 382-G-DAT-00001-001 | DATA SHEET FOR 382P3888A/B WORKSTATION BUILDING SANITARY PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070209 | SO6001-EJ2E-TDS-38210002-001 | 382-G-DAT-00002-001 | DATA SHEET FOR 382P3889A/B/C FINAL SANITARY PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070209 | SO6001-EJ2E-TDS-38210003-001 | 382-G-DAT-00003-001 | DATA SHEET FOR 382P3890A/B #3 SULPHUR PLANT TOILET SANITARY PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070209 | SO6001-EJ2E-TDS-38210004-001 | 382-G-DAT-00004-001 | DATA SHEET FOR 382P3891A/B UTILITIES TOILET SANITARY PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070210 | SO6001-EJ2E-TDS-04120001-001 | 041-K-DAT-00001-001 | DATA SHEET FOR COMBUSTION AIR BLOWERS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 3 - REVIEWED WITH COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070211 | SO6001-EJ2E-TDS-09420001-001 | 094-K-DAT-00001-001 | DATA SHEET FOR 2SHF EXHAUST FAN SULPHUR STORAGE TANK | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 2
CON-BMP-TRA-070212 | SO6001-EJ2E-TDS-09820002-001 | 098-K-DAT-00002-001 | DATA SHEET FOR I.D. FAN | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 2
CON-BMP-TRA-070213 | SO6001-EJ2E-TDS-09920002-001 | 099-K-DAT-00002-001 | DATA SHEET FOR I.D. FAN | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070214 | SO6001-EJ2E-TDS-03610006-001 | 036-G-DAT-00006-001 | DATA SHEET FOR 036P0006A/B AMINE SUMP PUMP | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070215 | SO6001-EJ2E-TDS-04410007-001 | 044-G-DAT-00007-001 | DATA SHEET FOR 044P0007A/B AMINE SUMP PUMP | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070216 | SO6001-EJ2E-TDS-04610006-001 | 046-G-DAT-00006-001 | DATA SHEET FOR 046P0006A/B SOUR WATER SUMP PUMP | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070217 | SO6001-EJ2E-TDS-04810005-001 | 048-G-DAT-00005-001 | DATA SHEET FOR 048P0005A/B AMINE SUMP PUMP | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070217 | SO6001-EJ2E-TDS-04810008-001 | 048-G-DAT-00008-001 | DATA SHEET FOR 048P0008A/B NO3 SULPHUR PLANT SLOP OIL SUMP PUMP | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 2
CON-BMP-TRA-070218 | SO6001-EJ2E-TDS-37254015-001 | 372-G-DAT-54015-001 | DATA SHEET FOR 372P3736A/B ACTIVATED CARBON FILTERS BACKWASH PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070219 | SO6001-EJ2E-TDS-00510001-001 | 005-G-DAT-00001-001 | DATA SHEET FOR 005P5040A/B C3 TRANSFER PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070219 | SO6001-EJ2E-TDS-00510002-001 | 005-G-DAT-00002-001 | DATA SHEET FOR 005P5041A/B C3 EXPORT PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070219 | SO6001-EJ2E-TDS-00510003-001 | 005-G-DAT-00003-001 | DATA SHEET FOR 005P5042A/B C4 TRANSFER PUMPS (TO EXISTING LPG FACILITIES) | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070219 | SO6001-EJ2E-TDS-00510004-001 | 005-G-DAT-00004-001 | DATA SHEET FOR 005P5043A/B C4 EXPORT PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070219 | SO6001-EJ2E-TDS-00510005-001 | 005-G-DAT-00005-001 | DATA SHEET FOR C4 005P5044A/B INJECTION PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070219 | SO6001-EJ2E-TDS-00510006-001 | 005-G-DAT-00006-001 | DATA SHEET FOR 005P5045A/B OFFSPEC LPG PUMPS | A | 2018-06-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 2
CON-BMP-TRA-070220 | SO6001-ES0D-PFD-03600001-001 | 036-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KHUFF GAS TREATMENT UNIT (2BAGRU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-070220 | SO6001-ES0D-PFD-03600001-002 | 036-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (2BAGRU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-070220 | SO6001-ES0D-PFD-03600001-003 | 036-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (2BAGRU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 1
CON-BMP-TRA-070221 | SO6001-ES0D-PFD-03700001-001 | 037-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KHUFF GAS TREATMENT UNIT (3BAGRU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 1
CON-BMP-TRA-070221 | SO6001-ES0D-PFD-03700001-002 | 037-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (3BAGRU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 1
CON-BMP-TRA-070221 | SO6001-ES0D-PFD-03700001-003 | 037-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (3BAGRU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 1
CON-BMP-TRA-070222 | SO6001-ES0D-PFD-04800001-001 | 048-A-PFD-00001-001 | PROCESS FLOW DIAGRAM AMINE REGENERATION (2ARU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 1
CON-BMP-TRA-070222 | SO6001-ES0D-PFD-04800001-002 | 048-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE REGENERATION (2ARU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 1
CON-BMP-TRA-070222 | SO6001-ES0D-PFD-04800001-003 | 048-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (2ARU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 1
CON-BMP-TRA-070222 | SO6001-ES0D-PFD-04800001-004 | 048-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (2ARU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 1
CON-BMP-TRA-070223 | SO6001-ES0D-PFD-04900001-001 | 049-A-PFD-00001-001 | PROCESS FLOW DIAGRAM AMINE REGENERATION (3ARU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070223 | SO6001-ES0D-PFD-04900001-002 | 049-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3ARU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070223 | SO6001-ES0D-PFD-04900001-003 | 049-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (3ARU) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070224 | SO6001-ES0D-PFD-08300001-001 | 083-A-PFD-00001-001 | PROCESS FLOW DIAGRAM NITROGEN SYSTEM BLOCK 1N2 | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-14 | CLASS 1
CON-BMP-TRA-070225 | SO6001-ES0D-PFD-08800001-001 | 088-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KERO RERUN UNIT (EX BRB-22960 SH 01) | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-070225 | SO6001-ES0D-PFD-08800001-002 | 088-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-19 | CLASS 1
CON-BMP-TRA-070226 | SO6001-ES0D-PFD-37254001-001 | 372-A-PFD-54001-001 | PROCESS FLOW DIAGRAM FED STORAGE | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-070226 | SO6001-ES0D-PFD-37254001-010 | 372-A-PFD-54001-010 | PROCESS FLOW DIAGRAM DEMINERALIZED WATER STORAGE | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-070226 | SO6001-ES0D-PFD-37254001-011 | 372-A-PFD-54001-011 | PROCESS FLOW DIAGRAM DEAREATION AND BFW DISTRIBUTION | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-070226 | SO6001-ES0D-PFD-37254002-001 | 372-A-PFD-54002-001 | PROCESS FLOW DIAGRAM UTILITY WATER HEADER | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-070226 | SO6001-ES0D-PFD-37254002-002 | 372-A-PFD-54002-002 | PROCESS FLOW DIAGRAM DEMIN WATER HEADER | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-070226 | SO6001-ES0D-PFD-37254002-003 | 372-A-PFD-54002-003 | PROCESS FLOW DIAGRAM BFW HEADER | B | 2018-06-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-070227 | SO6001-EJ1E-TDS-04700005-002-001 | 047-E-GAD-00002-001 | MECHANICAL DATA SHEET FOR 047E0001 A-B FEED-BOTTOM EXCHANGER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070227 | SO6001-EJ1E-TDS-04700005-002-002 | 047-E-GAD-00002-002 | MECHANICAL DATA SHEET FOR 047E0001 A-B FEED-BOTTOM EXCHANGER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070227 | SO6001-EJ1E-TDS-04700005-002-003 | 047-E-GAD-00002-003 | MECHANICAL DATA SHEET FOR 047E0001 A-B FEED-BOTTOM EXCHANGER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070227 | SO6001-EJ1E-TDS-04700005-002-004 | 047-E-GAD-00002-004 | MECHANICAL DATA SHEET FOR 047E0001 A-B FEED-BOTTOM EXCHANGER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070227 | SO6001-EJ1E-TDS-04700005-002-005 | 047-E-GAD-00002-005 | MECHANICAL DATA SHEET FOR 047E0001 A-B FEED-BOTTOM EXCHANGER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070228 | SO6001-EJ1E-TDS-09900014-002-001 | 099-E-GAD-00004-001 | 099E0004 DEAERATOR WATER PREHEATER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070228 | SO6001-EJ1E-TDS-09900014-002-002 | 099-E-GAD-00004-002 | 099E0004 DEAERATOR WATER PREHEATER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070228 | SO6001-EJ1E-TDS-09900014-002-003 | 099-E-GAD-00004-003 | 099E0004 DEAERATOR WATER PREHEATER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070228 | SO6001-EJ1E-TDS-09900014-002-004 | 099-E-GAD-00004-004 | 099E0004 DEAERATOR WATER PREHEATER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070228 | SO6001-EJ1E-TDS-09900014-002-005 | 099-E-GAD-00004-005 | 099E0004 DEAERATOR WATER PREHEATER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-001 | 044-A-PFD-00001-001 | PROCESS FLOW DIAGRAM TAIL GAS REACTOR QUENCH COLUMN (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-002 | 044-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE ABSORBER REGENERATOR AND STORAGE (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-003 | 044-A-PFD-00001-003 | PROCESS FLOW DIAGRAM INCINERATOR (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-004 | 044-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HP STEAM AND CONDENSATE SECTION (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-005 | 044-A-PFD-00001-005 | PROCESS FLOW DIAGRAM LP STEAM AND BLOWDOWN SECTION (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-006 | 044-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-007 | 044-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-008 | 044-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-009 | 044-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070229 | SO6001-ES0D-PFD-04400001-010 | 044-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070230 | SO6001-ES0D-PFD-04500001-001 | 045-A-PFD-00001-001 | PROCESS FLOW DIAGRAM TAIL GAS REACTOR AND QUENCH COLUMN (4TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070230 | SO6001-ES0D-PFD-04500001-002 | 045-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE ABSORBER, REGENERATOR AND STORAGE (4TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070230 | SO6001-ES0D-PFD-04500001-003 | 045-A-PFD-00001-003 | PROCESS FLOW DIAGRAM INCINERATOR (4TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070230 | SO6001-ES0D-PFD-04500001-004 | 045-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (4TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070230 | SO6001-ES0D-PFD-04500001-005 | 045-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (4TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070230 | SO6001-ES0D-PFD-04500001-006 | 045-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (4TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070230 | SO6001-ES0D-PFD-04500001-007 | 045-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (4TGTU) | B | 2018-06-07 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 1
CON-BMP-TRA-070231 | SO6001-EJ1E-TDS-04400018-001 | 044-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0012 60 STEAM BLOWDOWN COOLER | A | 2018-06-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070232 | SO6001-EJ1E-TDS-37200008-001 | 372-E-DAT-55001-001 | PLATE AND FRAME HEAT EXCHANGER DATA SHEET FOR 372E0031 FED WATER COOLER | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070232 | SO6001-EJ1E-TDS-37200009-001 | 372-E-DAT-55002-001 | PLATE AND FRAME HEAT EXCHANGER DATA SHEET FOR 372E0032 FED WATER COOLER | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070232 | SO6001-EJ1E-TDS-37200010-001 | 372-E-DAT-55003-001 | PLATE AND FRAME HEAT EXCHANGER DATA SHEET FOR 372E0032 FED WATER COOLER | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070232 | SO6001-EJ1E-TDS-37200011-001 | 372-E-DAT-55004-001 | PLATE AND FRAME HEAT EXCHANGER DATA SHEET FOR 372E0034 RECOVERED CONDENSATE COOLER | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070233 | SO6001-ES0D-PFD-01600001-001 | 016-A-PFD-00001-001 | PROCESS FLOW DIAGRAM MEROX PROCESS UNIT - TRAIN A AND B | B | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-070233 | SO6001-ES0D-PFD-01600001-003 | 016-A-PFD-00001-003 | PROCESS FLOW DIAGRAM MEROX PROCESS UNIT - HEAT MATERIAL BALANCE | A | 2018-06-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-18 | CLASS 1
CON-BMP-TRA-070234 | SO6001-ES0D-MSD-03600001-001 | 036-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (2BAGRU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070234 | SO6001-ES0D-MSD-03600001-002 | 036-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (2BAGRU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070235 | SO6001-ES0D-MSD-03700001-001 | 037-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (3BAGRU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070235 | SO6001-ES0D-MSD-03700001-002 | 037-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (3BAGRU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070236 | SO6001-ES0D-MSD-04400001-001 | 044-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM TAIL GAS REACTOR AND DCC (3TGTU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070236 | SO6001-ES0D-MSD-04400001-002 | 044-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE ABSORBER REGENERATOR AND STORAGE (3TGTU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070236 | SO6001-ES0D-MSD-04400001-003 | 044-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM INCINERATOR (3TGTU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070236 | SO6001-ES0D-MSD-04400001-004 | 044-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM STEAM CONDENSATE AND BLOWDOWN SECTION (3TGTU & 4TGTU ) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070236 | SO6001-ES0D-MSD-04400001-005 | 044-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM UNIT (3TGTU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070236 | SO6001-ES0D-MSD-04400001-006 | 044-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM UNIT (3TGTU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070236 | SO6001-ES0D-MSD-04400001-007 | 044-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM UNIT (3TGTU & 4TGTU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070237 | SO6001-ES0D-MSD-04800001-001 | 048-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (2ARU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070237 | SO6001-ES0D-MSD-04800001-002 | 048-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (2ARU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070237 | SO6001-ES0D-MSD-04800001-003 | 048-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (2ARU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-22 | CLASS 2
CON-BMP-TRA-070238 | SO6001-ES0D-MSD-04900001-001 | 049-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (3ARU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070238 | SO6001-ES0D-MSD-04900001-002 | 049-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (3ARU) | B | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070239 | SO6001-EJ1E-TDS-09800016-001 | 098-E-DAT-00007-001 | PLATE AND SHELL HEAT EXCHANGER DATA SHEET FOR 098E00068 HP STRIPPER FEED EFFLUENT EXCHANGER | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070240 | SO6001-EJ1E-TDS-09900016-001 | 099-E-DAT-00007-001 | PLATE AND SHELL HEAT EXCHANGER DATA SHEET FOR 099E0008 HP STRIPPER FEED EFFLUENT EXCHANGER | A | 2018-06-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-21 | CLASS 2
CON-BMP-TRA-070241 | SO6001-EJ2E-TDS-01620001-001 | 016-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 016K9614D AIR COMPRESSOR SYSTEM | A | 2018-06-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-25 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-23 | CLASS 2
CON-BMP-TRA-070242 | 076551C-000S-MR-0610-005 | 000-E-MRQ-80004-001 | MATERIAL REQUISITION FOR SULPHUR CONDENSER | A | 2018-06-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-25 | CLASS 1
CON-BMP-TRA-070243 | 076551C-000S-MR-0511-001 | 000-C-MRQ-80006-001 | MATERIAL REQUISITION FOR C.S COLUMNS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070244 | SO6001-EJ1E-TDS-03600017-002-001 | 036-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 036D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070244 | SO6001-EJ1E-TDS-03600017-002-002 | 036-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 036D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070244 | SO6001-EJ1E-TDS-03600017-002-003 | 036-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 036D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070245 | SO6001-EJ1E-TDS-03700015-002-001 | 037-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 037D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070245 | SO6001-EJ1E-TDS-03700015-002-002 | 037-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 037D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070245 | SO6001-EJ1E-TDS-03700015-002-003 | 037-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 037D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070246 | SO6001-EJ1E-TDS-04400036-002-001 | 044-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 044D0001 LEAN AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070246 | SO6001-EJ1E-TDS-04400036-002-002 | 044-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 044D0001 LEAN AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070246 | SO6001-EJ1E-TDS-04400036-002-003 | 044-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 044D0001 LEAN AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070247 | SO6001-EJ1E-TDS-04500022-002-001 | 045-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 045D0001 LEAN AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070247 | SO6001-EJ1E-TDS-04500022-002-002 | 045-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 045D0001 LEAN AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070247 | SO6001-EJ1E-TDS-04500022-002-003 | 045-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 045D0001 LEAN AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070248 | SO6001-EJ1E-TDS-04600013-002-001 | 046-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 046D0001 SOUR WATER SKIM TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070248 | SO6001-EJ1E-TDS-04600013-002-002 | 046-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 046D0001 SOUR WATER SKIM TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070248 | SO6001-EJ1E-TDS-04600013-002-003 | 046-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 046D0001 SOUR WATER SKIM TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070249 | SO6001-EJ1E-TDS-04700011-002-001 | 047-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 047D0001 SOUR WATER SKIM TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070249 | SO6001-EJ1E-TDS-04700011-002-002 | 047-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 047D0001 SOUR WATER SKIM TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070249 | SO6001-EJ1E-TDS-04700011-002-003 | 047-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 047D0001 SOUR WATER SKIM TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070250 | SO6001-EJ1E-TDS-04800020-002-001 | 048-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 048D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070250 | SO6001-EJ1E-TDS-04800020-002-002 | 048-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 048D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070250 | SO6001-EJ1E-TDS-04800020-002-003 | 048-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 048D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070250 | SO6001-EJ1E-TDS-04800021-002-001 | 048-D-GAD-00002-001 | MECHANICAL DATA SHEET FOR 048D0002 AMINE MAKE-UP TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070250 | SO6001-EJ1E-TDS-04800021-002-002 | 048-D-GAD-00002-002 | MECHANICAL DATA SHEET FOR 048D0002 AMINE MAKE-UP TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070250 | SO6001-EJ1E-TDS-04800021-002-003 | 048-D-GAD-00002-003 | MECHANICAL DATA SHEET FOR 048D0002 AMINE MAKE-UP TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070251 | SO6001-EJ1E-TDS-04900013-002-001 | 049-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 049D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070251 | SO6001-EJ1E-TDS-04900013-002-002 | 049-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 049D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070251 | SO6001-EJ1E-TDS-04900013-002-003 | 049-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 049D0001 AMINE SURGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070252 | SO6001-EJ1E-TDS-09400003-002-001 | 094-D-GAD-00001-001 | MECHANICAL DATA SHEET FOR 094D0001 2SHF SULPHUR STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070252 | SO6001-EJ1E-TDS-09400003-002-002 | 094-D-GAD-00001-002 | MECHANICAL DATA SHEET FOR 094D0001 2SHF SULPHUR STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070252 | SO6001-EJ1E-TDS-09400003-002-003 | 094-D-GAD-00001-003 | MECHANICAL DATA SHEET FOR 094D0001 2SHF SULPHUR STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200005-002-001 | 372-D-GAD-55001-001 | MECHANICAL DATA SHEET FOR '372D0015A/B RECOVERED CONDENSATE STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200005-002-002 | 372-D-GAD-55001-002 | MECHANICAL DATA SHEET FOR '372D0015A/B RECOVERED CONDENSATE STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200005-002-003 | 372-D-GAD-55001-003 | MECHANICAL DATA SHEET FOR 372D0015A/B RECOVERED CONDENSATE STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200006-002-001 | 372-D-GAD-55002-001 | MECHANICAL DATA SHEET FOR 372D0016A/B CONDENSATE POLISHING FEED STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200006-002-002 | 372-D-GAD-55002-002 | MECHANICAL DATA SHEET FOR 372D0016A/B CONDENSATE POLISHING FEED STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200006-002-003 | 372-D-GAD-55002-003 | MECHANICAL DATA SHEET FOR 372D0016A/B CONDENSATE POLISHING FEED STORAGE TANK | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200007-002-001 | 372-D-GAD-55003-001 | MECHANICAL DATA SHEET FOR 372D0017 DEMINERALIZED WATER STORAGE TANKS | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200007-002-002 | 372-D-GAD-55003-002 | MECHANICAL DATA SHEET FOR 372D0017 DEMINERALIZED WATER STORAGE TANKS | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070253 | SO6001-EJ1E-TDS-37200007-002-003 | 372-D-GAD-55003-003 | MECHANICAL DATA SHEET FOR 372D0017 DEMINERALIZED WATER STORAGE TANKS | A | 2018-06-12 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070254 | 076551C-000S-MR-0570-001 | 000-C-MRQ-80008-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS COLUMNS | A | 2018-06-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-28 | 3 - REVIEWED WITH COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070255 | SO6001-EJIE-TDS-09800006-001 | 098-C-DAT-00012-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098V0007 DEAERATOR | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS |  | CLASS 2
CON-BMP-TRA-070256 | SO6001-EJIE-TDS-09900006-001 | 099-C-DAT-00012-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099V0007 DEAERATOR | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070257 | SO6001-EJIE-TDS-37200012-001 | 372-C-DAT-55006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 372V0031A/B CONDENSATE RECOVERY VESSELS | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070257 | SO6001-EJIE-TDS-37200013-001 | 372-C-DAT-55007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 372V0032A/B BOILER FEED WATER DEAERATORS | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070258 | SO6001-EJIE-TDS-01600002-002 | 016-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 016E1603 FEED COOLER TRAIN C | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070259 | SO6001-EJIE-TDS-01600002-002-001 | 016-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 016E1603 FEED COOLER TRAIN C | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070259 | SO6001-EJIE-TDS-01600002-002-002 | 016-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 016E1603 FEED COOLER TRAIN C | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070259 | SO6001-EJIE-TDS-01600002-002-003 | 016-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 016E1603 FEED COOLER TRAIN C | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070259 | SO6001-EJIE-TDS-01600002-002-004 | 016-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 016E1603 FEED COOLER TRAIN C | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070259 | SO6001-EJIE-TDS-01600002-002-005 | 016-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 016E1603 FEED COOLER TRAIN C | A | 2018-06-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070260 | SO6001-EJ1E-TDS-03600009-001 | 036-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036V0003 RICH AMINE FLASH DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070261 | SO6001-EJ1E-TDS-03700009-001 | 037-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037V0003 RICH AMINE FLASH DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070262 | SO6001-EJ1E-TDS-04400020-001 | 044-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0001 ACID GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070263 | SO6001-EJ1E-TDS-04800009-001 | 048-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048V0001 RICH AMINE FLASH DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070264 | SO6001-EJ1E-TDS-04900007-001 | 049-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 049V0001 RICH AMINE FLASH DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070265 | SO6001-EJ1E-TDS-09900019-001 | 099-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099V0006 PSA FEED KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070266 | SO6001-EJ1E-TDS-09800019-001 | 098-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098V0006 PSA FEED KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-02 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070267 | SO6001-EJ1E-TDS-03600017-001 | 036-D-DAT-00001-001 | TANK DATA SHEET FOR 036D0001 AMINE SURGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070268 | SO6001-EJ1E-TDS-03700015-001 | 037-D-DAT-00001-001 | TANK DATA SHEET FOR 037D0001 AMINE SURGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070269 | SO6001-EJ1E-TDS-04400036-001 | 044-D-DAT-00001-001 | TANK DATA SHEET FOR 044D0001 LEAN AMINE SURGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070270 | SO6001-EJ1E-TDS-04500022-001 | 045-D-DAT-00001-001 | TANK DATA SHEET FOR 045D0001 LEAN AMINE SURGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070271 | SO6001-EJ1E-TDS-04600013-001 | 046-D-DAT-00001-001 | TANK DATA SHEET FOR 046D0001 SOUR WATER SKIM TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070272 | SO6001-EJ1E-TDS-04700011-001 | 047-D-DAT-00001-001 | TANK DATA SHEET FOR 047D0001 SOUR WATER SKIM TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070273 | SO6001-EJ1E-TDS-04800020-001 | 048-D-DAT-00001-001 | TANK DATA SHEET FOR 048D0001 AMINE SURGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070273 | SO6001-EJ1E-TDS-04800021-001 | 048-D-DAT-00002-001 | TANK DATA SHEET FOR 048D0002 AMINE MAKE-UP TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070274 | SO6001-EJ1E-TDS-04900013-001 | 049-D-DAT-00001-001 | TANK DATA SHEET FOR 049D0001 AMINE SURGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-27 | CLASS 2
CON-BMP-TRA-070275 | SO6001-EJ1E-TDS-09400003-001 | 094-D-DAT-00001-001 | TANK DATA SHEET FOR 2SHF 094D0001 SULPHUR STORAGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070276 | SO6001-EJ1E-TDS-37200005-001 | 372-D-DAT-55001-001 | TANK DATA SHEET FOR 372D0015A/B RECOVERED CONDENSATE STORAGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070276 | SO6001-EJ1E-TDS-37200006-001 | 372-D-DAT-55002-001 | TANK DATA SHEET FOR 372D0016A/B CONDENSATE POLISHING FEED STORAGE TANK | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070276 | SO6001-EJ1E-TDS-37200007-001 | 372-D-DAT-55003-001 | TANK DATA SHEET FOR 372D0017A/B DEMINERALIZED WATER STORAGE TANKS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-26 | CLASS 2
CON-BMP-TRA-070277 | SO6001-EK0E-TDS-00080001-001 | 000-J-DAT-80001-001 | DATASHEET ¿ ON-OFF VALVE (BALL) | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-070277 | SO6001-EK0E-TDS-00080002-001 | 000-J-DAT-80002-001 | DATASHEET ¿ ON-OFF VALVE (BUTTERFLY) | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-070277 | SO6001-EK0E-TDS-00080003-001 | 000-J-DAT-80003-001 | DATASHEET ¿ ON-OFF VALVE (GATE/PLUG) | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-070278 | SO6001-EJ1E-TDS-00500001-001 | 005-C-DAT-55001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 005V5001 C3 STORAGE BULLET | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070278 | SO6001-EJ1E-TDS-00500002-001 | 005-C-DAT-55002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 005V5002 C3 STORAGE BULLET | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070278 | SO6001-EJ1E-TDS-00500003-001 | 005-C-DAT-55003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 005V5003 C4 STORAGE BULLET | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070278 | SO6001-EJ1E-TDS-00500004-001 | 005-C-DAT-55004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 005V5004 C4 STORAGE BULLET | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070278 | SO6001-EJ1E-TDS-00500005-001 | 005-C-DAT-55005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 005V5005 OFF-SPEC/SPARE LPG STORAGE BULLET | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070278 | SO6001-EJ1E-TDS-00500006-001 | 005-C-DAT-55006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 005V5006 OFF-SPEC/SPARE LPG STORAGE BULLET | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070279 | SO6001-EJ1E-TDS-03600010-001 | 036-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036V0008 AMINE SUMP | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070279 | SO6001-EJ1E-TDS-03600011-001 | 036-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036V0007 REGENERATOR REBOILER CONDENSATE POT | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070280 | SO6001-EJ1E-TDS-03700010-001 | 037-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037V0007 REGENERATOR REBOILER CONDENSATE POT | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070281 | SO6001-EJ1E-TDS-04100015-001 | 041-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 041V0001 ACID GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070281 | SO6001-EJ1E-TDS-04100016-001 | 041-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 041V0002 SWS OFF GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400019-001 | 044-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0011 AMINE SUMP | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400021-001 | 044-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0002A/B CONDENSATE POT | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400022-001 | 044-C-DAT-00008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0008 FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400023-001 | 044-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0009 FLASH GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400024-001 | 044-C-DAT-00010-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0013 60# STEAM BLOWDOWN DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400025-001 | 044-C-DAT-00011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0014 600# STEAM BLOWDOWN DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400026-001 | 044-C-DAT-00012-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0015 LP CONDENSATE FLASH DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400027-001 | 044-C-DAT-00013-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0016 HP CONDENSATE FLASH DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070282 | SO6001-EJ1E-TDS-04400029-001 | 044-C-DAT-00015-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0007 CAUSTIC INJECTION VESSEL | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070283 | SO6001-EJ1E-TDS-04500015-001 | 045-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045V0002A/B CONDENSATE POT | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070283 | SO6001-EJ1E-TDS-04500016-001 | 045-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045V0007 CAUSTIC INJECTION VESSEL | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070284 | SO6001-EJ1E-TDS-04600007-001 | 046-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046V0001 DEGASSING DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070284 | SO6001-EJ1E-TDS-04600008-001 | 046-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046V0005 SOUR WATER SUMP | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070284 | SO6001-EJ1E-TDS-04600009-001 | 046-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046V0002A/B CONDENSATE POTS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070284 | SO6001-EJ1E-TDS-04600010-001 | 046-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046V0004 OIL SKIMMING DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070285 | SO6001-EJ1E-TDS-04700007-001 | 047-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 047V0001 DEGASSING DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070285 | SO6001-EJ1E-TDS-04700008-001 | 047-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 047V0002A/B CONDENSATE POTS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070286 | SO6001-EJ1E-TDS-04800010-001 | 048-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048V0007 AMINE SUMP | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070286 | SO6001-EJ1E-TDS-04800011-001 | 048-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048V0005A/B CONDENSATE POTS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070286 | SO6001-EJ1E-TDS-04800013-001 | 048-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048V0009 N°3 SULPHUR PLANT SLOP OIL SUMP | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070286 | SO6001-EJ1E-TDS-04800014-001 | 048-C-DAT-00007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048V0010 ARU LP CONDENSATE FLASH DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070287 | SO6001-EJ1E-TDS-04900008-001 | 049-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 049V0005A/B CONDENSATE POTS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070288 | SO6001-EJ1E-TDS-09800017-001 | 098-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098V0012 FEED KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070288 | SO6001-EJ1E-TDS-09800018-001 | 098-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098V0005 BLOWDOWN DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070288 | SO6001-EJ1E-TDS-09800020-001 | 098-C-DAT-00008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098V0008 FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070288 | SO6001-EJ1E-TDS-09800021-001 | 098-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098V0010 PROCESS FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070289 | SO6001-EJ1E-TDS-09900017-001 | 099-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099V0012 FEED KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070289 | SO6001-EJ1E-TDS-09900018-001 | 099-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099V0005 BLOWDOWN DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070289 | SO6001-EJ1E-TDS-09900020-001 | 099-C-DAT-00008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099V0008 FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070289 | SO6001-EJ1E-TDS-09900021-001 | 099-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099V0010 PROCESS FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070290 | SO6001-EJ1E-TDS-31000003-001 | 310-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 310V0001 N.10 HP BOILER FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070290 | SO6001-EJ1E-TDS-31000004-001 | 310-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 310V0002 CONTINUOUS BLOWDOWN DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070290 | SO6001-EJ1E-TDS-31000005-001 | 310-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 310V0003 INTERMITTENT BLOWDOWN DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070291 | SO6001-EJ1E-TDS-31100003-001 | 311-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 311V0001 N.11 HP BOILER FUEL GAS KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070291 | SO6001-EJ1E-TDS-31100004-001 | 311-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 311V0002 CONTINUOUS BLOWDOWN DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070291 | SO6001-EJ1E-TDS-31100005-001 | 311-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 311V0003 INTERMITTENT BLOWDOWN DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070292 | SO6001-EJ1E-TDS-37100007-001 | 371-C-DAT-55001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 371V0006 60 PSIG EXCESS STEAM CONDENSATE DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070293 | SO6001-EJ1E-TDS-37200001-001 | 372-C-DAT-55002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 372V0033 98% SULPHURIC ACID STORAGE DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070293 | SO6001-EJ1E-TDS-37200002-001 | 372-C-DAT-55003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 372V0034 47% CAUSTIC SODA STORAGE DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-28 | CLASS 2
CON-BMP-TRA-070294 | SO6001-EJ1E-TDS-01600004-001 | 016-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 016V1643 CAUSTIC SETTLER TRAIN C MISC-P1051-B2-N | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070294 | SO6001-EJ1E-TDS-01600005-001 | 016-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 016V1644 WATER WASH TRAIN C MISC-P1055-B2-N | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070294 | SO6001-EJ1E-TDS-01600006-001 | 016-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 016V1645 SALT DRIER TRAIN C MISC-P1053-B1-N | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070295 | SO6001-EJ1E-TDS-03600007-001 | 036-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036V0001 FEED KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070295 | SO6001-EJ1E-TDS-03600008-001 | 036-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036V0002 ABSORBER OVERHEAD KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070296 | SO6001-EJ1E-TDS-03700007-001 | 037-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037V0001 FEED KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070296 | SO6001-EJ1E-TDS-03700008-001 | 037-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037V0002 ABSORBER OVERHEAD KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070297 | SO6001-EJ1E-TDS-04400028-001 | 044-C-DAT-00014-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044V0017 NO.3 SULPHUR PLANT FLARE KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070298 | SO6001-EJ1E-TDS-04800012-001 | 048-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048V0011 ARU FLARE KO DRUM | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070299 | SO6001-EJ1E-TDS-34100001-001 | 341-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 341V0141A/B COMPRESSED AIR RECEIVERS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070299 | SO6001-EJ1E-TDS-34100002-001 | 341-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 341V0142A/B/C/D DRIED AIR RECEIVERS | A | 2018-06-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070300 | SO6001-EJ1E-TDS-03600010-002-001 | 036-C-GAD-00006-001 | MECHANICAL DATA SHEET FOR 036V0008 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070300 | SO6001-EJ1E-TDS-03600010-003-002 | 036-C-GAD-00006-002 | MECHANICAL DATA SHEET FOR 036V0008 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070300 | SO6001-EJ1E-TDS-03600010-004-003 | 036-C-GAD-00006-003 | MECHANICAL DATA SHEET FOR 036V0008 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070300 | SO6001-EJ1E-TDS-03600011-002-001 | 036-C-GAD-00007-001 | MECHANICAL DATA SHEET FOR 036V0007 REGENERATOR REBOILER CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070300 | SO6001-EJ1E-TDS-03600011-002-002 | 036-C-GAD-00007-002 | MECHANICAL DATA SHEET FOR 036V0007 REGENERATOR REBOILER CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070300 | SO6001-EJ1E-TDS-03600011-002-003 | 036-C-GAD-00007-003 | MECHANICAL DATA SHEET FOR 036V0007 REGENERATOR REBOILER CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070301 | SO6001-EJ1E-TDS-03700010-002-001 | 037-C-GAD-00006-001 | MECHANICAL DATA SHEET FOR 037V0007 REGENERATOR REBOILER CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070301 | SO6001-EJ1E-TDS-03700010-002-002 | 037-C-GAD-00006-002 | MECHANICAL DATA SHEET FOR 037V0007 REGENERATOR REBOILER CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070301 | SO6001-EJ1E-TDS-03700010-002-003 | 037-C-GAD-00006-003 | MECHANICAL DATA SHEET FOR 037V0007 REGENERATOR REBOILER CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070302 | SO6001-EJ1E-TDS-04100015-002-001 | 041-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 041V0001 ACID GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070302 | SO6001-EJ1E-TDS-04100015-002-002 | 041-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 041V0001 ACID GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070302 | SO6001-EJ1E-TDS-04100015-002-003 | 041-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 041V0001 ACID GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070302 | SO6001-EJ1E-TDS-04100016-002-001 | 041-C-GAD-00004-001 | MECHANICAL DATA SHEET FOR 041V0002 SWS OFF GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070302 | SO6001-EJ1E-TDS-04100016-002-002 | 041-C-GAD-00004-002 | MECHANICAL DATA SHEET FOR 041V0002 SWS OFF GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070302 | SO6001-EJ1E-TDS-04100016-002-003 | 041-C-GAD-00004-003 | MECHANICAL DATA SHEET FOR 041V0002 SWS OFF GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400019-002-001 | 044-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 044V0011 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400019-002-002 | 044-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 044V0011 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400019-002-003 | 044-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 044V0011 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400021-002-001 | 044-C-GAD-00007-001 | MECHANICAL DATA SHEET FOR 044V0002A/B CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400021-002-002 | 044-C-GAD-00007-002 | MECHANICAL DATA SHEET FOR 044V0002A/B CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400021-002-003 | 044-C-GAD-00007-003 | MECHANICAL DATA SHEET FOR 044V0002A/B CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400022-002-001 | 044-C-GAD-00008-001 | MECHANICAL DATA SHEET FOR 044V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400022-002-002 | 044-C-GAD-00008-002 | MECHANICAL DATA SHEET FOR 044V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400022-002-003 | 044-C-GAD-00008-003 | MECHANICAL DATA SHEET FOR 044V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400023-002-001 | 044-C-GAD-00009-001 | MECHANICAL DATA SHEET FOR 044V0009 FLASH GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400023-002-002 | 044-C-GAD-00009-002 | MECHANICAL DATA SHEET FOR 044V0009 FLASH GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400023-002-003 | 044-C-GAD-00009-003 | MECHANICAL DATA SHEET FOR 044V0009 FLASH GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400024-002-001 | 044-C-GAD-00010-001 | MECHANICAL DATA SHEET FOR 044V0013 60# STEAM BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400024-002-002 | 044-C-GAD-00010-002 | MECHANICAL DATA SHEET FOR 044V0013 60# STEAM BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400024-002-003 | 044-C-GAD-00010-003 | MECHANICAL DATA SHEET FOR 044V0013 60# STEAM BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400025-002-001 | 044-C-GAD-00011-001 | MECHANICAL DATA SHEET FOR 044V0014 600# STEAM BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400025-002-002 | 044-C-GAD-00011-002 | MECHANICAL DATA SHEET FOR 044V0014 600# STEAM BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400025-002-003 | 044-C-GAD-00011-003 | MECHANICAL DATA SHEET FOR 044V0014 600# STEAM BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400026-002-001 | 044-C-GAD-00012-001 | MECHANICAL DATA SHEET FOR 044V0015 LP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400026-002-002 | 044-C-GAD-00012-002 | MECHANICAL DATA SHEET FOR 044V0015 LP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400026-002-003 | 044-C-GAD-00012-003 | MECHANICAL DATA SHEET FOR 044V0015 LP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400027-002-001 | 044-C-GAD-00013-001 | MECHANICAL DATA SHEET FOR 044V0016 HP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400027-002-002 | 044-C-GAD-00013-002 | MECHANICAL DATA SHEET FOR 044V0016 HP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400027-002-003 | 044-C-GAD-00013-003 | MECHANICAL DATA SHEET FOR 044V0016 HP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400029-002-001 | 044-C-GAD-00015-001 | MECHANICAL DATA SHEET FOR 044V0007 CAUSTIC INJECTION VESSEL | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400029-002-002 | 044-C-GAD-00015-002 | MECHANICAL DATA SHEET FOR 044V0007 CAUSTIC INJECTION VESSEL | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070303 | SO6001-EJ1E-TDS-04400029-002-003 | 044-C-GAD-00015-003 | MECHANICAL DATA SHEET FOR 044V0007 CAUSTIC INJECTION VESSEL | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070304 | SO6001-EJ1E-TDS-04500015-002-001 | 045-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 045V0002A/B CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070304 | SO6001-EJ1E-TDS-04500015-002-002 | 045-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 045V0002A/B CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070304 | SO6001-EJ1E-TDS-04500015-002-003 | 045-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 045V0002A/B CONDENSATE POT | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070304 | SO6001-EJ1E-TDS-04500016-002-001 | 045-C-GAD-00006-001 | MECHANICAL DATA SHEET FOR045V0007 CAUSTIC INJECTION VESSEL | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070304 | SO6001-EJ1E-TDS-04500016-002-002 | 045-C-GAD-00006-002 | MECHANICAL DATA SHEET FOR 045V0007 CAUSTIC INJECTION VESSEL | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070304 | SO6001-EJ1E-TDS-04500016-002-003 | 045-C-GAD-00006-003 | MECHANICAL DATA SHEET FOR 045V0007 CAUSTIC INJECTION VESSEL | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600007-002-001 | 046-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 046V0001 DEGASSING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600007-002-002 | 046-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 046V0001 DEGASSING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600007-002-003 | 046-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 046V0001 DEGASSING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600008-002-001 | 046-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 046V0005 SOUR WATER SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600008-002-002 | 046-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 046V0005 SOUR WATER SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600008-002-003 | 046-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 046V0005 SOUR WATER SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600009-002-001 | 046-C-GAD-00004-001 | MECHANICAL DATA SHEET FOR 046V0002A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600009-002-002 | 046-C-GAD-00004-002 | MECHANICAL DATA SHEET FOR 046V0002A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600009-002-003 | 046-C-GAD-00004-003 | MECHANICAL DATA SHEET FOR 046V0002A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600010-002-001 | 046-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 046V0004 OIL SKIMMING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600010-002-002 | 046-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 046V0004 OIL SKIMMING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070305 | SO6001-EJ1E-TDS-04600010-002-003 | 046-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 046V0004 OIL SKIMMING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070306 | SO6001-EJ1E-TDS-04700007-002-001 | 047-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 047V0001 DEGASSING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070306 | SO6001-EJ1E-TDS-04700007-002-002 | 047-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 047V0001 DEGASSING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070306 | SO6001-EJ1E-TDS-04700007-002-003 | 047-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 047V0001 DEGASSING DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070306 | SO6001-EJ1E-TDS-04700008-002-001 | 047-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 047V0002A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070306 | SO6001-EJ1E-TDS-04700008-002-002 | 047-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 047V0002A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070306 | SO6001-EJ1E-TDS-04700008-002-003 | 047-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 047V0002A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800010-002-001 | 048-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 048V0007 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800010-002-002 | 048-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 048V0007 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800010-002-003 | 048-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 048V0007 AMINE SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800011-002-001 | 048-C-GAD-00004-001 | MECHANICAL DATA SHEET FOR 048V0005A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800011-002-002 | 048-C-GAD-00004-002 | MECHANICAL DATA SHEET FOR 048V0005A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800011-002-003 | 048-C-GAD-00004-003 | MECHANICAL DATA SHEET FOR 048V0005A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800013-002-001 | 048-C-GAD-00006-001 | MECHANICAL DATA SHEET FOR 048V0009 N°3 SULPHUR PLANT SLOP OIL SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800013-002-002 | 048-C-GAD-00006-002 | MECHANICAL DATA SHEET FOR 048V0009 N°3 SULPHUR PLANT SLOP OIL SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800013-002-003 | 048-C-GAD-00006-003 | MECHANICAL DATA SHEET FOR 048V0009 N°3 SULPHUR PLANT SLOP OIL SUMP | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800014-002-001 | 048-C-GAD-00007-001 | MECHANICAL DATA SHEET FOR 048V0010 ARU LP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800014-002-002 | 048-C-GAD-00007-002 | MECHANICAL DATA SHEET FOR 048V0010 ARU LP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070307 | SO6001-EJ1E-TDS-04800014-002-003 | 048-C-GAD-00007-003 | MECHANICAL DATA SHEET FOR 048V0010 ARU LP CONDENSATE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070308 | SO6001-EJ1E-TDS-04900008-002-001 | 049-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 049V0005A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070308 | SO6001-EJ1E-TDS-04900008-002-002 | 049-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 049V0005A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070308 | SO6001-EJ1E-TDS-04900008-002-003 | 049-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 049V0005A/B CONDENSATE POTS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800017-002-001 | 098-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 098V0012 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800017-002-002 | 098-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 098V0012 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800017-002-003 | 098-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 098V0012 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800018-002-001 | 098-C-GAD-00006-001 | MECHANICAL DATA SHEET FOR 098V0005 BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800018-002-002 | 098-C-GAD-00006-002 | MECHANICAL DATA SHEET FOR 098V0005 BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800018-002-003 | 098-C-GAD-00006-003 | MECHANICAL DATA SHEET FOR 098V0005 BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800020-002-001 | 098-C-GAD-00008-001 | MECHANICAL DATA SHEET FOR 098V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800020-002-002 | 098-C-GAD-00008-002 | MECHANICAL DATA SHEET FOR 098V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800020-002-003 | 098-C-GAD-00008-003 | MECHANICAL DATA SHEET FOR 098V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800021-002-001 | 098-C-GAD-00009-001 | MECHANICAL DATA SHEET FOR 098V0010 PROCESS FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800021-002-002 | 098-C-GAD-00009-002 | MECHANICAL DATA SHEET FOR 098V0010 PROCESS FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070309 | SO6001-EJ1E-TDS-09800021-002-003 | 098-C-GAD-00009-003 | MECHANICAL DATA SHEET FOR 098V0010 PROCESS FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900017-002-001 | 099-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 099V0012 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900017-002-002 | 099-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 099V0012 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900017-002-003 | 099-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 099V0012 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900018-002-001 | 099-C-GAD-00006-001 | MECHANICAL DATA SHEET FOR 099V0005 BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900018-002-002 | 099-C-GAD-00006-002 | MECHANICAL DATA SHEET FOR 099V0005 BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900018-002-003 | 099-C-GAD-00006-003 | MECHANICAL DATA SHEET FOR 099V0005 BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900020-002-001 | 099-C-GAD-00008-001 | MECHANICAL DATA SHEET FOR 099V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900020-002-002 | 099-C-GAD-00008-002 | MECHANICAL DATA SHEET FOR 099V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900020-002-003 | 099-C-GAD-00008-003 | MECHANICAL DATA SHEET FOR 099V0008 FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900021-002-001 | 099-C-GAD-00009-001 | MECHANICAL DATA SHEET FOR 099V0010 PROCESS FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900021-002-002 | 099-C-GAD-00009-002 | MECHANICAL DATA SHEET FOR 099V0010 PROCESS FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070310 | SO6001-EJ1E-TDS-09900021-002-003 | 099-C-GAD-00009-003 | MECHANICAL DATA SHEET FOR 099V0010 PROCESS FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000003-002-001 | 310-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 310V0001 N.10 HP BOILER FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000003-002-002 | 310-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 310V0001 N.10 HP BOILER FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000003-002-003 | 310-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 310V0001 N.10 HP BOILER FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000004-002-001 | 310-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 310V0002 CONTINUOUS BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000004-002-002 | 310-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 310V0002 CONTINUOUS BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000004-002-003 | 310-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 310V0002 CONTINUOUS BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000005-002-001 | 310-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 310V0003 INTERMITTENT BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000005-002-002 | 310-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 310V0003 INTERMITTENT BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070311 | SO6001-EJ1E-TDS-31000005-002-003 | 310-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 310V0003 INTERMITTENT BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100003-002-001 | 311-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 311V0001 N.11 HP BOILER FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100003-002-002 | 311-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 311V0001 N.11 HP BOILER FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100003-002-003 | 311-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 311V0001 N.11 HP BOILER FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100004-002-001 | 311-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 311V0002 CONTINUOUS BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100004-002-002 | 311-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 311V0002 CONTINUOUS BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100004-002-003 | 311-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 311V0002 CONTINUOUS BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100005-002-001 | 311-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 311V0003 INTERMITTENT BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100005-002-002 | 311-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 311V0003 INTERMITTENT BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070312 | SO6001-EJ1E-TDS-31100005-002-003 | 311-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 311V0003 INTERMITTENT BLOWDOWN DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070313 | SO6001-EJ1E-TDS-37100007-002-001 | 371-C-GAD-55001-001 | MECHANICAL DATA SHEET FOR 371V0006 60 PSIG EXCESS STEAM CONDENSATE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070313 | SO6001-EJ1E-TDS-37100007-002-002 | 371-C-GAD-55001-002 | MECHANICAL DATA SHEET FOR 371V0006 60 PSIG EXCESS STEAM CONDENSATE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070313 | SO6001-EJ1E-TDS-37100007-002-003 | 371-C-GAD-55001-003 | MECHANICAL DATA SHEET FOR 371V0006 60 PSIG EXCESS STEAM CONDENSATE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070314 | SO6001-EJ1E-TDS-37200001-002-001 | 372-C-GAD-55002-001 | MECHANICAL DATA SHEET FOR 372V0033 98% SULPHURIC ACID STORAGE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070314 | SO6001-EJ1E-TDS-37200001-002-002 | 372-C-GAD-55002-002 | MECHANICAL DATA SHEET FOR 372V0033 98% SULPHURIC ACID STORAGE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070314 | SO6001-EJ1E-TDS-37200001-002-003 | 372-C-GAD-55002-003 | MECHANICAL DATA SHEET FOR 372V0033 98% SULPHURIC ACID STORAGE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070314 | SO6001-EJ1E-TDS-37200002-002-001 | 372-C-GAD-55003-001 | MECHANICAL DATA SHEET FOR 372V0034 47% CAUSTIC SODA STORAGE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070314 | SO6001-EJ1E-TDS-37200002-002-002 | 372-C-GAD-55003-002 | MECHANICAL DATA SHEET FOR 372V0034 47% CAUSTIC SODA STORAGE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070314 | SO6001-EJ1E-TDS-37200002-002-003 | 372-C-GAD-55003-003 | MECHANICAL DATA SHEET FOR 372V0034 47% CAUSTIC SODA STORAGE DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-06-29 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600003-002-001 | 016-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 016V1643 CAUSTIC SETTLER TRAIN C MISC-P1051-B2-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600003-002-002 | 016-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 016V1643 CAUSTIC SETTLER TRAIN C MISC-P1051-B2-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600003-002-003 | 016-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 016V1643 CAUSTIC SETTLER TRAIN C MISC-P1051-B2-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600004-002-001 | 016-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 016V1644 WATER WASH TRAIN C MISC-P1055-B2-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600004-002-002 | 016-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 016V1644 WATER WASH TRAIN C MISC-P1055-B2-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600004-002-003 | 016-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 016V1644 WATER WASH TRAIN C MISC-P1055-B2-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600005-002-001 | 016-C-GAD-00004-001 | MECHANICAL DATA SHEET FOR 016V1645 SALT DRIER TRAIN C MISC-P1053-B1-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600005-002-002 | 016-C-GAD-00004-002 | MECHANICAL DATA SHEET FOR 016V1645 SALT DRIER TRAIN C MISC-P1053-B1-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070315 | SO6001-EJ1E-TDS-01600005-002-003 | 016-C-GAD-00004-003 | MECHANICAL DATA SHEET FOR 016V1645 SALT DRIER TRAIN C MISC-P1053-B1-N | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070316 | SO6001-EJ1E-TDS-03600007-002-001 | 036-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 036V0001 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070316 | SO6001-EJ1E-TDS-03600007-002-002 | 036-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 036V0001 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070316 | SO6001-EJ1E-TDS-03600007-002-003 | 036-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 036V0001 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070316 | SO6001-EJ1E-TDS-03600008-002-001 | 036-C-GAD-00004-001 | MECHANICAL DATA SHEET FOR 036V0002 ABSORBER OVERHEAD KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070316 | SO6001-EJ1E-TDS-03600008-002-002 | 036-C-GAD-00004-002 | MECHANICAL DATA SHEET FOR 036V0002 ABSORBER OVERHEAD KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070316 | SO6001-EJ1E-TDS-03600008-002-003 | 036-C-GAD-00004-003 | MECHANICAL DATA SHEET FOR 036V0002 ABSORBER OVERHEAD KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070317 | SO6001-EJ1E-TDS-03700007-002-001 | 037-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 037V0001 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070317 | SO6001-EJ1E-TDS-03700007-002-002 | 037-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 037V0001 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070317 | SO6001-EJ1E-TDS-03700007-002-003 | 037-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 037V0001 FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070317 | SO6001-EJ1E-TDS-03700008-002-001 | 037-C-GAD-00004-001 | MECHANICAL DATA SHEET FOR 037V0002 ABSORBER OVERHEAD KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070317 | SO6001-EJ1E-TDS-03700008-002-002 | 037-C-GAD-00004-002 | MECHANICAL DATA SHEET FOR 037V0002 ABSORBER OVERHEAD KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070317 | SO6001-EJ1E-TDS-03700008-002-003 | 037-C-GAD-00004-003 | MECHANICAL DATA SHEET FOR 037V0002 ABSORBER OVERHEAD KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-01 | CLASS 2
CON-BMP-TRA-070318 | SO6001-EJ1E-TDS-04400028-002-001 | 044-C-GAD-00014-001 | MECHANICAL DATA SHEET FOR 044V0017 NO.3 SULPHUR PLANT FLARE KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070318 | SO6001-EJ1E-TDS-04400028-002-002 | 044-C-GAD-00014-002 | MECHANICAL DATA SHEET FOR 044V0017 NO.3 SULPHUR PLANT FLARE KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070318 | SO6001-EJ1E-TDS-04400028-002-003 | 044-C-GAD-00014-003 | MECHANICAL DATA SHEET FOR 044V0017 NO.3 SULPHUR PLANT FLARE KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070319 | SO6001-EJ1E-TDS-04800012-002-001 | 048-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 048V0011 ARU FLARE KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070319 | SO6001-EJ1E-TDS-04800012-002-002 | 048-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 048V0011 ARU FLARE KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070319 | SO6001-EJ1E-TDS-04800012-002-003 | 048-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 048V0011 ARU FLARE KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070320 | SO6001-EJ1E-TDS-34100001-002-001 | 341-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 341V0141A/B COMPRESSED AIR RECEIVERS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070320 | SO6001-EJ1E-TDS-34100001-002-002 | 341-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 341V0141A/B COMPRESSED AIR RECEIVERS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070320 | SO6001-EJ1E-TDS-34100001-002-003 | 341-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 341V0141A/B COMPRESSED AIR RECEIVERS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070320 | SO6001-EJ1E-TDS-34100002-002-001 | 341-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 341V0142A/B/C/D DRIED AIR RECEIVERS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070320 | SO6001-EJ1E-TDS-34100002-002-002 | 341-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 341V0142A/B/C/D DRIED AIR RECEIVERS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070320 | SO6001-EJ1E-TDS-34100002-002-003 | 341-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 341V0142A/B/C/D DRIED AIR RECEIVERS | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070321 | SO6001-EJ1E-TDS-03600009-002-001 | 036-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 036V0003 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070321 | SO6001-EJ1E-TDS-03600009-002-002 | 036-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 036V0003 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070321 | SO6001-EJ1E-TDS-03600009-002-003 | 036-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 036V0003 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070322 | SO6001-EJ1E-TDS-03700009-002-001 | 037-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 037V0003 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070322 | SO6001-EJ1E-TDS-03700009-002-002 | 037-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 037V0003 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070322 | SO6001-EJ1E-TDS-03700009-002-003 | 037-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 037V0003 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070323 | SO6001-EJ1E-TDS-04400020-002-001 | 044-C-GAD-00006-001 | MECHANICAL DATA SHEET FOR 044V0001 ACID GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070323 | SO6001-EJ1E-TDS-04400020-002-002 | 044-C-GAD-00006-002 | MECHANICAL DATA SHEET FOR 044V0001 ACID GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070323 | SO6001-EJ1E-TDS-04400020-002-003 | 044-C-GAD-00006-003 | MECHANICAL DATA SHEET FOR 044V0001 ACID GAS KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070324 | SO6001-EJ1E-TDS-04800009-002-001 | 048-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 048V0001 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070324 | SO6001-EJ1E-TDS-04800009-002-002 | 048-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 048V0001 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070324 | SO6001-EJ1E-TDS-04800009-002-003 | 048-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 048V0001 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070325 | SO6001-EJ1E-TDS-04900007-002-001 | 049-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 049V0001 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070325 | SO6001-EJ1E-TDS-04900007-002-002 | 049-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 049V0001 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070325 | SO6001-EJ1E-TDS-04900007-002-003 | 049-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 049V0001 RICH AMINE FLASH DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070326 | SO6001-EJ1E-TDS-09800019-002-001 | 098-C-GAD-00007-001 | MECHANICAL DATA SHEET FOR 098V0006 PSA FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070326 | SO6001-EJ1E-TDS-09800019-002-002 | 098-C-GAD-00007-002 | MECHANICAL DATA SHEET FOR 098V0006 PSA FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070326 | SO6001-EJ1E-TDS-09800019-002-003 | 098-C-GAD-00007-003 | MECHANICAL DATA SHEET FOR 098V0006 PSA FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070327 | SO6001-EJ1E-TDS-09900019-002-001 | 099-C-GAD-00007-001 | MECHANICAL DATA SHEET FOR 099V0006 PSA FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070327 | SO6001-EJ1E-TDS-09900019-002-002 | 099-C-GAD-00007-002 | MECHANICAL DATA SHEET FOR 099V0006 PSA FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070327 | SO6001-EJ1E-TDS-09900019-002-003 | 099-C-GAD-00007-003 | MECHANICAL DATA SHEET FOR 099V0006 PSA FEED KO DRUM | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500001-002-001 | 005-C-GAD-55001-001 | MECHANICAL DATA SHEET FOR 005V5001 C3 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500001-002-002 | 005-C-GAD-55001-002 | MECHANICAL DATA SHEET FOR 005V5001 C3 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500001-002-003 | 005-C-GAD-55001-003 | MECHANICAL DATA SHEET FOR 005V5001 C3 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500002-002-001 | 005-C-GAD-55002-001 | MECHANICAL DATA SHEET FOR 005V5002 C3 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500002-002-002 | 005-C-GAD-55002-002 | MECHANICAL DATA SHEET FOR 005V5002 C3 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500002-002-003 | 005-C-GAD-55002-003 | MECHANICAL DATA SHEET FOR 005V5002 C3 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500003-002-001 | 005-C-GAD-55003-001 | MECHANICAL DATA SHEET FOR 005V5003 C4 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500003-002-002 | 005-C-GAD-55003-002 | MECHANICAL DATA SHEET FOR 005V5003 C4 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500003-002-003 | 005-C-GAD-55003-003 | MECHANICAL DATA SHEET FOR 005V5003 C4 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500004-002-001 | 005-C-GAD-55004-001 | MECHANICAL DATA SHEET FOR 005V5004 C4 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500004-002-002 | 005-C-GAD-55004-002 | MECHANICAL DATA SHEET FOR 005V5004 C4 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500004-002-003 | 005-C-GAD-55004-003 | MECHANICAL DATA SHEET FOR 005V5004 C4 STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500005-002-001 | 005-C-GAD-55005-001 | MECHANICAL DATA SHEET FOR 005V5005 OFF-SPEC/SPARE LPG STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500005-002-002 | 005-C-GAD-55005-002 | MECHANICAL DATA SHEET FOR 005V5005 OFF-SPEC/SPARE LPG STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500005-002-003 | 005-C-GAD-55005-003 | MECHANICAL DATA SHEET FOR 005V5005 OFF-SPEC/SPARE LPG STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500006-002-001 | 005-C-GAD-55006-001 | MECHANICAL DATA SHEET FOR 005V5006 OFF-SPEC/SPARE LPG STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500006-002-002 | 005-C-GAD-55006-002 | MECHANICAL DATA SHEET FOR 005V5006 OFF-SPEC/SPARE LPG STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070328 | SO6001-EJ1E-TDS-00500006-002-003 | 005-C-GAD-55006-003 | MECHANICAL DATA SHEET FOR 005V5006 OFF-SPEC/SPARE LPG STORAGE BULLET | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070329 | SO6001-EJ2E-TDS-04400001-001 | 044-S-DAT-00001-001 | MECHANICAL DATA SHEET 044U0002 PHOSPHATE INJECTION PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070330 | SO6001-EJ2E-TDS-04600001-001 | 046-S-DAT-00001-001 | MECHANICAL DATA SHEET 046U0001 CAUSTIC PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070331 | SO6001-EJ2E-TDS-04700001-001 | 047-S-DAT-00001-001 | MECHANICAL DATA SHEET 047U0001 CAUSTIC PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070332 | SO6001-EJ2E-TDS-04800001-001 | 048-S-DAT-00001-001 | MECHANICAL DATA SHEET 048U0001 ANTIFOAM INJECTION PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070333 | SO6001-EJ2E-TDS-09800002-001 | 098-S-DAT-00002-001 | MECHANICAL DATA SHEET 098U0003 SCALE CORROSION INHIBITOR DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070333 | SO6001-EJ2E-TDS-09800003-001 | 098-S-DAT-00003-001 | MECHANICAL DATA SHEET 098U0004 NEUTRALIZING AMINE DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070334 | SO6001-EJ2E-TDS-09900002-001 | 099-S-DAT-00002-001 | MECHANICAL DATA SHEET 099U0003 SCALE CORROSION INHIBITOR DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070334 | SO6001-EJ2E-TDS-09900003-001 | 099-S-DAT-00003-001 | MECHANICAL DATA SHEET 099U0004 NEUTRALIZING AMINE DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070335 | SO6001-EJ2E-TDS-31000001-001 | 310-S-DAT-00001-001 | MECHANICAL DATA SHEET 310U0001 SCALE CORROSION INHIBITOR DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 2
CON-BMP-TRA-070336 | SO6001-ES0D-PID-08300001-001 | 083-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM NO.1 NITROGEN PLANT PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070336 | SO6001-ES0D-PID-08300002-001 | 083-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN PROCESS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070336 | SO6001-ES0D-PID-08300003-001 | 083-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070336 | SO6001-ES0D-PID-08300004-001 | 083-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY WATER DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070336 | SO6001-ES0D-PID-08300005-001 | 083-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT, YARD AIR DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070336 | SO6001-ES0D-PID-08300006-001 | 083-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070336 | SO6001-ES0D-PID-08300006-002 | 083-A-PID-00006-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400001-001 | 094-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM BMP SULPHUR HANDLING FACILITIES SULPHUR STORAGE TANK | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400002-001 | 094-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM BMP SULPHUR HANDLING FACILITIES PRECONDITIONER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400003-001 | 094-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM BMP SULPHUR HANDLING FACILITIES PELLETIZER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400004-001 | 094-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM BMP SULPHUR HANDLING FACILITIES PELLETIZER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400005-001 | 094-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR HANDLING FACILITIES NEUTRALIZATION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400006-001 | 094-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR HANDLING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400007-001 | 094-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR HANDLING FACILITIES COOLING WATER SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400008-001 | 094-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR HANDLING PACKAGE ATTACHMENT 5 - SHEET 2 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400009-001 | 094-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR HANDLING PACKAGE ATTACHMENT 5 - SHEET 3 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400010-001 | 094-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR HANDLING PACKAGE ATTACHMENT 5 - SHEET 4 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400011-001 | 094-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR HANDLING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400012-001 | 094-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070337 | SO6001-ES0D-PID-09400013-001 | 094-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM BMP SULPHUR HANDLING FACILITIES BATTERY LIMITS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070338 | SO6001-ES0D-PID-09600001-001 | 096-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM PROPOSAL FOR SULPHUR STORAGE TANK OPTION WHEN SHF TANK D9600 IS OUT OF SERVICE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070338 | SO6001-ES0D-PID-09600001-002 | 096-A-PID-00001-002 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR HANDLING FACILITIES SULPHUR STORAGE TANK | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070338 | SO6001-ES0D-PID-09600001-010 | 096-A-PID-00001-010 | PIPING & INSTRUMENTATION DIAGRAM PROPOSAL FOR SULPHUR STORAGE TANK OPTION WHEN SHF TANK D0600 IS OUT OF SERVICE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800001-001 | 098-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM INLET FEED SEPARATION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800002-001 | 098-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM ZINC OXIDE DRUMS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800003-001 | 098-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM MIXED TEE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800004-001 | 098-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM PRIMARY REFORMER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800005-001 | 098-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM CONVECTION SECTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800006-001 | 098-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM I. D. FAN | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800007-001 | 098-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM DRUM AND PROCESS GAS BOILER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800008-001 | 098-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM HIGH TEMPERATURE SHIFT REACTOR | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800009-001 | 098-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM PSA RETREATMENT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800010-001 | 098-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM PSA UNIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800011-001 | 098-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM REFORMER FUEL SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800012-001 | 098-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM BURNER DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800013-001 | 098-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM DISTRIBUTION SUPERHEATED STEAM OPTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800014-001 | 098-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM DEAERATOR | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800015-001 | 098-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM 098P0001A/B BFW PUMPS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800016-001 | 098-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM PROCESS FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800017-001 | 098-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM HIGH PRESSURE STRIPPER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800018-001 | 098-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM BLOWDOWN DRUM AND BLOWDOWN COOLER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800019-001 | 098-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM CIRCULATING N2 COMPRESSOR | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070339 | SO6001-ES0D-PID-09800020-001 | 098-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800021-001 | 098-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800022-001 | 098-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM 550# AND 60# STEAM AND CONDENSATE SYSTEMS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800023-001 | 098-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM WATER COOLING SUPPLY / RETURN SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800024-001 | 098-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY/DRINKING WATER SYSTEMS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800025-001 | 098-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AIR YARD AIR/NITROGEN SYSTEMS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800026-001 | 098-A-PID-00026-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT INTERFACE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800026-002 | 098-A-PID-00026-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT INTERFACE (2/2) | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800027-001 | 098-A-PID-00027-001 | PIPING & INSTRUMENTATION DIAGRAM O2 SCAVENGER DOSING PACKAGE 098U0002 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800028-001 | 098-A-PID-00028-001 | PIPING & INSTRUMENTATION DIAGRAM SCALE CORROSION INHIBITOR DOSING PACKAGE 098U0003 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070340 | SO6001-ES0D-PID-09800029-001 | 098-A-PID-00029-001 | PIPING & INSTRUMENTATION DIAGRAM NEUTRALIZING AMINE DOSING PACKAGE 098U0004 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900001-001 | 099-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM INLET FEED SEPARATION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900002-001 | 099-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM ZINC OXIDE DRUMS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900003-001 | 099-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM MIXED TEE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900004-001 | 099-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM PRIMARY REFORMER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900005-001 | 099-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM CONVECTION SECTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900006-001 | 099-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM I. D. FAN | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900007-001 | 099-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM DRUM AND PROCESS GAS BOILER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900008-001 | 099-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM HIGH TEMPERATURE SHIFT REACTOR | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900009-001 | 099-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM PSA RETREATMENT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900010-001 | 099-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM PSA UNIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900011-001 | 099-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM REFORMER FUEL SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900012-001 | 099-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM BURNER DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900013-001 | 099-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM DISTRIBUTION SUPERHEATED STEAM OPTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900014-001 | 099-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM DEAERATOR | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900015-001 | 099-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM 099P0001A/B BFW PUMPS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900016-001 | 099-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM PROCESS FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900017-001 | 099-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM HIGH PRESSURE STRIPPER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900018-001 | 099-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM BLOWDOWN DRUM AND BLOWDOWN COOLER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900019-001 | 099-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM CIRCULATING N2 COMPRESSOR | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070341 | SO6001-ES0D-PID-09900020-001 | 099-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900021-001 | 099-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900022-001 | 099-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM 550# AND 60# STEAM AND CONDENSATE SYSTEMS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900023-001 | 099-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM WATER COOLING SUPPLY / RETURN SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900024-001 | 099-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY/DRINKING WATER SYSTEMS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900025-001 | 099-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AIR YARD AIR/NITROGEN SYSTEMS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900026-001 | 099-A-PID-00026-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT INTERFACE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900027-001 | 099-A-PID-00027-001 | PIPING & INSTRUMENTATION DIAGRAM O2 SCAVENGER DOSING PACKAGE 099U0002 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900028-001 | 099-A-PID-00028-001 | PIPING & INSTRUMENTATION DIAGRAM SCALE CORROSION INHIBITOR DOSING PACKAGE 099U0003 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070342 | SO6001-ES0D-PID-09900029-001 | 099-A-PID-00029-001 | PIPING & INSTRUMENTATION DIAGRAM NEUTRALIZING AMINE DOSING PACKAGE 099U0004 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000001-001 | 310-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM NO.10 HP BOILER WATER, STEAM, DRUM & DRAINS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000002-001 | 310-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FLUE GAS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000003-001 | 310-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM FUEL SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000004-001 | 310-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM NO.10 HP BOILER BURNER-1 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000005-001 | 310-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM NO.10 HP BOILER BURNER-2 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000006-001 | 310-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM NO.10 HP BOILER BURNER-3 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000007-001 | 310-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM NO.10 HP BOILER BURNER-4 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000008-001 | 310-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM SAMPLING SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000009-001 | 310-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM 60# STEAM DESUPERHEATER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000010-001 | 310-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM NO.10 HP BOILER FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000011-001 | 310-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM BLOWDOWN SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070343 | SO6001-ES0D-PID-31000012-001 | 310-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM SCALE CORROSION INHIBITOR DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 |  |  | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100001-001 | 311-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM NO.11 HP BOILER WATER, STEAM, DRUM & DRAINS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100002-001 | 311-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FLUE GAS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100003-001 | 311-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM FUEL SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100004-001 | 311-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM NO.11 HP BOILER BURNER-1 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100005-001 | 311-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM NO.11 HP BOILER BURNER-2 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100006-001 | 311-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM NO.11 HP BOILER BURNER-3 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100007-001 | 311-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM NO.11 HP BOILER BURNER-4 | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100008-001 | 311-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM SAMPLING SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100009-001 | 311-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM 60# STEAM DESUPERHEATER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100010-001 | 311-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM NO.11 HP BOILER FUEL GAS KO DRUM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070344 | SO6001-ES0D-PID-31100011-001 | 311-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM BLOWDOWN SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100050-001 | 341-A-PID-00050-001 | PIPING & INSTRUMENTATION DIAGRAM AIR COMPRESSOR K3415A (STEAM TURBINE DRIVEN) | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100051-001 | 341-A-PID-00051-001 | PIPING & INSTRUMENTATION DIAGRAM AIR COMPRESSOR STEAM TURBINE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100052-001 | 341-A-PID-00052-001 | PIPING & INSTRUMENTATION DIAGRAM K3415A LUBE OIL SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100053-001 | 341-A-PID-00053-001 | PIPING & INSTRUMENTATION DIAGRAM AIR COMPRESSOR K3415B (STEAM TURBINE DRIVEN) | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100054-001 | 341-A-PID-00054-001 | PIPING & INSTRUMENTATION DIAGRAM AIR COMPRESSOR STEAM TURBINE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100055-001 | 341-A-PID-00055-001 | PIPING & INSTRUMENTATION DIAGRAM K3415B LUBE OIL SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100056-001 | 341-A-PID-00056-001 | PIPING & INSTRUMENTATION DIAGRAM AIR COMPRESSOR K3415C (EL. MOTOR DRIVEN) | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100057-001 | 341-A-PID-00057-001 | PIPING & INSTRUMENTATION DIAGRAM K3415C LUBE OIL SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100058-001 | 341-A-PID-00058-001 | PIPING & INSTRUMENTATION DIAGRAM AIR COMPRESSOR K3415D (EL. MOTOR DRIVEN) | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100059-001 | 341-A-PID-00059-001 | PIPING & INSTRUMENTATION DIAGRAM K3415D LUBE OIL SYSTEM | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100060-001 | 341-A-PID-00060-001 | PIPING & INSTRUMENTATION DIAGRAM COMPRESSED AIR RECEIVERS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100061-001 | 341-A-PID-00061-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AIR DRYERS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100062-001 | 341-A-PID-00062-001 | PIPING & INSTRUMENTATION DIAGRAM DRIED AIR RECEIVERS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100063-001 | 341-A-PID-00063-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AIR DRYERS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100064-001 | 341-A-PID-00064-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100064-002 | 341-A-PID-00064-002 | PIPING & INSTRUMENTATION DIAGRAM STEAM CONDENSATE AND BFW DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100064-003 | 341-A-PID-00064-003 | PIPING & INSTRUMENTATION DIAGRAM UTILITY WATER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100064-004 | 341-A-PID-00064-004 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100064-005 | 341-A-PID-00064-005 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND YARD AIR DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100065-001 | 341-A-PID-00065-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100065-002 | 341-A-PID-00065-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070345 | SO6001-ES0D-PID-34100065-003 | 341-A-PID-00065-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600001-001 | 356-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM 6 DESAL FEED STRAINERS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600002-001 | 356-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 6 DESALINATION PLANT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600003-001 | 356-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM DRINKING WATER PUMPS AND COOLER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600004-001 | 356-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM ANTISCALE DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600005-001 | 356-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM ANTIFOAM DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600006-001 | 356-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM SODIUM BISULFITE DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600007-001 | 356-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH EVAPORATED AND DRINKING QUALITY DISTILLATE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600008-001 | 356-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM SALT WATER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600009-001 | 356-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM DISTRIBUTION | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600010-001 | 356-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM CONDENSATE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600011-001 | 356-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY AND DRINKING WATER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600012-001 | 356-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND YARD AIR | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600013-001 | 356-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600013-002 | 356-A-PID-00013-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070346 | SO6001-ES0D-PID-35600013-003 | 356-A-PID-00013-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070347 | SO6001-ES0D-PID-35700001-001 | 357-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM 7 DESAL FEED STRAINERS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070347 | SO6001-ES0D-PID-35700002-001 | 357-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 7 DESALINATION PLANT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070347 | SO6001-ES0D-PID-35700003-001 | 357-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM DRINKING WATER PUMPS AND COOLER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070347 | SO6001-ES0D-PID-35700004-001 | 357-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM ANTISCALE DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070347 | SO6001-ES0D-PID-35700005-001 | 357-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM ANTIFOAM DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070347 | SO6001-ES0D-PID-35700006-001 | 357-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM SODIUM BISULFITE DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070348 | SO6001-ES0D-PID-35800001-001 | 358-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM 8 DESAL FEED STRAINERS | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070348 | SO6001-ES0D-PID-35800002-001 | 358-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 8 DESALINATION PLANT | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070348 | SO6001-ES0D-PID-35800003-001 | 358-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM DRINKING WATER PUMPS AND COOLER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070348 | SO6001-ES0D-PID-35800004-001 | 358-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM ANTISCALE DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070348 | SO6001-ES0D-PID-35800005-001 | 358-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM ANTIFOAM DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070348 | SO6001-ES0D-PID-35800006-001 | 358-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM SODIUM BISULFITE DOSING PACKAGE | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070349 | SO6001-ES0D-PID-37900001-001 | 379-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM SALT WATER SYSTEM REFINERY | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070349 | SO6001-ES0D-PID-37900001-002 | 379-A-PID-00001-002 | PIPING & INSTRUMENTATION DIAGRAM SALT WATER SYSTEM REFINERY | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070349 | SO6001-ES0D-PID-37900001-005 | 379-A-PID-00001-005 | PIPING & INSTRUMENTATION DIAGRAM SALT WATER SYSTEM REFINERY | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070350 | SO6001-ES0D-PID-38200050-001 | 382-A-PID-00050-001 | PIPING & INSTRUMENTATION DIAGRAM OILY WATER BASIN | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070350 | SO6001-ES0D-PID-38200051-001 | 382-A-PID-00051-001 | PIPING & INSTRUMENTATION DIAGRAM CONTAMINATED STORM WATER SURGE BASIN | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070350 | SO6001-ES0D-PID-38200052-001 | 382-A-PID-00052-001 | PIPING & INSTRUMENTATION DIAGRAM CLEAN WATER SEWER | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070350 | SO6001-ES0D-PID-38200054-001 | 382-A-PID-00054-001 | PIPING & INSTRUMENTATION DIAGRAM #3 SULPHUR PLANT TOILET SANITARY BASIN | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070350 | SO6001-ES0D-PID-38200055-001 | 382-A-PID-00055-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITIES TOILET SANITARY BASIN | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070350 | SO6001-ES0D-PID-38200056-001 | 382-A-PID-00056-001 | PIPING & INSTRUMENTATION DIAGRAM WORKSTATION BUILDING SANITARY BASIN | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070350 | SO6001-ES0D-PID-38200058-001 | 382-A-PID-00058-001 | PIPING & INSTRUMENTATION DIAGRAM FINAL SANITARY BASIN | A | 2018-06-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-03 | CLASS 1
CON-BMP-TRA-070351 | SO6001-ES0R-HAZ-09400001-001 | 094-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE-OUT REPORT (DURING EPC) 2SHF (UNIT 094) AND SEWER SYSTEM (UNIT 382) | 0 | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 3 - REVIEWED WITH COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070352 | SO6001-ES0R-HAZ-00500001-001 | 005-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE-OUT REPORT (DURING EPC) LPG C3C4 STORAGE FACILITY AT REFINERY | 0 | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070353 | SO6001-ES0R-HAZ-09800001-001 | 098-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE-OUT REPORT (DURING EPC) NO.3 AND NO.4 H2 PLANT (UNIT 098 AND 099) | 0 | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-070354 | SO6001-ES0R-HAZ-93200001-001 | 932-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE-OUT REPORT (DURING EPC) SULPHUR BLOCK | 0 | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-04 | CLASS 2
CON-BMP-TRA-070355 | SO6001-ES0R-HAZ-34100001-001 | 341-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE-OUT REPORT (DURING EPC) 2IAS (UNIT 341) | 0 | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070356 | SO6001-ES0R-HAZ-31000001-001 | 310-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE-OUT REPORT (DURING EPC) UNIT 310, 311, 356, 371 AND 378 | 0 | 2018-06-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-05 |  |  | CLASS 2
CON-BMP-TRA-070357 | 076551C-000S-DL-4171-001 | 000-S-IDL-80009-001 | DEVIATION LIST FOR AIR DRYERS PACKAGE | A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-070357 | 076551C-000S-ITP-4171-001 | 000-S-ITP-80009-001 | INSPECTION AND TES PLAN FOR AIR DRYERS PACKAGE | A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-070357 | 076551C-000S-MR-4171-001 | 000-S-MRQ-80009-001 | MATERIAL REQUISITION FOR AIR DRYERS PACKAGE | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-070357 | 076551C-000S-SP-4171-001 | 000-S-GRD-80009-001 | SCOPE OF SUPPLY FOR AIR DRYERS PACKAGE | A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-070357 | 076551C-000S-SR-4171-001 | 000-S-SOW-80009-001 | SCOPE OF SUPPLY FOR AIR DRYERS PACKAGE | A | 2018-06-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-05 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-02 | CLASS 1
CON-BMP-TRA-070358 | SO6001-EJ2E-TDS-09800001-001 | 098-S-DAT-00001-001 | MECHANICAL DATA SHEET 098U0002 O2 SCAVENGER DOSING PACKAGE | A | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070359 | SO6001-EJ2E-TDS-09900001-001 | 099-S-DAT-00001-001 | MECHANICAL DATA SHEET 099U0002 O2 SCAVENGER DOSING PACKAGE | A | 2018-06-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-06 | 3 - REVIEWED WITH COMMENTS | 2018-07-03 | CLASS 2
CON-BMP-TRA-070360 | SO6001-ES0R-HAZ-37000001-001 | 370-A-HZR-00001-001 | FEED HAZOP2 RECOMMENDATIONS CLOSE-OUT REPORT (DURING EPC) UNIT 370 | 0 | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070361 | SO6001-EJ2E-TDS-37000001-001 | 370-S-DAT-00001-001 | DUTY SPECIFICATION FOR 370U0002 ACTIVATED CARBON FILTERS PACKAGE | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070362 | SO6001-EJ1E-TDS-00500007-001 | 005-C-DAT-55007-001 | FILTER DATA SHEET FOR 005V5007A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070363 | SO6001-EJ1E-TDS-03600012-001 | 036-C-DAT-00008-001 | FILTER DATA SHEET FOR 036V0004A/B AMINE PRE FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070363 | SO6001-EJ1E-TDS-03600013-001 | 036-C-DAT-00009-001 | FILTER DATA SHEET FOR 036V0005 AMINE CARBON FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070363 | SO6001-EJ1E-TDS-03600014-001 | 036-C-DAT-00010-001 | FILTER DATA SHEET FOR 036V0006 AMINE AFTER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070363 | SO6001-EJ1E-TDS-03600015-001 | 036-C-DAT-00011-001 | FILTER DATA SHEET FOR 036V0009 AMINE SUMP FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070363 | SO6001-EJ1E-TDS-03600016-001 | 036-C-DAT-00012-001 | FILTER DATA SHEET FOR 036V0010A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070364 | SO6001-EJ1E-TDS-03700011-001 | 037-C-DAT-00007-001 | FILTER DATA SHEET FOR 037V0004A/B AMINE PRE FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070364 | SO6001-EJ1E-TDS-03700012-001 | 037-C-DAT-00008-001 | FILTER DATA SHEET FOR 037V0005 AMINE CARBON FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070364 | SO6001-EJ1E-TDS-03700013-001 | 037-C-DAT-00009-001 | FILTER DATA SHEET FOR 037V0006 AMINE AFTER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070364 | SO6001-EJ1E-TDS-03700014-001 | 037-C-DAT-00010-001 | FILTER DATA SHEET FOR 037V0010A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070365 | SO6001-EJ1E-TDS-04100020-001 | 041-C-DAT-00008-001 | FILTER DATA SHEET FOR 041V0007A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070366 | SO6001-EJ1E-TDS-04200018-001 | 042-C-DAT-00006-001 | FILTER DATA SHEET FOR 042V0007A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070367 | SO6001-EJ1E-TDS-04300018-001 | 043-C-DAT-00006-001 | FILTER DATA SHEET FOR 043V0007A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070368 | SO6001-EJ1E-TDS-04400030-001 | 044-C-DAT-00016-001 | FILTER DATA SHEET FOR 044V0003A/B AMINE PRE FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070368 | SO6001-EJ1E-TDS-04400031-001 | 044-C-DAT-00017-001 | FILTER DATA SHEET FOR 044V0004 AMINE CARBON FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070368 | SO6001-EJ1E-TDS-04400032-001 | 044-C-DAT-00018-001 | FILTER DATA SHEET FOR 044V0005 AMINE AFTER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070368 | SO6001-EJ1E-TDS-04400033-001 | 044-C-DAT-00019-001 | FILTER DATA SHEET FOR 044V0012 AMINE SUMP FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070368 | SO6001-EJ1E-TDS-04400034-001 | 044-C-DAT-00020-001 | FILTER DATA SHEET FOR 044V0006A/B QUENCH WATER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070368 | SO6001-EJ1E-TDS-04400035-001 | 044-C-DAT-00021-001 | FILTER DATA SHEET FOR 044V0018A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070369 | SO6001-EJ1E-TDS-04500017-001 | 045-C-DAT-00007-001 | FILTER DATA SHEET FOR 045V0003A/B AMINE PRE FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070369 | SO6001-EJ1E-TDS-04500018-001 | 045-C-DAT-00008-001 | FILTER DATA SHEET FOR 045V0004 AMINE CARBON FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070369 | SO6001-EJ1E-TDS-04500019-001 | 045-C-DAT-00009-001 | FILTER DATA SHEET FOR 045V0005 AMINE AFTER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070369 | SO6001-EJ1E-TDS-04500020-001 | 045-C-DAT-00010-001 | FILTER DATA SHEET FOR 045V0006A/B QUENCH WATER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070369 | SO6001-EJ1E-TDS-04500021-001 | 045-C-DAT-00011-001 | FILTER DATA SHEET FOR 045V0018A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070370 | SO6001-EJ1E-TDS-04600011-001 | 046-C-DAT-00006-001 | FILTER DATA SHEET FOR 046V0003 STRIPPED WATER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070370 | SO6001-EJ1E-TDS-04600012-001 | 046-C-DAT-00007-001 | FILTER DATA SHEET FOR 046V0006A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070371 | SO6001-EJ1E-TDS-04800015-001 | 048-C-DAT-00008-001 | FILTER DATA SHEET FOR 048V0002A/B AMINE PRE FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070371 | SO6001-EJ1E-TDS-04800016-001 | 048-C-DAT-00009-001 | FILTER DATA SHEET FOR 048V0003A/B AMINE CARBON FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070371 | SO6001-EJ1E-TDS-04800017-001 | 048-C-DAT-00010-001 | FILTER DATA SHEET FOR 048V0004 AMINE AFTER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070371 | SO6001-EJ1E-TDS-04800018-001 | 048-C-DAT-00011-001 | FILTER DATA SHEET FOR 048V0008 AMINE SUMP FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070371 | SO6001-EJ1E-TDS-04800019-001 | 048-C-DAT-00012-001 | FILTER DATA SHEET FOR 048V0012A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070372 | SO6001-EJ1E-TDS-04900010-001 | 049-C-DAT-00005-001 | FILTER DATA SHEET FOR 049V0003A/B AMINE CARBON FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070372 | SO6001-EJ1E-TDS-04900011-001 | 049-C-DAT-00006-001 | FILTER DATA SHEET FOR 049V0004 AMINE AFTER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070372 | SO6001-EJ1E-TDS-04900012-001 | 049-C-DAT-00007-001 | FILTER DATA SHEET FOR 049V0012A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070373 | SO6001-EJ1E-TDS-09400002-001 | 094-C-DAT-00002-001 | FILTER DATA SHEET FOR 094V0006A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070374 | SO6001-EJ1E-TDS-09800023-001 | 098-C-DAT-00011-001 | FILTER DATA SHEET FOR 098V0018A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070375 | SO6001-EJ1E-TDS-09900023-001 | 099-C-DAT-00011-001 | FILTER DATA SHEET FOR 099V0018A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070376 | SO6001-EJ1E-TDS-35600001-001 | 356-C-DAT-00001-001 | FILTER DATA SHEET FOR 356V0007A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070376 | SO6001-EJ1E-TDS-35600002-001 | 356-C-DAT-00002-001 | FILTER DATA SHEET FOR 356V0008A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070377 | SO6001-EJ1E-TDS-37000003-001 | 370-C-DAT-00004-001 | FILTER DATA SHEET FOR 370V0007A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070377 | SO6001-EJ1E-TDS-37000004-001 | 370-C-DAT-00005-001 | FILTER DATA SHEET FOR 370V0008A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-05 | CLASS 2
CON-BMP-TRA-070378 | SO6001-EJ1E-TDS-04700009-001 | 047-C-DAT-00004-001 | FILTER DATA SHEET FOR 047V0003 STRIPPED WATER FILTER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070378 | SO6001-EJ1E-TDS-04700010-001 | 047-C-DAT-00005-001 | FILTER DATA SHEET FOR 047V0006A/B INSTRUMENT AIR FILTERS | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-001 | 016-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM FEED SECTION KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-002 | 016-A-PID-00001-002 | PIPING & INSTRUMENTATION DIAGRAM PREWASH SECTION - TRAIN A KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-003 | 016-A-PID-00001-003 | PIPING & INSTRUMENTATION DIAGRAM TRAIN B PREWASH SECTION KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-006 | 016-A-PID-00001-006 | PIPING & INSTRUMENTATION DIAGRAM STANDBY REACTOR SECTION KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-007 | 016-A-PID-00001-007 | PIPING & INSTRUMENTATION DIAGRAM TREATMENT SECTION - TRAIN A | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-009 | 016-A-PID-00001-009 | PIPING & INSTRUMENTATION DIAGRAM CAUSTIC STORAGE SECTION | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-010 | 016-A-PID-00001-010 | PIPING & INSTRUMENTATION DIAGRAM AIR COMPRESSOR SECTION KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-011 | 016-A-PID-00001-011 | PIPING & INSTRUMENTATION DIAGRAM CAUSTIC CIRCULATION &WATER WASH SECTION KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-012 | 016-A-PID-00001-012 | PIPING & INSTRUMENTATION DIAGRAM 110# STEAM KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-013 | 016-A-PID-00001-013 | PIPING & INSTRUMENTATION DIAGRAM SALT / POTABLE WATER EVAPORATED DISTILLATE KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-014 | 016-A-PID-00001-014 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN / INSTRUMENT AIR / YARD AIR KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-015 | 016-A-PID-00001-015 | PIPING & INSTRUMENTATION DIAGRAM FLARE HEADER KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-016 | 016-A-PID-00001-016 | PIPING & INSTRUMENTATION DIAGRAM OIL MIST LUBRICATION SYSTEM KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600001-017 | 016-A-PID-00001-017 | PIPING & INSTRUMENTATION DIAGRAM PUMP AUXILLIARY PIPING KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600050-001 | 016-A-PID-00050-001 | PIPING & INSTRUMENTATION DIAGRAM TRAIN C PREWASH SECTION KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600050-002 | 016-A-PID-00050-002 | PIPING & INSTRUMENTATION DIAGRAM TRAIN C REACTOR SECTION KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070379 | SO6001-ES0D-PID-01600050-003 | 016-A-PID-00050-003 | PIPING & INSTRUMENTATION DIAGRAM TRAIN C TREATMENT SECTION KERO MEROX PLANT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600001-001 | 036-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM FEED KO DRUM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600002-001 | 036-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE ABSORBER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600003-001 | 036-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM ABSORBER OVERHEAD KO DRUM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600004-001 | 036-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH DRUM AND FLASH GAS ABSORBER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600005-001 | 036-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH DRUM PUMP AND LEAN/RICH AMINE EXCHANGER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600006-001 | 036-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600007-001 | 036-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM PUMP AROUND PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600008-001 | 036-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR PUMP AROUND COOLER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600009-001 | 036-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR REBOILER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600010-001 | 036-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR BOTTOM PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600011-001 | 036-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE COOLER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600012-001 | 036-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE SURGE TANK & PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600013-001 | 036-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE FILTERS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600014-001 | 036-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE SUMP AND PUMP | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600015-001 | 036-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM HP LEAN AMINE PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600016-001 | 036-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600017-001 | 036-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE HEADER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600017-002 | 036-A-PID-00017-002 | PIPING & INSTRUMENTATION DIAGRAM FLARE PURGE GAS/NITROGEN SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600018-001 | 036-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM & CONDENSATE | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070380 | SO6001-ES0D-PID-03600019-001 | 036-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM DEMIN WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070381 | SO6001-ES0D-PID-03600020-001 | 036-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070381 | SO6001-ES0D-PID-03600021-001 | 036-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070381 | SO6001-ES0D-PID-03600022-001 | 036-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070381 | SO6001-ES0D-PID-03600023-001 | 036-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUSILIARY | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070381 | SO6001-ES0D-PID-03600023-002 | 036-A-PID-00023-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUSILIARY | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070381 | SO6001-ES0D-PID-03600024-001 | 036-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070381 | SO6001-ES0D-PID-03600024-002 | 036-A-PID-00024-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070381 | SO6001-ES0D-PID-03600024-003 | 036-A-PID-00024-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700001-001 | 037-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM FEED KO DRUM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700002-001 | 037-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE ABSORBER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700003-001 | 037-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM ABSORBER OVERHEAD KO DRUM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700004-001 | 037-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH DRUM & FLASH GAS ABSORBER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700005-001 | 037-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH DRUM PUMP & LEAN/RICH AMINE EXCHANGER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700006-001 | 037-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700007-001 | 037-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM PUMP AROUND PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700008-001 | 037-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR PUMP AROUND COOLER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700009-001 | 037-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR REBOILER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700010-001 | 037-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR BOTTOM PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700011-001 | 037-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE COOLER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700012-001 | 037-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE SURGE TANK & PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700013-001 | 037-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE FILTERS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700015-001 | 037-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM HP LEAN AMINE PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700016-001 | 037-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700017-001 | 037-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE HEADER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700017-002 | 037-A-PID-00017-002 | PIPING & INSTRUMENTATION DIAGRAM FLARE PURGE GAS / NITROGEN SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700018-001 | 037-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM & CONDENSATE | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700019-001 | 037-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM DEMIN WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070382 | SO6001-ES0D-PID-03700020-001 | 037-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070383 | SO6001-ES0D-PID-03700021-001 | 037-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-070383 | SO6001-ES0D-PID-03700022-001 | 037-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-070383 | SO6001-ES0D-PID-03700023-001 | 037-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-070383 | SO6001-ES0D-PID-03700023-002 | 037-A-PID-00023-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-070383 | SO6001-ES0D-PID-03700024-001 | 037-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-070383 | SO6001-ES0D-PID-03700024-002 | 037-A-PID-00024-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-070383 | SO6001-ES0D-PID-03700024-003 | 037-A-PID-00024-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100001-001 | 041-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM ACID GAS KO DRUM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100002-001 | 041-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM SWS OFF GAS KO DRUM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100003-001 | 041-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM COMBUSTION AIR BLOWER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100004-001 | 041-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM SRU FEED CONTROL | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100005-001 | 041-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM ACID GAS & COMBUSTION AIR PREHEATER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100006-001 | 041-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM REACTION FURNACE BURNER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100007-001 | 041-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100008-001 | 041-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM NO.1 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100009-001 | 041-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM NO.1 CONVERTER AND NO.1 REHEAT EXCHANGER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100010-001 | 041-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM NO.2 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100011-001 | 041-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM NO.2 CONVERTER AND NO.2 REHEAT EXCHANGER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100012-001 | 041-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM NO.3 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100013-001 | 041-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM CONDENSER COOLER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100014-001 | 041-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR DEGASSING PIT & EJECTOR | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100015-001 | 041-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR STORAGE PIT & TRANFER PUMP | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100016-001 | 041-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100017-001 | 041-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100017-002 | 041-A-PID-00017-002 | PIPING & INSTRUMENTATION DIAGRAM FLARE PURGE GAS SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100018-001 | 041-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070384 | SO6001-ES0D-PID-04100019-001 | 041-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM BOILER FEED WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100020-001 | 041-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100021-001 | 041-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100022-001 | 041-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100023-001 | 041-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100024-001 | 041-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100024-002 | 041-A-PID-00024-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100025-001 | 041-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100025-002 | 041-A-PID-00025-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070385 | SO6001-ES0D-PID-04100025-003 | 041-A-PID-00025-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200004-001 | 042-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM SRU FEED CONTROL | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200005-001 | 042-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM ACID GAS & COMBUSTION AIR PREHEATER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200006-001 | 042-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM REACTION FURNACE BURNER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200007-001 | 042-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200008-001 | 042-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 1 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200009-001 | 042-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 1 CONVERTER AND NO. 1 REHEAT EXCHANGER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200010-001 | 042-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 2 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200011-001 | 042-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 2 CONVERTER AND NO. 2 REHEAT EXCHANGER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200012-001 | 042-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 3 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200013-001 | 042-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM CONDENSER COOLER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200014-001 | 042-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR DEGASSING PIT & EJECTOR | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200015-001 | 042-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR STORAGE PIT & TRANFER PUMP | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200016-001 | 042-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200017-001 | 042-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200017-002 | 042-A-PID-00017-002 | PIPING & INSTRUMENTATION DIAGRAM FLARE PURGE GAS SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200018-001 | 042-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200019-001 | 042-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM BOILER FEED WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200020-001 | 042-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200021-001 | 042-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070386 | SO6001-ES0D-PID-04200022-001 | 042-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070387 | SO6001-ES0D-PID-04200023-001 | 042-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070387 | SO6001-ES0D-PID-04200024-001 | 042-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070387 | SO6001-ES0D-PID-04200024-002 | 042-A-PID-00024-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070387 | SO6001-ES0D-PID-04200025-001 | 042-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070387 | SO6001-ES0D-PID-04200025-002 | 042-A-PID-00025-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070387 | SO6001-ES0D-PID-04200025-003 | 042-A-PID-00025-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300004-001 | 043-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM SRU FEED CONTROL | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300005-001 | 043-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM ACID GAS & COMBUSTION AIR PREHEATER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300006-001 | 043-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM REACTION FURNACE BURNER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300007-001 | 043-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300008-001 | 043-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 1 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300009-001 | 043-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 1 CONVERTER AND NO. 1 REHEAT EXCHANGER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300010-001 | 043-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 2 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300011-001 | 043-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 2 CONVERTER AND NO. 2 REHEAT EXCHANGER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300012-001 | 043-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM NO. 3 SULPHUR CONDENSER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300013-001 | 043-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM CONDENSER COOLER | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300014-001 | 043-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR DEGASSING PIT & EJECTOR | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300015-001 | 043-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR STORAGE PIT & TRANSFER PUMPS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300016-001 | 043-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300017-001 | 043-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300017-002 | 043-A-PID-00017-002 | PIPING & INSTRUMENTATION DIAGRAM FLARE PURGE GAS SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300018-001 | 043-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300019-001 | 043-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM BOILER FEED WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300020-001 | 043-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300021-001 | 043-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070388 | SO6001-ES0D-PID-04300022-001 | 043-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070389 | SO6001-ES0D-PID-04300023-001 | 043-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070389 | SO6001-ES0D-PID-04300024-001 | 043-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070389 | SO6001-ES0D-PID-04300024-002 | 043-A-PID-00024-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070389 | SO6001-ES0D-PID-04300025-001 | 043-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070389 | SO6001-ES0D-PID-04300025-002 | 043-A-PID-00025-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070389 | SO6001-ES0D-PID-04300025-003 | 043-A-PID-00025-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070390 | SO6001-ES0D-PID-08800001-003 | 088-A-PID-00001-003 | PIPING & INSTRUMENTATION DIAGRAM MAIN FRACTIONATION SECTION | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-070390 | SO6001-ES0D-PID-08800001-004 | 088-A-PID-00001-004 | PIPING & INSTRUMENTATION DIAGRAM KERO RETRUN UNIT | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-070390 | SO6001-ES0D-PID-08800001-005 | 088-A-PID-00001-005 | PIPING & INSTRUMENTATION DIAGRAM STEAM/COOLING WATER/FIRE WATER/UTILITY | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-070390 | SO6001-ES0D-PID-08800001-006 | 088-A-PID-00001-006 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT / UTILITY AIR SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-070390 | SO6001-ES0D-PID-08800001-007 | 088-A-PID-00001-007 | PIPING & INSTRUMENTATION DIAGRAM RELIEF AND FLARE SYSTEM | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-070390 | SO6001-ES0D-PID-08800050-001 | 088-A-PID-00050-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-06 | CLASS 1
CON-BMP-TRA-070391 | SO6001-EJ1E-TDS-01600007-001 | 016-C-DAT-00006-001 | COALESCER DATA SHEET FOR 016V1641 WATER COALESCER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070392 | SO6001-EJ1E-TDS-09800022-001 | 098-C-DAT-00010-001 | COALESCER DATA SHEET FOR 098V0009 HYDROGEN RECYCLE GAS COALESCER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070393 | SO6001-EJ1E-TDS-09900022-001 | 099-C-DAT-00010-001 | COALESCER DATA SHEET FOR 099V0009 HYDROGEN RECYCLE GAS COALESCER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 |  |  | CLASS 2
CON-BMP-TRA-070394 | SO6001-EJ1E-TDS-04100017-001 | 041-C-DAT-00005-001 | SULPHUR LOCK DATA SHEET FOR 041V0004 NO.1 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070394 | SO6001-EJ1E-TDS-04100018-001 | 041-C-DAT-00006-001 | SULPHUR LOCK DATA SHEET FOR 041V0005 NO.2 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070394 | SO6001-EJ1E-TDS-04100019-001 | 041-C-DAT-00007-001 | SULPHUR LOCK DATA SHEET FOR 041V0006 NO.3 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070395 | SO6001-EJ1E-TDS-04200015-001 | 042-C-DAT-00003-001 | SULPHUR LOCK DATA SHEET FOR 042V0004 NO.1 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070395 | SO6001-EJ1E-TDS-04200016-001 | 042-C-DAT-00004-001 | SULPHUR LOCK DATA SHEET FOR 042V0005 NO.2 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070395 | SO6001-EJ1E-TDS-04200017-001 | 042-C-DAT-00005-001 | SULPHUR LOCK DATA SHEET FOR 042V0006 NO.3 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070396 | SO6001-EJ1E-TDS-04300015-001 | 043-C-DAT-00003-001 | SULPHUR LOCK DATA SHEET FOR 043V0004 NO.1 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070396 | SO6001-EJ1E-TDS-04300016-001 | 043-C-DAT-00004-001 | SULPHUR LOCK DATA SHEET FOR 043V0005 NO.2 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070396 | SO6001-EJ1E-TDS-04300017-001 | 043-C-DAT-00005-001 | SULPHUR LOCK DATA SHEET FOR 043V0006 NO.3 SULPHUR LOCK | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070397 | SO6001-EJ1E-TDS-04400038-001 | 044-S-DAT-00003-001 | DESUPERHEATER DATA SHEET FOR 044DS0001 600# STEAM DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070397 | SO6001-EJ1E-TDS-04400039-001 | 044-S-DAT-00004-001 | DESUPERHEATER DATA SHEET FOR 044DS0001 500# STEAM DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070398 | SO6001-EJ1E-TDS-04500024-001 | 045-S-DAT-00001-001 | DESUPERHEATER DATA SHEET FOR 045DS0001 600# STEAM DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070399 | SO6001-EJ1E-TDS-09400004-001 | 094-S-DAT-00006-001 | DESUPERHEATER DATA SHEET FOR 094DS0001 2SHF 70 STEAM DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070400 | SO6001-EJ1E-TDS-34100003-001 | 341-S-DAT-00003-001 | DESUPERHEATER DATA SHEET FOR 341DS0140A/B T3410A/B DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000014-001 | 370-S-DAT-00006-001 | DESUPERHEATER DATA SHEET FOR 370DS0001 T0006A DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000016-001 | 370-S-DAT-00008-001 | DESUPERHEATER DATA SHEET FOR 370DS0004 T0007B DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000017-001 | 370-S-DAT-00009-001 | DESUPERHEATER DATA SHEET FOR 370DS0005 T0008A DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000018-001 | 370-S-DAT-00010-001 | DESUPERHEATER DATA SHEET FOR 370DS0007 T0009A DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000019-001 | 370-S-DAT-00011-001 | DESUPERHEATER DATA SHEET FOR 370DS0009 T0012A DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000020-001 | 370-S-DAT-00012-001 | DESUPERHEATER DATA SHEET FOR 370DS0010 T0012B DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000021-001 | 370-S-DAT-00007-001 | DESUPERHEATER DATA SHEET FOR 370DS0003 T0007A DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000022-001 | 370-S-DAT-00014-001 | DESUPERHEATER DATA SHEET FOR 370DS0006 T0008B DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070401 | SO6001-EJ1E-TDS-37000023-001 | 370-S-DAT-00015-001 | DESUPERHEATER DATA SHEET FOR 370DS0008 T0009B DESUPERHEATER | A | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070402 | SO6001-EJ2E-TDS-34120001-001 | 341-K-DAT-00001-001 | DATASHEET FOR INTEGRALLY GEARED CENTRIFUGAL COMPRESSORS 341K 3415 A-B-C-D AIR COMPRESSORS | C | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070402 | SO6001-EJ2E-TDS-34120002-001 | 341-K-DAT-00002-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES 341T3410 A-B AIR COMPRESSOR STEAM TURBINES | B | 2018-06-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070403 | 076551C-000S-DL-1013-001 | 000-K-IDL-80003-001 | DEVIATION LIST FOR INTEGRALLY GEARED CENTRIFUGAL COMPRESSORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070403 | 076551C-000S-ITP-1013-001 | 000-K-ITP-80003-001 | INSPECTION AND TEST PLAN FOR INTEGRALLY GEARED CENTRIFUGAL COMPRESSORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070403 | 076551C-000S-SP-1013-001 | 000-K-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR INTEGRALLY GEARED CENTRIFUGAL COMPRESSORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070403 | 076551C-000S-SR-1013-001 | 000-K-SOW-80003-001 | SCOPE OF SUPPLY FOR INTEGRALLY GEARED CENTRIFUGAL COMPRESSORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070404 | SO6001-EJ1E-TDS-04900009-001 | 049-C-DAT-00004-001 | FILTER DATA SHEET FOR 049V0002 A-B AMINE PRE FILTERS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070405 | SO6001-EJ1E-TDS-37000015-001 | 370-S-DAT-00013-001 | DESUPERHEATER DATA SHEET FOR 370DS0002 T0006B DESUPERHEATER | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070406 | SO6001-EJ1E-TDS-04100021-001 | 041-H-DAT-00001-001 | EJECTOR DATA SHEET FOR 041H0001A/B SULPHUR PIT EJECTORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-070407 | SO6001-EJ1E-TDS-04200019-001 | 042-H-DAT-00001-001 | EJECTOR DATA SHEET FOR 042H0001A/B SULPHUR PIT EJECTORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-070408 | SO6001-EJ1E-TDS-04300019-001 | 043-H-DAT-00001-001 | EJECTOR DATA SHEET FOR 043H0001A/B SULPHUR PIT EJECTORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-070409 | SO6001-EJ1E-TDS-04400037-001 | 044-H-DAT-00001-001 | EJECTOR DATA SHEET FOR 044H0001 START-UP GAS STEAM EJECTOR | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-070410 | SO6001-EJ1E-TDS-04500023-001 | 045-H-DAT-00001-001 | EJECTOR DATA SHEET FOR 045H0001 START-UP GAS STEAM EJECTOR | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-070411 | SO6001-EJ1E-TDS-04600014-001 | 046-H-DAT-00001-001 | EJECTOR DATA SHEET FOR 046H0001 DEGASSING DRUM EJECTORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-10 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 1
CON-BMP-TRA-070412 | SO6001-EJ1E-TDS-04700012-001 | 047-H-DAT-00001-001 | EJECTOR DATA SHEET FOR 047H0001 DEGASSING DRUM EJECTORS | A | 2018-06-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 1
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010001-001 | 370-G-DAT-00001-001 | DATA SHEET FOR 370P0001 A-B-C RECOVERED CONDENSATE PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010002-001 | 370-G-DAT-00002-001 | DATA SHEET FOR 370P0002 A-B-C A.C. FILTERS FEED PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010004-001 | 370-G-DAT-00004-001 | DATA SHEET FOR 370P0004 A-B-C CONDENSATE POLISHING FEED PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010005-001 | 370-G-DAT-00005-001 | DATA SHEET FOR 370P0005 A-B-C DEMINERALIZED WATER PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010006-001 | 370-G-DAT-00006-001 | DATA SHEET FOR 370P0006 A-B-C DEAERATOR FEED WATER PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010007-001 | 370-G-DAT-00007-001 | DATA SHEET FOR 370P0007 A-B-C HOTWELL FEED WATER PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010008-001 | 370-G-DAT-00008-001 | DATA SHEET FOR 370P0008 A-B-C HP BFW PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010009-001 | 370-G-DAT-00009-001 | DATA SHEET FOR 370P0009 A-B-C LP BFW PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070413 | SO6001-EJ2E-TDS-37010012-001 | 370-G-DAT-00012-001 | DATA SHEET FOR 370P0012 A-B-C HP BOILER FEED WATER PUMPS | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070414 | SO6001-EJ2E-TDS-37020006-001 | 370-K-DAT-00006-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 370T0006 A-B DEAERATOR FEED WATER PUMPS TURBINES | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070414 | SO6001-EJ2E-TDS-37020007-001 | 370-K-DAT-00007-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 370T0007 A-B HOTWELL FEED WATER PUMPS TURBINES | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070414 | SO6001-EJ2E-TDS-37020008-001 | 370-K-DAT-00008-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 370T0008 A-B HP BFW PUMPS TURBINES | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070414 | SO6001-EJ2E-TDS-37020009-001 | 370-K-DAT-00009-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 370T0009 A-B LP BFW PUMPS TURBINES | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070414 | SO6001-EJ2E-TDS-37020012-001 | 370-K-DAT-00012-001 | DATA SHEET FOR GENERAL PURPOSE STEAM TURBINES 370T0012 A-B HP BOILER FEED WATER PUMPS TURBINES | A | 2018-06-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-11 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070415 | SO6001-EJ2E-TDS-03600001-001 | 036-S-DAT-00001-001 | DATA SHEET FOR 036OMG0001 2 AND 3BAGRU OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070416 | SO6001-EJ2E-TDS-04400002-001 | 044-S-DAT-00002-001 | DATA SHEET FOR 044OMG0001 3TGTU OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070417 | SO6001-EJ2E-TDS-04600002-001 | 046-S-DAT-00002-001 | DATA SHEET FOR 046OMG0001 5SWS OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070417 | SO6001-EJ2E-TDS-04600003-001 | 046-S-DAT-00003-001 | DATA SHEET FOR 046U5602 5SWS OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070418 | SO6001-EJ2E-TDS-04800002-001 | 048-S-DAT-00002-001 | DATA SHEET FOR 048OMG0001 2ARU OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070419 | SO6001-EJ2E-TDS-09400005-001 | 094-S-DAT-00005-001 | DATA SHEET FOR 094OMG0001 2SHF OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070420 | SO6001-EJ2E-TDS-09800006-001 | 098-S-DAT-00006-001 | DATA SHEET FOR 098U0005 HYDROGEN OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070421 | SO6001-EJ2E-TDS-37000005-001 | 370-S-DAT-00005-001 | DATA SHEET FOR 370OMG0001 BFW OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070422 | SO6001-EJ2E-TDS-37100001-001 | 371-S-DAT-55001-001 | DATA SHEET FOR 371U0001 STM G&D OIL MIST GENERATOR | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070423 | SO6001-EJ2E-TDS-37000002-001 | 370-S-DAT-00002-001 | DUTY SPECIFICATION FOR CONDENSATE POLISHING MIXED BED PACKAGE (PREVIOUSLY ISSUE WITH 372-S-DAT-540002-001) | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070423 | SO6001-EJ2E-TDS-37000003-001 | 370-S-DAT-00003-001 | DUTY SPECIFICATION FOR FED POLISHING MIXED BED PACKAGE (PREVIOUSLY ISSUE WITH 372-S-DAT-540003-001) | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-06 | CLASS 2
CON-BMP-TRA-070424 | SO6001-EJ2E-TDS-35600002-001 | 356-S-DAT-00002-001 | DUTY SPECIFICATION FOR 356U0002 NO6 DESALINATION PLANT SALT WAATER FEED STRAINERS PACKAGE | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 2
CON-BMP-TRA-070425 | SO6001-EJ2E-TDS-35700002-001 | 357-S-DAT-00002-001 | DUTY SPECIFICATION FOR 356U0002 NO 7 DESALINATION PLANT SALT WATER FEED STRAINERS PACKAGE | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070426 | SO6001-EJ2E-TDS-35800002-001 | 358-S-DAT-00002-001 | DUTY SPECIFICATION FOR 358U0002 NO 8 DESALINATION PLANT SALT WATER FEED STRAINERS PACKAGE | A | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070428 | SO6001-EJ1E-TDS-04100013-001 | 041-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070429 | SO6001-EJ1E-TDS-04200013-001 | 042-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 042E0007 COMBUSTION PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070430 | SO6001-EJ1E-TDS-04300013-001 | 043-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070431 | SO6001-EJ1E-TDS-04400013-001 | 044-E-DAT-00008-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070432 | SO6001-EJ1E-TDS-04500010-001 | 045-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGERS DATA SHEET FOR 045E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070433 | SO6001-EJ1E-TDS-04100013-002-001 | 041-E-GAD-00003-001 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070433 | SO6001-EJ1E-TDS-04100013-002-002 | 041-E-GAD-00003-002 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070433 | SO6001-EJ1E-TDS-04100013-002-003 | 041-E-GAD-00003-003 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070433 | SO6001-EJ1E-TDS-04100013-002-004 | 041-E-GAD-00003-004 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070433 | SO6001-EJ1E-TDS-04100013-002-005 | 041-E-GAD-00003-005 | MECHANICAL DATA SHEET FOR 041E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070434 | SO6001-EJ1E-TDS-04200013-002-001 | 042-E-GAD-00003-001 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070434 | SO6001-EJ1E-TDS-04200013-002-002 | 042-E-GAD-00003-002 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070434 | SO6001-EJ1E-TDS-04200013-002-003 | 042-E-GAD-00003-003 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070434 | SO6001-EJ1E-TDS-04200013-002-004 | 042-E-GAD-00003-004 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070434 | SO6001-EJ1E-TDS-04200013-002-005 | 042-E-GAD-00003-005 | MECHANICAL DATA SHEET FOR 042E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070435 | SO6001-EJ1E-TDS-04300013-002-001 | 043-E-GAD-00003-001 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070435 | SO6001-EJ1E-TDS-04300013-002-002 | 043-E-GAD-00003-002 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070435 | SO6001-EJ1E-TDS-04300013-002-003 | 043-E-GAD-00003-003 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070435 | SO6001-EJ1E-TDS-04300013-002-004 | 043-E-GAD-00003-004 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070435 | SO6001-EJ1E-TDS-04300013-002-005 | 043-E-GAD-00003-005 | MECHANICAL DATA SHEET FOR 043E0007 COMBUSTION AIR PREHEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070436 | SO6001-EJ1E-TDS-04400013-002-001 | 044-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070436 | SO6001-EJ1E-TDS-04400013-002-002 | 044-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070436 | SO6001-EJ1E-TDS-04400013-002-003 | 044-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070436 | SO6001-EJ1E-TDS-04400013-002-004 | 044-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070436 | SO6001-EJ1E-TDS-04400013-002-005 | 044-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 044E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070437 | SO6001-EJ1E-TDS-04500010-001-001 | 045-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070437 | SO6001-EJ1E-TDS-04500010-001-002 | 045-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070437 | SO6001-EJ1E-TDS-04500010-001-003 | 045-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070437 | SO6001-EJ1E-TDS-04500010-001-004 | 045-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070437 | SO6001-EJ1E-TDS-04500010-001-005 | 045-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 045E0001 FEED HEATER | B | 2018-06-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-12 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070438 | 076551C-000S-DL-0610-004 | 000-E-IDL-80003-001 | DEVIATION LIST FOR CS SHELL AND TUBE HEAT EXCHANGERS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 |  |  | CLASS 1
CON-BMP-TRA-070438 | 076551C-000S-ITP-0610-004 | 000-E-ITP-80003-001 | INSPECTION AND TEST PLAN FOR CS SHELL AND TUBE HEAT EXCHANGERS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 |  |  | CLASS 1
CON-BMP-TRA-070438 | 076551C-000S-MR-0610-004 | 000-E-MRQ-80003-001 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGERS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-070438 | 076551C-000S-SP-0610-004 | 000-E-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS SHELL AND TUBE HEAT EXCHANGERS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 |  |  | CLASS 1
CON-BMP-TRA-070438 | 076551C-000S-SR-0610-004 | 000-E-SOW-80003-001 | SCOPE OF SUPPLY FOR CS SHELL AND TUBE HEAT EXCHANGERS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-12 |  |  | CLASS 1
CON-BMP-TRA-070439 | 076551C-000S-DL-0630-001 | 000-E-IDL-80005-001 | INSPECTION AND TEST PLAN FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-070439 | 076551C-000S-ITP-0630-001 | 000-E-ITP-80005-001 | INSPECTION AND TEST PLAN FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-070439 | 076551C-000S-MR-0630-001 | 000-E-MRQ-80005-001 | MATERIAL REQUISITION FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-070439 | 076551C-000S-SP-0630-001 | 000-E-GRD-80005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-070439 | 076551C-000S-SR-0630-001 | 000-E-SOW-80005-001 | SCOPE OF SUPPLY FOR HAIR PIN TYPE HEAT EXCHANGER | A | 2018-06-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 3 - REVIEWED WITH COMMENTS | 2018-07-11 | CLASS 1
CON-BMP-TRA-070440 | 076551C-000S-DL-0213-001 | 000-S-IDL-80001-001 | DEVIATION LIST FOR POLISHING PACKAGE | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 |  |  | CLASS 1
CON-BMP-TRA-070440 | 076551C-000S-ITP-0213-001 | 000-S-ITP-80001-001 | INSPECTION AND TEST PLAN FOR POLISHING PACKAGE | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 |  |  | CLASS 1
CON-BMP-TRA-070440 | 076551C-000S-MR-0213-001 | 000-S-MRQ-80001-001 | MATERIAL REQUISITION FOR POLISHING PACKAGE | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-09 | CLASS 1
CON-BMP-TRA-070440 | 076551C-000S-SP-0213-001 | 000-S-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR POLISHING PACKAGE | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 |  |  | CLASS 1
CON-BMP-TRA-070440 | 076551C-000S-SR-0213-001 | 000-S-SOW-80001-001 | SCOPE OF SUPPLY FOR POLISHING PACKAGE | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-13 |  |  | CLASS 1
CON-BMP-TRA-070441 | SO6001-EJ2E-TDS-03610001-001 | 036-G-DAT-00001-001 | DATA SHEET FOR 036P0001A/B RICH AMINE FLASH DRUM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070441 | SO6001-EJ2E-TDS-03610002-001 | 036-G-DAT-00002-001 | DATA SHEET FOR 036P0002A/B REGENERATOR BOTTOM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070441 | SO6001-EJ2E-TDS-03610003-001 | 036-G-DAT-00003-001 | DATA SHEET FOR 036P0003A/B REGENERATOR PUMP AROUND PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070441 | SO6001-EJ2E-TDS-03610004-001 | 036-G-DAT-00004-001 | DATA SHEET FOR 036P0004A/B LP LEAN AMINE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070442 | SO6001-EJ2E-TDS-03710001-001 | 037-G-DAT-00001-001 | DATA SHEET FOR 037P0001A/B RICH AMINE FLASH DRUM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070442 | SO6001-EJ2E-TDS-03710002-001 | 037-G-DAT-00002-001 | DATA SHEET FOR 037P0002A/B REGENERATOR BOTTOM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070442 | SO6001-EJ2E-TDS-03710003-001 | 037-G-DAT-00003-001 | DATA SHEET FOR 037P0003A/B REGENERATOR PUMP AROUND PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070442 | SO6001-EJ2E-TDS-03710004-001 | 037-G-DAT-00004-001 | DATA SHEET FOR 037P0004A/B LP LEAN AMINE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070443 | SO6001-EJ2E-TDS-04410001-001 | 044-G-DAT-00001-001 | DATA SHEET FOR 044P0001A/B QUENCH WATER CIRCULATION PUMP/COMMON PUMP (1, 10) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070443 | SO6001-EJ2E-TDS-04410002-001 | 044-G-DAT-00002-001 | DATA SHEET FOR 044P0002 QUENCH WATER CIRCULATION PUMP (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070443 | SO6001-EJ2E-TDS-04410003-001 | 044-G-DAT-00003-001 | DATA SHEET FOR 044P0003 A/B RICH AMINE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070443 | SO6001-EJ2E-TDS-04410004-001 | 044-G-DAT-00004-001 | DATA SHEET FOR 044P0004 A/B REGENERATOR BOTTOM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070443 | SO6001-EJ2E-TDS-04410005-001 | 044-G-DAT-00005-001 | DATA SHEET FOR 044P0005 A/B AMINE REGENERATOR PUMP AROUND PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070443 | SO6001-EJ2E-TDS-04410006-001 | 044-G-DAT-00006-001 | DATA SHEET FOR 044P0006 A/B LEAN AMINE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070443 | SO6001-EJ2E-TDS-04410008-001 | 044-G-DAT-00008-001 | DATA SHEET FOR 044P0008 A/B N.3 SULPHUR PLANT FLARE KO DRUM PUMPS (14) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070443 | SO6001-EJ2E-TDS-04410009-001 | 044-G-DAT-00009-001 | DATA SHEET FOR 044P0009 A/B CONDENSATE TRANSFER PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070444 | SO6001-EJ2E-TDS-04510001-001 | 045-G-DAT-00001-001 | DATA SHEET FOR 045P0001A/B QUENCH WATER CIRCULATION PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070444 | SO6001-EJ2E-TDS-04510002-001 | 045-G-DAT-00002-001 | DATA SHEET FOR 045P0002 QUENCH WATER PUMP (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070444 | SO6001-EJ2E-TDS-04510003-001 | 045-G-DAT-00003-001 | DATA SHEET FOR 045P0003 A/B RICH AMINE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070444 | SO6001-EJ2E-TDS-04510004-001 | 045-G-DAT-00004-001 | DATA SHEET FOR 045P0004 A/B REGENERATOR BOTTOM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070444 | SO6001-EJ2E-TDS-04510005-001 | 045-G-DAT-00005-001 | DATA SHEET FOR 045P0005 A/B AMINE REGENERATOR PUMP AROUND PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070444 | SO6001-EJ2E-TDS-04510006-001 | 045-G-DAT-00006-001 | DATA SHEET FOR 045P0006 A/B LEAN AMINE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070445 | SO6001-EJ2E-TDS-04610001-001 | 046-G-DAT-00001-001 | DATA SHEET FOR 046P0001A/B SOUR WATER TRANSFER PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070445 | SO6001-EJ2E-TDS-04610002-001 | 046-G-DAT-00002-001 | DATA SHEET FOR 046P0002A/B SOUR WATER STRIPPER FEED PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070445 | SO6001-EJ2E-TDS-04610003-001 | 046-G-DAT-00003-001 | DATA SHEET FOR 046P0003A/B STRIPPED WATER PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070445 | SO6001-EJ2E-TDS-04610004-001 | 046-G-DAT-00004-001 | DATA SHEET FOR 046P0004A/B STRIPPER PUMP AROUND PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070445 | SO6001-EJ2E-TDS-04610007-001 | 046-G-DAT-00007-001 | DATA SHEET FOR 046P0007 OIL SKIMMING PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070446 | SO6001-EJ2E-TDS-04710001-001 | 047-G-DAT-00001-001 | DATA SHEET FOR 047P0001A/B SOUR WATER TRANSFER PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070446 | SO6001-EJ2E-TDS-04710002-001 | 047-G-DAT-00002-001 | DATA SHEET FOR 047P0002A/B SOUR WATER STRIPPER FEED PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070446 | SO6001-EJ2E-TDS-04710003-001 | 047-G-DAT-00003-001 | DATA SHEET FOR 047P0003A/B STRIPPED WATER PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070446 | SO6001-EJ2E-TDS-04710004-001 | 047-G-DAT-00004-001 | DATA SHEET FOR 047P0004A/B STRIPPER PUMPAROUND PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070447 | SO6001-EJ2E-TDS-04810001-001 | 048-G-DAT-00001-001 | DATA SHEET FOR 048P0001A/B RICH AMINE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070447 | SO6001-EJ2E-TDS-04810002-001 | 048-G-DAT-00002-001 | DATA SHEET FOR 048P0002A/B REGENERATOR BOTTOM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070447 | SO6001-EJ2E-TDS-04810003-001 | 048-G-DAT-00003-001 | DATA SHEET FOR 048P0003A/B REGENERATOR PUMP AROUND PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070447 | SO6001-EJ2E-TDS-04810006-001 | 048-G-DAT-00006-001 | DATA SHEET FOR 048P0006 FRESH AMINE MAKE UP PUMP (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070447 | SO6001-EJ2E-TDS-04810007-001 | 048-G-DAT-00007-001 | DATA SHEET FOR 048P0007 A/B ARU CONDENSATE TRANSFER PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070447 | SO6001-EJ2E-TDS-04810009-001 | 048-G-DAT-00009-001 | DATA SHEET FOR 048P0009 A/B ARU FLARE KO DRUM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 2
CON-BMP-TRA-070448 | SO6001-EJ2E-TDS-04910001-001 | 049-G-DAT-00001-001 | DATA SHEET FOR 049P0001A/B RICH AMINE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070448 | SO6001-EJ2E-TDS-04910002-001 | 049-G-DAT-00002-001 | DATA SHEET FOR 049P0002A/B REGENERATOR BOTTOM PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070448 | SO6001-EJ2E-TDS-04910003-001 | 049-G-DAT-00003-001 | DATA SHEET FOR 049P0003A/B REGENERATOR PUMP AROUND PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070449 | SO6001-EJ2E-TDS-09810008-001 | 098-G-DAT-00008-001 | DATA SHEET FOR 098P0008A/B PROCESS CONDENSATE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070450 | SO6001-EJ2E-TDS-09910008-001 | 099-G-DAT-00008-001 | DATA SHEET FOR 099P0008A/B PROCESS CONDENSATE PUMPS (1) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070451 | SO6001-EJ2E-TDS-01610001-001 | 016-G-DAT-00001-001 | DATA SHEET FOR 016P9600D KEROSENE FEED PUMP TRAIN C | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070452 | 076511C-000S-DL-0910-001 | 000-G-IDL-80001-001 | DEVIATION LIST FOR OH2 API 610 PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-070452 | 076511C-000S-ITP-0910-001 | 000-G-ITP-80001-001 | INSPECTION AND TEST PLAN FOR OH2 API 610 PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-070452 | 076511C-000S-MR-0910-001 | 000-G-MRQ-80001-001 | MATERIAL REQUISITION FOR OH2 API 610 PUMPS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-070452 | 076511C-000S-SP-0910-001 | 000-G-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR OH2 API 610 PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-070452 | 076511C-000S-SR-0910-001 | 000-G-SOW-80001-001 | SCOPE OF SUPPLY FOR OH2 API 610 PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-15 | CLASS 1
CON-BMP-TRA-070453 | SO6001-EJ2E-TDS-03610005-001 | 036-G-DAT-00005-001 | DATA SHEET FOR 036P0005A/B HP LEAN AMINE PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070454 | SO6001-EJ2E-TDS-03710005-001 | 037-G-DAT-00005-001 | DATA SHEET FOR 037P0005A/B HP LEAN AMINE PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070455 | SO6001-EJ2E-TDS-04810004-001 | 048-G-DAT-00004-001 | DATASHEET FOR 048P0004A/B LEAN AMINE PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070456 | SO6001-EJ2E-TDS-04910004-001 | 049-G-DAT-00004-001 | DATASHEET FOR 049P0004A/B LEAN AMINE PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070457 | SO6001-EJ2E-TDS-09810001-001 | 098-G-DAT-00001-001 | DATASHEET FOR 098P0001A/B HP BFW PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070458 | SO6001-EJ2E-TDS-09910001-001 | 099-G-DAT-00001-001 | DATASHEET FOR 099P0001A/B HP BFW PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070459 | SO6001-EJ2E-TDS-37810001-001 | 378-G-DAT-00001-001 | DATASHEET FOR 378P1229 N.9 HIGH LIFT UNIT PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070460 | 076551C-000S-DL-0910-003 | 000-G-IDL-80003-001 | DEVIATION LIST FOR BB1, BB2 AND BB3 PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070460 | 076551C-000S-ITP-0910-003 | 000-G-ITP-80003-001 | INSPECTION AND TEST PLAN FOR BB1, BB2 AND BB3 PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070460 | 076551C-000S-MR-0910-003 | 000-G-MRQ-80003-001 | MATERIAL REQUISITION FOR BB1, BB2 AND BB3 PUMPS | A | 2018-06-15 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070460 | 076551C-000S-SP-0910-003 | 000-G-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB1, BB2 AND BB3 PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070460 | 076551C-000S-SR-0910-003 | 000-G-SOW-80003-001 | SCOPE OF SUPPLY FOR BB1, BB2 AND BB3 PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070461 | SO6001-EJ2E-TDS-00510001-001 | 005-G-DAT-55001-001 | DATA SHEET FOR 005P5040A/B C3 TRANSFER PUMPS (EX BAPCO CODE: 005-G-DAT-00001-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 |  |  | CLASS 2
CON-BMP-TRA-070461 | SO6001-EJ2E-TDS-00510002-001 | 005-G-DAT-55002-001 | DATA SHEET FOR 005P5041A/B C3 EXPORT PUMPS (EX BAPCO CODE: 005-G-DAT-00002-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 |  |  | CLASS 2
CON-BMP-TRA-070461 | SO6001-EJ2E-TDS-00510003-001 | 005-G-DAT-55003-001 | DATA SHEET FOR 005P5042A/B C4 TRANSFER PUMPS (TO EXISTING LPG FACILITIES) (EX BAPCO CODE: 005-G-DAT-00003-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 |  |  | CLASS 2
CON-BMP-TRA-070461 | SO6001-EJ2E-TDS-00510004-001 | 005-G-DAT-55004-001 | DATA SHEET FOR 005P5043A/B C4 EXPORT PUMPS (EX BAPCO CODE: 005-G-DAT-00004-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 |  |  | CLASS 2
CON-BMP-TRA-070461 | SO6001-EJ2E-TDS-00510005-001 | 005-G-DAT-55005-001 | DATA SHEET FOR C4 005P5044A/B INJECTION PUMPS (EX BAPCO CODE: 005-G-DAT-00005-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 |  |  | CLASS 2
CON-BMP-TRA-070461 | SO6001-EJ2E-TDS-00510006-001 | 005-G-DAT-55006-001 | DATA SHEET FOR 005P5045A/B OFFSPEC LPG PUMPS (EX BAPCO CODE: 005-G-DAT-00006-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 |  |  | CLASS 2
CON-BMP-TRA-070461_REV1 | SO6001-EJ2E-TDS-00510001-001 | 005-G-DAT-55001-001 | DATA SHEET FOR 005P5040A/B C3 TRANSFER PUMPS (EX BAPCO CODE: 005-G-DAT-00001-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070461_REV1 | SO6001-EJ2E-TDS-00510002-001 | 005-G-DAT-55002-001 | DATA SHEET FOR 005P5041A/B C3 EXPORT PUMPS (EX BAPCO CODE: 005-G-DAT-00002-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070461_REV1 | SO6001-EJ2E-TDS-00510003-001 | 005-G-DAT-55003-001 | DATA SHEET FOR 005P5042A/B C4 TRANSFER PUMPS (TO EXISTING LPG FACILITIES) (EX BAPCO CODE: 005-G-DAT-00003-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070461_REV1 | SO6001-EJ2E-TDS-00510004-001 | 005-G-DAT-55004-001 | DATA SHEET FOR 005P5043A/B C4 EXPORT PUMPS (EX BAPCO CODE: 005-G-DAT-00004-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070461_REV1 | SO6001-EJ2E-TDS-00510005-001 | 005-G-DAT-55005-001 | DATA SHEET FOR C4 005P5044A/B INJECTION PUMPS (EX BAPCO CODE: 005-G-DAT-00005-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070461_REV1 | SO6001-EJ2E-TDS-00510006-001 | 005-G-DAT-55006-001 | DATA SHEET FOR 005P5045A/B OFFSPEC LPG PUMPS (EX BAPCO CODE: 005-G-DAT-00006-001 REV.A) | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070462 | SO6001-EJ2E-TDS-03610006-001 | 036-G-DAT-00006-001 | DATA SHEET FOR 036P0006A/B AMINE SUMP PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070463 | SO6001-EJ2E-TDS-04410007-001 | 044-G-DAT-00007-001 | DATA SHEET FOR 044P0007A/B AMINE SUMP PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070464 | SO6001-EJ2E-TDS-04610006-001 | 046-G-DAT-00006-001 | DATA SHEET FOR 046P0006A/B SOUR WATER SUMP PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070465 | SO6001-EJ2E-TDS-04810005-001 | 048-G-DAT-00005-001 | DATA SHEET FOR 048P0005A/B AMINE SUMP PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070465 | SO6001-EJ2E-TDS-04810008-001 | 048-G-DAT-00008-001 | DATA SHEET FOR 048P0008A/B NO3 SULPHUR PLANT SLOP OIL SUMP PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070466 | 076551C-000S-DL-0910-006 | 000-G-IDL-80004-001 | DEVIATION LIST FOR VERTICAL PUMPS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070466 | 076551C-000S-ITP-0910-006 | 000-G-ITP-80004-001 | INSPECTION AND TEST PLAN FOR VERTICAL PUMPS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070466 | 076551C-000S-MR-0910-006 | 000-G-MRQ-80004-001 | MATERIAL REQUISITION FOR VERTICAL PUMPS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070466 | 076551C-000S-SP-0910-006 | 000-G-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR VERTICAL PUMPS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070466 | 076551C-000S-SR-0910-006 | 000-G-SOW-80004-001 | SCOPE OF WORK FOR VERTICAL PUMPS | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070467 | SO6001-ES0B-PHL-37155001-001 | 371-A-BOD-55001-001 | BASIS OF DESIGN STM G AND D (UNIT 371) STEAM GENERATION AND DISTRIBUTION | 0 | 2018-06-28 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-TRA-070468 | SO6001-EJ1E-TDS-09800016-001 | 098-E-DAT-00007-001 | PLATE AND SHELL HEAT EXCHANGER DATA SHEET FOR 098E00068 HP STRIPPER FEED EFFLUENT EXCHANGER | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070469 | SO6001-EJ1E-TDS-09900016-001 | 099-E-DAT-00007-001 | PLATE AND SHELL HEAT EXCHANGER DATA SHEET FOR 099E0008 HP STRIPPER FEED EFFLUENT EXCHANGER | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070470 | 076551C-000S-DL-0610-006 | 000-E-IDL-80008-001 | DEVIATION LIST FOR PLATE AND SHELL HEAT EXCHANGER | A | 2018-06-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070470 | 076551C-000S-ITP-0610-006 | 000-E-ITP-80008-001 | INSPECTION AND TEST PLAN FOR PLATE AND SHELL HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070470 | 076551C-000S-MR-0610-006 | 000-E-MRQ-80008-001 | MATERIAL REQUISITION FOR PLATE AND SHELL HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070470 | 076551C-000S-SP-0610-006 | 000-E-GRD-80008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR PLATE AND SHELL HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070470 | 076551C-000S-SR-0610-006 | 000-E-SOW-80008-001 | SCOPE OF SUPPLY FOR PLATE AND SHELL HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070471 | SO6001-EN0D-SLD-03680102-001 | 036-P-SLD-80102-001 | KEY SINGLE LINE DIAGRAM SUBSTATION SST036R01 | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070472 | SO6001-EN0D-SLD-04180102-001 | 041-P-SLD-80102-001 | KEY SINGLE LINE DIAGRAM SUBSTATION SST041R01 | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070473 | SO6001-EN0D-SLD-09480102-001 | 094-P-SLD-80102-001 | KEY SINGLE LINE DIAGRAM SUBSTATION SST094R01 | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070474 | SO6001-EN0D-SLD-09880102-001 | 098-P-SLD-80102-001 | KEY SINGLE LINE DIAGRAM SUBSTATION SST098R01 | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070475 | SO6001-EN0D-SLD-35680102-001 | 356-P-SLD-80102-001 | KEY SINGLE LINE DIAGRAM SUBSTATION SST356R01 | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070476 | 076551C-000S-DL-0660-001 | 000-E-IDL-80006-001 | DEVIATION LIST FOR PLATE AND FRAME HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070476 | 076551C-000S-ITP-0660-001 | 000-E-ITP-80006-001 | INSPECTION AND TEST PLAN FOR PLATE AND FRAME HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070476 | 076551C-000S-MR-0660-001 | 000-E-MRQ-80006-001 | MATERIAL REQUISITION FOR PLATE AND FRAME HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070476 | 076551C-000S-SP-0660-001 | 000-E-GRD-80006-001 | PARTICULAR TECHNICAL SPECIFICATION FOR PLATE AND FRAME HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070476 | 076551C-000S-SR-0660-001 | 000-E-SOW-80006-001 | SCOPE OF SUPPLY FOR PLATE AND FRAME HEAT EXCHANGER | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070477 | SO6001-EJ2E-TDS-38210005-001 | 382-G-DAT-00005-001 | DATA SHEET FOR 382P3881A/B | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070477 | SO6001-EJ2E-TDS-38210006-001 | 382-G-DAT-00006-001 | DATA SHEET FOR 382P3882A/B | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070477 | SO6001-EJ2E-TDS-38210007-001 | 382-G-DAT-00007-001 | DATA SHEET FOR 382P3884A/B | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070478 | 076551C-000S-DL-0910-010 | 000-G-IDL-80006-001 | DEVIATION LIST FOR SUBMERSIBLE PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070478 | 076551C-000S-ITP-0910-010 | 000-G-ITP-80006-001 | INSPECTION AND TEST PLAN FOR SUBMERSIBLE PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070478 | 076551C-000S-MR-0910-010 | 000-G-MRQ-80006-001 | MATERIAL REQUISITION FOR SUBMERSIBLE PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070478 | 076551C-000S-SP-0910-010 | 000-G-GRD-80006-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SUBMERSIBLE PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070478 | 076551C-000S-SR-0910-010 | 000-G-SOW-80006-001 | SCOPE OF SUPPLY FOR SUBMERSIBLE PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070479 | SO6001-EJ2E-TDS-01610002-001 | 016-G-DAT-00002-001 | DATA SHEET FOR 016P9604D CAUSTIC CIRCULATION PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070480 | SO6001-EJ2E-TDS-09410001-001 | 094-G-DAT-00001-001 | DATA SHEET FOR 094P0008A/B 2SHF FOUL WATER PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070480 | SO6001-EJ2E-TDS-09410002-001 | 094-G-DAT-00002-001 | DATA SHEET FOR 094P0009A/B 2SHF NEUTRALIZATION PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070481 | SO6001-EJ2E-TDS-31010001-001 | 310-G-DAT-00001-001 | DATA SHEET FOR 310P0001A/B BLOWDOWN PUMP | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070482 | SO6001-EJ2E-TDS-38210001-001 | 382-G-DAT-00001-001 | DATA SHEET FOR 382P3888A/B WORKSTATION BUILDING SANITARY PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070482 | SO6001-EJ2E-TDS-38210002-001 | 382-G-DAT-00002-001 | DATA SHEET FOR 382P3889A/B/C FINAL SANITARY PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070482 | SO6001-EJ2E-TDS-38210003-001 | 382-G-DAT-00003-001 | DATA SHEET FOR 382P3890A/B #3 SULPHUR PLANT TOILET SANITARY PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070482 | SO6001-EJ2E-TDS-38210004-001 | 382-G-DAT-00004-001 | DATA SHEET FOR 382P3891A/B UTILITIES TOILET SANITARY PUMPS | B | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070483 | 076551C-000S-DL-0910-002 | 000-G-IDL-80002-001 | DEVIATION LIST FOR ASME PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070483 | 076551C-000S-ITP-0910-002 | 000-G-ITP-80002-001 | INSPECTION AND TEST PLAN FOR ASME PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070483 | 076551C-000S-MR-0910-002 | 000-G-MRQ-80002-001 | MATERIAL REQUISITION FOR ASME PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070483 | 076551C-000S-SP-0910-002 | 000-G-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR ASME PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070483 | 076551C-000S-SR-0910-002 | 000-G-SOW-80002-001 | SCOPE OF SUPPLY FOR ASME PUMPS | A | 2018-06-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070484 | SO6001-EN0L-LOS-03680101-001 | 036-P-STS-80101-001 | LOAD BALANCE SUBSTATION SST036R01 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070485 | SO6001-EN0L-LOS-04180101-001 | 041-P-STS-80101-001 | LOAD BALANCE SUBSTATION SST041R01 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070486 | SO6001-EN0L-LOS-09480101-001 | 094-P-STS-80101-001 | LOAD BALANCE SUBSTATION SST094R01 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070487 | SO6001-EN0L-LOS-09880101-001 | 098-P-STS-80101-001 | LOAD BALANCE SUBSTATION SST098R01 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070488 | SO6001-EN0L-LOS-35680101-001 | 356-P-STS-80101-001 | LOAD BALANCE SUBSTATION SST356R01 | A | 2018-06-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070489 | SO6001-EJ1E-TDS-04800006-002-001 | 048-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070489 | SO6001-EJ1E-TDS-04800006-002-002 | 048-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070489 | SO6001-EJ1E-TDS-04800006-002-003 | 048-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070489 | SO6001-EJ1E-TDS-04800006-002-004 | 048-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070489 | SO6001-EJ1E-TDS-04800006-002-005 | 048-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 048E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070490 | SO6001-EJ1E-TDS-04900004-002-001 | 049-E-GAD-00001-001 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070490 | SO6001-EJ1E-TDS-04900004-002-002 | 049-E-GAD-00001-002 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070490 | SO6001-EJ1E-TDS-04900004-002-003 | 049-E-GAD-00001-003 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070490 | SO6001-EJ1E-TDS-04900004-002-004 | 049-E-GAD-00001-004 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070490 | SO6001-EJ1E-TDS-04900004-002-005 | 049-E-GAD-00001-005 | MECHANICAL DATA SHEET FOR 049E0003 A-B LEAN AMINE TRIM COOLER | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-11 | CLASS 2
CON-BMP-TRA-070491 | 076551C-000S-DL-0610-003 | 000-E-IDL-80002-001 | DEVIATION LIST FOR WET H2S AND SPECIAL SERVICE CS SHELL & TUBE HEAT EXCHANGER | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 |  |  | CLASS 1
CON-BMP-TRA-070491 | 076551C-000S-ITP-0610-003 | 000-E-ITP-80002-001 | INSPECTION AND TEST PLAN FOR WET H2S AND SPECIAL SERVICE CS SHELL & TUBE HEAT EXCHANGER | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 |  |  | CLASS 1
CON-BMP-TRA-070491 | 076551C-000S-MR-0610-003 | 000-E-MRQ-80002-001 | MATERIAL REQUISITION FOR WET H2S AND SPECIAL SERVICE CS SHELL & TUBE HEAT EXCHANGER | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-070491 | 076551C-000S-SP-0610-003 | 000-E-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR WET H2S AND SPECIAL SERVICE CS SHELL & TUBE HEAT EXCHANGER | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 |  |  | CLASS 1
CON-BMP-TRA-070491 | 076551C-000S-SR-0610-003 | 000-E-SOW-80002-001 | SCOPE OF SUPPLY FOR WET H2S AND SPECIAL SERVICE CS SHELL & TUBE HEAT EXCHANGER | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 |  |  | CLASS 1
CON-BMP-TRA-070492 | SO6001-EJ2E-TDS-04120001-001 | 041-K-DAT-00001-001 | DATA SHEET FOR COMBUSTION AIR BLOWERS | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070493 | SO6001-EJ2E-TDS-09420001-001 | 094-K-DAT-00001-001 | DATA SHEET FOR 2SHF EXHAUST FAN SULPHUR STORAGE TANK | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-10 | CLASS 2
CON-BMP-TRA-070494 | SO6001-EJ2E-TDS-09820002-001 | 098-K-DAT-00002-001 | DATA SHEET FOR I.D. FAN | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070495 | SO6001-EJ2E-TDS-09920002-001 | 099-K-DAT-00002-001 | DATA SHEET FOR I.D. FAN | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070496 | 076551C-000S-DL-1040-001 | 000-K-IDL-80004-001 | DEVIATION LIST FOR FAN AND BLOWERS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070496 | 076551C-000S-ITP-1040-001 | 000-K-ITP-80004-001 | INSPECTION AND TEST PLAN FOR FAN AND BLOWERS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070496 | 076551C-000S-MR-1040-001 | 000-K-MRQ-80004-001 | MATERIAL REQUISITION FOR FAN AND BLOWERS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070496 | 076551C-000S-SP-1040-001 | 000-K-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FAN AND BLOWERS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070496 | 076551C-000S-SR-1040-001 | 000-K-SOW-80004-001 | SCOPE OF SUPPLY FOR FAN AND BLOWERS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070497 | SO6001-EJ2E-TDS-01620001-001 | 016-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 016K9614D AIR COMPRESSOR SYSTEM | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070498 | 076551C-000S-DL-1020-002 | 000-K-IDL-80002-001 | LIST OF DEVIATION FOR RECIPROCATING COMPRESSOR | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070498 | 076551C-000S-ITP-1020-002 | 000-K-ITP-80002-001 | INSPECTION AND TESTS PLAN FOR RECIPROCATING COMPRESSOR | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070498 | 076551C-000S-MR-1020-002 | 000-K-MRQ-80002-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070498 | 076551C-000S-SP-1020-002 | 000-K-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070498 | 076551C-000S-SR-1020-002 | 000-K-SOW-80002-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 1
CON-BMP-TRA-070499 | SO6001-EJ2E-TDS-04110001-001 | 041-G-DAT-00001-001 | DATA SHEET FOR 041P0001A/B SULPHUR TRANSFER PUMPS | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-13 | CLASS 2
CON-BMP-TRA-070500 | SO6001-EJ2E-TDS-04210001-001 | 042-G-DAT-00001-001 | DATA SHEET FOR 042P0001A/B SULPHUR TRANSFER PUMPS | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070501 | SO6001-EJ2E-TDS-04310001-001 | 043-G-DAT-00001-001 | DATA SHEET FOR 043P0001A/B SULPHUR TRANSFER PUMPS | B | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 2
CON-BMP-TRA-070502 | 076551C-000S-DL-0910-007 | 000-G-IDL-80005-001 | DEVIATION LIST FOR SULPHUR TRANSFER PUMPS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-070502 | 076551C-000S-ITP-0910-007 | 000-G-ITP-80005-001 | INSPECTION AND TEST PLAN FOR SULPHUR TRANSFER PUMPS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-070502 | 076551C-000S-MR-0910-007 | 000-G-MRQ-80005-001 | MATERIAL REQUISITION FOR SULPHUR TRANSFER PUMPS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-070502 | 076551C-000S-SP-0910-007 | 000-G-GRD-80005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SULPHUR TRANSFER PUMPS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-070502 | 076551C-000S-SR-0910-007 | 000-G-SOW-80005-001 | SCOPE OF SUPPLY FOR SULPHUR TRANSFER PUMPS | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-12 | CLASS 1
CON-BMP-TRA-070503 | SO6001-EN0L-LOD-03680202-001 | 036-P-INX-80202-001 | ELECTRICAL CONSUMER LIST LIST SUBSTATION SST036R01 | A | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070504 | SO6001-EN0L-LOD-04180202-001 | 041-P-INX-80202-001 | ELECTRICAL CONSUMER LIST LIST SUBSTATION SST041R01 | A | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070505 | SO6001-EN0L-LOD-09480202-001 | 094-P-INX-80202-001 | ELECTRICAL CONSUMER LIST LIST SUBSTATION SST094R01 | A | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070506 | SO6001-EN0L-LOD-09880202-001 | 098-P-INX-80202-001 | ELECTRICAL CONSUMER LIST LIST SUBSTATION SST098R01 | A | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070507 | SO6001-EN0L-LOD-35680202-001 | 356-P-INX-80202-001 | ELECTRICAL CONSUMER LIST LIST SUBSTATION SST356R01 | A | 2018-06-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 2
CON-BMP-TRA-070508 | 076551C-000S-DL-1543-003 | 000-J-IDL-80028-001 | DEVIATION LIST FOR ON-OFF SPECIAL VALVE (PNEUMATIC / ELECTRIC / HYDRAULIC ACTUATORS) | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070508 | 076551C-000S-ITP-1543-003 | 000-J-ITP-80028-001 | INSPECTION AND TEST PLAN FOR ON-OFF SPECIAL VALVE (PNEUMATIC / ELECTRIC / HYDRAULIC ACTUATORS) | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070508 | 076551C-000S-MR-1543-003 | 000-J-MRQ-80028-001 | MATERIAL REQUISITION FOR ON-OFF SPECIAL VALVE (PNEUMATIC / ELECTRIC / HYDRAULIC ACTUATORS) | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070508 | 076551C-000S-SP-1543-003 | 000-J-GRD-80028-001 | PARTICULAR TECHNICAL SPECIFICATION FOR ON-OFF SPECIAL VALVE (PNEUMATIC / ELECTRIC / HYDRAULIC ACTUATORS) | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070508 | 076551C-000S-SR-1543-003 | 000-J-SOW-80028-001 | SCOPE OF SUPPLY FOR ON-OFF SPECIAL VALVE (PNEUMATIC / ELECTRIC / HYDRAULIC ACTUATORS) | A | 2018-06-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-16 | 3 - REVIEWED WITH COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400001-001 | 044-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM TAIL GAS DISTRIBUTION HEADER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400002-001 | 044-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM FEED HEATER & TAIL GAS REACTOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400003-001 | 044-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM WASTE HEAT BOILER & START UP GAS STEAM EJECTOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400004-001 | 044-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH GAS KO DRUM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400005-001 | 044-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM QUENCH COLUMN | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400006-001 | 044-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM QUENCH WATER CIRCULATION PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400007-001 | 044-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM QUENCH WATER FILTER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400008-001 | 044-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM QUENCH WATER COOLER & QUENCH WATER TRIM COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400009-001 | 044-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE ABSORBER & RICH AMINE PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400010-001 | 044-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN/RICH AMINE EXCHANGER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400011-001 | 044-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400012-001 | 044-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR PUMP AROUND | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400013-001 | 044-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR PUMP AROUND COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400014-001 | 044-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR REBOILER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400015-001 | 044-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR BOTTOM PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400016-001 | 044-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE COOLER AND TRIM COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400017-001 | 044-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE SURGE TANK & PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400018-001 | 044-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE FILTERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400019-001 | 044-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE SUMP AND PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400020-001 | 044-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM FUEL GAS KO DRUM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400021-001 | 044-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH GAS KO DRUM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400022-001 | 044-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM THERMAL OXIDISER PACKAGE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400023-001 | 044-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM THERMAL OXIDISER PACKAGE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400024-001 | 044-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM N° 3 SULPHUR PLANT FLARE KO DRUM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070509 | SO6001-ES0D-PID-04400025-001 | 044-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM 550# STEAM BLOWDOWN DRUM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400026-001 | 044-A-PID-00026-001 | PIPING & INSTRUMENTATION DIAGRAM 60# STEAM BLOWDOWN | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400027-001 | 044-A-PID-00027-001 | PIPING & INSTRUMENTATION DIAGRAM -3TGTU HP CONDENSATE FLASH DRUM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400028-001 | 044-A-PID-00028-001 | PIPING & INSTRUMENTATION DIAGRAM LP CONDENSATE FLASH DRUMS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400029-001 | 044-A-PID-00029-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE RECOVERY SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400030-001 | 044-A-PID-00030-001 | PIPING & INSTRUMENTATION DIAGRAM CAUSTIC SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400031-001 | 044-A-PID-00031-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400031-002 | 044-A-PID-00031-002 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400032-001 | 044-A-PID-00032-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400033-001 | 044-A-PID-00033-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400033-002 | 044-A-PID-00033-002 | PIPING & INSTRUMENTATION DIAGRAM STEAM SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400034-001 | 044-A-PID-00034-001 | PIPING & INSTRUMENTATION DIAGRAM BOILER FEED WATER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400035-001 | 044-A-PID-00035-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400036-001 | 044-A-PID-00036-001 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400037-001 | 044-A-PID-00037-001 | PIPING & INSTRUMENTATION DIAGRAM DEMINERALIZED WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400038-001 | 044-A-PID-00038-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400039-001 | 044-A-PID-00039-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400040-001 | 044-A-PID-00040-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400041-001 | 044-A-PID-00041-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400041-002 | 044-A-PID-00041-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400042-001 | 044-A-PID-00042-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400042-002 | 044-A-PID-00042-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400043-001 | 044-A-PID-00043-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400043-002 | 044-A-PID-00043-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400043-003 | 044-A-PID-00043-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070510 | SO6001-ES0D-PID-04400044-001 | 044-A-PID-00044-001 | PIPING & INSTRUMENTATION DIAGRAM PHOSPHATE INJECTION SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500001-001 | 045-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM TAIL GAS DISTRIBUTION HEADER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500002-001 | 045-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM FEED HEATER & TAIL GAS REACTOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500003-001 | 045-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM WASTE HEAT BOILER & START UP GAS STEAM EJECTOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500005-001 | 045-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM QUENCH COLUMN | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500006-001 | 045-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM QUENCH WATER CIRCULATION PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500007-001 | 045-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM QUENCH WATER FILTER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500008-001 | 045-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM QUENCH WATER COOLER & QUENCH WATER TRIM COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500009-001 | 045-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE ABSORBER & RICH AMINE PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500010-001 | 045-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN/RICH AMINE EXCHANGER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500011-001 | 045-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500012-001 | 045-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR PUMP AROUND | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500013-001 | 045-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR PUMP AROUND COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500014-001 | 045-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR REBOILER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500015-001 | 045-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR BOTTOM PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500016-001 | 045-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE COOLER AND TRIM COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500017-001 | 045-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE SURGE TANK & PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500018-001 | 045-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE FILTERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500022-001 | 045-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM THERMAL OXIDISER PACKAGE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500023-001 | 045-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM THERMAL OXIDISER PACKAGE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070511 | SO6001-ES0D-PID-04500030-001 | 045-A-PID-00030-001 | PIPING & INSTRUMENTATION DIAGRAM CAUSTIC SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500031-001 | 045-A-PID-00031-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500032-001 | 045-A-PID-00032-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500033-001 | 045-A-PID-00033-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500034-001 | 045-A-PID-00034-001 | PIPING & INSTRUMENTATION DIAGRAM BOILER FEED WATER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500035-001 | 045-A-PID-00035-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500036-001 | 045-A-PID-00036-001 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500037-001 | 045-A-PID-00037-001 | PIPING & INSTRUMENTATION DIAGRAM DEMINERALIZED WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500038-001 | 045-A-PID-00038-001 | P& ID -4TGTU UTILITY & DRINKING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500039-001 | 045-A-PID-00039-001 | P & ID - 4TGTU INSTRUMENT & YARD AIR SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500040-001 | 045-A-PID-00040-001 | P & ID -4TGTU NITROGEN SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500041-001 | 045-A-PID-00041-001 | P & ID - 4TGTU BATTERY LIMIT PROCESS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500041-002 | 045-A-PID-00041-002 | P & ID - 4TGTU BATTERY LIMIT PROCESS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500042-001 | 045-A-PID-00042-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500042-002 | 045-A-PID-00042-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500043-001 | 045-A-PID-00043-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500043-002 | 045-A-PID-00043-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070512 | SO6001-ES0D-PID-04500043-003 | 045-A-PID-00043-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600001-001 | 046-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM SOUR WATER (NON-PHENOLIC) DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600002-001 | 046-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM SOUR WATER DEGASSING DRUM & FEED PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600003-001 | 046-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM SOUR WATER SKIM TANK & PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600004-001 | 046-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM STRIPPER FEED BOTTOM EXCHANGER & PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600005-001 | 046-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM NON- PHENOLIC SOUR WATER STRIPPER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600006-001 | 046-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM STRIPPER REBOILER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600007-001 | 046-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM STRIPPER PUMP AROUND PUMPS AND COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600008-001 | 046-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM TREATED WATER COOLER & TRIM COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600009-001 | 046-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM SOUR WATER SUMP AND SUMP PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600010-001 | 046-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM SWS SKIMMED OIL | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600011-001 | 046-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600012-001 | 046-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600012-002 | 046-A-PID-00012-002 | PIPING & INSTRUMENTATION DIAGRAM FUEL GAS SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070513 | SO6001-ES0D-PID-04600013-001 | 046-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600014-001 | 046-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600015-001 | 046-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600016-001 | 046-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM DEMIN WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600017-001 | 046-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600018-001 | 046-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600019-001 | 046-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600020-001 | 046-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600020-002 | 046-A-PID-00020-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600021-001 | 046-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600021-002 | 046-A-PID-00021-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600021-003 | 046-A-PID-00021-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070514 | SO6001-ES0D-PID-04600022-001 | 046-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM CAUSTIC SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700001-001 | 047-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM SOUR WATER (PHENOLIC) DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700002-001 | 047-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM SOUR WATER DEGASSING DRUM & FEED PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700003-001 | 047-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM SOUR WATER SKIM TANK & PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700004-001 | 047-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM FEED BOTTOM EXCHANGER & PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700005-001 | 047-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM PHENOLIC SOUR WATER STRIPPER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700006-001 | 047-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM STRIPPER REBOILER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700007-001 | 047-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM STRIPPER PUMP AROUND PUMPS AND COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700008-001 | 047-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM TREATER WATER COOLER & TRIM COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700011-001 | 047-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700012-001 | 047-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700012-002 | 047-A-PID-00012-002 | PIPING & INSTRUMENTATION DIAGRAM FUEL GAS SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700013-001 | 047-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM & CONDENSATE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700015-001 | 047-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700016-001 | 047-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM DEMIN WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700017-001 | 047-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700018-001 | 047-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700019-001 | 047-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700020-001 | 047-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700020-002 | 047-A-PID-00020-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700021-001 | 047-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700021-002 | 047-A-PID-00021-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700021-003 | 047-A-PID-00021-003 | PIPING & INSTRUMENTATION DIAGRAM FLARE, NITROGEN, INSTRUMENT & YARD SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070515 | SO6001-ES0D-PID-04700022-001 | 047-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM CAUSTIC SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800001-001 | 048-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM RICH AMINE MANIFOLD | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800002-001 | 048-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH DRUM & FLASH GAS ABSORBER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800003-001 | 048-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM RICH AMINE PUMP & LEAN RICH AMINE EXCHANGER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800004-001 | 048-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800005-001 | 048-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR PUMP AROUND PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800006-001 | 048-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR PUMP AROUND COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800007-001 | 048-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR REBOILER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800008-001 | 048-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR BOTTOM PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800009-001 | 048-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800010-001 | 048-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE SURGE TANK & PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800011-001 | 048-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE FILTERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800012-001 | 048-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE SUMP AND PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800013-001 | 048-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE TRIM COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800014-001 | 048-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE MAKE- UP TANK | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800015-001 | 048-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM ARU FLARE KO DRUM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800016-001 | 048-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM LP CONDENSATE FLASH DRUM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800017-001 | 048-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE RECOVERY SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800018-001 | 048-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHUR BLOCK SLOP OIL DRAIN DRUM AND SLOP SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070516 | SO6001-ES0D-PID-04800019-001 | 048-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800020-001 | 048-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800020-002 | 048-A-PID-00020-002 | PIPING & INSTRUMENTATION DIAGRAM FUEL GAS DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800021-001 | 048-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800022-001 | 048-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM LP CONDENSATE DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800023-001 | 048-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800024-001 | 048-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM DEMIN SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800025-001 | 048-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRINKING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800026-001 | 048-A-PID-00026-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800027-001 | 048-A-PID-00027-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800028-001 | 048-A-PID-00028-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800028-002 | 048-A-PID-00028-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800029-001 | 048-A-PID-00029-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800029-002 | 048-A-PID-00029-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800029-003 | 048-A-PID-00029-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070517 | SO6001-ES0D-PID-04800030-001 | 048-A-PID-00030-001 | PIPING & INSTRUMENTATION DIAGRAM ANTIFOAM INJECTION SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900001-001 | 049-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM RICH AMINE MANIFOLD | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900002-001 | 049-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM FLASH DRUM & FLASH GAS ABSORBER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900003-001 | 049-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM RICH AMINE PUMP & LEAN/ RICH AMINE EXCHANGER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900004-001 | 049-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900005-001 | 049-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR PUMP AROUND PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900006-001 | 049-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR PUMP AROUND COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900007-001 | 049-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE REGENERATOR REBOILER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900008-001 | 049-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATOR BOTTOM PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900009-001 | 049-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900010-001 | 049-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM AMINE SURGE TANK & PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900011-001 | 049-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE FILTERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900013-001 | 049-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM LEAN AMINE TRIM COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900019-001 | 049-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900020-001 | 049-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070518 | SO6001-ES0D-PID-04900020-002 | 049-A-PID-00020-002 | PIPING & INSTRUMENTATION DIAGRAM FUEL GAS DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900021-001 | 049-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM STEAM DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900022-001 | 049-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM LP CONDENSATE DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900023-001 | 049-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900024-001 | 049-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM DEMIN SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900025-001 | 049-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY & DRIKING WATER SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900026-001 | 049-A-PID-00026-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT & YARD AIR SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900027-001 | 049-A-PID-00027-001 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900028-001 | 049-A-PID-00028-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900028-002 | 049-A-PID-00028-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT PROCESS AUXILIARY | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900029-001 | 049-A-PID-00029-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900029-002 | 049-A-PID-00029-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070519 | SO6001-ES0D-PID-04900029-003 | 049-A-PID-00029-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000001-001 | 370-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM FED WATER COOLERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000002-001 | 370-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM FED POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000003-001 | 370-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM FED POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000004-001 | 370-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM FED POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000005-001 | 370-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM FED POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000006-001 | 370-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM FED POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000007-001 | 370-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM 98% SULPHURIC ACID DAILY TANK AND PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000008-001 | 370-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM 47% CAUSTIC SODA DAILY TANK AND PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000009-001 | 370-A-PID-00009-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATION PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000010-001 | 370-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM AIR BLOWERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000011-001 | 370-A-PID-00011-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE RECOVERY SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000012-001 | 370-A-PID-00012-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE RECOVERY SYSTEM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000013-001 | 370-A-PID-00013-001 | PIPING & INSTRUMENTATION DIAGRAM RECOVERED CONDENSATE COOLER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000014-001 | 370-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE POLISHING FEED STORAGE TANK | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000015-001 | 370-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM AC FILTER FEED PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000016-001 | 370-A-PID-00016-001 | PIPING & INSTRUMENTATION DIAGRAM ACTIVATED CARBON FILTERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000017-001 | 370-A-PID-00017-001 | PIPING & INSTRUMENTATION DIAGRAM ACTIVATED CARBON FILTERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000018-001 | 370-A-PID-00018-001 | PIPING & INSTRUMENTATION DIAGRAM ACTIVATED CARBON FILTERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000019-001 | 370-A-PID-00019-001 | PIPING & INSTRUMENTATION DIAGRAM A.C. FILTERS BACKWASH BASIN | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000020-001 | 370-A-PID-00020-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE POLISHING FEED STORAGE TANK | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000021-001 | 370-A-PID-00021-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE POLISHING FEED PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000022-001 | 370-A-PID-00022-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070520 | SO6001-ES0D-PID-37000023-001 | 370-A-PID-00023-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000024-001 | 370-A-PID-00024-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000025-001 | 370-A-PID-00025-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000026-001 | 370-A-PID-00026-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE POLISHING MIXED BEDS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000027-001 | 370-A-PID-00027-001 | PIPING & INSTRUMENTATION DIAGRAM 98% SULPHURIC ACID DAILY TANK AND PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000028-001 | 370-A-PID-00028-001 | PIPING & INSTRUMENTATION DIAGRAM 47% CAUSTIC SODA DAILY TANK AND PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000029-001 | 370-A-PID-00029-001 | PIPING & INSTRUMENTATION DIAGRAM REGENERATION PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000030-001 | 370-A-PID-00030-001 | PIPING & INSTRUMENTATION DIAGRAM AIR BLOWERS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000031-001 | 370-A-PID-00031-001 | PIPING & INSTRUMENTATION DIAGRAM NEUTRALIZATION BASIN AND PUMPS SECTION A | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000032-001 | 370-A-PID-00032-001 | PIPING & INSTRUMENTATION DIAGRAM NEUTRALIZATION BASIN AND PUMP SECTION B | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000033-001 | 370-A-PID-00033-001 | PIPING & INSTRUMENTATION DIAGRAM SULPHURIC ACID AND CAUSTIC SODA DRUMS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000034-001 | 370-A-PID-00034-001 | PIPING & INSTRUMENTATION DIAGRAM DENIM STORAGE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000035-001 | 370-A-PID-00035-001 | PIPING & INSTRUMENTATION DIAGRAM DENIM WATER PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000036-001 | 370-A-PID-00036-001 | PIPING & INSTRUMENTATION DIAGRAM DEAERATOR FEED WATER PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000037-001 | 370-A-PID-00037-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0006A STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000038-001 | 370-A-PID-00038-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0006B STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000039-001 | 370-A-PID-00039-001 | PIPING & INSTRUMENTATION DIAGRAM HOTWELL FEED WATER PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000040-001 | 370-A-PID-00040-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0007A STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000041-001 | 370-A-PID-00041-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0007B STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000042-001 | 370-A-PID-00042-001 | PIPING & INSTRUMENTATION DIAGRAM DEAERATOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000043-001 | 370-A-PID-00043-001 | PIPING & INSTRUMENTATION DIAGRAM DEAERATOR | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000044-001 | 370-A-PID-00044-001 | PIPING & INSTRUMENTATION DIAGRAM HP BFW PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000045-001 | 370-A-PID-00045-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0008A STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000046-001 | 370-A-PID-00046-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0008B STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000047-001 | 370-A-PID-00047-001 | PIPING & INSTRUMENTATION DIAGRAM LP BFW PUMP | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070521 | SO6001-ES0D-PID-37000048-001 | 370-A-PID-00048-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0009A STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000049-001 | 370-A-PID-00049-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0009B STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000050-001 | 370-A-PID-00050-001 | PIPING & INSTRUMENTATION DIAGRAM HP BOILER FEED WATER PUMPS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000051-001 | 370-A-PID-00051-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0012A STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000052-001 | 370-A-PID-00052-001 | PIPING & INSTRUMENTATION DIAGRAM 370P0012B STEAM TURBINE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000053-001 | 370-A-PID-00053-001 | PIPING & INSTRUMENTATION DIAGRAM FUEL GAS DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000054-001 | 370-A-PID-00054-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000055-001 | 370-A-PID-00055-001 | PIPING & INSTRUMENTATION DIAGRAM 550# STEAM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000056-001 | 370-A-PID-00056-001 | PIPING & INSTRUMENTATION DIAGRAM 110# STEAM | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000057-001 | 370-A-PID-00057-001 | PIPING & INSTRUMENTATION DIAGRAM 60# STEAM DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000058-001 | 370-A-PID-00058-001 | PIPING & INSTRUMENTATION DIAGRAM LP BFW | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000059-001 | 370-A-PID-00059-001 | PIPING & INSTRUMENTATION DIAGRAM 550# CONDENSATE DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000060-001 | 370-A-PID-00060-001 | PIPING & INSTRUMENTATION DIAGRAM 110# CONDENSATE DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000061-001 | 370-A-PID-00061-001 | PIPING & INSTRUMENTATION DIAGRAM 60# CONDENSATE DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000062-001 | 370-A-PID-00062-001 | PIPING & INSTRUMENTATION DIAGRAM COOLING WATER DISTRIBUTION | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000063-001 | 370-A-PID-00063-001 | PIPING & INSTRUMENTATION DIAGRAM UTILITY AND DRINKING WATER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000064-001 | 370-A-PID-00064-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT, YARD AIR AND NITROGEN | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000065-001 | 370-A-PID-00065-001 | PIPING & INSTRUMENTATION DIAGRAM PROCESS LINE AT UNIT BATTERY LIMIT | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000065-002 | 370-A-PID-00065-002 | PIPING & INSTRUMENTATION DIAGRAM PROCESS LINE AT UNIT BATTERY LIMIT | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000065-003 | 370-A-PID-00065-003 | PIPING & INSTRUMENTATION DIAGRAM PROCESS LINE AT UNIT BATTERY LIMIT | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000066-001 | 370-A-PID-00066-001 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000066-002 | 370-A-PID-00066-002 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000066-003 | 370-A-PID-00066-003 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000066-004 | 370-A-PID-00066-004 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000067-001 | 370-A-PID-00067-001 | PIPING & INSTRUMENTATION DIAGRAM BFW TREATMENT DOSING PACKAGE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070522 | SO6001-ES0D-PID-37000068-001 | 370-A-PID-00068-001 | PIPING & INSTRUMENTATION DIAGRAM BFW TREATMENT DOSING PACKAGE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-17 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200001-001 | 932-A-PID-00001-001 | PIPING & INSTRUMENTATION DIAGRAM INTERCONNECTING PROCESS SULPHUR BLOCK | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200001-002 | 932-A-PID-00001-002 | PIPING & INSTRUMENTATION DIAGRAM INTERCONNECTING PROCESS SULPHUR BLOCK | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200001-003 | 932-A-PID-00001-003 | PIPING & INSTRUMENTATION DIAGRAM INTERCONNECTING PROCESS SULPHUR BLOCK | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200001-004 | 932-A-PID-00001-004 | PIPING & INSTRUMENTATION DIAGRAM INTERCONNECTING PROCESS SULPHUR BLOCK | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200002-001 | 932-A-PID-00002-001 | PIPING & INSTRUMENTATION DIAGRAM FLARE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200002-002 | 932-A-PID-00002-002 | PIPING & INSTRUMENTATION DIAGRAM FUEL GAS/ FLARE PURGE GAS | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200003-001 | 932-A-PID-00003-001 | PIPING & INSTRUMENTATION DIAGRAM 50# STEAM/ 60# STEAM/ 110# STEAM/ 550# STEAM INTERCONNECTING | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200004-001 | 932-A-PID-00004-001 | PIPING & INSTRUMENTATION DIAGRAM BOILER FEED WATER BLOWDOWN (LP/HP) | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200005-001 | 932-A-PID-00005-001 | PIPING & INSTRUMENTATION DIAGRAM CONDENSATE | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200006-001 | 932-A-PID-00006-001 | PIPING & INSTRUMENTATION DIAGRAM CW INTERCONNECTING | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200007-001 | 932-A-PID-00007-001 | PIPING & INSTRUMENTATION DIAGRAM DEMI WATER UTILITY WATER DRINKING WATER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200007-002 | 932-A-PID-00007-002 | PIPING & INSTRUMENTATION DIAGRAM CHILLED WATER | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070523 | SO6001-ES0D-PID-93200008-001 | 932-A-PID-00008-001 | PIPING & INSTRUMENTATION DIAGRAM INST.AIR/ PROCESS AIR/ NITROGEN IA/ A/ N | A | 2018-07-02 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070524 | SO6001-ES0D-PID-37100027-009 | 371-A-PID-00027-009 | PIPING & INSTRUMENTATION DIAGRAM EAT 550-110 PSIG LETDOWN STATION | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070524 | SO6001-ES0D-PID-37100027-010 | 371-A-PID-00027-010 | PIPING & INSTRUMENTATION DIAGRAM EAT 110-60 PSIG LETDOWN STATION | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070524 | SO6001-ES0D-PID-37100027-011 | 371-A-PID-00027-011 | PIPING & INSTRUMENTATION DIAGRAM STM AND G AND D 60PSIG EXCESS STEAM CONDENSATE SYSTEM | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070524 | SO6001-ES0D-PID-37100027-012 | 371-A-PID-00027-012 | PIPING & INSTRUMENTATION DIAGRAM AIR FIN DETAILS | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-001 | 005-A-PID-00050-001 | PIPING & INSTRUMENTATION DIAGRAM C3 MOUNDED BULLET 005V5001 | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-002 | 005-A-PID-00050-002 | PIPING & INSTRUMENTATION DIAGRAM C3 MOUNDED BULLET 005V5002 | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-003 | 005-A-PID-00050-003 | PIPING & INSTRUMENTATION DIAGRAM C3 TRANSFER PUMPS (TO EXISTING LPG FACILITIES) 005P5040A/B | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-004 | 005-A-PID-00050-004 | PIPING & INSTRUMENTATION DIAGRAM C3 EXPORT PUMPS (TO WHARF) | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-005 | 005-A-PID-00050-005 | PIPING & INSTRUMENTATION DIAGRAM C4 MOUNDED BULLET 005V5003 | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-006 | 005-A-PID-00050-006 | PIPING & INSTRUMENTATION DIAGRAM C4 MOUNDED BULLET 005V5004 | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-007 | 005-A-PID-00050-007 | PIPING & INSTRUMENTATION DIAGRAM C4 TRANSFER PUMPS (TO EXISTING LPG FACILITIES) 005P5042 A/B | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-008 | 005-A-PID-00050-008 | PIPING & INSTRUMENTATION DIAGRAM C4 EXPORT PUMPS (TO SITRA WHARF RLPG FACILITIES) | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-009 | 005-A-PID-00050-009 | PIPING & INSTRUMENTATION DIAGRAM C4 INJECTION PUMPS (INTO NAPHTHA/GASOLINE) | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-010 | 005-A-PID-00050-010 | PIPING & INSTRUMENTATION DIAGRAM OFFSPEC/SPARE LPG MOUNDED BULLET 005V5005 | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-011 | 005-A-PID-00050-011 | PIPING & INSTRUMENTATION DIAGRAM OFFSPEC LPG PUMPS 005P5045A/B | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-012 | 005-A-PID-00050-012 | PIPING & INSTRUMENTATION DIAGRAM OFF SPEC/SPARE LPG MOUNDED BULLET 005V5006 | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-013 | 005-A-PID-00050-013 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-014 | 005-A-PID-00050-014 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-015 | 005-A-PID-00050-015 | PIPING & INSTRUMENTATION DIAGRAM FLARE SYSTEM | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-016 | 005-A-PID-00050-016 | PIPING & INSTRUMENTATION DIAGRAM UTILITY AND STEAM SYSTEM | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-017 | 005-A-PID-00050-017 | PIPING & INSTRUMENTATION DIAGRAM NITROGEN, INSTRUMENT AIR & YARD AIR SYSTEM | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-018 | 005-A-PID-00050-018 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070525 | SO6001-ES0D-PID-00500050-019 | 005-A-PID-00050-019 | PIPING & INSTRUMENTATION DIAGRAM BATTERY LIMIT UTILITIES | A | 2018-07-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-18 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070526 | 076551C-000S-DL-0610-002 | 000-E-IDL-80001-001 | DEVIATION LIST FOR SS AND CLAD SHELL AND TUBES HEAT EXCHANGERS | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070526 | 076551C-000S-ITP-0610-002 | 000-E-ITP-80001-001 | INSPECTION AND TEST PLAN FOR SS AND CLAD SHELL AND TUBES HEAT EXCHANGERS | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070526 | 076551C-000S-MR-0610-002 | 000-E-MRQ-80001-001 | MATERIAL REQUISITION FOR SS AND CLAD SHELL AND TUBES HEAT EXCHANGERS | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070526 | 076551C-000S-SP-0610-002 | 000-E-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SS AND CLAD SHELL AND TUBES HEAT EXCHANGERS | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070526 | 076551C-000S-SR-0610-002 | 000-E-SOW-80001-001 | SCOPE OF SUPPLY FOR SS AND CLAD SHELL AND TUBES HEAT EXCHANGERS | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-19 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-16 | CLASS 1
CON-BMP-TRA-070527 | SO6001-EH1D-PID-00500050-021 | 005-A-PID-00050-021 | PIPING & INSTRUMENTATION DIAGRAM FIRE FIGHTING SYSTEM (C3/C4 LPG STORAGE FACILITY) | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070528 | SO6001-EH1D-PID-01600001-019 | 016-A-PID-00001-019 | PIPING & INSTRUMENTATION DIAGRAM FIRE FIGHTING SYSTEM (KERO MEROX UNIT) | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070529 | SO6001-EH1D-PID-09400015-001 | 094-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM FIRE FIGHTING SYSTEM (SULPHUR HANDLING FACILITIES) | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070530 | SO6001-EH1D-PID-09800031-001 | 098-A-PID-00031-001 | PIPING & INSTRUMENTATION DIAGRAM FIRE FIGHTING SYSTEM (HYDROGEN UNIT) | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070531 | SO6001-EH1D-PID-31000014-001 | 310-A-PID-00014-001 | PIPING & INSTRUMENTATION DIAGRAM FIRE FIGHTING SYSTEM (UTILITY UNIT 2) | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070532 | SO6001-EH1D-PID-35600015-001 | 356-A-PID-00015-001 | PIPING & INSTRUMENTATION DIAGRAM FIRE FIGHTING SYSTEM (UTILITY UNIT 1) | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070533 | SO6001-EH1D-PID-93200010-001 | 932-A-PID-00010-001 | PIPING & INSTRUMENTATION DIAGRAM FIRE FIGHTING SYSTEM (SULPHUR BLOCK 1) | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070533 | SO6001-EH1D-PID-93200010-002 | 932-A-PID-00010-002 | PIPING & INSTRUMENTATION DIAGRAM FIRE FIGHTING SYSTEM (SULPHUR BLOCK 2) | A | 2018-07-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 1
CON-BMP-TRA-070534 | SO6001-EH0D-PLO-09800001-001 | 098-A-PPN-80000-001 | PLOT PLAN 098-3HPU / 083-1N2 PLANT NO.3 HYDROGEN / NO.1 NITROGEN | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070534 | SO6001-EH0D-PLO-09800001-002 | 098-A-PPN-80000-002 | PLOT PLAN 098-3HPU / 083-1N2 PLANT NO.3 HYDROGEN / NO.1 NITROGEN | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070535 | SO6001-EH0D-PLO-09900001-001 | 099-A-PPN-80000-001 | PLOT PLAN 099-4HPU NO.4 HYDROGEN | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 3 - REVIEWED WITH COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070536 | SO6001-ES0D-PID-37400001-002 | 374-A-PID-00001-002 | PIPING & INSTRUMENTATION DIAGRAM REFINERY WELL WATER AND REUSE WATER SYSTEMS | A | 2018-07-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-20 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070537 | SO6001-EJ2E-TDS-01610003-001 | 016-G-DAT-00003-001 | DATA SHEET FOR CAUSTIC INJECTION PUMP TRAIN C | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070538 | SO6001-EJ2E-TDS-04400001-001 | 044-S-DAT-00001-001 | DATA SHEET FOR 044U0002 PHOSPHATE INJECTION PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070539 | SO6001-EJ2E-TDS-04600001-001 | 046-S-DAT-00001-001 | DATA SHEET FOR 046U0001 CAUSTIC PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070539 | SO6001-EJ2E-TDS-04700001-001 | 047-S-DAT-00001-001 | DATA SHEET FOR 047U0001 CAUSTIC PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070540 | SO6001-EJ2E-TDS-04800001-001 | 048-S-DAT-00001-001 | DATA SHEET FOR 048U0001 ANTIFOAM INJECTION PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070541 | SO6001-EJ2E-TDS-09800001-001 | 098-S-DAT-00001-001 | DATA SHEET FOR 098U0002 O2 SCAVENGER DOSING PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070541 | SO6001-EJ2E-TDS-09800002-001 | 098-S-DAT-00002-001 | DATA SHEET FOR 098U0003 SCALE CORROSION INHIBITOR DOSING PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070541 | SO6001-EJ2E-TDS-09800003-001 | 098-S-DAT-00003-001 | DATA SHEET FOR 098U0004 NEUTRALIZING AMINE DOSING PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070541 | SO6001-EJ2E-TDS-09900001-001 | 099-S-DAT-00001-001 | DATA SHEET FOR 099U0002 O2 SCAVENGER DOSING PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070541 | SO6001-EJ2E-TDS-09900002-001 | 099-S-DAT-00002-001 | DATA SHEET FOR 099U0003 SCALE CORROSION INHIBITOR DOSING PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070541 | SO6001-EJ2E-TDS-09900003-001 | 099-S-DAT-00003-001 | DATA SHEET FOR 099U0004 NEUTRALIZING AMINE DOSING PACKAGE | B | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070542 | SO6001-EJ2E-TDS-37000004-001 | 370-S-DAT-00004-001 | DATA SHEET FOR 370U0004 BFW TREATMENT PACKAGE | A | 2018-07-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-070543 | 076551C-000S-DL-0510-001 | 000-C-IDL-80005-001 | DEVIATION LIST FOR DEAERATORS | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070543 | 076551C-000S-ITP-0510-001 | 000-C-ITP-80005-001 | INSPECTION AND TEST PLAN FOR DEAERATORS | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070543 | 076551C-000S-MR-0510-001 | 000-C-MRQ-80005-001 | MATERIAL REQUISITION FOR DEAERATORS | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070543 | 076551C-000S-SP-0510-001 | 000-C-GRD-80005-001 | PARTICULAR TECHNICAL SPEC IFICATION FOR DEAERATORS | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070543 | 076551C-000S-SR-0510-001 | 000-C-SOW-80005-001 | SCOPE OF SUPPLY FOR DEAERATORS | A | 2018-07-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-17 | CLASS 2
CON-BMP-TRA-070544 | SO6001-EJ2E-TDS-00500001-001 | 005-S-DAT-55001-001 | DATA SHEET FOR 005U5001 RLPG OIL MIST GENERATOR | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-070545 | SO6001-EJ2E-TDS-04100001-001 | 041-S-DAT-00001-001 | DATA SHEET FOR 041OMG0001 5SRU OIL MIST GENERATOR | A | 2018-07-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-23 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-18 | CLASS 2
CON-BMP-TRA-070546 | SO6001-EJ2E-TDS-31000001-001 | 310-S-DAT-00001-001 | MECHANICAL DATA SHEET FOR 310U0001 SCALE CORROSION INHIBITOR DOSING PACKAGE | B | 2018-07-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 2
CON-BMP-TRA-070547 | 076551C-000S-DL-4046-001 | 000-S-IDL-80005-001 | DEVIATION LIST FOR DOSING SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070547 | 076551C-000S-ITP-4046-001 | 000-S-ITP-80005-001 | INSPECTION AND TEST PLAN FOR DOSING SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070547 | 076551C-000S-MR-4046-001 | 000-S-MRQ-80005-001 | MATERIAL REQUISITION FOR DOSING SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070547 | 076551C-000S-SP-4046-001 | 000-S-GRD-80005-001 | PARTICULA TECHNICAL SPECIFICATION FOR DOSING SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070547 | 076551C-000S-SR-4046-001 | 000-S-SOW-80005-001 | SCOPE OF SUPPLY FOR DOSING SYSTEM | A | 2018-07-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-19 | CLASS 1
CON-BMP-TRA-070548 | 076551C-000S-DL-2520-001 | 000-D-IDL-80001-001 | DEVIATION LIST FOR STORAGE TANKS | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-070548 | 076551C-000S-ITP-2520-001 | 000-D-ITP-80001-001 | INSPECTION AND TEST PLAN FOR STORAGE TANKS | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-070548 | 076551C-000S-MR-2520-001 | 000-D-MRQ-80001-001 | MATERIAL REQUISITION FOR STORAGE TANKS | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-070548 | 076551C-000S-SP-2520-001 | 000-D-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR STORAGE TANKS | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-070548 | 076551C-000S-SR-2520-001 | 000-D-SOW-80001-001 | SCOPE OF SUPPLY FOR STORAGE TANKS | A | 2018-07-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-23 | CLASS 1
CON-BMP-TRA-070549 | SO6001-EH0D-PLO-03680000-001 | 036-A-PPN-80000-001 | PLOT PLAN 036-2BAGRU / 037-3BAGRU NO. 2 / NO. 3 BULK ACID GAS REMOVAL UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-070549 | SO6001-EH0D-PLO-03680000-002 | 036-A-PPN-80000-002 | PLOT PLAN 036-2BAGRU / 037-3BAGRU NO. 2 / NO. 3 BULK ACID GAS REMOVAL UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-070550 | SO6001-EH0D-PLO-04180000-001 | 041-A-PPN-80000-001 | PLOT PLAN 041-5SRU / 042-6SRU / 043-7SRU NO. 5/ NO. 6/ NO. 7 SULPHUR RECOVERY UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-070550 | SO6001-EH0D-PLO-04180000-002 | 041-A-PPN-80000-002 | PLOT PLAN 041-5SRU / 042-6SRU / 043-7SRU NO. 5/ NO. 6/ NO. 7 SULPHUR RECOVERY UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-070551 | SO6001-EH0D-PLO-04480000-001 | 044-A-PPN-80000-001 | PLOT PLAN 044-3TGTU / 045-4TGTU NO. 3 /NO.4 TAIL GAS TREATMENT UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-070551 | SO6001-EH0D-PLO-04480000-002 | 044-A-PPN-80000-002 | PLOT PLAN 044-3TGTU / 045-4TGTU NO. 3 /NO.4 TAIL GAS TREATMENT UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 1
CON-BMP-TRA-070552 | SO6001-EH0D-PLO-04680000-001 | 046-A-PPN-80000-001 | PLOT PLAN S046-5SWS / S047-6SWS NO. 5 SOUR WATER / NO. 6 SOUR WATER | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-070552 | SO6001-EH0D-PLO-04680000-002 | 046-A-PPN-80000-002 | PLOT PLAN S046-5SWS / S047-6SWS NO. 5 SOUR WATER / NO. 6 SOUR WATER | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-070553 | SO6001-EH0D-PLO-04880000-001 | 048-A-PPN-80000-001 | PLOT PLAN 048-2ARU / 049-3ARU NO. 2 / NO. 3 AMINE RECOVERY UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-070553 | SO6001-EH0D-PLO-04880000-002 | 048-A-PPN-80000-002 | PLOT PLAN 048-2ARU / 049-3ARU NO. 2 / NO. 3 AMINE RECOVERY UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 1
CON-BMP-TRA-070554 | SO6001-EH0D-PLO-93280000-001 | 932-A-PPN-80000-001 | PLOT PLAN 932-SULPHUR COMPLEX | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-070554 | SO6001-EH0D-PLO-93280000-002 | 932-A-PPN-80000-002 | PLOT PLAN 932-SULPHUR COMPLEX SUBSTATION & RACKROOM | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 1
CON-BMP-TRA-070555 | 076551C-000S-DL-2543-001 | 000-C-IDL-80002-001 | DEVIATION LIST FOR STORAGE BULLETS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-070555 | 076551C-000S-ITP-2543-001 | 000-C-ITP-80002-001 | INSPECTION AND TEST PLAN FOR STORAGE BULLETS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-070555 | 076551C-000S-MR-2543-001 | 000-C-MRQ-80002-001 | MATERIAL REQUISITION FOR STORAGE BULLETS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-070555 | 076551C-000S-SP-2543-001 | 000-C-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR STORAGE BULLETS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-070555 | 076551C-000S-SR-2543-001 | 000-C-SOW-80002-001 | SCOPE OF SUPPLY FOR STORAGE BULLETS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26 | CLASS 2
CON-BMP-TRA-070556 | SO6001-EJ1E-TDS-04100015-001 | 041-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 041V0001 ACID GAS KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070557 | SO6001-EJ1E-TDS-04600007-001 | 046-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046V0001 DEGASSING DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070558 | SO6001-EJ1E-TDS-04700007-001 | 047-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 047V0001 DEGASSING DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070559 | SO6001-EJ1E-TDS-04100015-002-001 | 041-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 041V0001 ACID GAS KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070559 | SO6001-EJ1E-TDS-04100015-002-002 | 041-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 041V0001 ACID GAS KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070559 | SO6001-EJ1E-TDS-04100015-002-003 | 041-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 041V0001 ACID GAS KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070560 | 076551C-000S-DL-0811-003 | 000-C-IDL-80003-001 | DEVIATION LIST FOR CS VESSEL BELOW 19 MM HICNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070560 | 076551C-000S-ITP-0811-003 | 000-C-ITP-80003-001 | INSPECTION AND TEST PLAN FOR CS VESSEL BELOW 19 MM HICNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070560 | 076551C-000S-MR-0811-003 | 000-C-MRQ-80003-001 | MATERIAL REQUISITION FOR CS VESSEL BELOW 19 MM THICNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070560 | 076551C-000S-SP-0811-003 | 000-C-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS VESSEL BELOW 19 MM HICNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070560 | 076551C-000S-SR-0811-003 | 000-C-SOW-80003-001 | SCOPE OF SUPPLY FOR CS VESSEL BELOW 19 MM HICNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070561 | SO6001-EJ1E-TDS-04800012-001 | 048-C-DAT-00005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048V0011 ARU FLARE KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070562 | SO6001-EJ1E-TDS-03600007-002-001 | 036-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 036V0001 FEED KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070562 | SO6001-EJ1E-TDS-03600007-002-002 | 036-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 036V0001 FEED KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070562 | SO6001-EJ1E-TDS-03600007-002-003 | 036-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 036V0001 FEED KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070562 | SO6001-EJ1E-TDS-03600008-002-001 | 036-C-GAD-00004-001 | MECHANICAL DATA SHEET FOR 036V0002 ABSORBER OVERHEAD KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070562 | SO6001-EJ1E-TDS-03600008-002-002 | 036-C-GAD-00004-002 | MECHANICAL DATA SHEET FOR 036V0002 ABSORBER OVERHEAD KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070562 | SO6001-EJ1E-TDS-03600008-002-003 | 036-C-GAD-00004-003 | MECHANICAL DATA SHEET FOR 036V0002 ABSORBER OVERHEAD KO DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070563 | 076551C-000S-DL-0811-004 | 000-C-IDL-80013-001 | DEVIATION LIST FOR CS VESSEL ABOVE 19 MM THICKNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070563 | 076551C-000S-ITP-0811-004 | 000-C-ITP-80013-001 | INSPECTION AND TEST PLAN FOR CS VESSEL ABOVE 19 MM THICKNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070563 | 076551C-000S-MR-0811-004 | 000-C-MRQ-80013-001 | MATERIAL REQUISITION FOR CS VESSEL ABOVE 19 MM THICKNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070563 | 076551C-000S-SP-0811-004 | 000-C-GRD-80013-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS VESSEL ABOVE 19 MM THICKNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070563 | 076551C-000S-SR-0811-004 | 000-C-SOW-80013-001 | SCOPE OF SUPPLY FOR CS VESSEL ABOVE 19 MM THICKNESS - 20 TON | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070564 | SO6001-PV1P-EXE-005001 | 005-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET C3/C4 LPG STORAGE FACILITY AT REFINERY | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26
CON-BMP-TRA-070565 | SO6001-PV1P-EXE-016001 | 016-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET KERO MEROX UNIT | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26
CON-BMP-TRA-070566 | SO6001-PV1P-EXE-036001 | 036-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET BULK ACID GAS REMOVAL UNIT (#1 BAGRU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26
CON-BMP-TRA-070567 | SO6001-PV1P-EXE-037001 | 037-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET BULK ACID GAS REMOVAL UNIT (#2 BAGRU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070568 | SO6001-PV1P-EXE-041001 | 041-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET SULPHUR RECOVERY UNIT (#5 SRU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070569 | SO6001-PV1P-EXE-042001 | 042-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET SULPHUR RECOVERY UNIT (#6 SRU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070570 | SO6001-PV1P-EXE-043001 | 043-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET SULPHUR RECOVERY UNIT (#7 SRU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26
CON-BMP-TRA-070571 | SO6001-PV1P-EXE-044001 | 044-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET TAIL GAS TREATMENT UNIT (#3 TGT) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070572 | SO6001-PV1P-EXE-045001 | 045-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET TAIL GAS TREATMENT UNIT (#4 TGT) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070573 | SO6001-PV1P-EXE-046001 | 046-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET SOUR WATER STRIPPER UNIT (#5 SWS) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070574 | SO6001-PV1P-EXE-047001 | 047-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET SOUR WATER STRIPPER UNIT (#6 SWS) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26
CON-BMP-TRA-070575 | SO6001-PV1P-EXE-048001 | 048-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET AMINE RECOVERY UNIT (#2 ARU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070576 | SO6001-PV1P-EXE-049001 | 049-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET AMINE RECOVERY UNIT (#3 ARU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070577 | SO6001-PV1P-EXE-083001 | 083-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET NITROGEN PLANT | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27
CON-BMP-TRA-070578 | SO6001-PV1P-EXE-088001 | 088-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET KERO RE-RUN UNIT | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24
CON-BMP-TRA-070579 | SO6001-PV1P-EXE-094001 | 094-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET SULPHUR HANDLING FACILITY (#2 SHF) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30
CON-BMP-TRA-070580 | SO6001-PV1P-EXE-098001 | 098-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET HYDROGEN PRODUCTION UNIT (#3 HPU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-26
CON-BMP-TRA-070581 | SO6001-PV1P-EXE-099001 | 099-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET HYDROGEN PRODUCTION UNIT (#4 HPU) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070582 | SO6001-PV1P-EXE-310001 | 310-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET HP BOILER (#10 BOILER) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30
CON-BMP-TRA-070583 | SO6001-PV1P-EXE-311001 | 311-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET HP BOILER (#11 BOILER) | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30
CON-BMP-TRA-070584 | SO6001-PV1P-EXE-341001 | 341-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET AIR COMPRESSOR, DRYERS AND DISTRIBUTION | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30
CON-BMP-TRA-070585 | SO6001-PV1P-EXE-356001 | 356-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET DESALINATIONS PLANT | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070586 | SO6001-PV1P-EXE-357001 | 357-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET DESALINATIONS PLANT | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070587 | SO6001-PV1P-EXE-358001 | 358-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET DESALINATIONS PLANT | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-27
CON-BMP-TRA-070588 | SO6001-PV1P-EXE-370001 | 370-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET BOILER FEED WATER & CONDENSATE DISTRIBUTION | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-26
CON-BMP-TRA-070589 | SO6001-PV1P-EXE-371001 | 371-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET STEAM DISTRIBUTION | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30
CON-BMP-TRA-070590 | SO6001-PV1P-EXE-379001 | 378-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET HIGH LIFT PUMP HOUSE | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30
CON-BMP-TRA-070591 | SO6001-PV1P-EXE-382001 | 382-A-STS-80001-001 | EQUIPMENT / MATERIAL CRITICALITY LEVEL CALCULATION SHEET SEWER SYSTEM AND BASINS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 3 - REVIEWED WITH COMMENTS | 2018-07-30
CON-BMP-TRA-070592 | SO6001-EJ1E-TDS-03600009-002-001 | 036-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 036V0003 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070592 | SO6001-EJ1E-TDS-03600009-002-002 | 036-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 036V0003 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070592 | SO6001-EJ1E-TDS-03600009-002-003 | 036-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 036V0003 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070593 | SO6001-EJ1E-TDS-03700009-002-001 | 037-C-GAD-00005-001 | MECHANICAL DATA SHEET FOR 037V0003 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070593 | SO6001-EJ1E-TDS-03700009-002-002 | 037-C-GAD-00005-002 | MECHANICAL DATA SHEET FOR 037V0003 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070593 | SO6001-EJ1E-TDS-03700009-002-003 | 037-C-GAD-00005-003 | MECHANICAL DATA SHEET FOR 037V0003 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070594 | SO6001-EJ1E-TDS-04800009-002-001 | 048-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 048V0001 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070594 | SO6001-EJ1E-TDS-04800009-002-002 | 048-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 048V0001 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070594 | SO6001-EJ1E-TDS-04800009-002-003 | 048-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 048V0001 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070595 | SO6001-EJ1E-TDS-04900007-002-001 | 049-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 049V0001 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070595 | SO6001-EJ1E-TDS-04900007-002-002 | 049-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 049V0001 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070595 | SO6001-EJ1E-TDS-04900007-002-003 | 049-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 049V0001 RICH AMINE FLASH DRUM | B | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070596 | 076551C-000S-DL-0811-002 | 000-C-IDL-80001-001 | DEVIATION LIST FOR STAINLESS STEEL AND CLAD VESSELS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070596 | 076551C-000S-ITP-0811-002 | 000-C-ITP-80001-001 | INSPECTION AND TEST PLAN FOR STAINLESS STEEL AND CLAD VESSELS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070596 | 076551C-000S-MR-0811-002 | 000-C-MRQ-80001-001 | MATERIAL REQUISITION FOR STAINLESS STEEL AND CLAD VESSELS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070596 | 076551C-000S-SP-0811-002 | 000-C-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR STAINLESS STEEL AND CLAD VESSELS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070596 | 076551C-000S-SR-0811-002 | 000-C-SOW-80001-001 | SCOPE OF SUPPLY FOR STAINLESS STEEL AND CLAD VESSELS | A | 2018-07-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070597 | SO6001-EH0D-PLO-35680000-001 | 356-A-PPN-80000-001 | PLOT PLAN U341-U356-U357-U358 AIR COMPR DRYERS UNIT DESALINATION UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-070597 | SO6001-EH0D-PLO-35680000-002 | 356-A-PPN-80000-002 | PLOT PLAN U341-U356-U357-U358 AIR COMPR DRYERS UNIT DESALINATION UNIT | A | 2018-07-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-07-30 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 1
CON-BMP-TRA-070598 | 076551C-000S-DL-0848-001 | 000-S-IDL-80011-001 | DEVIATION LIST FOR FEED STRAINERS / ACTIVATED CARBON FILTERS PACKAGE | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070598 | 076551C-000S-ITP-0848-001 | 000-S-ITP-80011-001 | INSPECTION AND TEST PLAN FOR FEED STRAINERS / ACTIVATED CARBON FILTERS PACKAGE | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070598 | 076551C-000S-MR-0848-001 | 000-S-MRQ-80011-001 | MATERIAL REQUISITION FOR FEED STRAINERS / ACTIVATED CARBON FILTERS PACKAGE | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070598 | 076551C-000S-SP-0848-001 | 000-S-GRD-80011-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FEED STRAINERS / ACTIVATED CARBON FILTERS PACKAGE | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070598 | 076551C-000S-SR-0848-001 | 000-S-SOW-80011-001 | SCOPE OF SUPPLY FOR FEED STRAINERS / ACTIVATED CARBON FILTERS PACKAGE | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070599 | SO6001-EJ1E-TDS-04400038-001 | 044-S-DAT-00003-001 | DESUPERHEATER DESIGN SPECIFICATION SHEET FOR 044DS0001 600# STEAM DESUPERHEATER | B | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070599 | SO6001-EJ1E-TDS-04400039-001 | 044-S-DAT-00004-001 | DESUPERHEATER DESIGN SPECIFICATION SHEET FOR 044DS0002 50# STEAM DESUPERHEATER | B | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070600 | SO6001-EJ1E-TDS-04500024-001 | 045-S-DAT-00001-001 | DESUPERHEATER DESIGN SPECIFICATION SHEET FOR 045DS0001 600# STEAM DESUPERHEATER | B | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-25 | CLASS 2
CON-BMP-TRA-070601 | 076551C-000S-DL-0852-001 | 000-H-IDL-80001-001 | DEVIATION LIST FOR DESUPERHEATER | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070601 | 076551C-000S-ITP-0852-001 | 000-H-ITP-80001-001 | INSPECTION AND TEST PLAN FOR DESUPERHEATER | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070601 | 076551C-000S-MR-0852-001 | 000-H-MRQ-80001-001 | MATERIAL REQUISITION FOR DESUPERHEATER | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070601 | 076551C-000S-SP-0852-001 | 000-H-GRD-80001-001 | PARTICULAR TECHNICAL SSPECIFICATION FOR DESUPERHEATER | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070601 | 076551C-000S-SR-0852-001 | 000-H-SOW-80001-001 | SCOPE OF SUPPLY FOR DESUPERHEATER | A | 2018-07-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-07-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070602 | SO6001-EJ1E-TDS-04400007-001 | 044-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 044U4401 | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070602 | SO6001-EJ1E-TDS-04500007-001 | 045-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 045U4501 | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-24 | CLASS 2
CON-BMP-TRA-070603 | SO6001-EJ1E-TDS-31000001-001 | 310-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 310F0001 AUXILIARY STEAM BOILER | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070603 | SO6001-EJ1E-TDS-31100001-001 | 311-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 311F0001 AUXILIARY STEAM BOILER | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-27 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04100007-001 | 041-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 041F0001 REACTION FURNACE | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04100008-001 | 041-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 041V0003 HP STEAM DRUM | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04100009-001 | 041-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 041E0001 WASTE HEAT BOILER | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04100010-001 | 041-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 041BU0001 REACTION FURNACE BURNER | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04200007-001 | 042-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 041F0001 REACTION FURNACE | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04200008-001 | 042-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 042V0003 HP STEAM DRUM | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04200009-001 | 042-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 042E0001WASTE HEAT BOILER | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04200010-001 | 042-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 042BU0001 REACTION FURNACE BURNER | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04300007-001 | 043-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 043F0001 REACTION FURNACE | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04300008-001 | 043-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 043V40001 HP STEAM DRUM | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04300009-001 | 043-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 043E0001 WASTE HEAT BOILER | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070604 | SO6001-EJ1E-TDS-04300010-001 | 043-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 043BU0001 REACTION FURNACE BURNER | 0 | 2018-07-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-02 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070605 | SO6001-EJ1E-TDS-09800007-001 | 098-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 098F0001 REFORMING FURNACE | 0 | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070605 | SO6001-EJ1E-TDS-09800008-001 | 098-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 098V0004 STEAM DRUM | 0 | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070605 | SO6001-EJ1E-TDS-09800009-001 | 098-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 098E0001 PROCESS GAS BOILER | 0 | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070605 | SO6001-EJ1E-TDS-09800010-001 | 098-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 098F0001 REFORMING FURNACE BURNERS | 0 | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070605 | SO6001-EJ1E-TDS-09900007-001 | 099-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 099F0001 REFORMING FURNACE | 0 | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070605 | SO6001-EJ1E-TDS-09900008-001 | 099-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 099V0004 STEAM DRUM | 0 | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070605 | SO6001-EJ1E-TDS-09900009-001 | 099-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 099E0001 PROCESS GAS BOILER | 0 | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070605 | SO6001-EJ1E-TDS-09900010-001 | 099-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 099F0001 REFORMING FURNACE BURNERS | 0 | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070606 | SO6001-EK0E-TDS-00080003-001 | 000-J-DAT-80003-001 | DATASHEET ¿ ON-OFF VALVE (GATE/PLUG) | B | 2018-07-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070607 | SO6001-EH0D-PLO-31080000-001 | 310-A-PPN-80000-001 | PLOT PLAN U310 / U311 / U370 / U371 HP BOILER #10/ HP BOILER #11 / BFW&CONDENSATE DISTRIBUTION / STEAM DISTRIBUTION | A | 2018-07-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-070607 | SO6001-EH0D-PLO-31080000-002 | 310-A-PPN-80000-002 | PLOT PLAN U310 / U311 / U370 / U371 HP BOILER #10/ HP BOILER #11 / BFW&CONDENSATE DISTRIBUTION / STEAM DISTRIBUTION | A | 2018-07-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-070608 | SO6001-EH0K-MMC-93200002-001 | 932-J-MOM-00001-001 | SOC-RELOCATION OF RACKROOM IN SUPLHUR BLOCKS AREA | 0 | 2018-07-19 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-070610 | SO6001-EJ2E-TDS-37110001-001 | 371-G-DAT-55001-001 | DATA SHEET FOR 60 PSIG EXCESS STEAM CONDENSATE PUMPS | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-070611 | SO6001-EJ2E-TDS-09400003-001 | 094-S-DAT-00003-001 | DUTY SPECIFICATION FOR 094W0001 SULPHUR HANDLING WEIGHING BRIDGE IN | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-070611 | SO6001-EJ2E-TDS-09400004-001 | 094-S-DAT-00004-001 | DUTY SPECIFICATION FOR 094W0002 SULPHUR HANDLING WEIGHING BRIDGE OUT | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04100017-001 | 041-C-DAT-00005-001 | SULPHUR LOCK DATA SHEET FOR 041V0004 NO.1 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04100018-001 | 041-C-DAT-00006-001 | SULPHUR LOCK DATA SHEET FOR 041V0005 NO.2 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04100019-001 | 041-C-DAT-00007-001 | SULPHUR LOCK DATA SHEET FOR 041V0006 NO.3 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04200015-001 | 042-C-DAT-00003-001 | SULPHUR LOCK DATA SHEET FOR 042V0004 NO.1 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04200016-001 | 042-C-DAT-00004-001 | SULPHUR LOCK DATA SHEET FOR 042V0005 NO.2 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04200017-001 | 042-C-DAT-00005-001 | SULPHUR LOCK DATA SHEET FOR 042V0006 NO.3 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04300015-001 | 043-C-DAT-00003-001 | SULPHUR LOCK DATA SHEET FOR 043V0004 NO.1 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04300016-001 | 043-C-DAT-00004-001 | SULPHUR LOCK DATA SHEET FOR 043V0005 NO.2 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070612 | SO6001-EJ1E-TDS-04300017-001 | 043-C-DAT-00005-001 | SULPHUR LOCK DATA SHEET FOR 043V0006 NO.3 SULPHUR LOCK | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070613 | 076551C-000S-DL-0841-003 | 000-C-IDL-80011-001 | DEVIATION LIST FOR SULPHUR LOCK | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070613 | 076551C-000S-ITP-0841-003 | 000-C-ITP-80011-001 | INSPECTION AND TEST PLAN FOR SULPHUR LOCK | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070613 | 076551C-000S-MR-0841-003 | 000-C-MRQ-80011-001 | MATERIAL REQUISITION FOR SULPHUR LOCK | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070613 | 076551C-000S-SP-0841-003 | 000-C-GRD-80011-001 | PARTICULAR TERCHNICAL SPECIFICATION FOR SULPHUR LOCK | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070613 | 076551C-000S-SR-0841-003 | 000-C-SOW-80011-001 | SCOPE OF SUPPLY FOR SULPHUR LOCK | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070614 | SO6001-EK0E-TDS-00080002-001 | 000-J-DAT-80002-001 | DATASHEET ¿ ON-OFF VALVE (BUTTERFLY) | B | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-30 | CLASS 2
CON-BMP-TRA-070615 | 076551C-000S-DL-0841-002 | 000-C-IDL-80010-001 | DEVIATION LIST FOR COALESCER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070615 | 076551C-000S-ITP-0841-002 | 000-C-ITP-80010-001 | INSPECTION AND TEST PLAN FOR COALESCER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070615 | 076551C-000S-MR-0841-002 | 000-C-MRQ-80010-001 | MATERIAL REQUISITION FOR COALESCER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070615 | 076551C-000S-SP-0841-002 | 000-C-GRD-80010-001 | PARTICULAR TECHNICAL SPECIFICATION FOR COALESCER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070615 | 076551C-000S-SR-0841-002 | 000-C-SOW-80010-001 | SCOPE OF SUPPLY FOR COALESCER | A | 2018-07-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-06 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-07-31 | CLASS 2
CON-BMP-TRA-070616 | SO6001-EH0D-PLO-37880000-001 | 378-A-PPN-80000-001 | PLOT PLAN - 378-HLPH HIGH LIFT PUMP HOUSE | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-070617 | SO6001-EH0D-PLO-38280000-001 | 382-A-PPN-80000-001 | PLOT PLAN 382 - SEWER SYSTEM | A | 2018-07-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-06 | 3 - REVIEWED WITH COMMENTS | 2018-08-01 | CLASS 1
CON-BMP-TRA-070618 | SO6001-EK0E-TDS-00080032-001 | 000-J-DAT-80032-001 | DATASHEET - PRESSURE REGULATING VALVES | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 3 - REVIEWED WITH COMMENTS | 2018-08-06 | CLASS 2
CON-BMP-TRA-070619 | SO6001-EK0E-TDS-00080033-001 | 000-J-DAT-80033-001 | DATASHEET - PRESSURE REGULATING VALVES | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-070620 | SO6001-EH0P-MOD-000001 | 000-A-PRO-80003-001 | SOC 30% MODEL REVIEW PLAN | A | 2018-07-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-07 | CLASS 2
CON-BMP-TRA-070621 | SO6001-PP2P-DOC-000001 | 000-A-PRI-80001-001 | INSTRUCTION FOR THE EXCHANGE OF VENDOR DOCUMENTS BETWEEN SAMSUNG (SOC) AND VENDORS | A | 2018-07-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-09 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-08 | CLASS 2
CON-BMP-TRA-070622 | 076551C-000S-TBT-0113-001 | 000-F-TBE-80001-001 | TECHNICAL BID EVALUATIONS FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-07-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-06 | CLASS 2
CON-BMP-TRA-070623 | SO6001-EH0D-PLO-08800001-001 | 088-A-PPN-00001-001 | UNIT PLOT PLAN 1 KERO RERUN UNIT/REFINERY GAS SYSTEM PLANT NO. 088-058 | 13B | 2018-07-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 1
CON-BMP-TRA-070624 | SO6001-EH0D-PLO-01600001-001 | 016-A-PPN-00001-001 | PLOT PLAN FOR KERO MEROX ON PLOT FACILITIES | 5B | 2018-07-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-07 | CLASS 1
CON-BMP-TRA-070625 | SO6001-EH0D-PLO-09600001-001 | 096-A-PPN-00001-001 | PLOT PLAN NO.1 / NO. 2 SULPHUR HANDLING FACILITIES | 4B | 2018-07-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 3 - REVIEWED WITH COMMENTS | 2018-08-08 | CLASS 1
CON-BMP-TRA-070626 | SO6001-EH0D-PLO-00555001-001 | 005-A-PPN-55001-001 | PLOT PLAN 005 - C3 AND C4 LPG STORAGE AT REFINERY 005 | A | 2018-07-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-06 | CLASS 1
CON-BMP-TRA-070627 | SO6001-EH0L-LIN-08300001-001 | 083-L-INX-00001-001 | CONSTRUCTION LINE LIST 083 - 1N2 PLANT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-070628 | SO6001-EH0L-LIN-09800001-001 | 098-L-INX-00001-001 | CONSTRUCTION LINE LIST 098 - 3N2 PLANT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-070629 | SO6001-EH0L-LIN-09900001-001 | 099-L-INX-00001-001 | CONSTRUCTION LINE LIST 099 - 4N2 PLANT | A | 2018-07-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-20 | 3 - REVIEWED WITH COMMENTS | 2018-08-09 | CLASS 2
CON-BMP-TRA-070630 | 076551C-000S-TBT-0119-004 | 000-F-TBE-80002-001 | TECHNICAL BID EVALUATIONS FOR REACTION FURNACE - WASTE HEAT BOILER AND STREAM DRUM | A | 2018-07-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-10 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-06 | CLASS 2
CON-BMP-TRA-070632 | SO6001-EJ1E-TDS-04100021-001 | 041-H-DAT-00001-001 | EJECTOR DESIGN SPECIFICATION SHEET FOR 041H0001A/B SULPHUR PIT EJECTORS | B | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070632 | SO6001-EJ1E-TDS-04200019-001 | 042-H-DAT-00001-001 | EJECTOR DESIGN SPECIFICATION SHEET FOR 042H0001A/B SULPHUR PIT EJECTORS | B | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070632 | SO6001-EJ1E-TDS-04300019-001 | 043-H-DAT-00001-001 | EJECTOR DESIGN SPECIFICATION SHEET FOR 043H0001A/B SULPHUR PIT EJECTORS | B | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070632 | SO6001-EJ1E-TDS-04400037-001 | 044-H-DAT-00001-001 | EJECTOR DESIGN SPECIFICATION SHEET FOR 044H0001 START-UP GAS STEAM EJECTOR | B | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070632 | SO6001-EJ1E-TDS-04500023-001 | 045-H-DAT-00001-001 | EJECTOR DESIGN SPECIFICATION SHEET FOR 045H0001 START-UP GAS STEAM EJECTOR | B | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070632 | SO6001-EJ1E-TDS-04600014-001 | 046-H-DAT-00001-001 | EJECTOR DESIGN SPECIFICATION SHEET FOR 046H0001 DEGASSING DRUM EJECTORS | B | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070632 | SO6001-EJ1E-TDS-04700012-001 | 047-H-DAT-00001-001 | EJECTOR DESIGN SPECIFICATION SHEET FOR 047H0001 DEGASSING DRUM EJECTORS | B | 2018-07-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070633 | 076551C-000S-DL-0852-002 | 000-H-IDL-80002-001 | DEVIATION LIST FOR EJECTOR | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070633 | 076551C-000S-ITP-0852-002 | 000-H-ITP-80002-001 | INSPECTION AND TEST PLAN FOR EJECTOR | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070633 | 076551C-000S-MR-0852-002 | 000-H-MRQ-80002-001 | MATERIAL REQUISITION FOR EJECTOR | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070633 | 076551C-000S-SP-0852-002 | 000-H-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR EJECTOR | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070633 | 076551C-000S-SR-0852-002 | 000-H-SOW-80002-001 | SCOPE OF SUPPLY FOR EJECTOR | A | 2018-07-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070634 | 076551C-000S-TBT-0710-002 | 000-E-TBE-80007-001 | TECHNICAL BID EVALUATIONS FOR AIR COOLERS | A | 2018-07-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-10 | CLASS 1
CON-BMP-TRA-070635 | 076551C-000S-TBT-4352-001 | 000-S-TBE-80010-001 | TECHNICAL BID EVALUATIONS FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-07-31 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-14 | CLASS 1
CON-BMP-TRA-070637 | 076551C-000S-DL-0841-001 | 000-C-IDL-80009-001 | DEVIATION LIST FOR FILTER | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070637 | 076551C-000S-ITP-0841-001 | 000-C-ITP-80009-001 | INSPECTION ADN TEST PLAN FOR FILTER | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070637 | 076551C-000S-MR-0841-001 | 000-C-MRQ-80009-001 | MATERIAL REQUISITION FOR FILTER | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070637 | 076551C-000S-SP-0841-001 | 000-C-GRD-80009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FILTER | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070637 | 076551C-000S-SR-0841-001 | 000-C-SOW-80009-001 | SCOPE OF SUPPLY FOR FILTER | A | 2018-08-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-24 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-13 | CLASS 2
CON-BMP-TRA-070638 | 076551C-000S-TBT-4010-001 | 000-S-TBE-80003-001 | TECHNICAL BID EVALUATION FOR BMP SULPHUR HANDLING PACKAGE | A | 2018-08-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-08-22 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 1
CON-BMP-TRA-070639 | SO6001-EN0E-TDS-03680003 | 036-P-DAT-80003-001 | DATA SHEET FOR HV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070640 | SO6001-EN0E-TDS-04180003-001 | 041-P-DAT-80003-001 | DATA SHEET FOR HV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070641 | SO6001-EN0E-TDS-09480003-001 | 094-P-DAT-80003-001 | DATA SHEET FOR HV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070642 | SO6001-EN0E-TDS-09880003-001 | 098-P-DAT-80003-001 | DATA SHEET FOR HV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070643 | SO6001-EN0E-TDS-35680003-001 | 356-P-DAT-80003-001 | DATA SHEET FOR HV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-27 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070644 | SO6001-EN0E-TDS-03680005-001 | 036-P-DAT-80005-001 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070644 | SO6001-EN0E-TDS-03680005-002 | 036-P-DAT-80005-002 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070644 | SO6001-EN0E-TDS-03680005-003 | 036-P-DAT-80005-003 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070645 | SO6001-EN0E-TDS-04180005-001 | 041-P-DAT-80005-001 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070645 | SO6001-EN0E-TDS-04180005-002 | 041-P-DAT-80005-002 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070645 | SO6001-EN0E-TDS-04180005-003 | 041-P-DAT-80005-003 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070645 | SO6001-EN0E-TDS-04180005-004 | 041-P-DAT-80005-004 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070645 | SO6001-EN0E-TDS-04180005-005 | 041-P-DAT-80005-005 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070646 | SO6001-EN0E-TDS-09480005-001 | 094-P-DAT-80005-001 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070646 | SO6001-EN0E-TDS-09480005-002 | 094-P-DAT-80005-002 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070646 | SO6001-EN0E-TDS-09480005-003 | 094-P-DAT-80005-003 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070647 | SO6001-EN0E-TDS-09880005-001 | 098-P-DAT-80005-001 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070647 | SO6001-EN0E-TDS-09880005-002 | 098-P-DAT-80005-002 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070647 | SO6001-EN0E-TDS-09880005-003 | 098-P-DAT-80005-003 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070647 | SO6001-EN0E-TDS-09880005-004 | 098-P-DAT-80005-004 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070648 | SO6001-EN0E-TDS-35680005-001 | 356-P-DAT-80005-001 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070648 | SO6001-EN0E-TDS-35680005-002 | 356-P-DAT-80005-002 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070648 | SO6001-EN0E-TDS-35680005-003 | 356-P-DAT-80005-003 | DATA SHEET FOR LV SWITCHGEARS | A | 2018-08-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070649 | SO6001-EN0E-TDS-03680002-001 | 036-P-DAT-80002-001 | DATA SHEET FOR HV/HV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070650 | SO6001-EN0E-TDS-03680002-011 | 036-P-DAT-80002-011 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070650 | SO6001-EN0E-TDS-03680002-012 | 036-P-DAT-80002-012 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070651 | SO6001-EN0E-TDS-03680002-031 | 036-P-DAT-80002-031 | DATA SHEET FOR NEUTRAL EARTHING RESISTORS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070652 | SO6001-EN0E-TDS-04180002-011 | 041-P-DAT-80002-011 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070652 | SO6001-EN0E-TDS-04180002-012 | 041-P-DAT-80002-012 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070652 | SO6001-EN0E-TDS-04180002-013 | 041-P-DAT-80002-013 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070652 | SO6001-EN0E-TDS-04180002-014 | 041-P-DAT-80002-014 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-28 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070653 | SO6001-EN0E-TDS-09480002-001 | 094-P-DAT-80002-001 | DATA SHEET FOR HV/HV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070654 | SO6001-EN0E-TDS-09480002-011 | 094-P-DAT-80002-011 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070654 | SO6001-EN0E-TDS-09480002-012 | 094-P-DAT-80002-012 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070655 | SO6001-EN0E-TDS-09480002-031 | 094-P-DAT-80002-031 | DATA SHEET FOR NEUTRAL EARTHING RESISTORS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070656 | SO6001-EN0E-TDS-09880002-001 | 098-P-DAT-80002-001 | DATA SHEET FOR HV/HV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-070657 | SO6001-EN0E-TDS-09880002-011 | 098-P-DAT-80002-011 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-070657 | SO6001-EN0E-TDS-09880002-012 | 098-P-DAT-80002-012 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-070657 | SO6001-EN0E-TDS-09880002-013 | 098-P-DAT-80002-013 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-070658 | SO6001-EN0E-TDS-09880002-031 | 098-P-DAT-80002-031 | DATA SHEET FOR NEUTRAL EARTHING RESISTORS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070659 | SO6001-EN0E-TDS-35680002-001 | 356-P-DAT-80002-001 | DATA SHEET FOR HV/HV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-070660 | SO6001-EN0E-TDS-35680002-011 | 356-P-DAT-80002-011 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-070660 | SO6001-EN0E-TDS-35680002-012 | 356-P-DAT-80002-012 | DATA SHEET FOR HV/LV POWER TRANSFORMERS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-17 | CLASS 2
CON-BMP-TRA-070661 | SO6001-EN0E-TDS-35680002-031 | 356-P-DAT-80002-031 | DATA SHEET FOR NEUTRAL EARTHING RESISTORS | A | 2018-08-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-29 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-16 | CLASS 2
CON-BMP-TRA-070662 | SO6001-EJ2E-TDS-35600001-001 | 356-S-DAT-00001-001 | DUTY SPECIFICATION FOR 356U0001 NO6 DESALINATION PLANT | B | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-070662 | SO6001-EJ2E-TDS-35700001-001 | 357-S-DAT-00001-001 | DUTY SPECIFICATION FOR 356U0001 NO7 DESALINATION PLANT | B | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-070662 | SO6001-EJ2E-TDS-35800001-001 | 358-S-DAT-00001-001 | DUTY SPECIFICATION FOR 356U0001 NO8 DESALINATION PLANT | B | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-070663 | SO6001-EH1D-LAY-01600001-001 | 016-S-GAD-00001-001 | DETAILED FIRE FIGHTING LAYOUT KERO MEROX UNIT | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-070664 | SO6001-EH1D-LAY-09400001-001 | 094-S-GAD-00001-001 | DETAILED FIRE FIGHTING LAYOUT SULPHUR HANDLING FACILITIES | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070665 | SO6001-EH1D-LAY-09800001-001 | 098-S-GAD-00001-001 | DETAILED FIRE FIGHTING LAYOUT HYDROGEN UNIT | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070666 | SO6001-EH1D-LAY-31000001-001 | 310-S-GAD-00001-001 | DETAILED FIRE FIGHTING LAYOUT UTILITY UNIT 2 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070667 | SO6001-EH1D-LAY-35600001-001 | 356-S-GAD-00001-001 | DETAILED FIRE FIGHTING LAYOUT UTILITY UNIT 1 | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070668 | SO6001-EH1D-LAY-93200001-001 | 932-S-GAD-00001-001 | DETAILED FIRE FIGHTING LAYOUT SULPHUR BLOCK | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070669 | 076551C-000S-TBT-0140-001 | 000-F-TBE-80003-001 | TECHNICAL BIDS EVALUATION FOR INCINERATOR PACKAGE | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070669 REV.1 | 076551C-000S-TBT-0140-001 | 000-F-TBE-80003-001 | TECHNICAL BIDS EVALUATION FOR INCINERATOR PACKAGE | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070670 | SO6001-ES0C-HYD-01600001-001 | 016-A-CAL-00001-001 | HYDRAULIC CALCULATION REPORT - KMU | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 3 - REVIEWED WITH COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070671 | SO6001-ES0C-HYD-03600001-001 | 036-A-CAL-00001-001 | HYDRAULIC CALCULATION REPORT - SULPHUR BLOCK | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070672 | SO6001-ES0C-HYD-09400001-001 | 094-A-CAL-00001-001 | HYDRAULIC CALCULATION REPORT - SHF | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070673 | SO6001-ES0C-HYD-09800001-001 | 098-A-CAL-00001-001 | HYDRAULIC CALCULATION REPORT - HYDROGEN | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070674 | SO6001-ES0C-HYD-37000001-001 | 370-A-CAL-00001-001 | HYDRAULIC CALCULATION REPORT - STEAM & CONDENSATE | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070675 | SO6001-ES0C-HYD-38200001-001 | 382-A-CAL-00001-001 | HYDRAULIC CALCULATION REPORT - SEWER | A | 2018-08-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-08-31 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-22 | CLASS 2
CON-BMP-TRA-070676 | SO6001-ESOL-EQP-00555001-001 | 005-A-EQL-55001-001 | ITEM INDEX (EQUIPMENT LIST) C3/C4 LPG STORAGE FACILITY AT REFINERY | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070677 | SO6001-ESOL-EQP-01600001-001 | 016-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) KERO MEROX UNIT | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070678 | SO6001-ESOL-EQP-03600001-001 | 036-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO.2 BULK ACID GAS REMOVAL UNIT (2BAGRU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-070679 | SO6001-ESOL-EQP-03700001-001 | 037-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 3 BULK ACID GAS REMOVAL UNIT (3BAGRU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070680 | SO6001-ESOL-EQP-04100001-001 | 041-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 5 SULPHUR RECOVERY UNIT (5SRU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-070681 | SO6001-ESOL-EQP-04200001-001 | 042-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 6 SULPHUR RECOVERY UNIT (6SRU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-070682 | SO6001-ESOL-EQP-04300001-001 | 043-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 7 SULPHUR RECOVERY UNIT (7SRU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070683 | SO6001-ESOL-EQP-04400001-001 | 044-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 7 TAIL GAS TREATING UNIT (3TGTU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070684 | SO6001-ESOL-EQP-04500001-001 | 045-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 4 TAIL GAS TREATING UNIT (4TGTU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070685 | SO6001-ESOL-EQP-04600001-001 | 046-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 5 SOUR WATER STRIPPER UNIT (5SWS) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070686 | SO6001-ESOL-EQP-04700001-001 | 047-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 6 SOUR WATER STRIPPER UNIT (6SWS) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-070687 | SO6001-ESOL-EQP-04800001-001 | 048-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 2 AMINE REGENERATION UNIT (2ARU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-070688 | SO6001-ESOL-EQP-04900001-001 | 049-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 3 AMINE REGENERATION UNIT (3ARU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-070689 | SO6001-ESOL-EQP-08300001-001 | 083-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NITROGEN PLANT (083) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-070690 | SO6001-ESOL-EQP-08800001-001 | 088-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) KERO RE-RUN UNIT | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070691 | SO6001-ESOL-EQP-09400001-001 | 094-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 2 SULPHUR HANDLING FACILITIES (2SHF) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-070692 | SO6001-ESOL-EQP-09800001-001 | 098-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 3 HYDROGEN PRODUCTION UNIT (3HPU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070693 | SO6001-ESOL-EQP-09900001-001 | 099-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 4 HYDROGEN PRODUCTION UNIT (4HPU) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070694 | SO6001-ESOL-EQP-31000001-001 | 310-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 10 HP BOILER (310) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-070695 | SO6001-ESOL-EQP-31100001-001 | 311-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO. 11 HP BOILER (311) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070696 | SO6001-ESOL-EQP-34100001-001 | 341-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) AIR COMPRESSORS, DRYERS AND DISTRIBUTION (341) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-070697 | SO6001-ESOL-EQP-35600001-001 | 356-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO.6 DESALINATION PLANT (356) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-23 | CLASS 2
CON-BMP-TRA-070698 | SO6001-ESOL-EQP-35700001-001 | 357-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) NO.7 DESALINATION PLANT (357) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-070700 | SO6001-ESOL-EQP-37000001-001 | 370-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) BFW & CONDENSATE DISTRIBUTION (370) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070701 | SO6001-ESOL-EQP-37155001-001 | 371-A-EQL-55001-001 | ITEM INDEX (EQUIPMENT LIST) STEAM DISTRIBUTION (371) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070702 | SO6001-ESOL-EQP-37900001-001 | 379-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) HIGH LIFT PUMP HOUSE (379) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070703 | SO6001-ESOL-EQP-38200001-001 | 382-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) SEWER SYSTEMS AND BASINS (382) | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070704 | SO6001-EJ2E-TDS-09400003-001 | 094-S-DAT-00003-001 | DUTY SPECIFICATION FOR 094W0001/094W0002 SULPHUR HANDLING WEIGHING BRIDGE IN/OUT | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-21 | CLASS 2
CON-BMP-TRA-070705 | SO6001-EK0E-TDS-00080001-001 | 000-J-DAT-80001-001 | DATASHEET ¿ ON-OFF VALVE (BALL) | B | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-03 |  |  | CLASS 2
CON-BMP-TRA-070706 | 076551C-000S-TBT-0150-001 | 000-F-TBE-80004-001 | TECHNICAL BIDS EVALUATION FOR NO. 10 HP BOILER & NO. 11 HP BOILER | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-01 |  |  | CLASS 2
CON-BMP-TRA-070707 | 076551C-000S-TBT-0215-001 | 000-S-TBE-80002-001 | TECHNICAL BIDS EVALUATIONS FOR MULTI EFFECT DESALINATION PACKAGE | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-01 |  |  | CLASS 2
CON-BMP-TRA-070708 | 076551C-000S-TBT-4112-001 | 000-S-TBE-80008-001 | TECHNICAL BIDS EVALUATIONS FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | A | 2018-08-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-01 | 3 - REVIEWED WITH COMMENTS | 2018-08-24 | CLASS 2
CON-BMP-TRA-070709 | SO6001-EH0L-LIN-03600001-001 | 036-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-070710 | 076551C-000S-DL-4041-001 | 000-S-IDL-80004-001 | DEVIATION LIST FOR TRUCK SCALE WEIGHING BRIDGES | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-070710 | 076551C-000S-ITP-4041-001 | 000-S-ITP-80004-001 | INSPECTION AND TEST PLAN FOR TRUCK SCALE WEIGHING BRIDGES | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-070710 | 076551C-000S-MR-4041-001 | 000-S-MRQ-80004-001 | MATERIAL REQUISITION FOR TRUCK SCALE WEIGHING BRIDGES | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-070710 | 076551C-000S-SP-4041-001 | 000-S-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR TRUCK SCALE WEIGHING BRIDGES | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-070710 | 076551C-000S-SR-4041-001 | 000-S-SOW-80004-001 | SCOPE OF SUPPLY FOR TRUCK SCALE WEIGHING BRIDGES | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-29 | CLASS 2
CON-BMP-TRA-070711 | SO6001-EH0L-LIN-03700001-001 | 037-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070712 | SO6001-EH0L-LIN-04800001-001 | 048-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-30 | CLASS 2
CON-BMP-TRA-070713 | SO6001-EH0L-LIN-04900001-001 | 049-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070714 | SO6001-EH0L-LIN-93200001-001 | 932-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 3 - REVIEWED WITH COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070715 | SO6001-EH0L-LIN-31000001-001 | 310-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070716 | SO6001-EH0L-LIN-31100001-001 | 311-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070717 | SO6001-EH0L-LIN-34100001-001 | 341-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070718 | SO6001-EH0L-LIN-35600001-001 | 356-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070719 | SO6001-EH0L-LIN-35700001-001 | 357-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070720 | SO6001-EH0L-LIN-35800001-001 | 358-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070721 | SO6001-EH0L-LIN-37000001-001 | 370-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070722 | SO6001-EH0L-LIN-04100001-001 | 041-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070723 | SO6001-EH0L-LIN-04200001-001 | 042-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070724 | SO6001-EH0L-LIN-04300001-001 | 043-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070725 | SO6001-EH0L-LIN-04400001-001 | 044-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070726 | SO6001-EH0L-LIN-04500001-001 | 045-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070727 | SO6001-EH0L-LIN-04600001-001 | 046-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070728 | SO6001-EH0L-LIN-04700001-001 | 047-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 | 2 - REVIEWED WITH MINOR COMMENTS | 2018-08-31 | CLASS 2
CON-BMP-TRA-070729 | SO6001-EH0L-LIN-37155001-001 | 371-L-INX-55001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070730 | SO6001-EH0L-LIN-00555001-001 | 005-L-INX-55001-001 | CONSTRUCTION LINE LIST | A | 2018-08-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-04 |  |  | CLASS 2
CON-BMP-TRA-070731 | SO6001-EH0L-LIN-01650001-001 | 016-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070732 | SO6001-EH0L-LIN-08850001-001 | 088-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070733 | SO6001-EH0L-LIN-09400001-001 | 094-L-INX-00001-001 | CONSTRUCTION LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070734 | SO6001-EH0L-LIN-09650001-001 | 096-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070735 | SO6001-EH0L-LIN-37450001-001 | 374-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070736 | SO6001-EH0L-LIN-38250001-001 | 382-L-INX-50001-001 | CONSTRUCTION LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070737 | SO6001-EH0L-LIN-08300001-001 | 083-L-INX-00001-001 | CONSTRUCTION LINE LIST | B | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070738 | SO6001-EH0L-LIN-09800001-001 | 098-L-INX-00001-001 | CONSTRUCTION LINE LIST | B | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070739 | SO6001-EH0L-LIN-09900001-001 | 099-L-INX-00001-001 | CONSTRUCTION LINE LIST | B | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-03600004-001 | 036-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-03700004-001 | 037-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04100004-001 | 041-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04200004-001 | 042-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04300004-001 | 043-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04400004-001 | 044-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04500004-001 | 045-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04600004-001 | 046-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04700004-001 | 047-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04800004-001 | 048-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-04900004-001 | 049-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070740 | SO6001-EH0L-LIN-93200004-001 | 932-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070741 | SO6001-EK0E-TDS-00080004-001 | 000-J-DAT-80004-001 | DATASHEET - SAFETY RELIEF VALVES AND RUPTURE DISC | A | 2018-08-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-05 |  |  | CLASS 2
CON-BMP-TRA-070742 | SO6001-EH0P-MOD-000001 | 000-A-PRO-80003-001 | SOC 30% MODEL REVIEW PLAN | B | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070743 | SO6001-ES0C-HYD-00500001-001 | 005-A-CAL-55001-001 | HYDRAULIC CALCULATION REPORT - LPG | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070744 | SO6001-EH1D-LAY-00555001-001 | 005-S-GAD-55001-001 | DETAILED FIRE FIGHTING LAYOUT C3/C4 LPG STORAGE FACILITY | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-00555004-001 | 005-L-INX-55004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-08300004-001 | 083-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-09400004-001 | 094-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-09800004-001 | 098-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-09900004-001 | 099-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-31000004-001 | 310-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-31100004-001 | 311-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-34100004-001 | 341-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-35600004-001 | 356-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-35700004-001 | 357-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-35800004-001 | 358-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-37000004-001 | 370-L-INX-00004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070745 | SO6001-EH0L-LIN-37155004-001 | 371-L-INX-55004-001 | CRITICAL LINE LIST | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070746 | SO6001-EK0E-TDS-00080002-001 | 000-J-DAT-80002-001 | DATASHEET ¿ ON-OFF VALVE (BUTTERFLY) | C | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070747 | SO6001-SZ0P-CTR-000001 | 000-A-RPT-80001-001 | SOC CONSTRUCTABILITY REPORT | 0 | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070748 | SO6001-EJ1E-TDS-08300001-001 | 083-C-DAT-00001-001 | FILTER DESIGN SPECIFICATION SHEET FOR 083V0001A/B INSTRUMENT AIR FILTERS | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070748 | SO6001-EJ1E-TDS-08300002-001 | 083-C-DAT-00002-001 | FILTER DESIGN SPECIFICATION SHEET FOR 083V0002A/B INSTRUMENT AIR FILTERS | A | 2018-08-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070749 | SO6001-EJ1E-TDS-09400001-001 | 094-H-DAT-00001-001 | EDUCTOR DESIGN SPECIFICATION SHEET FOR 094H0001 2SHF MIXING EDUCTOR | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070750 | SO6001-EJ1E-TDS-01600008-001 | 016-C-DAT-50007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 016V1646 CLAY FILTER TRAIN C MISC-P1054-B1-N | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-06 |  |  | CLASS 2
CON-BMP-TRA-070751 | SO6001-EJ1E-TDS-01600008-002 | 016-C-GAD-50005-001 | MECHANICAL DRAWING FOR 016V1646 CLAY FILTER TRAIN C MISC-P1054-B1-N | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070751 | SO6001-EJ1E-TDS-01600008-003 | 016-C-GAD-50005-002 | MECHANICAL DRAWING FOR 016V1646 CLAY FILTER TRAIN C MISC-P1054-B1-N | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070751 | SO6001-EJ1E-TDS-01600008-004 | 016-C-GAD-50005-003 | MECHANICAL DRAWING FOR 016V1646 CLAY FILTER TRAIN C MISC-P1054-B1-N | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070752 | SO6001-EJ1E-TDS-09800006-002 | 098-C-GAD-00010-001 | MECHANICAL DRAWINGS FOR 098V0007 DEAERATOR | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070752 | SO6001-EJ1E-TDS-09800006-003 | 098-C-GAD-00010-002 | MECHANICAL DRAWINGS FOR 098V0007 DEAERATOR | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070752 | SO6001-EJ1E-TDS-09800006-004 | 098-C-GAD-00010-003 | MECHANICAL DRAWINGS FOR 098V0007 DEAERATOR | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070753 | SO6001-EJ1E-TDS-09900006-002 | 099-C-GAD-00010-001 | MECHANICAL DRAWINGS FOR 099V0007 DEAERATOR | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070753 | SO6001-EJ1E-TDS-09900006-003 | 099-C-GAD-00010-002 | MECHANICAL DRAWINGS FOR 099V0007 DEAERATOR | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070753 | SO6001-EJ1E-TDS-09900006-004 | 099-C-GAD-00010-003 | MECHANICAL DRAWINGS FOR 099V0007 DEAERATOR | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070754 | SO6001-EN0D-CAB-04680331-001 | 046-P-CRD-80331-001 | CABLE TRENCH LAYOUT UNIT 046 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070754 | SO6001-EN0D-CAB-04680332-001 | 046-P-CRD-80332-001 | CABLE TRENCH LAYOUT UNIT 047 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070755 | SO6001-EN0D-CAB-03680331-001 | 036-P-CRD-80331-001 | CABLE TRENCH LAYOUT 036SSTR01 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070755 | SO6001-EN0D-CAB-03680332-001 | 036-P-CRD-80332-001 | CABLE TRENCH LAYOUT UNIT 048 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070755 | SO6001-EN0D-CAB-03680333-001 | 036-P-CRD-80333-001 | CABLE TRENCH LAYOUT UNIT 049 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070755 | SO6001-EN0D-CAB-03680334-001 | 036-P-CRD-80334-001 | CABLE TRENCH LAYOUT UNIT 036 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070755 | SO6001-EN0D-CAB-03680335-001 | 036-P-CRD-80335-001 | CABLE TRENCH LAYOUT UNIT 037 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070756 | SO6001-EN0D-CAB-04180331-001 | 041-P-CRD-80331-001 | CABLE TRENCH LAYOUT 041SSTR01 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070756 | SO6001-EN0D-CAB-04180332-001 | 041-P-CRD-80332-001 | CABLE TRENCH LAYOUT UNIT 044/045 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070756 | SO6001-EN0D-CAB-04180333-001 | 041-P-CRD-80333-001 | CABLE TRENCH LAYOUT UNIT 041/044/045 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070756 | SO6001-EN0D-CAB-04180334-001 | 041-P-CRD-80334-001 | CABLE TRENCH LAYOUT UNIT 044/045 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070756 | SO6001-EN0D-CAB-04180335-001 | 041-P-CRD-80335-001 | CABLE TRENCH LAYOUT UNIT 042/044/045 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070756 | SO6001-EN0D-CAB-04180336-001 | 041-P-CRD-80336-001 | CABLE TRENCH LAYOUT UNIT 046/047 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070756 | SO6001-EN0D-CAB-04180337-001 | 041-P-CRD-80337-001 | CABLE TRENCH LAYOUT UNIT 043/046/047 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070757 | 076551C-000S-TBT-0511-001 | 000-C-TBE-80006-001 | TECHNICAL BID EVALUATIONS FOR CS COLUMNS | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070758 | 076551C-000S-TBT-0511-002 | 000-C-TBE-80007-001 | TECHNICAL BID EVALUATIONS FOR CLADDED COLUMNS | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680301-001 | 356-P-CRD-80301-001 | CABLE TRENCH LAYOUT - KEY PLAN 310 - HP BOILER / 356 DESALINATION PLANT | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680302-001 | 356-P-CRD-80302-001 | CABLE TRENCH LAYOUT - KEY PLAN 310 - HP BOILER / 356 DESALINATION PLANT | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680331-001 | 356-P-CRD-80331-001 | CABLE TRENCH LAYOUT 356SSTR01 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680332-001 | 356-P-CRD-80332-001 | CABLE TRENCH LAYOUT UNIT 370 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680333-001 | 356-P-CRD-80333-001 | CABLE TRENCH LAYOUT UNIT 310 / 311 / 370 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680334-001 | 356-P-CRD-80334-001 | CABLE TRENCH LAYOUT UNIT 370 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680335-001 | 356-P-CRD-80335-001 | CABLE TRENCH LAYOUT UNIT 311 / 370 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680336-001 | 356-P-CRD-80336-001 | CABLE TRENCH LAYOUT UNIT 356 / 357 / 358 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680337-001 | 356-P-CRD-80337-001 | CABLE TRENCH LAYOUT UNIT 341 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070759 | SO6001-EN0D-CAB-35680338-001 | 356-P-CRD-80338-001 | CABLE TRENCH LAYOUT H162BLD01 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070760 | SO6001-EN0D-CAB-09880301-001 | 098-P-CRD-80301-001 | CABLE TRENCH LAYOUT - KEY PLAN UNIT 098/099/083 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070760 | SO6001-EN0D-CAB-09880302-001 | 098-P-CRD-80302-001 | CABLE TRENCH LAYOUT - OVERALL UNIT 098/099/083 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070760 | SO6001-EN0D-CAB-09880331-001 | 098-P-CRD-80331-001 | CABLE TRENCH LAYOUT 098SSTR01 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070760 | SO6001-EN0D-CAB-09880332-001 | 098-P-CRD-80332-001 | CABLE TRENCH LAYOUT UNIT 098 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070760 | SO6001-EN0D-CAB-09880333-001 | 098-P-CRD-80333-001 | CABLE TRENCH LAYOUT UNIT 083/098 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070760 | SO6001-EN0D-CAB-09880334-001 | 098-P-CRD-80334-001 | CABLE TRENCH LAYOUT UNIT 099 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070760 | SO6001-EN0D-CAB-09880335-001 | 098-P-CRD-80335-001 | CABLE TRENCH LAYOUT UNIT 099 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070760 | SO6001-EN0D-CAB-09880336-001 | 098-P-CRD-80336-001 | CABLE TRENCH LAYOUT OPERATOR SHELTER | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070761 | SO6001-EN0D-CAB-93280301-001 | 932-P-CRD-80301-001 | CABLE TRENCH LAYOUT - KEY PLAN UNIT 036/037/048/049/041 /042/ 043/044/045/046/047 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070761 | SO6001-EN0D-CAB-93280302-001 | 932-P-CRD-80302-001 | CABLE TRENCH LAYOUT - OVERALL UNIT 036/037/048/049/041/042/043 /044/045/046/047 | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070762 | SO6001-EJ1E-TDS-01600003-001 | 016-C-DAT-50002-001 | ELECTROSTATIC COALESCER DESIGN SPECIFICATION SHEET FOR 16V1642 ELECTROSTATIC COALSCER TRAIN C MISC-P1048-B2-N | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070763 | SO6001-EH0L-LIN-01650004-001 | 016-L-INX-50004-001 | CRITICAL LINE LIST | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070763 | SO6001-EH0L-LIN-08850004-001 | 088-L-INX-50004-001 | CRITICAL LINE LIST | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070763 | SO6001-EH0L-LIN-09650004-001 | 096-L-INX-50004-001 | CRITICAL LINE LIST | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070763 | SO6001-EH0L-LIN-37450004-001 | 374-L-INX-50004-001 | CRITICAL LINE LIST | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070763 | SO6001-EH0L-LIN-38250004-001 | 382-L-INX-50004-001 | CRITICAL LINE LIST | A | 2018-08-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680111-001 | 036-P-SLD-80111-001 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6111L) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680111-002 | 036-P-SLD-80111-002 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6112L) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680121-001 | 036-P-SLD-80121-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6121N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680121-002 | 036-P-SLD-80121-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6121N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680121-003 | 036-P-SLD-80121-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6122N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680121-004 | 036-P-SLD-80121-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6122N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680121-005 | 036-P-SLD-80121-005 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6122N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680122-001 | 036-P-SLD-80122-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6123N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680122-002 | 036-P-SLD-80122-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6123N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680122-003 | 036-P-SLD-80122-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6124N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680122-004 | 036-P-SLD-80122-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6124N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680122-005 | 036-P-SLD-80122-005 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6124N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680131-001 | 036-P-SLD-80131-001 | SINGLE LINE DIAGRAM 400V EMER. SWITCHGEAR & MCC (BUS 6141N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680131-002 | 036-P-SLD-80131-002 | SINGLE LINE DIAGRAM 400V EMER. SWITCHGEAR & MCC (BUS 6141N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680141-001 | 036-P-SLD-80141-001 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6153N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680141-002 | 036-P-SLD-80141-002 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6153N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680151-001 | 036-P-SLD-80151-001 | SINGLE LINE DIAGRAM MOV DISTRIBUTION BOARD (BUS 6131N) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680161-001 | 036-P-SLD-80161-001 | SINGLE LINE DIAGRAM 110V DC UPS (CHG 6123N1 & CHG 6141N1) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680162-001 | 036-P-SLD-80162-001 | SINGLE LINE DIAGRAM 115V AC UPS (UPS 6123N1 & UPS 6141N1) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070764 | SO6001-EN0D-SLD-03680162-002 | 036-P-SLD-80162-002 | SINGLE LINE DIAGRAM 115V AC UPS (UPS 6123N2 & UPS 6141N2) 3 SULPHUR PLANT WEST SUBSTATION 036SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180111-001 | 041-P-SLD-80111-001 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6211L) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180111-002 | 041-P-SLD-80111-002 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6212L) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180121-001 | 041-P-SLD-80121-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6221N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180121-002 | 041-P-SLD-80121-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6221N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180121-003 | 041-P-SLD-80121-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6221N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180121-004 | 041-P-SLD-80121-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6222N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180121-005 | 041-P-SLD-80121-005 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6222N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180122-001 | 041-P-SLD-80122-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6223N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180122-002 | 041-P-SLD-80122-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6223N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180122-003 | 041-P-SLD-80122-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6224N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070765 | SO6001-EN0D-SLD-04180122-004 | 041-P-SLD-80122-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6224N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180123-001 | 041-P-SLD-80123-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6225N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180123-002 | 041-P-SLD-80123-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6225N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180123-003 | 041-P-SLD-80123-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6226N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180123-004 | 041-P-SLD-80123-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6226N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180124-001 | 041-P-SLD-80124-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6227N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180124-002 | 041-P-SLD-80124-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6228N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180124-003 | 041-P-SLD-80124-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6228N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180124-004 | 041-P-SLD-80124-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6228N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180131-001 | 041-P-SLD-80131-001 | SINGLE LINE DIAGRAM 400V EMER. SWITCHGEAR & MCC (BUS 6241N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180141-001 | 041-P-SLD-80141-001 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6253N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180141-002 | 041-P-SLD-80141-002 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6253N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180141-003 | 041-P-SLD-80141-003 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6253N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180151-001 | 041-P-SLD-80151-001 | SINGLE LINE DIAGRAM MOV DISTRIBUTION BOARD (BUS 6231N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180151-002 | 041-P-SLD-80151-002 | SINGLE LINE DIAGRAM MOV DISTRIBUTION BOARD (BUS 6232N) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070766 | SO6001-EN0D-SLD-04180161-001 | 041-P-SLD-80161-001 | SINGLE LINE DIAGRAM 110V DC UPS (CHG 6221N1 & CHG 6241N1) 3 SULPHUR PLANT EST SUBSTATION 041SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880111-001 | 098-P-SLD-80111-001 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6511L) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880111-002 | 098-P-SLD-80111-002 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6512L) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880121-001 | 098-P-SLD-80121-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6521N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880121-002 | 098-P-SLD-80121-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6521N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880121-003 | 098-P-SLD-80121-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6521N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880121-004 | 098-P-SLD-80121-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6522N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880121-005 | 098-P-SLD-80121-005 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6522N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880122-001 | 098-P-SLD-80122-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6523N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880122-002 | 098-P-SLD-80122-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6523N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880122-003 | 098-P-SLD-80122-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6524N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880122-004 | 098-P-SLD-80122-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6524N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880123-001 | 098-P-SLD-80123-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6525N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880123-002 | 098-P-SLD-80123-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6525N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880131-001 | 098-P-SLD-80131-001 | SINGLE LINE DIAGRAM 400V EMER. SWITCHGEAR & MCC (BUS 6541N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880131-002 | 098-P-SLD-80131-002 | SINGLE LINE DIAGRAM 400V EMER. SWITCHGEAR & MCC (BUS 6541N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880141-001 | 098-P-SLD-80141-001 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6553N) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880161-001 | 098-P-SLD-80161-001 | SINGLE LINE DIAGRAM 110V DC UPS (CHG6522N1 & CHG6541N1) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880162-001 | 098-P-SLD-80162-001 | SINGLE LINE DIAGRAM 115V AC UPS (UPS6521N1 & UPS6541N1) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070767 | SO6001-EN0D-SLD-09880162-002 | 098-P-SLD-80162-002 | SINGLE LINE DIAGRAM 115V AC UPS (UPS6522N1 & UPS6541N2) H2/N2 SUBSTATION 098SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680111-001 | 356-P-SLD-80111-001 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6711L) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680111-002 | 356-P-SLD-80111-002 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6711L) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680111-003 | 356-P-SLD-80111-003 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6712L) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680111-004 | 356-P-SLD-80111-004 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6712L) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680121-001 | 356-P-SLD-80121-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6721N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680121-002 | 356-P-SLD-80121-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6721N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680121-003 | 356-P-SLD-80121-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6721N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680121-004 | 356-P-SLD-80121-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6721N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680121-005 | 356-P-SLD-80121-005 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6722N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680121-006 | 356-P-SLD-80121-006 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6722N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680121-007 | 356-P-SLD-80121-007 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6722N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680121-008 | 356-P-SLD-80121-008 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6722N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680122-001 | 356-P-SLD-80122-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6723N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680122-002 | 356-P-SLD-80122-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6723N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680122-003 | 356-P-SLD-80122-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6724N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680122-004 | 356-P-SLD-80122-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6724N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070768 | SO6001-EN0D-SLD-35680122-005 | 356-P-SLD-80122-005 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6724N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680131-001 | 356-P-SLD-80131-001 | SINGLE LINE DIAGRAM 400V EMER. SWITCHGEAR & MCC (BUS 6741N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680131-002 | 356-P-SLD-80131-002 | SINGLE LINE DIAGRAM 400V EMER. SWITCHGEAR & MCC (BUS 6741N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680141-001 | 356-P-SLD-80141-001 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6753N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680151-001 | 356-P-SLD-80151-001 | SINGLE LINE DIAGRAM MOV DISTRIBUTION BOARD (BUS 6731N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680151-002 | 356-P-SLD-80151-002 | SINGLE LINE DIAGRAM MOV DISTRIBUTION BOARD (BUS 6732N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680151-003 | 356-P-SLD-80151-003 | SINGLE LINE DIAGRAM MOV DISTRIBUTION BOARD (BUS 6733N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680151-004 | 356-P-SLD-80151-004 | SINGLE LINE DIAGRAM MOV DISTRIBUTION BOARD (BUS 6734N) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680161-001 | 356-P-SLD-80161-001 | SINGLE LINE DIAGRAM 110V DC UPS (CHG6721N1 & CHG6741N1) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680162-001 | 356-P-SLD-80162-001 | SINGLE LINE DIAGRAM 115V AC UPS (UPS6721N1 & UPS6741N1) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070769 | SO6001-EN0D-SLD-35680162-002 | 356-P-SLD-80162-002 | SINGLE LINE DIAGRAM 115V AC UPS (UPS6721N2 & UPS6741N2) UTILITY SUBSTATION 356SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480111-001 | 094-P-SLD-80111-001 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6811L) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480111-002 | 094-P-SLD-80111-002 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR & MCC (BUS 6812L) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480121-001 | 094-P-SLD-80121-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6821N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480121-002 | 094-P-SLD-80121-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6821N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480121-003 | 094-P-SLD-80121-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6821N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480121-004 | 094-P-SLD-80121-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6822N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480121-005 | 094-P-SLD-80121-005 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6822N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480121-006 | 094-P-SLD-80121-006 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6822N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480122-001 | 094-P-SLD-80122-001 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6823N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480122-002 | 094-P-SLD-80122-002 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6823N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480122-003 | 094-P-SLD-80122-003 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6824N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480122-004 | 094-P-SLD-80122-004 | SINGLE LINE DIAGRAM 400V SWITCHGEAR & MCC (BUS 6824N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480131-001 | 094-P-SLD-80131-001 | SINGLE LINE DIAGRAM 400V EMER. SWITCHGEAR & MCC (BUS 6841N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480141-001 | 094-P-SLD-80141-001 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6853N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480141-002 | 094-P-SLD-80141-002 | SINGLE LINE DIAGRAM GENERAL SERVICE BOARD (BUS 6853N) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480161-001 | 094-P-SLD-80161-001 | SINGLE LINE DIAGRAM 110V DC UPS (CHG 6823N1 & CHG 6841N1) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480162-001 | 094-P-SLD-80162-001 | SINGLE LINE DIAGRAM 115V AC UPS (UPS 6823N1 & UPS 6841N1) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070770 | SO6001-EN0D-SLD-09480162-002 | 094-P-SLD-80162-002 | SINGLE LINE DIAGRAM 115V AC UPS (UPS 6824N1 & UPS 6841N2) 2 SHF SUBSTATION 094SSTR01 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-07 |  |  | CLASS 2
CON-BMP-TRA-070771 | SO6001-EQ1D-BDG-09415001-001 | 094-R-GAD-15001-001 | GROUND FLOOR PLAN & FINISHING SCHEDULE SUBSTASTION & RACK ROOM FOR SHF 094BLD01 (094SSTR01 / 164SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070771 | SO6001-EQ1D-BDG-09415002-001 | 094-R-GAD-15002-001 | FIRST FLOOR PLAN SUBSTASTION & RACK ROOM FOR SHF 094BLD01 (094SSTR01 / 164SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070771 | SO6001-EQ1D-BDG-09415003-001 | 094-R-GAD-15003-001 | ROOF PLAN SUBSTASTION & RACK ROOM FOR SHF 094BLD01 (094SSTR01 / 164SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070771 | SO6001-EQ1D-BDG-09415021-001 | 094-R-GAD-15021-001 | ELEVATION-1 SUBSTASTION & RACK ROOM FOR SHF 094BLD01 (094SSTR01 / 164SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070771 | SO6001-EQ1D-BDG-09415022-001 | 094-R-GAD-15022-001 | ELEVATION-2 SUBSTASTION & RACK ROOM FOR SHF 094BLD01 (094SSTR01 / 164SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070771 | SO6001-EQ1D-BDG-09415023-001 | 094-R-GAD-15023-001 | GENERAL SECTION SUBSTASTION & RACK ROOM FOR SHF 094BLD01 (094SSTR01 / 164SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070772 | SO6001-EQ1D-BDG-09815101-001 | 098-R-GAD-15101-001 | GROUND FLOOR PLAN & FINISHING SCHEDULE SUBSTASTION & RACK ROOM FOR HYDROGEN PLANT 098BLD02 (098SSTR01/159SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070772 | SO6001-EQ1D-BDG-09815102-001 | 098-R-GAD-15102-001 | FIRST FLOOR PLAN SUBSTASTION & RACK ROOM FOR HYDROGEN PLANT 098BLD02 (098SSTR01/159SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070772 | SO6001-EQ1D-BDG-09815103-001 | 098-R-GAD-15103-001 | ROOF PLAN SUBSTASTION & RACK ROOM FOR HYDROGEN PLANT 098BLD02 (098SSTR01/159SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070772 | SO6001-EQ1D-BDG-09815121-001 | 098-R-GAD-15121-001 | ELEVATION-1 SUBSTASTION & RACK ROOM FOR HYDROGEN PLANT 098BLD02 (098SSTR01/159SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070772 | SO6001-EQ1D-BDG-09815122-001 | 098-R-GAD-15122-001 | ELEVATION-2 SUBSTASTION & RACK ROOM FOR HYDROGEN PLANT 098BLD02 (098SSTR01/159SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070772 | SO6001-EQ1D-BDG-09815123-001 | 098-R-GAD-15123-001 | GENERAL SECTION SUBSTASTION & RACK ROOM FOR HYDROGEN PLANT 098BLD02 (098SSTR01/159SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070773 | SO6001-EQ1D-BDG-35615001-001 | 356-R-GAD-15001-001 | GROUND FLOOR PLAN & FINISHING SCHEDULE SUBSTASTION FOR UTILITIES 356BLD01 (356SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070773 | SO6001-EQ1D-BDG-35615002-001 | 356-R-GAD-15002-001 | FIRST FLOOR PLAN SUBSTASTION FOR UTILITIES 356BLD01 (356SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070773 | SO6001-EQ1D-BDG-35615003-001 | 356-R-GAD-15003-001 | ROOF PLAN SUBSTASTION FOR UTILITIES 356BLD01 (356SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070773 | SO6001-EQ1D-BDG-35615021-001 | 356-R-GAD-15021-001 | ELEVATION-1 SUBSTASTION FOR UTILITIES 356BLD01 (356SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070773 | SO6001-EQ1D-BDG-35615022-001 | 356-R-GAD-15022-001 | ELEVATION-2 SUBSTASTION FOR UTILITIES 356BLD01 (356SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070773 | SO6001-EQ1D-BDG-35615023-001 | 356-R-GAD-15023-001 | GENERAL SECTION SUBSTASTION FOR UTILITIES 356BLD01 (356SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215001-001 | 932-R-GAD-15001-001 | GROUND FLOOR PLAN & FINISHING SCHEDULE SUBSTATION FOR SULPHUR BLOCK 932BLD02 (041SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215002-001 | 932-R-GAD-15002-001 | FIRST FLOOR PLAN SUBSTATION FOR SULPHUR BLOCK 932BLD02 (041SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215003-001 | 932-R-GAD-15003-001 | ROOF PLAN SUBSTATION FOR SULPHUR BLOCK 932BLD02 (041SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215021-001 | 932-R-GAD-15021-001 | ELEVATION - 1 SUBSTATION FOR SULPHUR BLOCK 932BLD02 (041SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215022-001 | 932-R-GAD-15022-001 | ELEVATION - 2 SUBSTATION FOR SULPHUR BLOCK 932BLD02 (041SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215023-001 | 932-R-GAD-15023-001 | GENERAL SECTION SUBSTATION FOR SULPHUR BLOCK 932BLD02 (041SSTR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215101-001 | 932-R-GAD-15101-001 | GROUND FLOOR PLAN & FINISHING SCHEDULE SUBSTATION & RACK ROOM FOR SULPHUR BLOCK 932BLD01 (036SSTR01/158SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215102-001 | 932-R-GAD-15102-001 | FIRST FLOOR PLAN SUBSTATION & RACK ROOM FOR SULPHUR BLOCK 932BLD01 (036SSTR01/158SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215103-001 | 932-R-GAD-15103-001 | ROOF PLAN SUBSTATION & RACK ROOM FOR SULPHUR BLOCK 932BLD01 (036SSTR01/158SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215121-001 | 932-R-GAD-15121-001 | ELEVATION - 1 SUBSTATION & RACK ROOM FOR SULPHUR BLOCK 932BLD01 (036SSTR01/158SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215122-001 | 932-R-GAD-15122-001 | ELEVATION - 2 SUBSTATION & RACK ROOM FOR SULPHUR BLOCK 932BLD01 (036SSTR01/158SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070774 | SO6001-EQ1D-BDG-93215123-001 | 932-R-GAD-15123-001 | GENERAL SECTION SUBSTATION & RACK ROOM FOR SULPHUR BLOCK 932BLD01 (036SSTR01/158SRR01) | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070775 | 076551C-000S-DL-1652-001 | 000-P-IDL-80003-001 | DEVIATION LIST FOR HV SWITCHGEARS | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-070775 | 076551C-000S-ITP-1652-001 | 000-P-ITP-80003-001 | INSPECTION AND TEST PLAN FOR HV SWITCHGEARS | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-070775 | 076551C-000S-MR-1652-001 | 000-P-MRQ-80003-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-070775 | 076551C-000S-SP-1652-001 | 000-P-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HV SWITCHGEARS | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-070775 | 076551C-000S-SR-1652-001 | 000-P-SOW-80003-001 | SCOPE OF SUPPLY FOR HV SWITCHGEARS | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-070776 | SO6001-EH0D-PLO-09800001-001 | 098-A-PPN-00001-001 | PLOT PLAN 3H2 PLANT / 1N2 PLANT (EX BAPCO CODE: 098-A-PPN-80000-001 REV.A) | B | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-070776 | SO6001-EH0D-PLO-09800001-002 | 098-A-PPN-00001-002 | PLOT PLAN 3H2 PLANT / 1N2 PLANT SUBSTATION / WORK STATION (EX BAPCO CODE: 098-A-PPN-80000-002 REV.A) | B | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-070777 | SO6001-EH0D-PLO-09900001-001 | 099-A-PPN-00001-001 | PLOT PLAN 4H2 PLANT (EX BAPCO CODE: 099-A-PPN-80000-001 REV.A) | B | 2018-08-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-10 |  |  | CLASS 1
CON-BMP-TRA-070778 | SO6001-TW0R-MAI-03600002-001 | 036-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 036-2BAGRU / 037-3BAGRU NO. 2/NO. 3 BULK ACID GAS REMOVAL UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070779 | SO6001-TW0R-MAI-04100002-001 | 041-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 041-5SRU / 042-6SRU / 043-7SRU NO. 5/NO. 6/NO. 7 SULPHUR RECOVERY UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070780 | SO6001-TW0R-MAI-04400002-001 | 044-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 044-3TGTU / 045-4TGTU NO. 3/NO. 4 TAIL GAS TREATMENT UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070781 | SO6001-TW0R-MAI-04600002-001 | 046-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT S046-5SWS / S047-6SWS NO. 5 SOUR WATER / NO. 6 SOUR WATER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070782 | SO6001-EJ1E-TDS-09800007-001 | 098-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 098F0001 REFORMING FURNACE | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070782 | SO6001-EJ1E-TDS-09800008-001 | 098-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 098V0004 STEAM DRUM | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070782 | SO6001-EJ1E-TDS-09800009-001 | 098-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 098E0001 PROCESS GAS BOILER | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070782 | SO6001-EJ1E-TDS-09800010-001 | 098-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 098F0001 REFORMING FURNACE BURNERS | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070783 | SO6001-EJ1E-TDS-09900007-001 | 099-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 099F0001 REFORMING FURNACE | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070783 | SO6001-EJ1E-TDS-09900008-001 | 099-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 099V0004 STEAM DRUM | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070783 | SO6001-EJ1E-TDS-09900009-001 | 099-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 099E0001 PROCESS GAS BOILER | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070783 | SO6001-EJ1E-TDS-09900010-001 | 099-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 099F0001 REFORMING FURNACE BURNERS | 0A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070784 | SO6001-TW0R-MAI-04800002-001 | 048-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 048-2 ARU / 049-3 ARU NO. 2 / NO. 3 AMINE RECOVERY UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070785 | SO6001-TW0R-MAI-03600001-001 | 036-A-RPT-00001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT 036-2BAGRU / 037-3BAGRU N.2 / N.3 BULK ACID GAS REMOVAL UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070786 | SO6001-TW0R-MAI-04100001-001 | 041-A-RPT-00001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT 041-5SRU / 042- 6SRU / 043-7SRU N.5 / N.6 / N.7 SULPHUR RECOVERY UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070787 | SO6001-TW0R-MAI-04400001-001 | 044-A-RPT-00001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT 044-3TGTU / 045-4TGTU N.3 / N.4 TAIL GAS TREATMENT UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070788 | SO6001-TW0R-MAI-04600001-001 | 046-A-RPT-00001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT S046-5SWS / S047-6SWS N.5 SOUR WATER / N.6 SOUR WATER | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070789 | SO6001-TW0R-MAI-04800001-001 | 048-A-RPT-00001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT 048-2ARU / 049-3ARU N.2 / N.3 AMNIE RECOVERY UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070790 | SO6001-TW0R-MAI-00555002-001 | 005-A-RPT-55002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 005 - C3 & C4 LPG STORAGE AT REFINERY | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070791 | SO6001-TW0R-MAI-01650002-001 | 016-A-RPT-50002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT KERO MEROX ON PLOT FACILITIES | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070792 | SO6001-TW0R-MAI-08850002-001 | 088-A-RPT-50002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 1 KERO RERUN UNIT / REFINERY GAS SYSTEM PLANT NO. 088 / 058 | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070793 | SO6001-TW0R-MAI-09400002-001 | 094-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT NO.1/NO.2 SULPHUR HANDLING FACILITIES | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070794 | SO6001-TW0R-MAI-09800002-001 | 098-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 098-3HPU / 083-1N2 PLANT NO.3 HYDROGEN / NO.1 NITROGEN | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070795 | SO6001-TW0R-MAI-09900002-001 | 099-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 099-4HPU NO.4 HYDROGEN | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070796 | SO6001-TW0R-MAI-31000002-001 | 310-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT U310/U311/U371 HP BOILER #10/ HP BOILER #11/ BFW&CONDENSATE DISTRIB/STEAM DIS | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070797 | SO6001-TW0R-MAI-35600002-001 | 356-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT U341/U356/U357/U258 AIR COMPR. DRYERS UNIT / DESALINATION UNIT | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070798 | SO6001-TW0R-MAI-38250002-001 | 382-A-RPT-50002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 382 - SEWER SYSTEM | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070799 | SO6001-TW0R-MAI-93200002-001 | 932-A-RPT-00002-001 | MAINTENANCE CONSIDERATIONS REPORT FOR UNIT 932 - SULPHUR COMPLEX | A | 2018-08-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070800 | SO6001-TW0R-MAI-00555001-001 | 005-A-RPT-55001-001 | OPERABILITY CONSIDERATION REPORT FOR UNIT 005 - C3 & C4 LPG STORAGE AT REFINERY | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070801 | SO6001-TW0R-MAI-01650001-001 | 016-A-RPT-50001-001 | OPERABILITY CONSIDERATION REPORT FOR UNIT KERO MEROX ON PLOT FACILITIES | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070802 | SO6001-TW0R-MAI-08850001-001 | 088-A-RPT-50001-001 | OPERABILITY CONSIDERATION REPORT FOR UNIT 1 KERO RERUN UNIT7REFINERY GAS SYSTEM PLANT N:-088/058 | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070803 | SO6001-TW0R-MAI-09400001-001 | 094-A-RPT-00001-001 | OPERABILITY CONSIDERATION REPORT FOR UNIT NO.17NO.2 SULPHUR HANDLING FACILITIES | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070804 | SO6001-TW0R-MAI-09800001-001 | 098-A-RPT-00001-001 | OPERABILITY CONSIDERATION REPORT FOR UNIT 098-3HPU / 083-1N2 PLANT NO.3 HYDROGEN / NO.1 NITROGEN | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070805 | SO6001-TW0R-MAI-09900001-001 | 099-A-RPT-00001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT 099-4HPU N.4 HYDROGEN | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070806 | SO6001-TW0R-MAI-31000001-001 | 310-A-RPT-00001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT U310-U311- U370-U371 HP BOILER #10 /HP BOILER #11/BFW&CONDENSATE DISTRIBUTION | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070807 | SO6001-TW0R-MAI-35600001-001 | 356-A-RPT-00001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT U341 / U356 / U357 / U358 /AIR COMPR. DRYERS UNIT / DESALINATION UNIT | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070808 | SO6001-TW0R-MAI-38250001-001 | 382-A-RPT-50001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT 382 - SEWER SYSTEM | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070809 | SO6001-TW0R-MAI-93200001-001 | 932-A-RPT-50001-001 | OPERABILITY CONSIDERATIONS REPORT FOR UNIT 932 - SULPHUR COMPLEX | A | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-10 |  |  | CLASS 2
CON-BMP-TRA-070810 | SO6001-ESOR-PDS-00080001-001 | 000-E-STS-80001-001 | THERMAL RATING RESULT REPORT | 0 | 2018-08-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-11 |  |  | CLASS 2
CON-BMP-TRA-070811 | 076551C-000S-DL-1641-001 | 000-P-IDL-80002-001 | DEVIATION LIST FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070811 | 076551C-000S-ITP-1641-001 | 000-P-ITP-80002-001 | INSPECTION AND TEST PLAN FOR POWER TRANSFORMERS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070811 | 076551C-000S-ITP-1641-002 | 000-P-ITP-80002-002 | INSPECTION AND TEST PLAN FOR NEUTRAL EARTHING RESISTORS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070811 | 076551C-000S-MR-1641-001 | 000-P-MRQ-80002-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070811 | 076551C-000S-SP-1641-001 | 000-P-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070811 | 076551C-000S-SR-1641-001 | 000-P-SOW-80002-001 | SCOPE OF SUPPLY FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070812 | SO6001-EJ1E-TDS-31000001-001 | 310-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 310F0001 NO. 10 HP BOILER | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070812 | SO6001-EJ1E-TDS-31100001-001 | 311-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 311F0001 NO. 11 HP BOILER | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070813 | SO6001-EJ1E-TDS-04400007-001 | 044-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 044U0001 INCINERATOR PACKAGE | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070813 | SO6001-EJ1E-TDS-04500007-001 | 045-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 045U0001 INCINERATOR PACKAGE | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04100007-001 | 041-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 041F0001 REACTION FURNACE | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04100008-001 | 041-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 041V0003 HP STEAM DRUM | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04100009-001 | 041-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 041E0001 WASTE HEAT BOILER | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04100010-001 | 041-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 041BU0001 REACTION FURNACE BURNER | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04200007-001 | 042-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 042F0001 REACTION FURNACE | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04200008-001 | 042-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 042V0003 HP STEAM DRUM | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04200009-001 | 042-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 042E0001 WASTE HEAT BOILER | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04200010-001 | 042-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 042BU0001 REACTION FURNACE BURNER | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04300007-001 | 043-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 043F0001 REACTION FURNACE | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04300008-001 | 043-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 043V40001 HP STEAM DRUM | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04300009-001 | 043-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 043E0001 WASTE HEAT BOILER | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070814 | SO6001-EJ1E-TDS-04300010-001 | 043-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 043BU0001 REACTION FURNACE BURNER | 0A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070815 | SO6001-EK0D-LGD-37000001-001 | 370-J-PHD-00001-001 | CAUSE & EFFECT MATRIX (370 UTILITY UNIT) | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070816 | SO6001-EN0D-LAY-09880211-001 | 098-P-GAD-80211-001 | ELECTRICAL EQUIPMENT LAYOUT PLAN H27N2 SUBSTATION 098SSTR01 | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070816 | SO6001-EN0D-LAY-09880221-001 | 098-P-GAD-80221-001 | ELECTRICAL EQUIPMENT LAYOUT SECTION H27N2 SUBSTATION 098SSTR01 | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070816 | SO6001-EN0D-LAY-35680211-001 | 356-P-GAD-80211-001 | ELECTRICAL EQUIPMENT LAYOUT PLAN UTILITY SUBSTATION 356SSTR01 | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070816 | SO6001-EN0D-LAY-35680221-001 | 356-P-GAD-80221-001 | ELECTRICAL EQUIPMENT LAYOUT SECTION UTILITY SUBSTATION 356SSTR01 | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070817 | 076551C-000S-DL-1654-001 | 000-P-IDL-80005-001 | DEVIATION LIST FOR LV SWITCHGEARS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070817 | 076551C-000S-ITP-1654-001 | 000-P-ITP-80005-001 | INSPECTION AND TEST PLAN FOR LV SWITCHGEARS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070817 | 076551C-000S-MR-1654-001 | 000-P-MRQ-80005-001 | MATERIAL REQUISITION FOR LV SWITCHGEARS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070817 | 076551C-000S-SP-1654-001 | 000-P-GRD-80005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR LV SWITCHGEARS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070817 | 076551C-000S-SR-1654-001 | 000-P-SOW-80005-001 | SCOPE OF SUPPLY FOR LV SWITCHGEARS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070818 | SO6001-ES0D-HAZ-31000001-001 | 310-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION DRAWINGS U310 / U311 / U370 / U371 HP BOILER #10 / #11 / BFW & CONDENSATE DISTRI./STEAM | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070818 | SO6001-ES0D-HAZ-31000001-002 | 310-P-HAC-00001-002 | HAZARDOUS AREA CLASSIFICATION DRAWINGS U310 / U311 / U370 / U371 HP BOILER #10 / #11 / BFW & CONDENSATE DISTRI./STEAM | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070819 | SO6001-ES0D-HAZ-35600001-001 | 356-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION DRAWINGS U341 / U356 / U357 / U358 AIR COMPR. DRYERS UNIT / DESALINATION UNITS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070819 | SO6001-ES0D-HAZ-35600001-002 | 356-P-HAC-00001-002 | HAZARDOUS AREA CLASSIFICATION DRAWINGS U341 / U356 / U357 / U358 AIR COMPR. DRYERS UNIT / DESALINATION UNITS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-12 |  |  | CLASS 2
CON-BMP-TRA-070820 | SO6001-ES0L-HAZ-31000001-001 | 310-P-HAC-00002-001 | HAZARDOUS SOURCE OF RELEASE LIST U310 / U311 / U370 / U371 HP BOILER #10 / #11 / BFW & CONDENSATE DISTRI. / STEAM DISTRI | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070821 | SO6001-ES0L-HAZ-35600001-001 | 356-P-HAC-00002-001 | HAZARDOUS SOURCE OF RELEASE LIST U341 / U356 / U357 / U358 AIR COMPR. DRYERS UNIT / DESALINATION UNITS | A | 2018-08-28 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070822 | SOC-BMS-MOM-00005 | 000-A-MOM-80001-001 | SOC IBD PID REVIEW MEETING - FIRE FIGHTING SYSTEM | 0 | 2018-08-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-070823 | SO6001-EJ1E-TDS-03600003-001 | 036-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036C0001 ABSORBER | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070823 | SO6001-EJ1E-TDS-03700003-001 | 037-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037C0001 ABSORBER | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070823 | SO6001-EJ1E-TDS-04400009-001 | 044-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0002 QUENCH COLUMN | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070823 | SO6001-EJ1E-TDS-04400010-001 | 044-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0003 ABSORBER | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070823 | SO6001-EJ1E-TDS-04500004-001 | 045-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0002 QUENCH COLUMN | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070823 | SO6001-EJ1E-TDS-04500005-001 | 045-C-DAT-00003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0003 ABSORBER | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-03600003-002-001 | 036-C-GAD-00001-001 | MECHANICAL DRAWINGS FOR 036C0001 ABSORBER | 0 | 2018-08-29 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-03600003-003-002 | 036-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 036C0001 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-03600003-004-003 | 036-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 036C0001 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-03700003-002-001 | 037-C-GAD-00001-001 | MECHANICAL DATA SHEET FOR 037C0001 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-03700003-003-002 | 037-C-GAD-00001-002 | MECHANICAL DATA SHEET FOR 037C0001 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-03700003-004-003 | 037-C-GAD-00001-003 | MECHANICAL DATA SHEET FOR 037C0001 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04400009-002-001 | 044-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 044C0001 QUENCH COLUMN | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04400009-003-002 | 044-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 044C0001 QUENCH COLUMN | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04400009-004-003 | 044-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 044C0001 QUENCH COLUMN | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04400010-002-001 | 044-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 044C0003 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04400010-002-002 | 044-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 044C0003 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04400010-002-003 | 044-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 044C0003 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04500004-002-001 | 045-C-GAD-00002-001 | MECHANICAL DATA SHEET FOR 045C0002 QUENCH COLUMN | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04500004-002-002 | 045-C-GAD-00002-002 | MECHANICAL DATA SHEET FOR 045C0002 QUENCH COLUMN | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04500004-002-003 | 045-C-GAD-00002-003 | MECHANICAL DATA SHEET FOR 045C0002 QUENCH COLUMN | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04500005-002-001 | 045-C-GAD-00003-001 | MECHANICAL DATA SHEET FOR 045C0003 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04500005-003-002 | 045-C-GAD-00003-002 | MECHANICAL DATA SHEET FOR 045C0003 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070824 | SO6001-EJ1E-TDS-04500005-0040-003 | 045-C-GAD-00003-003 | MECHANICAL DATA SHEET FOR 045C0003 ABSORBER | 0 | 2018-08-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-03600004-001 | 036-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036C0002 REGENERATOR | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-03700004-001 | 037-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037C0002 REGENERATOR | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-04400011-001 | 044-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0004 REGENERATOR | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-04500006-001 | 045-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0004 REGENERATOR | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-04600003-001 | 046-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046C0001 NON-PHENOLIC SOUR WATRER STRIPPER | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-04700003-001 | 047-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 047C0001 PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-04800005-001 | 048-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048C0001 AMINE REGENERATOR | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-04900003-001 | 049-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 049C0001 AMINE REGENERATOR | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-09800005-001 | 098-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098C0004 HIGH PRESSURE STRIPPER | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070825 | SO6001-EJ1E-TDS-09900005-001 | 099-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099C0004 HIGH PRESSURE STRIPPER | 0 | 2018-08-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-13 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-03600004-002-001 | 036-C-GAD-00002-001 | 036C0002 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-03600004-003-002 | 036-C-GAD-00002-002 | 036C0002 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-03600004-004-003 | 036-C-GAD-00002-003 | 036C0002 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-03700004-002-001 | 037-C-GAD-00002-001 | 037C0002 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-03700004-003-002 | 037-C-GAD-00002-002 | 037C0002 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-03700004-004-003 | 037-C-GAD-00002-003 | 037C0002 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-04400011-002-001 | 044-C-GAD-00004-001 | 044C0004 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-04400011-003-002 | 044-C-GAD-00004-002 | 044C0004 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-04400011-004-003 | 044-C-GAD-00004-003 | 044C0004 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-04500006-002-001 | 045-C-GAD-00004-001 | 045C0004 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-04500006-003-002 | 045-C-GAD-00004-002 | 045C0004 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070826 | SO6001-EJ1E-TDS-04500006-004-003 | 045-C-GAD-00004-003 | 045C0004 REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04600003-002-001 | 046-C-GAD-00001-001 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04600003-003-002 | 046-C-GAD-00001-002 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04600003-004-003 | 046-C-GAD-00001-003 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04700003-002-001 | 047-C-GAD-00001-001 | 047C0001 PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04700003-003-002 | 047-C-GAD-00001-002 | 047C0001 PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04700003-004-003 | 047-C-GAD-00001-003 | 047C0001 PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04800005-002-001 | 048-C-GAD-00001-001 | 048C0001 PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04800005-003-002 | 048-C-GAD-00001-002 | 048C0001 PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04800005-004-003 | 048-C-GAD-00001-003 | 048C0001 PHENOLIC SOUR WATER STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04900003-002-001 | 049-C-GAD-00001-001 | 049C0001 AMINE REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04900003-003-002 | 049-C-GAD-00001-002 | 049C0001 AMINE REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-04900003-004-003 | 049-C-GAD-00001-003 | 049C0001 AMINE REGENERATOR | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-09800005-002-001 | 098-C-GAD-00004-001 | 098C0004 HIGH PRESSURE STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-09800005-003-002 | 098-C-GAD-00004-002 | 098C0004 HIGH PRESSURE STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-09800005-004-003 | 098-C-GAD-00004-003 | 098C0004 HIGH PRESSURE STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-09900005-002-001 | 099-C-GAD-00004-001 | 099C0004 HIGH PRESSURE STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-09900005-003-002 | 099-C-GAD-00004-002 | 099C0004 HIGH PRESSURE STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070827 | SO6001-EJ1E-TDS-09900005-004-003 | 099-C-GAD-00004-003 | 099C0004 HIGH PRESSURE STRIPPER | 0 | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070828 | SO6001-EQ1D-BDG-09815001-001 | 098-R-GAD-15001-001 | GROUND FLOOR PLAN & FINISHING SCHEDULE OPERATOR WORKSTATION FOR HYDROGEN PLANT 098BLD01 (098OW01) | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070828 | SO6001-EQ1D-BDG-09815002-001 | 098-R-GAD-15002-001 | ROOF PLAN OPERATOR WORKSTATION FOR HYDROGEN PLANT 098BLD01 (098OW01) | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070828 | SO6001-EQ1D-BDG-09815021-001 | 098-R-GAD-15021-001 | ELEVATION-1 OPERATOR WORKSTATION FOR HYDROGEN PLANT 098BLD01 (098OW01) | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070828 | SO6001-EQ1D-BDG-09815022-001 | 098-R-GAD-15022-001 | ELEVATION-2 OPERATOR WORKSTATION FOR HYDROGEN PLANT 098BLD01 (098OW01) | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070828 | SO6001-EQ1D-BDG-09815023-001 | 098-R-GAD-15023-001 | GENERAL SECTION OPERATOR WORKSTATION FOR HYDROGEN PLANT 098BLD01 (098OW01) | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070829 | SO6001-EY1B-MSP-00080001-001 | 000-A-BOD-80001-001 | MATERIAL SELECTION BASIS PROCESS UNIT (036,037,041,042,043,044,045,046,047,048 AND 049) | A | 2018-08-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-14 |  |  | CLASS 1
CON-BMP-TRA-070829 | SO6001-EY1B-MSP-00080002-001 | 000-A-BOD-80002-001 | MATERIAL SELECTION BASIS UTILITY UNIT (98,99,310,311,341,356,357,358 AND 370) | A | 2018-08-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-14 |  |  | CLASS 1
CON-BMP-TRA-070829 | SO6001-EY1B-MSP-00080003-001 | 000-A-BOD-80003-001 | MATERIAL SELECTION BASIS OFFSITE & REVAMPING UNITS(005, 016, 088, 094 AND 382) | A | 2018-08-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-09-14 |  |  | CLASS 1
CON-BMP-TRA-070830 | 076551C-000S-TBT-0411-001 | 000-C-TBE-80004-001 | TECHNICAL BIDS EVALUATION FOR REACTORS | A | 2018-08-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070831 | SO6001-ES0D-HAZ-09800001-001 | 098-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION DRAWINGS 3H2 PLANT / 1N2 PLANT | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070831 | SO6001-ES0D-HAZ-09800001-002 | 098-P-HAC-00001-002 | HAZARDOUS AREA CLASSIFICATION DRAWINGS 3H2 PLANT / 1N2 PLANT SUBSTATION / WORK STATION | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070831 | SO6001-ES0D-HAZ-09900001-001 | 099-P-HAC-00001-001 | HAZARDOUS AREA CLASSIFICATION DRAWINGS 4H2 PLANT | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2
CON-BMP-TRA-070832 | SO6001-ES0L-HAZ-09800001-001 | 098-P-HAC-00002-001 | HAZARDOUS SOURCE OF RELEASE LIST 3H2 PLANT/4H2PLANT/1N2 PLANT-UNIT NO.098-3H2 PLANT/099-4H2 PLANT/083-1N2 PLANT | A | 2018-08-31 | FOR BAPCO REVIEW | BMP Project Director | 2018-09-14 |  |  | CLASS 2